## Cover
Advanced Calibration: Using the Lens Method
Hubbard Decision Research
2S410 Canterbury Ct
Glen Ellyn, IL 60137
www.hubbardresearch.com

## LOR Estimates
Log Odds Ratio Worksheet
Instructions: This spreadsheet shows an example of how to use the Log Odds Ratios (LOR) to apply several conditions to a single probability. This spreadsheet will estimate the conditional probability of on time project delivery (i.e., ≤5% schedule overrun) given the aggregate effect of several conditions. Further details are given in the areas to the right below.
Expand for Instructions →
|  | Time Period for Estimates (years): |  | 1 | In the yellow cells to the left, enter time period of your estimates in years and the initial probability of an event occurring in the that time period. For example, you might estimate the likelihood of an event over a 5 year period at 5%. This values is then converted to a baseline log odds ratio that will be adjusted based on the information you enter below. The number of combinations of the attributes are included for reference.
|  | Initial Probability of Event per Time Period: P(E) |  | 44%
|  | Baseline Log Odds |  | -0.24116
|  | Condition Combinations |  | 54
Expand for Instructions →
Conditions
| Prior Domain experience (team has completed similar projects) | Schedule Buffer % (Planned duration minus critical path duration divided by critical path duration) | Dependency Load on the Critical Path (proportion of critical-path activities that depend on external parties) | Contract Type | Each column represents a unique "class" of attributes that affect the likelihood of an event. Make sure the classes are non-overlapping and non-redundant.
X1 | Yes | >15% | ≤ 0.20 | Firm-Fixed-Price | Enter the possible attributes for each class. There is space for 4 attributes, but it is not necessary to fill out all 4. Some classes may have 2 attributes, others may have 3 or 4, etc. These attributes should be orthogonal; i.e., they should not overlap with each other. They should also cover all possible states of a class. For example, whether or not an app is on the web is either a "yes" or a "no". There is no overlap between those attributes and they cover all possible states of being on the web. For a continuous variable, such as age, you should define bins of logical sizes. For example, the bins might be: "<1 yr", "1-5 yrs", or "5+ yrs"
X2 | No | 5–15% | 0.21–0.40 | Time & Materials
X3 |  | <5% | > 0.40 | Cost-Plus
X4
P(E¦X1) | 50% | 52% | 60% | 46% | Enter the conditional probability of the event given each of the attributes listed above. Another way to phrase this question is, "Given a random project, the what is baseline probability of a successful project delivery with this attribute?".
P(E¦X2) | 34% | 47% | 44% | 44%
P(E¦X3) |  | 36% | 34% | 40%
P(E¦X4)
P(X1) | 60% | 20% | 20% | 40% | In this section, enter how frequently the attributes listed above occur. In other words, enter the percentage of applications that fall into that category. If this information is readily available, fill it out with actual values. Otherwise, provide calibrated estimates based on your knowledge of the environment.
P(X2) | 40% | 40% | 50% | 40%
P(X3) |  | 40% | 30% | 20%
P(X4)
Sum Check P(X) =100% | Good | Good | Good | Good | The sum of the probabilities of each attribute should equal 100%. In other words, the attributes should reflect all possible states for a given class. If this is the case, the cell will read "Good", otherwise it will display the value.
Test P( E) Computed=Stated | Good | Good | Good | Good | The weighted average of the conditional probabilities should be close to the baseline probability. If the weighted average is close to the baseline, this row will return "Good". Otherwise, you will see the actual weighted average, and you will need to adjust the conditional probabilities or frequency of attributes until this reads "Good" all the way across.
Count of Possible States | 2 | 3 | 3 | 3 | This simply counts the attributes for each class.
Log Odds change¦X1 | 0.24116 | 0.3212 | 0.64663 | 0.080819 | This is where the change in Log Odds Ratio is computed. You do not need to edit anything in this range of cells.
Log Odds change¦X2 | -0.42213 | 0.12102 | 0 | 0
Log Odds change¦X3 |  | -0.3342 | -0.42213 | -0.1643
Log Odds change¦X4
Condition State that Applies | Yes | >15% | 0.21–0.40 | Firm-Fixed-Price | Choose combinations of attributes to see how the conditional probability of an event changes (below).
Attribute Contribution to Likelihood | 0.24116 | 0.3212 | 0 | 0.080819 | Each attribute contributes to the likelihood of an event. The change in Log Odds Ratio is referenced from the rows above, then the sum of the changes is added to the baseline log odds ratio. Finally, the updated log odds ratio is converted back to a probability.
|  | Total Adjustment | 0.64319
|  | Conditional Probability | 59.92%

## Model Design Sheet
Lens Model Design
Model Definition
Design your model here. This table takes three types of data: classes, the type of each class, and a list of attributes for each class. Here each class, 1 per column, represents an independent variable which will inform the dependent variable. After you have stated and defined your classes define the type of each class. For this you will use the dropdown menu to select "Binary", Continuous", or "Discrete". A binary type will use one of two responses you can list below and it will be codified with a "1" for the first answer and "0" for the second answer. A continuous type will take any real number, and a discrete type will take up to three choices described in the cells using words. These classes and attributes will be used to generate a Lens list.
Class |  | Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type
Definition |  | Team has completed 2 or more similar projects | Planned duration minus critical path duration divided by critical path duration. | Proportion of critical-path activities that depend on external parties. | Procurement/commercial model specifying how costs are reimbursed and delivery risk is allocated.
Type |  | Binary | Continuous | Continuous | Discrete
Attributes |  | Yes |  |  | Firm-Fixed-Price
|  | No |  |  | Time & Materials
Cost-Plus
Cont. Min |  |  | 0% | 0
Cont. Max |  |  | 100% | 1
Building a Lens list
Unless you have specific choices you want to include in your list, the above table contains all the information you need to construct your Lens list. For the binary and discrete classes each field in that column will contain one of the attributes listed above. If you use continuous classes you will need to choose how to sample from the values between the minimum and maximum, one example would be to uniformly sample from the range. If you are not using duplicate pairs to do an analysis of the expert inconsistency each row should have a unique set of attributes. If you are using duplicate pairs to analyze the inconsistency of the SME being sampled choose places in the bottom third of your list which repeat rows sampled from the top. Note which rows contain duplicates in a separate spot. It is also suggested you hide all but the response sheet and lock all but the response cells so participants cannot sort or use an algorithm to answer the responses for them. It is suggested you put some example rows below and respond to them before you make your full list to make sure the classes and attributes have enough information to make an informed estimate.
Example List Rows
Index | Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type | Percent chance of On-Time Project Delivery
1 | Yes | 15% | 0.235 | Firm-Fixed-Price | ?
2 | Yes | 5% | 0.654 | Firm-Fixed-Price | ?
3 | Yes | 9% | 0.154 | Time & Materials | ?
4 | No | 8.75% | 0.45 | Cost-Plus | ?
5 | No | 10% | 0.325 | Firm-Fixed-Price | ?

## Responses
Lens Response Sheet
Instructions: To use this tool, put the Lens list below and estimate each row one at a time. This example estimates the probability of on time project delivery (i.e., ≤5% schedule overrun) given project features.
Index | Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type | Percent Chance of On-Time Project Delivery
1 | Yes | 29.8% | 0.438 | Firm-Fixed-Price | 72.5%
2 | Yes | 14.9% | 0.563 | Cost-Plus | 21.4%
3 | Yes | 4.9% | 0.233 | Time & Materials | 38.3%
4 | No | 20% | 0.453 | Time & Materials | 26.5%
5 | Yes | 26% | 0.237 | Firm-Fixed-Price | 62.8%
6 | Yes | 16.9% | 0.173 | Firm-Fixed-Price | 69%
7 | Yes | 15% | 0.131 | Firm-Fixed-Price | 62%
8 | No | 24.5% | 0.578 | Cost-Plus | 13.5%
9 | Yes | 13.9% | 0.661 | Time & Materials | 27.6%
10 | Yes | 16.1% | 0.446 | Time & Materials | 47.9%
11 | Yes | 29.2% | 0.52 | Firm-Fixed-Price | 54.2%
12 | No | 6.5% | 0.546 | Cost-Plus | 5.3%
13 | No | 15.1% | 0.449 | Cost-Plus | 19.6%
14 | Yes | 32.8% | 0.54 | Firm-Fixed-Price | 47.3%
15 | No | 25.8% | 0.109 | Firm-Fixed-Price | 48.5%
16 | Yes | 13.8% | 0.67 | Firm-Fixed-Price | 35.7%
17 | Yes | 5.8% | 0.393 | Firm-Fixed-Price | 59.2%
18 | No | 3.6% | 0.335 | Time & Materials | 11.5%
19 | No | 50.8% | 0.486 | Time & Materials | 58.4%
20 | No | 32.4% | 0.285 | Firm-Fixed-Price | 58.2%
21 | No | 21.8% | 0.273 | Time & Materials | 34.4%
22 | Yes | 10.2% | 0.382 | Firm-Fixed-Price | 50.7%
23 | Yes | 29.2% | 0.281 | Firm-Fixed-Price | 67.2%
24 | Yes | 12.2% | 0.296 | Firm-Fixed-Price | 60.9%
25 | Yes | 17.1% | 0.879 | Time & Materials | 25.1%
26 | Yes | 28.4% | 0.495 | Time & Materials | 45.8%
27 | No | 72.7% | 0.172 | Firm-Fixed-Price | 66.8%
28 | Yes | 60.5% | 0.454 | Time & Materials | 51%
29 | No | 2.6% | 0.266 | Time & Materials | 22.2%
30 | Yes | 30.6% | 0.358 | Firm-Fixed-Price | 60.7%
31 | No | 13.8% | 0.81 | Time & Materials | 17.4%
32 | Yes | 4.9% | 0.016 | Firm-Fixed-Price | 67.6%
33 | Yes | 9.1% | 0.46 | Firm-Fixed-Price | 24%
34 | No | 5.2% | 0.046 | Cost-Plus | 27.4%
35 | Yes | 10.1% | 0.885 | Cost-Plus | 10.5%
36 | No | 74% | 0.483 | Cost-Plus | 22.1%
37 | Yes | 13.3% | 0.32 | Firm-Fixed-Price | 52.6%
38 | Yes | 31.4% | 0.537 | Firm-Fixed-Price | 64.2%
39 | No | 35.7% | 0.098 | Time & Materials | 54.1%
40 | Yes | 31.9% | 0.275 | Time & Materials | 46.3%
41 | No | 26.5% | 0.472 | Firm-Fixed-Price | 41.9%
42 | No | 17.3% | 0.479 | Time & Materials | 17.4%
43 | No | 26.7% | 0.299 | Firm-Fixed-Price | 34.6%
44 | No | 22.9% | 0.827 | Cost-Plus | 5.9%
45 | Yes | 23.2% | 0.189 | Firm-Fixed-Price | 72.7%
46 | No | 17.9% | 0.224 | Time & Materials | 41%
47 | Yes | 18.1% | 0.038 | Firm-Fixed-Price | 73.7%
48 | No | 21.1% | 0.466 | Time & Materials | 29.5%
49 | No | 14.8% | 0.807 | Time & Materials | 14.8%
50 | No | 8.3% | 0.244 | Firm-Fixed-Price | 33.6%
51 | Yes | 17.8% | 0.494 | Cost-Plus | 25.8%
52 | Yes | 27.7% | 0.212 | Time & Materials | 61.6%
53 | No | 21% | 0.539 | Cost-Plus | 15.6%
54 | Yes | 13.9% | 0.244 | Cost-Plus | 42.2%
55 | Yes | 40.7% | 0.394 | Time & Materials | 56.3%
56 | No | 7.2% | 0.773 | Cost-Plus | 6.8%
57 | No | 14.3% | 0.312 | Firm-Fixed-Price | 48.8%
58 | No | 24.7% | 0.589 | Firm-Fixed-Price | 32.7%
59 | Yes | 12.9% | 0.256 | Firm-Fixed-Price | 50.9%
60 | Yes | 22.5% | 0.382 | Firm-Fixed-Price | 56.5%
61 | Yes | 3.2% | 0.176 | Firm-Fixed-Price | 47.7%
62 | No | 25.1% | 0.474 | Firm-Fixed-Price | 32.4%
63 | Yes | 13.8% | 0.655 | Cost-Plus | 15.7%
64 | Yes | 20.2% | 0.439 | Firm-Fixed-Price | 47.5%
65 | No | 23% | 0.391 | Firm-Fixed-Price | 37.9%
66 | No | 8.7% | 0.727 | Time & Materials | 7.1%
67 | No | 12% | 0.426 | Firm-Fixed-Price | 35.2%
68 | No | 29.1% | 0.641 | Cost-Plus | 11.3%
69 | Yes | 12.5% | 0.367 | Firm-Fixed-Price | 46.2%
70 | Yes | 14.2% | 0.88 | Cost-Plus | 13.1%
71 | No | 15.9% | 0.624 | Time & Materials | 23%
72 | No | 32.7% | 0.58 | Firm-Fixed-Price | 24.5%
73 | No | 39.3% | 0.202 | Firm-Fixed-Price | 48.6%
74 | No | 4.8% | 0.857 | Cost-Plus | 3.7%
75 | No | 30.1% | 0.719 | Time & Materials | 14%
76 | No | 3.1% | 0.364 | Time & Materials | 25.3%
77 | No | 13.3% | 0.298 | Time & Materials | 26.7%
78 | Yes | 69.9% | 0.224 | Firm-Fixed-Price | 76%
79 | No | 9% | 0.618 | Firm-Fixed-Price | 14%
80 | No | 18.9% | 0.038 | Firm-Fixed-Price | 59.7%
81 | No | 5.1% | 0.833 | Cost-Plus | 3.3%
82 | Yes | 33.2% | 0.791 | Time & Materials | 29.6%
83 | Yes | 26.6% | 0.428 | Firm-Fixed-Price | 60.1%
84 | Yes | 26.8% | 0.172 | Firm-Fixed-Price | 77.8%
85 | Yes | 33.1% | 0.674 | Firm-Fixed-Price | 38.1%
86 | Yes | 24.4% | 0.005 | Firm-Fixed-Price | 49.4%
87 | Yes | 17.2% | 0.305 | Time & Materials | 47.3%
88 | No | 18.2% | 0.393 | Time & Materials | 40.1%
89 | Yes | 29.2% | 0.484 | Cost-Plus | 35.9%
90 | No | 34.4% | 0.91 | Time & Materials | 15%
91 | Yes | 5.2% | 0.243 | Firm-Fixed-Price | 49.1%
92 | Yes | 11.9% | 0.247 | Time & Materials | 52.8%
93 | No | 9.3% | 0.651 | Time & Materials | 11.1%
94 | Yes | 5.5% | 0.236 | Time & Materials | 46.1%
95 | Yes | 7.9% | 0.554 | Time & Materials | 33%
96 | No | 27.5% | 0.48 | Time & Materials | 33.7%
97 | No | 11.9% | 0.622 | Time & Materials | 34.2%
98 | Yes | 14.7% | 0.409 | Time & Materials | 42.8%
99 | Yes | 55% | 0.342 | Firm-Fixed-Price | 66.6%
100 | Yes | 16.2% | 0.273 | Firm-Fixed-Price | 59.4%
101 | Yes | 22.4% | 0.595 | Firm-Fixed-Price | 33.6%
102 | No | 12.6% | 0.479 | Time & Materials | 17.3%
103 | Yes | 4.9% | 0.45 | Firm-Fixed-Price | 40.3%
104 | No | 5.7% | 0.176 | Time & Materials | 25.4%
105 | No | 10.3% | 0.542 | Cost-Plus | 10.9%
106 | No | 37.2% | 0.371 | Firm-Fixed-Price | 39.9%
107 | No | 13.5% | 0.281 | Time & Materials | 37.5%
108 | Yes | 71.2% | 0.369 | Time & Materials | 59.5%
109 | No | 25.7% | 0.498 | Firm-Fixed-Price | 37%
110 | Yes | 15.9% | 0.121 | Firm-Fixed-Price | 63.2%
111 | Yes | 7.1% | 0.228 | Firm-Fixed-Price | 57.2%
112 | Yes | 35.8% | 0.255 | Firm-Fixed-Price | 74.2%
113 | Yes | 5.6% | 0.579 | Cost-Plus | 12.3%
114 | No | 9.4% | 0.294 | Cost-Plus | 13.5%
115 | No | 31.8% | 0.306 | Time & Materials | 32.2%
116 | No | 5.6% | 0.736 | Cost-Plus | 4%
117 | No | 15.9% | 0.413 | Cost-Plus | 11.5%
118 | Yes | 18.5% | 0.688 | Firm-Fixed-Price | 38.3%
119 | Yes | 17.2% | 0.201 | Cost-Plus | 43.4%
120 | Yes | 20.4% | 0.558 | Time & Materials | 37.1%
121 | No | 20.3% | 0.337 | Cost-Plus | 19%
122 | No | 5% | 0.783 | Cost-Plus | 7.4%
123 | No | 20.4% | 0.34 | Firm-Fixed-Price | 40.3%
124 | Yes | 18.5% | 0.54 | Firm-Fixed-Price | 52.3%
125 | No | 14% | 0.374 | Firm-Fixed-Price | 35.9%
126 | No | 35.7% | 0.505 | Time & Materials | 29.1%
127 | No | 6% | 0.418 | Cost-Plus | 10%
128 | No | 2.1% | 0.774 | Cost-Plus | 2.2%
129 | Yes | 29.2% | 0.164 | Firm-Fixed-Price | 68.5%
130 | Yes | 17% | 0.666 | Time & Materials | 40.1%
131 | Yes | 27.2% | 0.248 | Time & Materials | 60.7%
132 | No | 25.3% | 0.177 | Firm-Fixed-Price | 59.4%
133 | Yes | 58.6% | 0.32 | Firm-Fixed-Price | 80%
134 | Yes | 23.3% | 0.341 | Firm-Fixed-Price | 60.9%
135 | Yes | 16% | 0.365 | Cost-Plus | 29.2%
136 | Yes | 15% | 0.58 | Firm-Fixed-Price | 39.9%
137 | No | 9.1% | 0.297 | Time & Materials | 24.1%
138 | No | 76.1% | 0.516 | Time & Materials | 41.4%
139 | Yes | 59.7% | 0.771 | Firm-Fixed-Price | 63.8%
140 | Yes | 7% | 0.584 | Cost-Plus | 15.7%
141 | No | 15.2% | 0.519 | Cost-Plus | 10.3%
142 | Yes | 20.6% | 0.392 | Firm-Fixed-Price | 56.6%
143 | Yes | 24.1% | 0.506 | Time & Materials | 43.9%
144 | Yes | 69.6% | 0.276 | Firm-Fixed-Price | 65.5%
145 | Yes | 30% | 0.364 | Firm-Fixed-Price | 42%
146 | Yes | 20% | 0.621 | Firm-Fixed-Price | 41.4%
147 | No | 9.4% | 0.626 | Time & Materials | 10.7%
148 | Yes | 10.4% | 0.128 | Time & Materials | 46.3%
149 | Yes | 10.7% | 0.7 | Firm-Fixed-Price | 36.2%
150 | Yes | 52.2% | 0.33 | Firm-Fixed-Price | 66.6%
151 | No | 28.2% | 0.809 | Cost-Plus | 12.6%
152 | No | 20.1% | 0.228 | Firm-Fixed-Price | 49.2%
153 | No | 29.4% | 0.334 | Firm-Fixed-Price | 48.3%
154 | Yes | 11.2% | 0.236 | Time & Materials | 51.3%
155 | Yes | 7.5% | 0.826 | Cost-Plus | 7.2%
156 | Yes | 19.2% | 0.84 | Firm-Fixed-Price | 44.8%
157 | Yes | 23.8% | 0.172 | Time & Materials | 54.6%
158 | No | 8.8% | 0.219 | Time & Materials | 34.2%
159 | No | 28.7% | 0.504 | Firm-Fixed-Price | 29.6%
160 | No | 14.3% | 0.452 | Time & Materials | 14.5%
161 | Yes | 15.1% | 0.082 | Firm-Fixed-Price | 73%
162 | No | 16.4% | 0.196 | Time & Materials | 36.9%
163 | Yes | 18% | 0.285 | Time & Materials | 39.4%
164 | No | 27.2% | 0.582 | Time & Materials | 17.3%
165 | No | 7.6% | 0.427 | Firm-Fixed-Price | 39.8%
166 | No | 31.1% | 0.801 | Cost-Plus | 5.7%
167 | No | 8.9% | 0.168 | Firm-Fixed-Price | 56.8%
168 | No | 28.2% | 0.23 | Firm-Fixed-Price | 42%
169 | Yes | 13.6% | 0.251 | Firm-Fixed-Price | 64.5%
170 | Yes | 0.7% | 0.48 | Time & Materials | 23.7%
171 | Yes | 21.2% | 0.029 | Time & Materials | 65.9%
172 | Yes | 39.6% | 0.22 | Firm-Fixed-Price | 66.8%
173 | Yes | 12.3% | 0.261 | Time & Materials | 43.9%
174 | No | 21.4% | 0.069 | Firm-Fixed-Price | 54.4%
175 | Yes | 20.9% | 0.569 | Time & Materials | 27.2%
176 | Yes | 53.7% | 0.533 | Firm-Fixed-Price | 68.1%
177 | No | 54.5% | 0.736 | Time & Materials | 19.8%
178 | Yes | 22.9% | 0.437 | Firm-Fixed-Price | 53.7%
179 | No | 59.2% | 0.86 | Cost-Plus | 7.2%
180 | Yes | 15.5% | 0.129 | Firm-Fixed-Price | 43.5%
181 | Yes | 7.4% | 0.79 | Firm-Fixed-Price | 30.3%
182 | No | 18% | 0.117 | Firm-Fixed-Price | 70.1%
183 | No | 18.9% | 0.749 | Cost-Plus | 10.2%
184 | No | 11% | 0.587 | Cost-Plus | 9.6%
185 | No | 7.1% | 0.543 | Firm-Fixed-Price | 24.5%
186 | No | 18.1% | 0.48 | Time & Materials | 23.2%
187 | Yes | 16.4% | 0.141 | Cost-Plus | 43.4%
188 | Yes | 24.6% | 0.36 | Time & Materials | 36.2%
189 | No | 25.3% | 0.568 | Time & Materials | 29.6%
190 | No | 21.5% | 0.649 | Firm-Fixed-Price | 34.8%
191 | No | 60.2% | 0.317 | Firm-Fixed-Price | 62.6%
192 | No | 14.1% | 0.9 | Cost-Plus | 6.2%
193 | No | 55.9% | 0.271 | Cost-Plus | 28.1%
194 | No | 20% | 0.249 | Time & Materials | 38.3%
195 | Yes | 23.9% | 0.784 | Firm-Fixed-Price | 45.8%
196 | No | 32.2% | 0.131 | Firm-Fixed-Price | 52.8%
197 | No | 4.9% | 0.13 | Time & Materials | 26.2%
198 | No | 16.1% | 0.48 | Cost-Plus | 13.4%
199 | No | 6.2% | 0.797 | Cost-Plus | 9.3%
200 | No | 9.9% | 0.449 | Time & Materials | 14.7%

## Codification
Codification Sheet
Instructions: This page requires no user input. The Codification sheet assigns values to the text fields in the table below. These codified values will be used on the regression tab to calculate the coefficients for the model.
Model Variables
Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type
Binary | Continuous | Continuous | Discrete
Yes |  |  | Firm-Fixed-Price
No |  |  | Time & Materials
Cost-Plus
Codification
0.51646
0.33987
0.15271
Response Data
Class 1 | Class 2 | Class 3 | Class 4 | Index | Responses
1 | 0.298 | 0.438 | Firm-Fixed-Price | 1 | 0.725
1 | 0.149 | 0.563 | Cost-Plus | 2 | 0.214
1 | 0.049 | 0.233 | Time & Materials | 3 | 0.383
0 | 0.2 | 0.453 | Time & Materials | 4 | 0.265
1 | 0.26 | 0.237 | Firm-Fixed-Price | 5 | 0.628
1 | 0.169 | 0.173 | Firm-Fixed-Price | 6 | 0.69
1 | 0.15 | 0.131 | Firm-Fixed-Price | 7 | 0.62
0 | 0.245 | 0.578 | Cost-Plus | 8 | 0.135
1 | 0.139 | 0.661 | Time & Materials | 9 | 0.276
1 | 0.161 | 0.446 | Time & Materials | 10 | 0.479
1 | 0.292 | 0.52 | Firm-Fixed-Price | 11 | 0.542
0 | 0.065 | 0.546 | Cost-Plus | 12 | 0.053
0 | 0.151 | 0.449 | Cost-Plus | 13 | 0.196
1 | 0.328 | 0.54 | Firm-Fixed-Price | 14 | 0.473
0 | 0.258 | 0.109 | Firm-Fixed-Price | 15 | 0.485
1 | 0.138 | 0.67 | Firm-Fixed-Price | 16 | 0.357
1 | 0.058 | 0.393 | Firm-Fixed-Price | 17 | 0.592
0 | 0.036 | 0.335 | Time & Materials | 18 | 0.115
0 | 0.508 | 0.486 | Time & Materials | 19 | 0.584
0 | 0.324 | 0.285 | Firm-Fixed-Price | 20 | 0.582
0 | 0.218 | 0.273 | Time & Materials | 21 | 0.344
1 | 0.102 | 0.382 | Firm-Fixed-Price | 22 | 0.507
1 | 0.292 | 0.281 | Firm-Fixed-Price | 23 | 0.672
1 | 0.122 | 0.296 | Firm-Fixed-Price | 24 | 0.609
1 | 0.171 | 0.879 | Time & Materials | 25 | 0.251
1 | 0.284 | 0.495 | Time & Materials | 26 | 0.458
0 | 0.727 | 0.172 | Firm-Fixed-Price | 27 | 0.668
1 | 0.605 | 0.454 | Time & Materials | 28 | 0.51
0 | 0.026 | 0.266 | Time & Materials | 29 | 0.222
1 | 0.306 | 0.358 | Firm-Fixed-Price | 30 | 0.607
0 | 0.138 | 0.81 | Time & Materials | 31 | 0.174
1 | 0.049 | 0.016 | Firm-Fixed-Price | 32 | 0.676
1 | 0.091 | 0.46 | Firm-Fixed-Price | 33 | 0.24
0 | 0.052 | 0.046 | Cost-Plus | 34 | 0.274
1 | 0.101 | 0.885 | Cost-Plus | 35 | 0.105
0 | 0.74 | 0.483 | Cost-Plus | 36 | 0.221
1 | 0.133 | 0.32 | Firm-Fixed-Price | 37 | 0.526
1 | 0.314 | 0.537 | Firm-Fixed-Price | 38 | 0.642
0 | 0.357 | 0.098 | Time & Materials | 39 | 0.541
1 | 0.319 | 0.275 | Time & Materials | 40 | 0.463
0 | 0.265 | 0.472 | Firm-Fixed-Price | 41 | 0.419
0 | 0.173 | 0.479 | Time & Materials | 42 | 0.174
0 | 0.267 | 0.299 | Firm-Fixed-Price | 43 | 0.346
0 | 0.229 | 0.827 | Cost-Plus | 44 | 0.059
1 | 0.232 | 0.189 | Firm-Fixed-Price | 45 | 0.727
0 | 0.179 | 0.224 | Time & Materials | 46 | 0.41
1 | 0.181 | 0.038 | Firm-Fixed-Price | 47 | 0.737
0 | 0.211 | 0.466 | Time & Materials | 48 | 0.295
0 | 0.148 | 0.807 | Time & Materials | 49 | 0.148
0 | 0.083 | 0.244 | Firm-Fixed-Price | 50 | 0.336
1 | 0.178 | 0.494 | Cost-Plus | 51 | 0.258
1 | 0.277 | 0.212 | Time & Materials | 52 | 0.616
0 | 0.21 | 0.539 | Cost-Plus | 53 | 0.156
1 | 0.139 | 0.244 | Cost-Plus | 54 | 0.422
1 | 0.407 | 0.394 | Time & Materials | 55 | 0.563
0 | 0.072 | 0.773 | Cost-Plus | 56 | 0.068
0 | 0.143 | 0.312 | Firm-Fixed-Price | 57 | 0.488
0 | 0.247 | 0.589 | Firm-Fixed-Price | 58 | 0.327
1 | 0.129 | 0.256 | Firm-Fixed-Price | 59 | 0.509
1 | 0.225 | 0.382 | Firm-Fixed-Price | 60 | 0.565
1 | 0.032 | 0.176 | Firm-Fixed-Price | 61 | 0.477
0 | 0.251 | 0.474 | Firm-Fixed-Price | 62 | 0.324
1 | 0.138 | 0.655 | Cost-Plus | 63 | 0.157
1 | 0.202 | 0.439 | Firm-Fixed-Price | 64 | 0.475
0 | 0.23 | 0.391 | Firm-Fixed-Price | 65 | 0.379
0 | 0.087 | 0.727 | Time & Materials | 66 | 0.071
0 | 0.12 | 0.426 | Firm-Fixed-Price | 67 | 0.352
0 | 0.291 | 0.641 | Cost-Plus | 68 | 0.113
1 | 0.125 | 0.367 | Firm-Fixed-Price | 69 | 0.462
1 | 0.142 | 0.88 | Cost-Plus | 70 | 0.131
0 | 0.159 | 0.624 | Time & Materials | 71 | 0.23
0 | 0.327 | 0.58 | Firm-Fixed-Price | 72 | 0.245
0 | 0.393 | 0.202 | Firm-Fixed-Price | 73 | 0.486
0 | 0.048 | 0.857 | Cost-Plus | 74 | 0.037
0 | 0.301 | 0.719 | Time & Materials | 75 | 0.14
0 | 0.031 | 0.364 | Time & Materials | 76 | 0.253
0 | 0.133 | 0.298 | Time & Materials | 77 | 0.267
1 | 0.699 | 0.224 | Firm-Fixed-Price | 78 | 0.76
0 | 0.09 | 0.618 | Firm-Fixed-Price | 79 | 0.14
0 | 0.189 | 0.038 | Firm-Fixed-Price | 80 | 0.597
0 | 0.051 | 0.833 | Cost-Plus | 81 | 0.033
1 | 0.332 | 0.791 | Time & Materials | 82 | 0.296
1 | 0.266 | 0.428 | Firm-Fixed-Price | 83 | 0.601
1 | 0.268 | 0.172 | Firm-Fixed-Price | 84 | 0.778
1 | 0.331 | 0.674 | Firm-Fixed-Price | 85 | 0.381
1 | 0.244 | 0.005 | Firm-Fixed-Price | 86 | 0.494
1 | 0.172 | 0.305 | Time & Materials | 87 | 0.473
0 | 0.182 | 0.393 | Time & Materials | 88 | 0.401
1 | 0.292 | 0.484 | Cost-Plus | 89 | 0.359
0 | 0.344 | 0.91 | Time & Materials | 90 | 0.15
1 | 0.052 | 0.243 | Firm-Fixed-Price | 91 | 0.491
1 | 0.119 | 0.247 | Time & Materials | 92 | 0.528
0 | 0.093 | 0.651 | Time & Materials | 93 | 0.111
1 | 0.055 | 0.236 | Time & Materials | 94 | 0.461
1 | 0.079 | 0.554 | Time & Materials | 95 | 0.33
0 | 0.275 | 0.48 | Time & Materials | 96 | 0.337
0 | 0.119 | 0.622 | Time & Materials | 97 | 0.342
1 | 0.147 | 0.409 | Time & Materials | 98 | 0.428
1 | 0.55 | 0.342 | Firm-Fixed-Price | 99 | 0.666
1 | 0.162 | 0.273 | Firm-Fixed-Price | 100 | 0.594
1 | 0.224 | 0.595 | Firm-Fixed-Price | 101 | 0.336
0 | 0.126 | 0.479 | Time & Materials | 102 | 0.173
1 | 0.049 | 0.45 | Firm-Fixed-Price | 103 | 0.403
0 | 0.057 | 0.176 | Time & Materials | 104 | 0.254
0 | 0.103 | 0.542 | Cost-Plus | 105 | 0.109
0 | 0.372 | 0.371 | Firm-Fixed-Price | 106 | 0.399
0 | 0.135 | 0.281 | Time & Materials | 107 | 0.375
1 | 0.712 | 0.369 | Time & Materials | 108 | 0.595
0 | 0.257 | 0.498 | Firm-Fixed-Price | 109 | 0.37
1 | 0.159 | 0.121 | Firm-Fixed-Price | 110 | 0.632
1 | 0.071 | 0.228 | Firm-Fixed-Price | 111 | 0.572
1 | 0.358 | 0.255 | Firm-Fixed-Price | 112 | 0.742
1 | 0.056 | 0.579 | Cost-Plus | 113 | 0.123
0 | 0.094 | 0.294 | Cost-Plus | 114 | 0.135
0 | 0.318 | 0.306 | Time & Materials | 115 | 0.322
0 | 0.056 | 0.736 | Cost-Plus | 116 | 0.04
0 | 0.159 | 0.413 | Cost-Plus | 117 | 0.115
1 | 0.185 | 0.688 | Firm-Fixed-Price | 118 | 0.383
1 | 0.172 | 0.201 | Cost-Plus | 119 | 0.434
1 | 0.204 | 0.558 | Time & Materials | 120 | 0.371
0 | 0.203 | 0.337 | Cost-Plus | 121 | 0.19
0 | 0.05 | 0.783 | Cost-Plus | 122 | 0.074
0 | 0.204 | 0.34 | Firm-Fixed-Price | 123 | 0.403
1 | 0.185 | 0.54 | Firm-Fixed-Price | 124 | 0.523
0 | 0.14 | 0.374 | Firm-Fixed-Price | 125 | 0.359
0 | 0.357 | 0.505 | Time & Materials | 126 | 0.291
0 | 0.06 | 0.418 | Cost-Plus | 127 | 0.1
0 | 0.021 | 0.774 | Cost-Plus | 128 | 0.022
1 | 0.292 | 0.164 | Firm-Fixed-Price | 129 | 0.685
1 | 0.17 | 0.666 | Time & Materials | 130 | 0.401
1 | 0.272 | 0.248 | Time & Materials | 131 | 0.607
0 | 0.253 | 0.177 | Firm-Fixed-Price | 132 | 0.594
1 | 0.586 | 0.32 | Firm-Fixed-Price | 133 | 0.8
1 | 0.233 | 0.341 | Firm-Fixed-Price | 134 | 0.609
1 | 0.16 | 0.365 | Cost-Plus | 135 | 0.292
1 | 0.15 | 0.58 | Firm-Fixed-Price | 136 | 0.399
0 | 0.091 | 0.297 | Time & Materials | 137 | 0.241
0 | 0.761 | 0.516 | Time & Materials | 138 | 0.414
1 | 0.597 | 0.771 | Firm-Fixed-Price | 139 | 0.638
1 | 0.07 | 0.584 | Cost-Plus | 140 | 0.157
0 | 0.152 | 0.519 | Cost-Plus | 141 | 0.103
1 | 0.206 | 0.392 | Firm-Fixed-Price | 142 | 0.566
1 | 0.241 | 0.506 | Time & Materials | 143 | 0.439
1 | 0.696 | 0.276 | Firm-Fixed-Price | 144 | 0.655
1 | 0.3 | 0.364 | Firm-Fixed-Price | 145 | 0.42
1 | 0.2 | 0.621 | Firm-Fixed-Price | 146 | 0.414
0 | 0.094 | 0.626 | Time & Materials | 147 | 0.107
1 | 0.104 | 0.128 | Time & Materials | 148 | 0.463
1 | 0.107 | 0.7 | Firm-Fixed-Price | 149 | 0.362
1 | 0.522 | 0.33 | Firm-Fixed-Price | 150 | 0.666
0 | 0.282 | 0.809 | Cost-Plus | 151 | 0.126
0 | 0.201 | 0.228 | Firm-Fixed-Price | 152 | 0.492
0 | 0.294 | 0.334 | Firm-Fixed-Price | 153 | 0.483
1 | 0.112 | 0.236 | Time & Materials | 154 | 0.513
1 | 0.075 | 0.826 | Cost-Plus | 155 | 0.072
1 | 0.192 | 0.84 | Firm-Fixed-Price | 156 | 0.448
1 | 0.238 | 0.172 | Time & Materials | 157 | 0.546
0 | 0.088 | 0.219 | Time & Materials | 158 | 0.342
0 | 0.287 | 0.504 | Firm-Fixed-Price | 159 | 0.296
0 | 0.143 | 0.452 | Time & Materials | 160 | 0.145
1 | 0.151 | 0.082 | Firm-Fixed-Price | 161 | 0.73
0 | 0.164 | 0.196 | Time & Materials | 162 | 0.369
1 | 0.18 | 0.285 | Time & Materials | 163 | 0.394
0 | 0.272 | 0.582 | Time & Materials | 164 | 0.173
0 | 0.076 | 0.427 | Firm-Fixed-Price | 165 | 0.398
0 | 0.311 | 0.801 | Cost-Plus | 166 | 0.057
0 | 0.089 | 0.168 | Firm-Fixed-Price | 167 | 0.568
0 | 0.282 | 0.23 | Firm-Fixed-Price | 168 | 0.42
1 | 0.136 | 0.251 | Firm-Fixed-Price | 169 | 0.645
1 | 0.007 | 0.48 | Time & Materials | 170 | 0.237
1 | 0.212 | 0.029 | Time & Materials | 171 | 0.659
1 | 0.396 | 0.22 | Firm-Fixed-Price | 172 | 0.668
1 | 0.123 | 0.261 | Time & Materials | 173 | 0.439
0 | 0.214 | 0.069 | Firm-Fixed-Price | 174 | 0.544
1 | 0.209 | 0.569 | Time & Materials | 175 | 0.272
1 | 0.537 | 0.533 | Firm-Fixed-Price | 176 | 0.681
0 | 0.545 | 0.736 | Time & Materials | 177 | 0.198
1 | 0.229 | 0.437 | Firm-Fixed-Price | 178 | 0.537
0 | 0.592 | 0.86 | Cost-Plus | 179 | 0.072
1 | 0.155 | 0.129 | Firm-Fixed-Price | 180 | 0.435
1 | 0.074 | 0.79 | Firm-Fixed-Price | 181 | 0.303
0 | 0.18 | 0.117 | Firm-Fixed-Price | 182 | 0.701
0 | 0.189 | 0.749 | Cost-Plus | 183 | 0.102
0 | 0.11 | 0.587 | Cost-Plus | 184 | 0.096
0 | 0.071 | 0.543 | Firm-Fixed-Price | 185 | 0.245
0 | 0.181 | 0.48 | Time & Materials | 186 | 0.232
1 | 0.164 | 0.141 | Cost-Plus | 187 | 0.434
1 | 0.246 | 0.36 | Time & Materials | 188 | 0.362
0 | 0.253 | 0.568 | Time & Materials | 189 | 0.296
0 | 0.215 | 0.649 | Firm-Fixed-Price | 190 | 0.348
0 | 0.602 | 0.317 | Firm-Fixed-Price | 191 | 0.626
0 | 0.141 | 0.9 | Cost-Plus | 192 | 0.062
0 | 0.559 | 0.271 | Cost-Plus | 193 | 0.281
0 | 0.2 | 0.249 | Time & Materials | 194 | 0.383
1 | 0.239 | 0.784 | Firm-Fixed-Price | 195 | 0.458
0 | 0.322 | 0.131 | Firm-Fixed-Price | 196 | 0.528
0 | 0.049 | 0.13 | Time & Materials | 197 | 0.262
0 | 0.161 | 0.48 | Cost-Plus | 198 | 0.134
0 | 0.062 | 0.797 | Cost-Plus | 199 | 0.093
0 | 0.099 | 0.449 | Time & Materials | 200 | 0.147

## Regression
Regression Sheet
Instructions: This page shows the resulting regression model and comparison of the model to the participant estimations. Below, the user can exclude any attribute from the model. The graph below shows the model's output compared to the average group response.
Regression Output: |  | R2 = | 0.86883
LINEST Calculation
Application Attributes Influencing Likelihood (Independent Variables) | [10 empty] | Contract Type | Dependency Load on the Critical Path | Schedule Buffer % | Prior Domain Experience | Intercept (b)
Variable | Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type | [5 empty] | Slope | 0.56589 | -0.38996 | 0.35854 | 0.1406 | 0.18474
Type | Binary | Continuous | Continuous | Discrete | [5 empty] | Std Err | 0.040927 | 0.025087 | 0.033982 | 0.010593 | 0.022533
Include? | Include | Include | Include | Include | [5 empty] | R^2, Std Err Y | 0.86883 | 0.072061 | #N/A | #N/A | #N/A
Coeff | 0.1406 | 0.35854 | -0.38996 | 0.56589 | [5 empty] | F, Deg Freedom | 322.896 | 195 | #N/A | #N/A | #N/A
Std Err | 0.010593 | 0.033982 | 0.025087 | 0.040927 | Model Prediction |  |  | Standard Error: | 0.065218 | SSreg, SSresid | 6.7069 | 1.0126 | #N/A | #N/A | #N/A
Index | Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type | Responses (Dependent Variable) | Group Average | Increments | Lower Bound | Upper Bound
1 | 1 | 0.298 | 0.438 | 0.51646 | 0.725 | 0.55364 | 0.01 | -0.097283 | 0.11728
2 | 1 | 0.149 | 0.563 | 0.15271 | 0.214 | 0.24563 | 0.02 | -0.087283 | 0.12728
3 | 1 | 0.049 | 0.233 | 0.33987 | 0.383 | 0.44438 | 0.03 | -0.077283 | 0.13728
4 | 0 | 0.2 | 0.453 | 0.33987 | 0.265 | 0.27213 | 0.04 | -0.067283 | 0.14728
5 | 1 | 0.26 | 0.237 | 0.51646 | 0.628 | 0.6184 | 0.05 | -0.057283 | 0.15728
6 | 1 | 0.169 | 0.173 | 0.51646 | 0.69 | 0.61073 | 0.06 | -0.047283 | 0.16728
7 | 1 | 0.15 | 0.131 | 0.51646 | 0.62 | 0.6203 | 0.07 | -0.037283 | 0.17728
8 | 0 | 0.245 | 0.578 | 0.15271 | 0.135 | 0.13361 | 0.08 | -0.027283 | 0.18728
9 | 1 | 0.139 | 0.661 | 0.33987 | 0.276 | 0.30974 | 0.09 | -0.017283 | 0.19728
10 | 1 | 0.161 | 0.446 | 0.33987 | 0.479 | 0.40147 | 0.1 | -0.0072834 | 0.20728
11 | 1 | 0.292 | 0.52 | 0.51646 | 0.542 | 0.51951 | 0.11 | 0.0027166 | 0.21728
12 | 0 | 0.065 | 0.546 | 0.15271 | 0.053 | 0.081549 | 0.12 | 0.012717 | 0.22728
13 | 0 | 0.151 | 0.449 | 0.15271 | 0.196 | 0.15021 | 0.13 | 0.022717 | 0.23728
14 | 1 | 0.328 | 0.54 | 0.51646 | 0.473 | 0.52462 | 0.14 | 0.032717 | 0.24728
15 | 0 | 0.258 | 0.109 | 0.51646 | 0.485 | 0.527 | 0.15 | 0.042717 | 0.25728
16 | 1 | 0.138 | 0.67 | 0.51646 | 0.357 | 0.4058 | 0.16 | 0.052717 | 0.26728
17 | 1 | 0.058 | 0.393 | 0.51646 | 0.592 | 0.48514 | 0.17 | 0.062717 | 0.27728
18 | 0 | 0.036 | 0.335 | 0.33987 | 0.115 | 0.25934 | 0.18 | 0.072717 | 0.28728
19 | 0 | 0.508 | 0.486 | 0.33987 | 0.584 | 0.36969 | 0.19 | 0.082717 | 0.29728
20 | 0 | 0.324 | 0.285 | 0.51646 | 0.582 | 0.48203 | 0.2 | 0.092717 | 0.30728
21 | 0 | 0.218 | 0.273 | 0.33987 | 0.344 | 0.34877 | 0.21 | 0.10272 | 0.31728
22 | 1 | 0.102 | 0.382 | 0.51646 | 0.507 | 0.50521 | 0.22 | 0.11272 | 0.32728
23 | 1 | 0.292 | 0.281 | 0.51646 | 0.672 | 0.61271 | 0.23 | 0.12272 | 0.33728
24 | 1 | 0.122 | 0.296 | 0.51646 | 0.609 | 0.54591 | 0.24 | 0.13272 | 0.34728
25 | 1 | 0.171 | 0.879 | 0.33987 | 0.251 | 0.2362 | 0.25 | 0.14272 | 0.35728
26 | 1 | 0.284 | 0.495 | 0.33987 | 0.458 | 0.42646 | 0.26 | 0.15272 | 0.36728
27 | 0 | 0.727 | 0.172 | 0.51646 | 0.668 | 0.67059 | 0.27 | 0.16272 | 0.37728
28 | 1 | 0.605 | 0.454 | 0.33987 | 0.51 | 0.55755 | 0.28 | 0.17272 | 0.38728
29 | 0 | 0.026 | 0.266 | 0.33987 | 0.222 | 0.28266 | 0.29 | 0.18272 | 0.39728
30 | 1 | 0.306 | 0.358 | 0.51646 | 0.607 | 0.58771 | 0.3 | 0.19272 | 0.40728
31 | 0 | 0.138 | 0.81 | 0.33987 | 0.174 | 0.11068 | 0.31 | 0.20272 | 0.41728
32 | 1 | 0.049 | 0.016 | 0.51646 | 0.676 | 0.62893 | 0.32 | 0.21272 | 0.42728
33 | 1 | 0.091 | 0.46 | 0.51646 | 0.24 | 0.47084 | 0.33 | 0.22272 | 0.43728
34 | 0 | 0.052 | 0.046 | 0.15271 | 0.274 | 0.27187 | 0.34 | 0.23272 | 0.44728
35 | 1 | 0.101 | 0.885 | 0.15271 | 0.105 | 0.10286 | 0.35 | 0.24272 | 0.45728
36 | 0 | 0.74 | 0.483 | 0.15271 | 0.221 | 0.34813 | 0.36 | 0.25272 | 0.46728
37 | 1 | 0.133 | 0.32 | 0.51646 | 0.526 | 0.5405 | 0.37 | 0.26272 | 0.47728
38 | 1 | 0.314 | 0.537 | 0.51646 | 0.642 | 0.52077 | 0.38 | 0.27272 | 0.48728
39 | 0 | 0.357 | 0.098 | 0.33987 | 0.541 | 0.46686 | 0.39 | 0.28272 | 0.49728
40 | 1 | 0.319 | 0.275 | 0.33987 | 0.463 | 0.52481 | 0.4 | 0.29272 | 0.50728
41 | 0 | 0.265 | 0.472 | 0.51646 | 0.419 | 0.38795 | 0.41 | 0.30272 | 0.51728
42 | 0 | 0.173 | 0.479 | 0.33987 | 0.174 | 0.25231 | 0.42 | 0.31272 | 0.52728
43 | 0 | 0.267 | 0.299 | 0.51646 | 0.346 | 0.45613 | 0.43 | 0.32272 | 0.53728
44 | 0 | 0.229 | 0.827 | 0.15271 | 0.059 | 0.03077 | 0.44 | 0.33272 | 0.54728
45 | 1 | 0.232 | 0.189 | 0.51646 | 0.727 | 0.62708 | 0.45 | 0.34272 | 0.55728
46 | 0 | 0.179 | 0.224 | 0.33987 | 0.41 | 0.3539 | 0.46 | 0.35272 | 0.56728
47 | 1 | 0.181 | 0.038 | 0.51646 | 0.737 | 0.66768 | 0.47 | 0.36272 | 0.57728
48 | 0 | 0.211 | 0.466 | 0.33987 | 0.295 | 0.271 | 0.48 | 0.37272 | 0.58728
49 | 0 | 0.148 | 0.807 | 0.33987 | 0.148 | 0.11544 | 0.49 | 0.38272 | 0.59728
50 | 0 | 0.083 | 0.244 | 0.51646 | 0.336 | 0.41161 | 0.5 | 0.39272 | 0.60728
51 | 1 | 0.178 | 0.494 | 0.15271 | 0.258 | 0.28294 | 0.51 | 0.40272 | 0.61728
52 | 1 | 0.277 | 0.212 | 0.33987 | 0.616 | 0.53431 | 0.52 | 0.41272 | 0.62728
53 | 0 | 0.21 | 0.539 | 0.15271 | 0.156 | 0.13627 | 0.53 | 0.42272 | 0.63728
54 | 1 | 0.139 | 0.244 | 0.15271 | 0.422 | 0.36645 | 0.54 | 0.43272 | 0.64728
55 | 1 | 0.407 | 0.394 | 0.33987 | 0.563 | 0.50995 | 0.55 | 0.44272 | 0.65728
56 | 0 | 0.072 | 0.773 | 0.15271 | 0.068 | 0.0001 | 0.56 | 0.45272 | 0.66728
57 | 0 | 0.143 | 0.312 | 0.51646 | 0.488 | 0.4066 | 0.57 | 0.46272 | 0.67728
58 | 0 | 0.247 | 0.589 | 0.51646 | 0.327 | 0.33587 | 0.58 | 0.47272 | 0.68728
59 | 1 | 0.129 | 0.256 | 0.51646 | 0.509 | 0.56402 | 0.59 | 0.48272 | 0.69728
60 | 1 | 0.225 | 0.382 | 0.51646 | 0.565 | 0.54931 | 0.6 | 0.49272 | 0.70728
61 | 1 | 0.032 | 0.176 | 0.51646 | 0.477 | 0.56044 | 0.61 | 0.50272 | 0.71728
62 | 0 | 0.251 | 0.474 | 0.51646 | 0.324 | 0.38215 | 0.62 | 0.51272 | 0.72728
63 | 1 | 0.138 | 0.655 | 0.15271 | 0.157 | 0.20581 | 0.63 | 0.52272 | 0.73728
64 | 1 | 0.202 | 0.439 | 0.51646 | 0.475 | 0.51883 | 0.64 | 0.53272 | 0.74728
65 | 0 | 0.23 | 0.391 | 0.51646 | 0.379 | 0.40699 | 0.65 | 0.54272 | 0.75728
66 | 0 | 0.087 | 0.727 | 0.33987 | 0.071 | 0.12476 | 0.66 | 0.55272 | 0.76728
67 | 0 | 0.12 | 0.426 | 0.51646 | 0.352 | 0.3539 | 0.67 | 0.56272 | 0.77728
68 | 0 | 0.291 | 0.641 | 0.15271 | 0.113 | 0.12553 | 0.68 | 0.57272 | 0.78728
69 | 1 | 0.125 | 0.367 | 0.51646 | 0.462 | 0.5193 | 0.69 | 0.58272 | 0.79728
70 | 1 | 0.142 | 0.88 | 0.15271 | 0.131 | 0.11951 | 0.7 | 0.59272 | 0.80728
71 | 0 | 0.159 | 0.624 | 0.33987 | 0.23 | 0.19074 | 0.71 | 0.60272 | 0.81728
72 | 0 | 0.327 | 0.58 | 0.51646 | 0.245 | 0.36807 | 0.72 | 0.61272 | 0.82728
73 | 0 | 0.393 | 0.202 | 0.51646 | 0.486 | 0.53914 | 0.73 | 0.62272 | 0.83728
74 | 0 | 0.048 | 0.857 | 0.15271 | 0.037 | 0.0001 | 0.74 | 0.63272 | 0.84728
75 | 0 | 0.301 | 0.719 | 0.33987 | 0.14 | 0.20461 | 0.75 | 0.64272 | 0.85728
76 | 0 | 0.031 | 0.364 | 0.33987 | 0.253 | 0.24624 | 0.76 | 0.65272 | 0.86728
77 | 0 | 0.133 | 0.298 | 0.33987 | 0.267 | 0.30855 | 0.77 | 0.66272 | 0.87728
78 | 1 | 0.699 | 0.224 | 0.51646 | 0.76 | 0.78087 | 0.78 | 0.67272 | 0.88728
79 | 0 | 0.09 | 0.618 | 0.51646 | 0.14 | 0.26827 | 0.79 | 0.68272 | 0.89728
80 | 0 | 0.189 | 0.038 | 0.51646 | 0.597 | 0.52995 | 0.8 | 0.69272 | 0.90728
81 | 0 | 0.051 | 0.833 | 0.15271 | 0.033 | 0.0001 | 0.81 | 0.70272 | 0.91728
82 | 1 | 0.332 | 0.791 | 0.33987 | 0.296 | 0.32825 | 0.82 | 0.71272 | 0.92728
83 | 1 | 0.266 | 0.428 | 0.51646 | 0.601 | 0.54607 | 0.83 | 0.72272 | 0.93728
84 | 1 | 0.268 | 0.172 | 0.51646 | 0.778 | 0.64662 | 0.84 | 0.73272 | 0.94728
85 | 1 | 0.331 | 0.674 | 0.51646 | 0.381 | 0.47344 | 0.85 | 0.74272 | 0.95728
86 | 1 | 0.244 | 0.005 | 0.51646 | 0.494 | 0.70313 | 0.86 | 0.75272 | 0.96728
87 | 1 | 0.172 | 0.305 | 0.33987 | 0.473 | 0.4604 | 0.87 | 0.76272 | 0.97728
88 | 0 | 0.182 | 0.393 | 0.33987 | 0.401 | 0.28907 | 0.88 | 0.77272 | 0.98728
89 | 1 | 0.292 | 0.484 | 0.15271 | 0.359 | 0.32771 | 0.89 | 0.78272 | 0.99728
90 | 0 | 0.344 | 0.91 | 0.33987 | 0.15 | 0.14554 | 0.9 | 0.79272 | 1.0073
91 | 1 | 0.052 | 0.243 | 0.51646 | 0.491 | 0.54148 | 0.91 | 0.80272 | 1.0173
92 | 1 | 0.119 | 0.247 | 0.33987 | 0.528 | 0.46402 | 0.92 | 0.81272 | 1.0273
93 | 0 | 0.093 | 0.651 | 0.33987 | 0.111 | 0.15655 | 0.93 | 0.82272 | 1.0373
94 | 1 | 0.055 | 0.236 | 0.33987 | 0.461 | 0.44536 | 0.94 | 0.83272 | 1.0473
95 | 1 | 0.079 | 0.554 | 0.33987 | 0.33 | 0.32996 | 0.95 | 0.84272 | 1.0573
96 | 0 | 0.275 | 0.48 | 0.33987 | 0.337 | 0.28849 | 0.96 | 0.85272 | 1.0673
97 | 0 | 0.119 | 0.622 | 0.33987 | 0.342 | 0.17718 | 0.97 | 0.86272 | 1.0773
98 | 1 | 0.147 | 0.409 | 0.33987 | 0.428 | 0.41088 | 0.98 | 0.87272 | 1.0873
99 | 1 | 0.55 | 0.342 | 0.51646 | 0.666 | 0.68143 | 0.99 | 0.88272 | 1.0973
100 | 1 | 0.162 | 0.273 | 0.51646 | 0.594 | 0.56922 | 1 | 0.89272 | 1.1073
101 | 1 | 0.224 | 0.595 | 0.51646 | 0.336 | 0.46589
102 | 0 | 0.126 | 0.479 | 0.33987 | 0.173 | 0.23546
103 | 1 | 0.049 | 0.45 | 0.51646 | 0.403 | 0.45968
104 | 0 | 0.057 | 0.176 | 0.33987 | 0.254 | 0.32888
105 | 0 | 0.103 | 0.542 | 0.15271 | 0.109 | 0.096733
106 | 0 | 0.372 | 0.371 | 0.51646 | 0.399 | 0.4657
107 | 0 | 0.135 | 0.281 | 0.33987 | 0.375 | 0.3159
108 | 1 | 0.712 | 0.369 | 0.33987 | 0.595 | 0.62906
109 | 0 | 0.257 | 0.498 | 0.51646 | 0.37 | 0.37495
110 | 1 | 0.159 | 0.121 | 0.51646 | 0.632 | 0.62742
111 | 1 | 0.071 | 0.228 | 0.51646 | 0.572 | 0.55414
112 | 1 | 0.358 | 0.255 | 0.51646 | 0.742 | 0.64652
113 | 1 | 0.056 | 0.579 | 0.15271 | 0.123 | 0.20605
114 | 0 | 0.094 | 0.294 | 0.15271 | 0.135 | 0.19022
115 | 0 | 0.318 | 0.306 | 0.33987 | 0.322 | 0.37176
116 | 0 | 0.056 | 0.736 | 0.15271 | 0.04 | 0.004229
117 | 0 | 0.159 | 0.413 | 0.15271 | 0.115 | 0.16712
118 | 1 | 0.185 | 0.688 | 0.51646 | 0.383 | 0.41564
119 | 1 | 0.172 | 0.201 | 0.15271 | 0.434 | 0.39505
120 | 1 | 0.204 | 0.558 | 0.33987 | 0.371 | 0.37321
121 | 0 | 0.203 | 0.337 | 0.15271 | 0.19 | 0.21253
122 | 0 | 0.05 | 0.783 | 0.15271 | 0.074 | 0.0001
123 | 0 | 0.204 | 0.34 | 0.51646 | 0.403 | 0.41756
124 | 1 | 0.185 | 0.54 | 0.51646 | 0.523 | 0.47335
125 | 0 | 0.14 | 0.374 | 0.51646 | 0.359 | 0.38135
126 | 0 | 0.357 | 0.505 | 0.33987 | 0.291 | 0.30814
127 | 0 | 0.06 | 0.418 | 0.15271 | 0.1 | 0.12967
128 | 0 | 0.021 | 0.774 | 0.15271 | 0.022 | 0.0001
129 | 1 | 0.292 | 0.164 | 0.51646 | 0.685 | 0.65834
130 | 1 | 0.17 | 0.666 | 0.33987 | 0.401 | 0.31891
131 | 1 | 0.272 | 0.248 | 0.33987 | 0.607 | 0.51848
132 | 0 | 0.253 | 0.177 | 0.51646 | 0.594 | 0.49869
133 | 1 | 0.586 | 0.32 | 0.51646 | 0.8 | 0.70292
134 | 1 | 0.233 | 0.341 | 0.51646 | 0.609 | 0.56816
135 | 1 | 0.16 | 0.365 | 0.15271 | 0.292 | 0.32679
136 | 1 | 0.15 | 0.58 | 0.51646 | 0.399 | 0.4452
137 | 0 | 0.091 | 0.297 | 0.33987 | 0.241 | 0.29388
138 | 0 | 0.761 | 0.516 | 0.33987 | 0.414 | 0.4487
139 | 1 | 0.597 | 0.771 | 0.51646 | 0.638 | 0.53099
140 | 1 | 0.07 | 0.584 | 0.15271 | 0.157 | 0.20912
141 | 0 | 0.152 | 0.519 | 0.15271 | 0.103 | 0.12327
142 | 1 | 0.206 | 0.392 | 0.51646 | 0.566 | 0.53859
143 | 1 | 0.241 | 0.506 | 0.33987 | 0.439 | 0.40676
144 | 1 | 0.696 | 0.276 | 0.51646 | 0.655 | 0.75952
145 | 1 | 0.3 | 0.364 | 0.51646 | 0.42 | 0.58322
146 | 1 | 0.2 | 0.621 | 0.51646 | 0.414 | 0.44714
147 | 0 | 0.094 | 0.626 | 0.33987 | 0.107 | 0.16666
148 | 1 | 0.104 | 0.128 | 0.33987 | 0.463 | 0.50504
149 | 1 | 0.107 | 0.7 | 0.51646 | 0.362 | 0.38299
150 | 1 | 0.522 | 0.33 | 0.51646 | 0.666 | 0.67607
151 | 0 | 0.282 | 0.809 | 0.15271 | 0.126 | 0.056793
152 | 0 | 0.201 | 0.228 | 0.51646 | 0.492 | 0.46016
153 | 0 | 0.294 | 0.334 | 0.51646 | 0.483 | 0.45217
154 | 1 | 0.112 | 0.236 | 0.33987 | 0.513 | 0.4658
155 | 1 | 0.075 | 0.826 | 0.15271 | 0.072 | 0.11654
156 | 1 | 0.192 | 0.84 | 0.51646 | 0.448 | 0.35887
157 | 1 | 0.238 | 0.172 | 0.33987 | 0.546 | 0.53593
158 | 0 | 0.088 | 0.219 | 0.33987 | 0.342 | 0.32322
159 | 0 | 0.287 | 0.504 | 0.51646 | 0.296 | 0.38336
160 | 0 | 0.143 | 0.452 | 0.33987 | 0.145 | 0.25208
161 | 1 | 0.151 | 0.082 | 0.51646 | 0.73 | 0.63976
162 | 0 | 0.164 | 0.196 | 0.33987 | 0.369 | 0.35944
163 | 1 | 0.18 | 0.285 | 0.33987 | 0.394 | 0.47107
164 | 0 | 0.272 | 0.582 | 0.33987 | 0.173 | 0.24764
165 | 0 | 0.076 | 0.427 | 0.51646 | 0.398 | 0.33774
166 | 0 | 0.311 | 0.801 | 0.15271 | 0.057 | 0.07031
167 | 0 | 0.089 | 0.168 | 0.51646 | 0.568 | 0.4434
168 | 0 | 0.282 | 0.23 | 0.51646 | 0.42 | 0.48842
169 | 1 | 0.136 | 0.251 | 0.51646 | 0.645 | 0.56848
170 | 1 | 0.007 | 0.48 | 0.33987 | 0.237 | 0.333
171 | 1 | 0.212 | 0.029 | 0.33987 | 0.659 | 0.58237
172 | 1 | 0.396 | 0.22 | 0.51646 | 0.668 | 0.67379
173 | 1 | 0.123 | 0.261 | 0.33987 | 0.439 | 0.45999
174 | 0 | 0.214 | 0.069 | 0.51646 | 0.544 | 0.52682
175 | 1 | 0.209 | 0.569 | 0.33987 | 0.272 | 0.37072
176 | 1 | 0.537 | 0.533 | 0.51646 | 0.681 | 0.60229
177 | 0 | 0.545 | 0.736 | 0.33987 | 0.198 | 0.28547
178 | 1 | 0.229 | 0.437 | 0.51646 | 0.537 | 0.52929
179 | 0 | 0.592 | 0.86 | 0.15271 | 0.072 | 0.14805
180 | 1 | 0.155 | 0.129 | 0.51646 | 0.435 | 0.62287
181 | 1 | 0.074 | 0.79 | 0.51646 | 0.303 | 0.33606
182 | 0 | 0.18 | 0.117 | 0.51646 | 0.701 | 0.49591
183 | 0 | 0.189 | 0.749 | 0.15271 | 0.102 | 0.046846
184 | 0 | 0.11 | 0.587 | 0.15271 | 0.096 | 0.081695
185 | 0 | 0.071 | 0.543 | 0.51646 | 0.245 | 0.29071
186 | 0 | 0.181 | 0.48 | 0.33987 | 0.232 | 0.25479
187 | 1 | 0.164 | 0.141 | 0.15271 | 0.434 | 0.41558
188 | 1 | 0.246 | 0.36 | 0.33987 | 0.362 | 0.46548
189 | 0 | 0.253 | 0.568 | 0.33987 | 0.296 | 0.24628
190 | 0 | 0.215 | 0.649 | 0.51646 | 0.348 | 0.301
191 | 0 | 0.602 | 0.317 | 0.51646 | 0.626 | 0.56923
192 | 0 | 0.141 | 0.9 | 0.15271 | 0.062 | 0.0001
193 | 0 | 0.559 | 0.271 | 0.15271 | 0.281 | 0.36591
194 | 0 | 0.2 | 0.249 | 0.33987 | 0.383 | 0.35168
195 | 1 | 0.239 | 0.784 | 0.51646 | 0.458 | 0.39756
196 | 0 | 0.322 | 0.131 | 0.51646 | 0.528 | 0.54137
197 | 0 | 0.049 | 0.13 | 0.33987 | 0.262 | 0.34395
198 | 0 | 0.161 | 0.48 | 0.15271 | 0.134 | 0.14171
199 | 0 | 0.062 | 0.797 | 0.15271 | 0.093 | 0.0001
200 | 0 | 0.099 | 0.449 | 0.33987 | 0.147 | 0.23747

## Calculator
Calculator | [5 empty] | Model Calculations →
Instructions: In each row, choose values for categorical variables using the drop-downs (e.g., Prior Domain Experience, Contract Type) and enter numeric values for continuous variables such as Schedule Buffer and Dependency Load. The sheet returns the predicted probability of on-time project delivery. See the Codification and Model Design tabs for variable encoding and definitions, and the Regression tab for coefficients and model settings. The calculation cells to the right (click + to expand) are copy-ready for use in another model. To modify this model, edit it on the Regression tab.
Index | Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type | Model Value |  | Prior Domain Experience | Schedule Buffer % | Dependency Load on the Critical Path | Contract Type | Intercept
1 | No | 10% | 0.2 | Firm-Fixed-Price | 43.49% |  | 0 | 0.035854 | -0.077993 | 0.29226 | 0.18474
2 | Yes | 5% | 0.5 | Time & Materials | 34.06% |  | 0.1406 | 0.017927 | -0.19498 | 0.19233 | 0.18474
3 | No | 5% | 0.8 | Time & Materials | 8.303% |  | 0 | 0.017927 | -0.31197 | 0.19233 | 0.18474
4 | Yes | 18% | 0.3 | Cost-Plus | 35.93% |  | 0.1406 | 0.064538 | -0.11699 | 0.08642 | 0.18474
5 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
6 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
7 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
8 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
9 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
10 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
11 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
12 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
13 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
14 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
15 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
16 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
17 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
18 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
19 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
20 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
21 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
22 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
23 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
24 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
25 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
26 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
27 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
28 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
29 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
30 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
31 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
32 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
33 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
34 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
35 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
36 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
37 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
38 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
39 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
40 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
41 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
42 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
43 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
44 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
45 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
46 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
47 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
48 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
49 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
50 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
51 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
52 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
53 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
54 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
55 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
56 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
57 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
58 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
59 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
60 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
61 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
62 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
63 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
64 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
65 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
66 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
67 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
68 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
69 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
70 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
71 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
72 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
73 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
74 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
75 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
76 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
77 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
78 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
79 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
80 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
81 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
82 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
83 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
84 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
85 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
86 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
87 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
88 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
89 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
90 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
91 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
92 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
93 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
94 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
95 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
96 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
97 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
98 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
99 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
100 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
101 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
102 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
103 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
104 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
105 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
106 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
107 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
108 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
109 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
110 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
111 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
112 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
113 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
114 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
115 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
116 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
117 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
118 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
119 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
120 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
121 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
122 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
123 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
124 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
125 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
126 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
127 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
128 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
129 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
130 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
131 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
132 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
133 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
134 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
135 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
136 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
137 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
138 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
139 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
140 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
141 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
142 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
143 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
144 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
145 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
146 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
147 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
148 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
149 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
150 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
151 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
152 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
153 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
154 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
155 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
156 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
157 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
158 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
159 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
160 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
161 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
162 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
163 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
164 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
165 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
166 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
167 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
168 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
169 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
170 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
171 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
172 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
173 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
174 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
175 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
176 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
177 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
178 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
179 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
180 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
181 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
182 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
183 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
184 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
185 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
186 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
187 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
188 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
189 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
190 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
191 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
192 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
193 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
194 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
195 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
196 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
197 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
198 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
199 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474
200 |  |  |  |  | 18.47% |  | 0 | 0 | 0 |  | 0.18474