## Gantt
Monte Carlo Gantt With Critical Path Analysis
This model is a Monte Carlo Simulation Gantt chart with 1000 trials of different uncertain task durations. Tasks are listed along with their minimum and maximum duration and any prerequisite tasks they may have. This simulation dynamically updates the critical path (Trial CP) for each trial (scenario) and the percentage of times a given task is computed (% CP or "criticality"). Critical path tasks for the trial are shown in red in the Gantt chart bars. The expected marginal contribution to duration (EMCD) of a task is the chance that it is on the critical path times the contribution to duration when it is on the critical path. Recalculate the sheet after updating task details by pressing the F9 key or using "Calculate Now" in the Formulas Ribbon.
Additional Metrics
Trial # | 568 | [27 empty] | Forecasted Cost (without risks) | [6 empty] | 1500000
[29 empty] | Expected Costs with Risks | [6 empty] | 2813162.68
Critical Path: |  | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a | [26 empty] | Expected Costs with Mitigated Risks | [6 empty] | 2675196.3344
[29 empty] | Risk Adjusted Timeline | [6 empty] | 55.3796 |  |  |  |  | Model # |  | 1
Duration Percentile: |  | 50% | 55.152
Critical Path Identification
Task Number | Task ID | Prerequisites | Min (Weeks) | Max (Weeks) | Actual | Delay | Start | End | Trial CP | % CP | EMCD | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 |  |  | Task# | Task Name | Prerequisites | Start | End | Latest Prereq Task # | Latest Prereq Task Name | Critical Path
1 | 1.a |  | 3 | 5 | 4.4942 | 1.7962 | 0 | 6.2904 | CP | 0% | 2.4674 | 1: 2; 2: 2; 3: 2; 4: 2; 5: 2; 6: 2; 7: 2 |  |  | 20 | 9.a | 7.a, 8.a, 8.b | 48.7431 | 54.5923 | #NAME? | #NAME? | 9.a
2 | 1.b |  | 5 | 11 | 5.8194 | 0 | 0 | 5.8194 |  | 0% | 0 | [72 empty] | 19 | 8.b | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 8.b -> 9.a | bar: 1 to 6
3 | 1.c |  | 6 | 10 | 6.1225 | 0 | 0 | 6.1225 |  | 0% | 0 | [72 empty] | #NAME? | 6.a | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 6.a -> 8.b -> 9.a | bar: 1 to 7
4 | 2.a |  | 8 | 12 | 11.5411 | 0 | 0 | 11.5411 |  | 0% | 0 | [72 empty] | #NAME? | 4.a | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 4.a -> 6.a -> 8.b -> 9.a | bar: 1 to 12
5 | 2.b | 1.a | 7 | 13 | 10.316 | 0 | #NAME? | #NAME? | CP | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | 3.a | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 3.a -> 4.a -> 6.a -> 8.b -> 9.a
6 | 2.c |  | 6 | 12 | 11.6292 | 0 | 0 | 11.6292 |  | 0% | 0 | [72 empty] | #NAME? | 2.b | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a | bar: 1 to 12
7 | 2.d |  | 11 | 16 | 15.6365 | 0 | 0 | 15.6365 |  | 0% | 0 | [72 empty] | #NAME? | 1.a | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a | bar: 1 to 16
8 | 3.a | 2.a, 2.b, 2.c, 2.d | 4 | 9 | 8.905 | 0 | #NAME? | #NAME? | CP | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
9 | 3.b | 2.b, 1.a | 4 | 12 | 10.4459 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
10 | 4.a | 1.a, 2.b, 3.a, 1.b | 4 | 9 | 6.2949 | 0 | #NAME? | #NAME? | CP | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
11 | 4.b | 1.a, 2.b, 3.a, 1.b | 4 | 15 | 5.4884 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
12 | 4.c | 1.a, 2.b, 3.a, 1.b | 4 | 9 | 5.6224 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
13 | 5.a | 2.b, 1.a | 11 | 16 | 11.7843 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
14 | 5.b | 2.b | 4 | 9 | 5.6508 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
15 | 6.a | 4.a, 4.b, 4.c | 4 | 15 | 12.7407 | 0 | #NAME? | #NAME? | CP | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
16 | 6.b | 4.a, 4.b, 4.c | 4 | 9 | 6.7263 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
17 | 7.a | 5.a,5.b | 4 | 13 | 12.1702 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
18 | 8.a | 7.a | 4 | 12 | 7.58 | 0 | #NAME? | #NAME? |  | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
19 | 8.b | 6.a,6.b | 4 | 9 | 4.1962 | 0 | #NAME? | #NAME? | CP | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
20 | 9.a | 7.a, 8.a, 8.b | 4 | 8 | 5.8492 | 0 | #NAME? | #NAME? | CP | 0% | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
21 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
22 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
23 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
24 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
25 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
26 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
27 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
28 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
29 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
30 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
31 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
32 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
33 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
34 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
35 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
36 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
37 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
38 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
39 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
40 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
41 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
42 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
43 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
44 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
45 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
46 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
47 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
48 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
49 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
50 | [83 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a
Expand for more space to extend the task list.
Main Simulations | [6 empty] | Data for Chart |  |  |  |  | 1: Task Contribution to Duration Simulations
Trial | Weeks Dur. | Critical Path | Inherent | Residual |  |  | Weeks | T > W | Distribution |  |  | 1: Task ID; 3: Duration if on CP; 5: For Trial # →
Current Trial -> | 54.5923 | 1.a -> 2.b -> 3.a -> 4.a -> 6.a -> 8.b -> 9.a | 241345.8361 | 241345.8361 |  |  | 44 | 0 | 0 |  |  |  | Current Trial ↓ |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492 | 493 | 494 | 495 | 496 | 497 | 498 | 499 | 500 | 501 | 502 | 503 | 504 | 505 | 506 | 507 | 508 | 509 | 510 | 511 | 512 | 513 | 514 | 515 | 516 | 517 | 518 | 519 | 520 | 521 | 522 | 523 | 524 | 525 | 526 | 527 | 528 | 529 | 530 | 531 | 532 | 533 | 534 | 535 | 536 | 537 | 538 | 539 | 540 | 541 | 542 | 543 | 544 | 545 | 546 | 547 | 548 | 549 | 550 | 551 | 552 | 553 | 554 | 555 | 556 | 557 | 558 | 559 | 560 | 561 | 562 | 563 | 564 | 565 | 566 | 567 | 568 | 569 | 570 | 571 | 572 | 573 | 574 | 575 | 576 | 577 | 578 | 579 | 580 | 581 | 582 | 583 | 584 | 585 | 586 | 587 | 588 | 589 | 590 | 591 | 592 | 593 | 594 | 595 | 596 | 597 | 598 | 599 | 600 | 601 | 602 | 603 | 604 | 605 | 606 | 607 | 608 | 609 | 610 | 611 | 612 | 613 | 614 | 615 | 616 | 617 | 618 | 619 | 620 | 621 | 622 | 623 | 624 | 625 | 626 | 627 | 628 | 629 | 630 | 631 | 632 | 633 | 634 | 635 | 636 | 637 | 638 | 639 | 640 | 641 | 642 | 643 | 644 | 645 | 646 | 647 | 648 | 649 | 650 | 651 | 652 | 653 | 654 | 655 | 656 | 657 | 658 | 659 | 660 | 661 | 662 | 663 | 664 | 665 | 666 | 667 | 668 | 669 | 670 | 671 | 672 | 673 | 674 | 675 | 676 | 677 | 678 | 679 | 680 | 681 | 682 | 683 | 684 | 685 | 686 | 687 | 688 | 689 | 690 | 691 | 692 | 693 | 694 | 695 | 696 | 697 | 698 | 699 | 700 | 701 | 702 | 703 | 704 | 705 | 706 | 707 | 708 | 709 | 710 | 711 | 712 | 713 | 714 | 715 | 716 | 717 | 718 | 719 | 720 | 721 | 722 | 723 | 724 | 725 | 726 | 727 | 728 | 729 | 730 | 731 | 732 | 733 | 734 | 735 | 736 | 737 | 738 | 739 | 740 | 741 | 742 | 743 | 744 | 745 | 746 | 747 | 748 | 749 | 750 | 751 | 752 | 753 | 754 | 755 | 756 | 757 | 758 | 759 | 760 | 761 | 762 | 763 | 764 | 765 | 766 | 767 | 768 | 769 | 770 | 771 | 772 | 773 | 774 | 775 | 776 | 777 | 778 | 779 | 780 | 781 | 782 | 783 | 784 | 785 | 786 | 787 | 788 | 789 | 790 | 791 | 792 | 793 | 794 | 795 | 796 | 797 | 798 | 799 | 800 | 801 | 802 | 803 | 804 | 805 | 806 | 807 | 808 | 809 | 810 | 811 | 812 | 813 | 814 | 815 | 816 | 817 | 818 | 819 | 820 | 821 | 822 | 823 | 824 | 825 | 826 | 827 | 828 | 829 | 830 | 831 | 832 | 833 | 834 | 835 | 836 | 837 | 838 | 839 | 840 | 841 | 842 | 843 | 844 | 845 | 846 | 847 | 848 | 849 | 850 | 851 | 852 | 853 | 854 | 855 | 856 | 857 | 858 | 859 | 860 | 861 | 862 | 863 | 864 | 865 | 866 | 867 | 868 | 869 | 870 | 871 | 872 | 873 | 874 | 875 | 876 | 877 | 878 | 879 | 880 | 881 | 882 | 883 | 884 | 885 | 886 | 887 | 888 | 889 | 890 | 891 | 892 | 893 | 894 | 895 | 896 | 897 | 898 | 899 | 900 | 901 | 902 | 903 | 904 | 905 | 906 | 907 | 908 | 909 | 910 | 911 | 912 | 913 | 914 | 915 | 916 | 917 | 918 | 919 | 920 | 921 | 922 | 923 | 924 | 925 | 926 | 927 | 928 | 929 | 930 | 931 | 932 | 933 | 934 | 935 | 936 | 937 | 938 | 939 | 940 | 941 | 942 | 943 | 944 | 945 | 946 | 947 | 948 | 949 | 950 | 951 | 952 | 953 | 954 | 955 | 956 | 957 | 958 | 959 | 960 | 961 | 962 | 963 | 964 | 965 | 966 | 967 | 968 | 969 | 970 | 971 | 972 | 973 | 974 | 975 | 976 | 977 | 978 | 979 | 980 | 981 | 982 | 983 | 984 | 985 | 986 | 987 | 988 | 989 | 990 | 991 | 992 | 993 | 994 | 995 | 996 | 997 | 998 | 999 | 1000
#NAME? |  |  | 1053426.5169 | 1053426.5169 |  |  | 45 | 994 | 6 |  |  | 1.a |  |  | 6.2904
#NAME? |  |  | 0 | 0 |  |  | 46 | 0 | 23 |  |  | 1.b |  |  | 0
#NAME? |  |  | 3915036.6982 | 3915036.6982 |  |  | 47 | 0 | 0 |  |  | 1.c |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 |  |  | 48 | 0 | 0 |  |  | 2.a |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 |  |  | 49 | 0 | 0 |  |  | 2.b |  |  | 10.316 | 0 | 8.4782 | 13.2096 | 0 | 11.4712 | 9.9646 | 7.2846 | 12.3653 | 12.2929 | 12.1336 | 7.9891 | 0 | 0 | 12.6292 | 0 | 9.347 | 9.819 | 7.5048 | 12.2917 | 12.7153 | 10.3331 | 7.9498 | 9.2534 | 9.486 | 10.6409 | 9.3111 | 11.23 | 7.4081 | 10.6797 | 12.5802 | 10.6409 | 14.679 | 11.1643 | 12.9841 | 0 | 11.9852 | 12.1864 | 8.981 | 11.2261 | 11.9123 | 10.9004 | 0 | 9.4926 | 10.7359 | 8.3737 | 12.599 | 0 | 10.4006 | 0 | 8.7773 | 8.1131 | 9.2979 | 14.2779 | 0 | 10.347 | 0 | 0 | 11.5643 | 10.2659 | 8.6258 | 9.843 | 0 | 8.1764 | 9.4782 | 9.4355 | 8.9991 | 11.9806 | 11.2705 | 11.9247 | 10.7212 | 12.6185 | 0 | 12.5389 | 12.0264 | 10.4647 | 8.4547 | 14.5615 | 0 | 0 | 11.3015 | 9.3607 | 10.9442 | 0 | 0 | 0 | 9.9191 | 0 | 0 | 15.1512 | 8.8269 | 8.5678 | 12.3988 | 12.6582 | 0 | 10.7012 | 9.3028 | 15.2448 | 0 | 9.7046 | 11.521 | 0 | 10.8691 | 9.3904 | 0 | 0 | 12.5697 | 11.4225 | 12.6794 | 10.6953 | 9.8114 | 0 | 12.1504 | 0 | 0 | 8.2708 | 12.1968 | 9.5416 | 10.3642 | 0 | 11.9441 | 11.7089 | 10.5538 | 7.8345 | 9.1127 | 0 | 11.6343 | 9.4522 | 0 | 0 | 11.7867 | 11.6122 | 12.6817 | 9.9712 | 8.1933 | 10.0223 | 8.8753 | 11.1692 | 9.1923 | 0 | 7.0379 | 11.1002 | 11.1148 | 11.0307 | 8.7024 | 8.696 | 11.4738 | 12.2375 | 12.8908 | 0 | 11.8784 | 0 | 9.3301 | 0 | 11.6107 | 12.4357 | 14.1918 | 0 | 11.1656 | 13.2884 | 11.0044 | 12.0506 | 11.8557 | 10.3978 | 11.6609 | 8.9582 | 12.488 | 8.7433 | 7.9903 | 0 | 10.931 | 12.9178 | 11.1264 | 11.4457 | 0 | 9.3265 | 0 | 12.588 | 10.4441 | 8.5138 | 7.7673 | 7.7854 | 7.9791 | 0 | 0 | 13.8004 | 12.5697 | 0 | 0 | 0 | 11.3998 | 12.3992 | 0 | 0 | 10.5427 | 0 | 11.5829 | 12.6415 | 0 | 9.6829 | 12.2837 | 11.7052 | 13.1716 | 12.7098 | 13.8248 | 0 | 7.4791 | 9.0153 | 0 | 11.4686 | 0 | 12.2824 | 12.7589 | 0 | 0 | 9.8188 | 11.6384 | 0 | 11.837 | 0 | 12.5665 | 0 | 8.2859 | 12.0338 | 11.5854 | 9.0315 | 12.4334 | 8.3622 | 10.9638 | 9.4414 | 12.1467 | 0 | 0 | 7.6833 | 12.6077 | 11.9065 | 10.074 | 0 | 8.9683 | 12.2661 | 10.266 | 0 | 0 | 10.4445 | 10.5173 | 11.4201 | 8.9403 | 11.4088 | 11.1238 | 0 | 0 | 0 | 12.963 | 7.8737 | 12.957 | 0 | 0 | 9.4113 | 12.2016 | 11.1753 | 9.0109 | 7.7859 | 7.6806 | 11.85 | 9.1558 | 7.125 | 0 | 0 | 10.656 | 8.551 | 0 | 0 | 9.1582 | 0 | 10.2768 | 11.4703 | 8.408 | 12.9103 | 12.5023 | 0 | 9.2304 | 13.7452 | 12.8404 | 12.5819 | 14.9612 | 9.2309 | 11.6521 | 7.2387 | 11.523 | 10.3374 | 11.7872 | 10.4895 | 12.5976 | 14.3243 | 9.6208 | 0 | 0 | 8.4314 | 8.7845 | 0 | 12.2218 | 12.1065 | 12.6812 | 12.1373 | 11.5692 | 12.9526 | 12.2655 | 11.24 | 12.642 | 8.6538 | 0 | 12.3866 | 0 | 0 | 0 | 12.9945 | 9.018 | 9.5071 | 11.7293 | 9.9818 | 11.1283 | 7.4735 | 0 | 8.3021 | 8.8333 | 10.9275 | 0 | 12.4525 | 7.8045 | 8.9831 | 10.3597 | 8.0574 | 14.6189 | 12.9547 | 0 | 0 | 11.1213 | 9.1449 | 7.8916 | 12.2255 | 0 | 14.9952 | 0 | 12.4978 | 11.6852 | 11.0646 | 10.4228 | 0 | 0 | 0 | 13.5683 | 0 | 11.718 | 12.3014 | 11.8519 | 12.5553 | 0 | 0 | 12.6651 | 10.8183 | 0 | 9.0252 | 12.901 | 7.4799 | 0 | 0 | 12.1096 | 12.0494 | 10.9463 | 0 | 10.337 | 11.4615 | 11.1973 | 15.2622 | 11.6429 | 0 | 11.2231 | 0 | 12.5471 | 0 | 8.5463 | 0 | 12.5726 | 10.4028 | 11.7355 | 12.3633 | 11.483 | 11.9521 | 8.3911 | 11.5085 | 11.0178 | 10.6984 | 10.7895 | 0 | 11.3053 | 14.2116 | 0 | 0 | 9.5284 | 11.7512 | 10.0462 | 8.05 | 8.2562 | 10.6921 | 0 | 0 | 12.2828 | 9.9607 | 16.2851 | 0 | 12.887 | 10.2673 | 12.3823 | 10.9592 | 12.5815 | 10.0194 | 7.0914 | 0 | 0 | 12.6717 | 12.2189 | 11.8455 | 8.3047 | 0 | 0 | 8.5605 | 0 | 13.8461 | 12.4795 | 11.4934 | 0 | 9.3794 | 12.2367 | 9.7694 | 10.9774 | 7.802 | 8.5737 | 8.2777 | 7.5226 | 10.4271 | 0 | 12.728 | 9.849 | 0 | 11.8741 | 0 | 0 | 0 | 10.0573 | 13.3746 | 10.9721 | 8.4603 | 0 | 0 | 12.0656 | 13.4891 | 0 | 0 | 8.0525 | 14.2767 | 0 | 11.4089 | 9.1857 | 8.7631 | 7.177 | 0 | 10.7075 | 12.8553 | 12.6151 | 12.2684 | 12.5518 | 0 | 0 | 11.7182 | 0 | 9.9095 | 11.5035 | 0 | 10.2204 | 8.5168 | 12.7136 | 8.1815 | 8.379 | 12.253 | 11.3355 | 7.9146 | 12.1725 | 0 | 0 | 11.863 | 11.4016 | 10.19 | 0 | 0 | 12.1425 | 0 | 10.8425 | 12.4438 | 10.9121 | 7.0882 | 11.6728 | 8.8835 | 0 | 11.9426 | 0 | 11.0419 | 0 | 14.1454 | 8.0887 | 12.7609 | 8.9967 | 0 | 12.498 | 0 | 12.1621 | 11.4643 | 11.5398 | 0 | 0 | 12.6467 | 0 | 0 | 0 | 11.0085 | 10.4787 | 12.9254 | 12.4038 | 11.7255 | 11.8983 | 0 | 0 | 12.4836 | 9.1412 | 11.8743 | 0 | 0 | 13.8726 | 7.9223 | 11.613 | 0 | 12.4962 | 0 | 7.9509 | 0 | 0 | 0 | 9.0004 | 9.3419 | 11.3092 | 11.1003 | 8.2404 | 9.8435 | 0 | 0 | 0 | 12.914 | 7.5221 | 0 | 10.5531 | 12.7837 | 0 | 7.3184 | 11.7501 | 0 | 7.1202 | 11.6368 | 12.1654 | 8.8707 | 10.316 | 0 | 12.532 | 10.1055 | 0 | 13.4098 | 11.5364 | 11.3953 | 0 | 10.2939 | 7.1678 | 8.6716 | 10.4256 | 11.2808 | 10.729 | 0 | 11.6167 | 0 | 0 | 7.8828 | 12.004 | 12.2581 | 10.2509 | 10.2583 | 10.853 | 8.7926 | 10.8316 | 7.6674 | 9.478 | 0 | 0 | 0 | 10.8743 | 7.4189 | 11.9008 | 10.8516 | 11.3641 | 9.8781 | 9.682 | 12.6362 | 10.2806 | 12.1251 | 7.2715 | 0 | 9.2651 | 10.2858 | 8.9304 | 12.7159 | 8.6289 | 11.2577 | 13.6341 | 13.6827 | 0 | 12.2171 | 11.4987 | 7.8771 | 12.569 | 12.9768 | 8.3585 | 12.6431 | 0 | 12.0156 | 11.5101 | 10.7953 | 0 | 10.1411 | 9.2958 | 9.586 | 12.6389 | 0 | 14.3867 | 0 | 13.6728 | 10.4293 | 11.483 | 10.1374 | 9.8868 | 12.0451 | 8.0732 | 7.4959 | 9.4788 | 10.5078 | 0 | 11.2253 | 0 | 0 | 0 | 8.7563 | 0 | 12.6016 | 11.069 | 8.6871 | 0 | 0 | 12.0629 | 10.4023 | 0 | 7.8879 | 9.0557 | 11.0498 | 0 | 11.9486 | 14.8803 | 0 | 12.6992 | 13.4812 | 15.7114 | 9.7679 | 0 | 12.1149 | 11.5287 | 0 | 0 | 10.5267 | 12.0104 | 8.4141 | 9.8432 | 9.229 | 10.0978 | 9.6052 | 11.1707 | 9.4455 | 8.0556 | 12.3402 | 0 | 0 | 0 | 0 | 9.3118 | 12.4672 | 8.6997 | 10.2774 | 0 | 0 | 10.9685 | 0 | 8.4395 | 11.5108 | 10.2728 | 0 | 8.3935 | 0 | 13.7293 | 0 | 10.1813 | 12.9891 | 11.5841 | 8.4462 | 11.8557 | 8.5264 | 14.5286 | 0 | 0 | 0 | 7.5041 | 0 | 0 | 0 | 12.8554 | 8.7075 | 7.8467 | 0 | 0 | 12.082 | 12.2346 | 0 | 11.1116 | 0 | 9.6594 | 13.8096 | 9.9608 | 12.2134 | 0 | 8.5337 | 0 | 12.1862 | 11.9146 | 9.2426 | 10.9023 | 12.6576 | 0 | 0 | 9.7578 | 8.4301 | 8.2305 | 14.3555 | 10.2385 | 12.5204 | 9.9033 | 9.5921 | 12.3575 | 11.5542 | 12.6069 | 0 | 12.6586 | 12.4947 | 10.4749 | 0 | 0 | 11.0537 | 0 | 12.1539 | 8.1093 | 11.0536 | 11.3293 | 9.8359 | 11.5362 | 8.0189 | 8.7558 | 9.5509 | 10.4742 | 7.639 | 10.3668 | 0 | 8.0165 | 11.4641 | 11.9825 | 8.2246 | 11.9271 | 0 | 12.7053 | 9.7309 | 11.7306 | 0 | 10.9251 | 9.3564 | 0 | 9.9685 | 11.2536 | 0 | 15.3411 | 12.1792 | 11.7141 | 10.3883 | 0 | 0 | 7.9829 | 11.7353 | 0 | 10.8763 | 11.5577 | 11.0863 | 10.4526 | 11.5141 | 0 | 0 | 11.8628 | 12.8186 | 12.56 | 13.2185 | 10.9896 | 11.7004 | 10.2936 | 11.3599 | 12.1298 | 0 | 12.7072 | 12.0057 | 0 | 9.7926 | 10.8963 | 12.0967 | 9.7234 | 12.2979 | 0 | 8.5685 | 9.8871 | 9.5809 | 8.3703 | 12.7252 | 0 | 14.1567 | 12.9967 | 9.9219 | 10.7508 | 7.7145 | 7.9475 | 8.8628 | 0 | 10.5392 | 16.6491 | 12.175 | 12.0504 | 10.6328 | 12.7776 | 0 | 11.0387 | 12.212 | 11.0796 | 9.569 | 8.4943 | 0 | 12.9109 | 9.2662 | 11.082 | 11.6225 | 10.2371 | 9.3926 | 11.4841 | 7.0766 | 11.3838 | 0 | 9.1912 | 0 | 0 | 12.0432 | 0 | 0 | 0 | 11.4678 | 0 | 10.2805 | 0 | 8.5507 | 0 | 11.1401 | 0 | 0 | 12.8098 | 11.5433 | 0 | 8.0794 | 12.6765 | 11.2645 | 0 | 7.6328 | 10.1231 | 0 | 0 | 7.9772 | 0 | 10.0789 | 10.7799 | 11.1091 | 10.6471 | 8.5064 | 11.0985 | 0 | 12.263 | 0 | 12.1872 | 0 | 10.5657 | 11.1669 | 0 | 11.166 | 7.5139 | 11.3983 | 0 | 8.3344 | 11.054 | 0 | 11.0321 | 7.0473 | 9.7086 | 16.1307 | 11.6397 | 0 | 9.5744 | 7.8798 | 0 | 11.894 | 10.8516 | 9.6093 | 0 | 11.7719 | 11.9678 | 9.8965 | 10.869 | 7.9071 | 7.9235 | 0 | 12.8547 | 0 | 12.5511 | 0 | 14.4973 | 12.2558 | 10.749 | 8.8147 | 10.0356 | 10.5899 | 11.6382 | 11.5868 | 10.6221 | 9.7016 | 7.5524 | 10.6824 | 12.2621 | 0 | 12.11 | 10.5421 | 8.4276 | 14.9902 | 0 | 10.6253 | 11.3711 | 14.3287 | 7.666 | 12.3405 | 11.2498 | 12.6827 | 0 | 9.0895 | 11.8974 | 0 | 10.984 | 11.998 | 0 | 11.0981 | 12.9607 | 0 | 9.9216 | 10.6773 | 12.035 | 11.3306 | 0 | 7.0782 | 7.7283 | 12.5215 | 13.9666 | 0 | 0 | 7.0719 | 0 | 7.3123 | 0 | 12.3179 | 0 | 8.7505 | 10.5566 | 12.4858 | 12.9432
#NAME? |  |  | 0 | 0 |  |  | 50 | 0 | 0 |  |  | 2.c |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 |  |  | 51 | 0 | 0 |  |  | 2.d |  |  | 0 | 12.8442 | 0 | 0 | 13.8924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.3269 | 13.5036 | 0 | 15.3839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.7698 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6411 | 0 | 0 | 0 | 0 | 14.8233 | 0 | 15.8522 | 0 | 0 | 0 | 0 | 13.7422 | 0 | 15.5217 | 14.6909 | 0 | 0 | 0 | 0 | 15.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7725 | 0 | 0 | 0 | 0 | 0 | 15.9158 | 14.7045 | 0 | 0 | 0 | 15.6545 | 15.9666 | 12.235 | 0 | 13.6618 | 14.9637 | 0 | 0 | 0 | 0 | 0 | 15.0849 | 0 | 0 | 0 | 15.3169 | 0 | 0 | 12.5316 | 0 | 0 | 15.9524 | 15.2358 | 0 | 0 | 0 | 0 | 0 | 15.1757 | 0 | 15.7692 | 13.9321 | 0 | 0 | 0 | 0 | 15.3352 | 0 | 0 | 0 | 0 | 0 | 14.4256 | 0 | 0 | 13.8885 | 15.1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.8657 | 0 | 13.8352 | 0 | 13.3964 | 0 | 0 | 0 | 14.8661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.696 | 0 | 0 | 0 | 0 | 14.6242 | 0 | 14.8048 | 0 | 0 | 0 | 0 | 0 | 0 | 15.76 | 15.5687 | 0 | 0 | 13.0594 | 13.3674 | 15.6664 | 0 | 0 | 15.844 | 14.0341 | 0 | 13.5572 | 0 | 0 | 14.4195 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6923 | 0 | 0 | 12.8048 | 0 | 15.7884 | 0 | 0 | 12.6994 | 15.1292 | 0 | 0 | 12.0288 | 0 | 14.421 | 0 | 12.4547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.8577 | 14.9351 | 0 | 0 | 0 | 0 | 15.6592 | 0 | 0 | 0 | 13.5596 | 14.428 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0509 | 14.3874 | 13.0352 | 0 | 0 | 0 | 13.5069 | 13.4069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.4424 | 15.6258 | 0 | 0 | 12.6358 | 14.7117 | 0 | 15.6885 | 0 | 0 | 0 | 0 | 0 | 13.9028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2474 | 15.2517 | 0 | 0 | 15.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.8787 | 0 | 15.1155 | 11.1258 | 15.6884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7516 | 0 | 0 | 0 | 15.3631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6754 | 14.3374 | 0 | 0 | 0 | 0 | 14.9513 | 0 | 12.756 | 0 | 0 | 0 | 0 | 13.7308 | 14.7563 | 15.3495 | 0 | 15.2321 | 0 | 0 | 0 | 0 | 14.0959 | 15.9174 | 0 | 0 | 15.5277 | 0 | 0 | 0 | 14.0974 | 15.1059 | 0 | 0 | 0 | 15.3806 | 0 | 0 | 0 | 0 | 0 | 15.8532 | 0 | 14.0415 | 0 | 13.0641 | 0 | 13.5476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.537 | 0 | 0 | 14.6033 | 15.4348 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8892 | 13.8226 | 0 | 0 | 0 | 14.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4126 | 13.4677 | 0 | 0 | 0 | 0 | 15.0124 | 15.3171 | 0 | 14.9757 | 0 | 0 | 0 | 15.5291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7612 | 0 | 0 | 13.5138 | 0 | 14.5759 | 15.1885 | 12.977 | 0 | 0 | 0 | 0 | 14.3306 | 13.8503 | 0 | 0 | 15.3534 | 15.0964 | 0 | 0 | 14.2081 | 0 | 0 | 0 | 0 | 15.537 | 0 | 0 | 0 | 0 | 0 | 15.164 | 12.3125 | 0 | 15.6228 | 0 | 0 | 14.8784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0277 | 12.0972 | 0 | 0 | 0 | 14.8946 | 12.9044 | 0 | 14.3114 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8067 | 0 | 14.1377 | 0 | 15.9418 | 0 | 0 | 0 | 0 | 15.4462 | 0 | 14.2529 | 0 | 0 | 0 | 14.9761 | 14.7742 | 0 | 15.1279 | 14.4346 | 15.367 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9842 | 13.937 | 0 | 0 | 0 | 15.6333 | 12.9985 | 0 | 0 | 0 | 15.0498 | 0 | 14.8374 | 0 | 13.0085 | 13.8878 | 13.2361 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6261 | 14.6449 | 15.4674 | 0 | 0 | 14.5915 | 0 | 0 | 14.2689 | 0 | 0 | 15.2165 | 0 | 0 | 0 | 0 | 0 | 14.5394 | 0 | 0 | 15.2818 | 0 | 0 | 0 | 15.1545 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0831 | 0 | 13.6148 | 14.6546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2174 | 15.3468 | 15.2413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.0618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.8807 | 0 | 0 | 0 | 13.8887 | 0 | 0 | 0 | 0 | 14.8287 | 0 | 15.897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5449 | 0 | 14.8771 | 15.928 | 15.2838 | 0 | 11.7358 | 0 | 0 | 0 | 12.9186 | 14.8722 | 0 | 0 | 15.572 | 0 | 0 | 0 | 12.3199 | 0 | 0 | 14.6256 | 0 | 0 | 0 | 0 | 14.1905 | 0 | 0 | 15.8536 | 15.4422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5467 | 14.0972 | 14.6577 | 14.9689 | 0 | 0 | 0 | 0 | 15.4429 | 13.1234 | 0 | 14.1098 | 0 | 0 | 0 | 12.9442 | 0 | 15.6287 | 0 | 13.5947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8934 | 15.6377 | 15.1454 | 0 | 14.3423 | 15.3648 | 11.8851 | 0 | 0 | 0 | 13.1811 | 14.8591 | 0 | 0 | 15.2549 | 0 | 12.4198 | 0 | 0 | 0 | 0 | 14.7196 | 0 | 14.8664 | 0 | 0 | 0 | 0 | 0 | 13.5537 | 15.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9885 | 0 | 0 | 0 | 14.3551 | 14.4862 | 0 | 13.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6684 | 0 | 0 | 0 | 0 | 0 | 13.9261 | 0 | 0 | 0 | 12.9452 | 0 | 0 | 15.0029 | 0 | 0 | 13.9031 | 0 | 0 | 0 | 0 | 14.2956 | 15.1484 | 0 | 0 | 15.2362 | 0 | 0 | 0 | 0 | 0 | 14.1795 | 15.4746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.25 | 0 | 0 | 14.6521 | 0 | 0 | 0 | 0 | 0 | 14.8308 | 0 | 0 | 0 | 0 | 0 | 15.2063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2586 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9617 | 0 | 0 | 0 | 0 | 0 | 15.4645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7087 | 0 | 14.4452 | 15.1637 | 0 | 15.3349 | 0 | 15.1859 | 0 | 14.6787 | 0 | 14.7697 | 0 | 15.2461 | 0 | 13.849 | 14.4487 | 0 | 0 | 14.9677 | 0 | 0 | 0 | 15.1286 | 0 | 0 | 11.6153 | 14.1189 | 0 | 13.8981 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1949 | 0 | 12.5436 | 0 | 14.9908 | 0 | 0 | 12.084 | 0 | 0 | 0 | 13.1877 | 0 | 0 | 12.0761 | 0 | 0 | 0 | 0 | 0 | 13.4535 | 0 | 0 | 15.8145 | 0 | 0 | 0 | 15.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 12.3457 | 0 | 14.8208 | 0 | 14.1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.0134 | 0 | 0 | 0 | 0 | 13.2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5846 | 0 | 0 | 12.3418 | 0 | 0 | 15.8807 | 0 | 0 | 13.8233 | 0 | 0 | 0 | 0 | 15.1641 | 0 | 0 | 0 | 0 | 13.2312 | 15.1136 | 0 | 15.8121 | 0 | 14.6959 | 0 | 14.0426 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 |  |  | 52 | 0 | 0 |  |  | 3.a |  |  | 8.905 | 5.7797 | 7.1238 | 6.9664 | 8.8181 | 5.1419 | 5.4544 | 0 | 7.5437 | 0 | 7.1671 | 5.4421 | 5.5484 | 7.9536 | 5.8668 | 8.7977 | 0 | 7.3372 | 0 | 0 | 0 | 7.7849 | 0 | 7.7757 | 0 | 7.4657 | 6.0725 | 7.6779 | 0 | 7.8432 | 6.8087 | 6.3377 | 0 | 0 | 5.1935 | 8.8161 | 8.6437 | 6.4898 | 5.1173 | 6.6741 | 0 | 6.6093 | 5.2427 | 6.2106 | 0 | 0 | 6.8396 | 7.8227 | 4.9006 | 5.1885 | 7.3311 | 6.0863 | 5.1179 | 7.5002 | 7.3689 | 5.551 | 7.81 | 7.2532 | 6.0307 | 7.7388 | 6.1976 | 0 | 6.0448 | 7.8776 | 8.79 | 7.2295 | 7.0235 | 0 | 8.4706 | 6.5372 | 8.5077 | 4.792 | 5.1937 | 0 | 0 | 0 | 7.2682 | 7.5965 | 6.5846 | 6.5246 | 5.4968 | 8.7946 | 0 | 5.1606 | 7.5277 | 8.1468 | 6.2289 | 5.0664 | 6.2435 | 5.1751 | 0 | 0 | 7.9515 | 8.6153 | 5.6717 | 5.5945 | 5.6308 | 5.4867 | 7.2936 | 8.9434 | 7.039 | 5.9731 | 5.5238 | 6.8217 | 7.0215 | 8.2888 | 6.5268 | 0 | 6.5886 | 8.0566 | 0 | 6.5366 | 6.1267 | 6.5363 | 6.5367 | 0 | 6.0032 | 7.7222 | 6.791 | 5.6233 | 5.4015 | 0 | 6.7157 | 5.9016 | 0 | 8.6164 | 0 | 7.4432 | 7.9333 | 4.9833 | 7.3759 | 0 | 0 | 6.0928 | 7.4412 | 0 | 7.8887 | 0 | 0 | 6.8957 | 8.1036 | 4.9104 | 5.3239 | 7.396 | 7.0941 | 5.9316 | 5.055 | 0 | 8.2478 | 7.8982 | 6.7066 | 5.1767 | 0 | 5.5836 | 0 | 5.5081 | 8.5252 | 7.8591 | 8.7746 | 6.3216 | 0 | 7.1661 | 8.1359 | 7.4224 | 5.4023 | 0 | 6.5582 | 5.0767 | 8.0146 | 8.0051 | 7.4727 | 8.4949 | 8.6808 | 6.4936 | 8.562 | 0 | 8.4416 | 5.089 | 8.9986 | 5.6061 | 5.6964 | 0 | 0 | 7.7209 | 8.0355 | 0 | 5.0178 | 6.7356 | 4.8046 | 5.3793 | 5.7906 | 0 | 8.7536 | 8.7335 | 5.6163 | 5.1642 | 7.4497 | 5.4439 | 8.4669 | 0 | 6.8749 | 7.6042 | 7.0065 | 8.5689 | 0 | 6.473 | 0 | 5.603 | 8.0136 | 0 | 7.3867 | 5.6382 | 8.037 | 7.0843 | 8.0219 | 7.349 | 8.8693 | 7.1042 | 5.7319 | 4.9068 | 7.0433 | 8.6906 | 0 | 5.5498 | 0 | 0 | 7.2073 | 0 | 5.6373 | 8.4694 | 6.7754 | 7.3526 | 8.4037 | 0 | 4.8812 | 0 | 6.9075 | 5.7083 | 0 | 8.2898 | 4.8242 | 5.0607 | 6.1352 | 0 | 0 | 6.3628 | 0 | 5.5473 | 4.8086 | 5.8107 | 6.8131 | 5.0542 | 7.087 | 6.8682 | 7.4465 | 6.5275 | 6.4848 | 8.5706 | 0 | 7.1905 | 7.8325 | 0 | 0 | 0 | 8.3263 | 0 | 8.1018 | 5.8361 | 8.2622 | 0 | 4.7724 | 6.0208 | 5.596 | 6.6618 | 0 | 7.8648 | 0 | 7.1115 | 8.0326 | 8.7476 | 7.1284 | 0 | 5.2347 | 8.8769 | 6.1623 | 7.235 | 6.6055 | 0 | 7.3945 | 8.2783 | 5.4506 | 8.0434 | 5.9233 | 7.6696 | 6.4465 | 8.2019 | 8.4024 | 0 | 0 | 5.3633 | 8.512 | 6.6956 | 0 | 6.6927 | 6.9797 | 8.7097 | 8.104 | 8.5517 | 6.75 | 6.6581 | 6.0946 | 0 | 7.8996 | 5.9712 | 6.1805 | 5.4963 | 5.2447 | 5.3253 | 8.1559 | 0 | 6.212 | 0 | 6.2978 | 0 | 8.8351 | 7.9588 | 7.5425 | 0 | 0 | 7.3706 | 8.6976 | 0 | 5.0906 | 8.1711 | 8.3835 | 7.296 | 6.4645 | 7.3857 | 6.7037 | 6.1917 | 5.8598 | 6.504 | 5.6896 | 8.2223 | 8.409 | 8.3968 | 6.3734 | 5.883 | 6.0707 | 5.8052 | 6.9768 | 5.3475 | 8.9456 | 5.1501 | 0 | 0 | 7.1851 | 7.6615 | 7.7864 | 0 | 5.8201 | 8.237 | 7.7436 | 6.2225 | 7.5811 | 5.3657 | 8.6571 | 0 | 6.8973 | 6.4417 | 8.3907 | 7.0642 | 6.0441 | 5.265 | 7.3903 | 7.9231 | 5.0012 | 5.7051 | 7.4188 | 8.3856 | 0 | 7.9475 | 5.5667 | 8.1739 | 0 | 5.637 | 8.4917 | 6.6272 | 0 | 8.0463 | 8.6444 | 6.9267 | 0 | 8.1353 | 7.5415 | 6.9322 | 7.4767 | 6.8686 | 6.9018 | 8.5056 | 6.5415 | 0 | 0 | 4.7051 | 8.8538 | 5.8237 | 8.5834 | 4.9581 | 0 | 8.8973 | 0 | 7.1731 | 7.8631 | 0 | 7.4508 | 7.1695 | 7.5813 | 6.1047 | 5.4096 | 0 | 7.2566 | 6.7008 | 8.924 | 5.4089 | 6.2074 | 7.827 | 7.9028 | 7.0008 | 8.1152 | 0 | 8.0352 | 0 | 7.9427 | 7.9098 | 0 | 0 | 0 | 6.2382 | 0 | 8.2727 | 5.9047 | 0 | 0 | 8.1713 | 5.6423 | 6.5353 | 6.1674 | 8.3403 | 7.0635 | 0 | 6.1195 | 0 | 6.3726 | 7.6597 | 7.6036 | 0 | 5.3492 | 7.6798 | 0 | 0 | 4.741 | 0 | 8.5373 | 5.4004 | 5.2111 | 5.7843 | 0 | 6.4871 | 8.0958 | 7.868 | 0 | 8.2349 | 7.7697 | 0 | 8.9015 | 0 | 6.723 | 5.5093 | 0 | 0 | 5.8648 | 0 | 5.8691 | 8.9476 | 8.7383 | 0 | 5.0948 | 5.2349 | 6.6757 | 5.4138 | 4.8493 | 8.6968 | 5.1903 | 6.2361 | 6.4289 | 8.8598 | 6.8008 | 7.8927 | 0 | 0 | 7.1312 | 0 | 5.886 | 0 | 7.9725 | 0 | 7.5549 | 0 | 0 | 7.8988 | 5.9546 | 8.6794 | 8.0722 | 8.5282 | 8.3369 | 8.0033 | 6.7013 | 8.1756 | 7.4784 | 7.1114 | 6.2796 | 7.3769 | 8.821 | 5.9507 | 7.261 | 7.6799 | 7.7868 | 6.7394 | 5.6994 | 5.3882 | 8.1703 | 7.6277 | 0 | 5.5955 | 8.2081 | 6.1745 | 8.7978 | 0 | 6.0029 | 6.8704 | 7.1981 | 7.8693 | 5.3918 | 7.704 | 6.592 | 4.9167 | 0 | 5.777 | 6.5989 | 6.2273 | 0 | 0 | 5.9967 | 7.4088 | 5.4416 | 6.297 | 8.3154 | 6.4974 | 5.25 | 0 | 6.3853 | 0 | 5.9795 | 7.2176 | 0 | 6.1267 | 7.7354 | 0 | 8.905 | 5.2721 | 5.8209 | 0 | 5.521 | 0 | 8.9178 | 6.3721 | 7.5516 | 0 | 6.653 | 0 | 8.7521 | 0 | 5.6536 | 8.3423 | 4.8181 | 8.553 | 8.0868 | 5.884 | 0 | 7.8944 | 0 | 0 | 5.9726 | 7.7771 | 8.0336 | 0 | 6.0384 | 5.4175 | 7.7677 | 6.1936 | 6.6384 | 0 | 5.5036 | 0 | 7.0229 | 0 | 0 | 0 | 0 | 7.5742 | 0 | 8.2915 | 6.9081 | 0 | 5.6847 | 0 | 7.6106 | 0 | 5.9828 | 5.5588 | 6.7093 | 6.2163 | 0 | 6.1342 | 0 | 8.5646 | 0 | 5.6718 | 8.8633 | 6.6763 | 0 | 5.574 | 7.6292 | 7.2798 | 0 | 8.0795 | 6.3103 | 7.3088 | 0 | 7.9345 | 5.0454 | 0 | 8.0643 | 6.9942 | 6.2798 | 0 | 0 | 0 | 5.2347 | 5.0276 | 6.6264 | 0 | 5.6397 | 6.1721 | 5.8886 | 0 | 5.4377 | 7.3744 | 0 | 5.595 | 8.4636 | 5.8669 | 0 | 8.014 | 6.3024 | 0 | 7.5954 | 0 | 7.6867 | 7.4761 | 8.1874 | 5.9596 | 0 | 6.1239 | 7.4448 | 8.3161 | 8.2821 | 5.9494 | 5.8583 | 8.4659 | 7.2373 | 7.8425 | 4.8854 | 5.0729 | 6.4661 | 0 | 6.7926 | 0 | 7.1948 | 5.5067 | 0 | 8.5146 | 6.4913 | 6.0745 | 6.7582 | 5.0799 | 6.231 | 6.0215 | 7.9345 | 7.5648 | 5.5185 | 7.4239 | 5.8298 | 7.7557 | 0 | 7.8781 | 8.6716 | 8.2423 | 6.2649 | 4.8526 | 8.7995 | 7.5521 | 8.4914 | 0 | 8.3869 | 0 | 0 | 6.7066 | 0 | 6.2406 | 5.6371 | 5.6499 | 0 | 7.245 | 8.9612 | 5.4972 | 0 | 0 | 0 | 8.8673 | 5.8631 | 8.5305 | 0 | 7.6088 | 4.8304 | 7.3055 | 0 | 0 | 0 | 4.9703 | 7.4521 | 0 | 7.2696 | 8.5953 | 0 | 7.6441 | 0 | 4.8724 | 6.4902 | 6.27 | 0 | 6.7641 | 5.3408 | 0 | 6.34 | 4.6378 | 6.1862 | 0 | 8.337 | 0 | 4.8983 | 6.413 | 8.9275 | 0 | 0 | 5.4499 | 6.1753 | 0 | 6.7871 | 7.5925 | 0 | 6.6752 | 5.4901 | 0 | 0 | 0 | 8.7943 | 8.9249 | 5.8803 | 8.611 | 0 | 5.7132 | 0 | 0 | 5.5562 | 0 | 6.036 | 5.5214 | 6.99 | 0 | 6.3921 | 7.2579 | 6.0372 | 4.7972 | 7.687 | 5.3146 | 0 | 5.3052 | 6.4868 | 5.2796 | 5.5247 | 0 | 8.3078 | 6.7804 | 5.1871 | 0 | 6.1077 | 0 | 5.5191 | 7.9542 | 0 | 0 | 7.9191 | 5.9028 | 7.2415 | 6.4909 | 8.7147 | 0 | 5.2614 | 0 | 8.9103 | 0 | 6.6195 | 8.8994 | 0 | 7.278 | 5.582 | 0 | 7.5095 | 8.5313 | 0 | 8.5272 | 6.5625 | 7.8787 | 0 | 6.0513 | 0 | 0 | 7.0236 | 7.6533 | 6.3627 | 5.4983 | 5.8167 | 0 | 5.8113 | 0 | 5.1428 | 7.7247 | 4.9539 | 0 | 8.2934 | 5.7247 | 0 | 6.954 | 0 | 5.6922 | 8.6649 | 0 | 8.8792 | 6.6426 | 8.314 | 6.5062 | 0 | 6.0637 | 6.4564 | 5.0313 | 0 | 0 | 8.0958 | 6.2667 | 8.4209 | 6.5875 | 7.3991 | 5.241 | 5.5694 | 6.2599 | 8.1216 | 0 | 8.8528 | 8.4777 | 6.0682 | 0 | 8.9702 | 0 | 4.936 | 6.8084 | 7.6112 | 8.2003 | 6.2967 | 0 | 8.8265 | 6.3345 | 5.5456 | 0 | 0 | 8.3176 | 7.1634 | 0 | 8.9614 | 0 | 4.9133 | 0 | 5.5426 | 8.3552 | 7.1843 | 6.1952 | 5.1126 | 7.9995 | 8.1917 | 6.1127 | 0 | 7.5814 | 5.2524 | 6.9192 | 4.5109 | 0 | 5.0411 | 4.9634 | 0 | 5.7001 | 7.8231 | 0 | 0 | 7.4429 | 5.2658 | 8.4988 | 7.4366 | 0 | 6.3072 | 5.8615 | 6.1259 | 8.0322 | 8.905 | 5.7748 | 7.4664 | 0 | 8.5315 | 6.413 | 6.3127 | 6.7415 | 6.0407 | 7.0738 | 5.2011 | 5.8563 | 6.4482 | 5.0814 | 5.4132 | 0 | 6.7609 | 8.1177 | 6.5055 | 8.4749 | 0 | 0 | 0 | 0 | 5.6048 | 7.9488 | 7.1094 | 7.3524 | 0 | 5.996 | 8.3797 | 5.419 | 5.9632 | 5.447 | 5.7484 | 0 | 0 | 5.0014 | 5.3596 | 0 | 5.5862 | 6.5642 | 0 | 0 | 5.4031 | 6.9899 | 0 | 8.1658 | 6.2797 | 5.5036 | 0 | 7.5014 | 6.9595 | 0 | 7.4825 | 0 | 7.0401 | 8.1998 | 7.4489 | 5.4182 | 8.2979 | 0 | 6.3813 | 8.7163 | 5.1606 | 0 | 5.5292 | 7.1552 | 7.0575
#NAME? |  |  | 0 | 0 |  |  | 53 | 0 | 0 |  |  | 3.b |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 4456414.2255 | 0 |  |  | 54 | 0 | 0 |  |  | 4.a |  |  | 6.2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.596 | 0 | 0 | 0 | 7.5003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9162 | 0 | 0 | 0 | 0 | 7.9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6543 | 0 | 0 | 0 | 0 | 0 | 8.8209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5223 | 0 | 0 | 0 | 8.8197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.993 | 0 | 0 | 0 | 0 | 8.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9246 | 0 | 0 | 8.7566 | 0 | 0 | 0 | 7.701 | 0 | 0 | 0 | 0 | 0 | 6.8745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0637 | 0 | 8.303 | 0 | 0 | 0 | 0 | 8.4349 | 0 | 7.7567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8978 | 8.877 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3387 | 0 | 0 | 0 | 8.4105 | 0 | 0 | 0 | 8.8815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7331 | 0 | 0 | 0 | 0 | 6.804 | 0 | 0 | 0 | 7.4844 | 0 | 0 | 8.0076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4979 | 0 | 0 | 0 | 0 | 0 | 8.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5041 | 0 | 0 | 0 | 8.5264 | 0 | 0 | 0 | 0 | 7.9653 | 0 | 8.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6033 | 0 | 7.6606 | 0 | 0 | 0 | 0 | 7.1437 | 8.0283 | 0 | 0 | 0 | 0 | 0 | 8.975 | 8.6775 | 0 | 6.6697 | 0 | 5.8981 | 0 | 0 | 8.9417 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9168 | 0 | 8.4488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1079 | 0 | 8.6574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2949 | 0 | 0 | 0 | 8.4305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7872 | 0 | 0 | 0 | 0 | 0 | 6.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4546 | 0 | 0 | 0 | 7.483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0074 | 0 | 0 | 0 | 0 | 5.5873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7625 | 7.3475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.077 | 0 | 0 | 0 | 0 | 0 | 7.9107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.454 | 0 | 0 | 0 | 0 | 8.7334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.349 | 0 | 0 | 7.0084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4448 | 0 | 0 | 0 | 7.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3867 | 0 | 0 | 0 | 0 | 0 | 8.7324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8726 | 0 | 0 | 0 | 8.5042 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 |  |  | 55 | 0 | 0 |  |  | 4.b |  |  | 0 | 10.9668 | 10.4347 | 10.9454 | 6.896 | 9.5525 | 12.1085 | 0 | 9.9805 | 0 | 8.4595 | 0 | 13.3769 | 10.9 | 6.5288 | 8.7485 | 0 | 0 | 0 | 0 | 0 | 11.792 | 0 | 10.1492 | 0 | 8.519 | 0 | 11.0711 | 0 | 11.4421 | 14.7143 | 0 | 0 | 0 | 14.0638 | 6.0828 | 13.7905 | 10.9556 | 12.0736 | 0 | 0 | 10.3532 | 9.6837 | 0 | 0 | 0 | 0 | 0 | 10.2729 | 14.2777 | 11.6604 | 11.3738 | 0 | 9.0191 | 9.8445 | 12.0921 | 14.4291 | 0 | 14.4292 | 14.2693 | 14.483 | 0 | 8.5259 | 0 | 10.7754 | 0 | 11.6826 | 0 | 8.2812 | 10.9661 | 10.2088 | 8.7906 | 14.7386 | 0 | 0 | 0 | 14.7292 | 13.2464 | 12.0914 | 14.4222 | 10.6502 | 12.8925 | 0 | 8.7204 | 13.0909 | 10.9267 | 5.1122 | 10.3001 | 14.4589 | 7.3212 | 0 | 0 | 12.8177 | 0 | 14.4098 | 7.9346 | 0 | 8.9661 | 11.2844 | 0 | 13.2772 | 13.6578 | 13.7894 | 10.7224 | 0 | 13.9072 | 4.9828 | 0 | 14.7501 | 6.4388 | 0 | 14.4801 | 0 | 13.5058 | 9.8672 | 0 | 12.3271 | 10.4011 | 13.576 | 11.8874 | 6.9924 | 0 | 14.2042 | 11.8901 | 0 | 13.6036 | 0 | 7.9522 | 14.4246 | 12.8666 | 11.1778 | 0 | 0 | 12.9158 | 11.1336 | 0 | 9.5218 | 0 | 0 | 13.5363 | 13.4773 | 11.3183 | 13.4621 | 14.4295 | 9.6807 | 11.5275 | 0 | 0 | 0 | 0 | 14.7883 | 0 | 0 | 9.5951 | 0 | 6.8266 | 14.2681 | 0 | 14.2814 | 7.7403 | 0 | 13.2319 | 14.8208 | 8.7259 | 14.0111 | 0 | 0 | 10.3356 | 12.4232 | 8.0591 | 9.31 | 9.5968 | 0 | 6.4653 | 10.8397 | 0 | 9.0859 | 10.1149 | 9.9106 | 0 | 9.4825 | 0 | 0 | 7.1862 | 5.989 | 0 | 13.0502 | 12.4098 | 14.2755 | 0 | 0 | 0 | 13.2758 | 0 | 0 | 13.8049 | 0 | 14.6117 | 14.1699 | 0 | 9.1113 | 14.8115 | 0 | 12.679 | 0 | 0 | 0 | 12.6298 | 14.6579 | 0 | 14.3324 | 11.7577 | 0 | 14.211 | 7.9217 | 14.3882 | 8.6546 | 0 | 13.7452 | 13.4881 | 12.3057 | 0 | 0 | 13.2688 | 0 | 0 | 10.0529 | 0 | 12.587 | 11.3885 | 8.7102 | 0 | 13.5635 | 0 | 10.7669 | 0 | 0 | 13.3718 | 0 | 14.6992 | 9.7304 | 14.7766 | 13.6958 | 0 | 0 | 7.1367 | 0 | 11.5915 | 13.442 | 0 | 10.9026 | 14.98 | 6.2065 | 0 | 0 | 12.3333 | 12.1048 | 10.7506 | 0 | 10.777 | 7.721 | 0 | 0 | 0 | 13.9577 | 0 | 10.2251 | 10.9548 | 14.1947 | 0 | 11.2686 | 13.9007 | 10.6737 | 10.4036 | 0 | 8.2251 | 0 | 9.0528 | 14.5188 | 10.4542 | 9.8802 | 0 | 11.2838 | 12.7554 | 0 | 12.564 | 7.4186 | 0 | 9.2066 | 10.2809 | 10.7377 | 14.3141 | 14.0548 | 0 | 10.4217 | 10.6672 | 0 | 0 | 0 | 13.4285 | 0 | 9.1147 | 0 | 14.7963 | 7.399 | 8.8874 | 0 | 10.4131 | 14.5785 | 7.8977 | 11.8329 | 0 | 14.853 | 12.8665 | 14.5809 | 9.0785 | 11.3745 | 9.6232 | 11.503 | 0 | 14.2992 | 0 | 11.4525 | 0 | 0 | 8.336 | 10.2343 | 0 | 0 | 12.4866 | 14.0146 | 0 | 12.1177 | 0 | 9.5849 | 0 | 0 | 7.2861 | 5.9966 | 11.2956 | 7.1224 | 11.3167 | 8.0806 | 0 | 12.5355 | 0 | 11.7607 | 9.4058 | 11.9658 | 9.7027 | 0 | 13.1508 | 0 | 14.7224 | 0 | 0 | 10.4371 | 9.7844 | 14.4255 | 0 | 0 | 5.9791 | 11.7726 | 10.1103 | 12.3984 | 11.8054 | 12.4157 | 0 | 0 | 12.8753 | 0 | 11.3497 | 7.6369 | 13.2371 | 13.0464 | 11.8419 | 9.0534 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5559 | 0 | 0 | 9.216 | 14.7646 | 0 | 0 | 10.5682 | 0 | 0 | 0 | 8.508 | 9.9622 | 12.7402 | 0 | 12.1709 | 12.5194 | 9.0686 | 0 | 0 | 7.7404 | 11.1906 | 8.6919 | 9.1675 | 9.1787 | 0 | 8.7363 | 0 | 14.9426 | 13.2094 | 0 | 11.7069 | 0 | 0 | 0 | 11.1916 | 0 | 0 | 13.8511 | 9.7864 | 0 | 0 | 8.3983 | 13.5688 | 0 | 12.6824 | 0 | 10.412 | 0 | 13.8289 | 11.2732 | 0 | 0 | 0 | 9.8751 | 0 | 0 | 8.8709 | 0 | 0 | 14.7999 | 13.6276 | 0 | 14.1661 | 9.649 | 7.6535 | 0 | 12.6876 | 0 | 0 | 14.1358 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2559 | 0 | 0 | 0 | 14.202 | 11.0353 | 0 | 13.4875 | 6.7536 | 14.0884 | 0 | 8.848 | 7.7294 | 0 | 13.5052 | 0 | 11.5555 | 10.154 | 0 | 0 | 12.8084 | 0 | 0 | 0 | 13.1109 | 0 | 0 | 8.6305 | 12.7117 | 11.0412 | 12.0212 | 0 | 14.2146 | 0 | 13.3218 | 10.2763 | 13.0916 | 9.2322 | 0 | 0 | 7.1422 | 0 | 10.2465 | 0 | 11.6217 | 0 | 13.8869 | 0 | 0 | 11.1984 | 11.6181 | 14.8953 | 0 | 12.8635 | 0 | 8.2916 | 0 | 13.9579 | 13.6955 | 8.0728 | 14.0089 | 0 | 0 | 10.5552 | 9.5895 | 10.2976 | 12.565 | 0 | 0 | 0 | 7.7976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2946 | 0 | 0 | 11.8588 | 10.7914 | 0 | 12.0853 | 0 | 0 | 0 | 10.7299 | 10.2025 | 0 | 0 | 11.6598 | 13.155 | 12.9285 | 11.2374 | 0 | 8.9526 | 0 | 0 | 10.9537 | 0 | 11.5257 | 9.8021 | 0 | 0 | 11.968 | 0 | 0 | 9.6845 | 8.085 | 0 | 0 | 0 | 7.5786 | 7.8609 | 14.3608 | 0 | 0 | 0 | 11.1944 | 0 | 13.2486 | 11.2513 | 9.2572 | 11.7566 | 0 | 12.6251 | 0 | 13.0759 | 0 | 0 | 0 | 5.7553 | 10.2292 | 0 | 11.0215 | 14.4716 | 6.0676 | 13.3212 | 13.1767 | 0 | 6.6434 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4422 | 0 | 0 | 8.8184 | 0 | 11.8904 | 0 | 14.9012 | 0 | 13.8265 | 9.5811 | 0 | 10.451 | 0 | 12.8137 | 0 | 9.8632 | 0 | 10.8611 | 13.8369 | 0 | 0 | 11.058 | 13.9276 | 0 | 0 | 11.4206 | 13.8465 | 9.7289 | 0 | 0 | 9.9937 | 0 | 13.3133 | 14.7716 | 10.7037 | 0 | 0 | 0 | 0 | 11.4184 | 13.4477 | 0 | 13.3732 | 9.9873 | 7.6446 | 0 | 14.276 | 6.4032 | 0 | 0 | 9.697 | 6.7757 | 0 | 13.7543 | 0 | 0 | 13.0829 | 0 | 0 | 12.2201 | 0 | 10.3302 | 0 | 10.2175 | 9.2822 | 12.7542 | 8.5765 | 0 | 0 | 13.7366 | 8.3822 | 0 | 13.8097 | 5.6533 | 12.2129 | 0 | 0 | 0 | 11.01 | 12.4985 | 0 | 12.0208 | 12.1977 | 13.8935 | 12.5702 | 13.7298 | 10.2994 | 0 | 9.619 | 0 | 13.6508 | 12.559 | 10.7352 | 11.6045 | 0 | 11.1144 | 10.0574 | 8.6688 | 0 | 8.5219 | 13.4832 | 7.5109 | 8.3675 | 0 | 5.5551 | 0 | 0 | 8.85 | 0 | 0 | 9.7385 | 13.5888 | 0 | 12.8541 | 0 | 0 | 0 | 0 | 0 | 13.0127 | 13.4487 | 0 | 0 | 10.6579 | 13.3405 | 12.1418 | 0 | 0 | 0 | 13.2267 | 8.1251 | 0 | 0 | 12.4481 | 0 | 12.7642 | 0 | 13.4253 | 14.6942 | 7.2846 | 0 | 10.7004 | 0 | 0 | 12.6622 | 11.6185 | 11.4123 | 0 | 8.4705 | 0 | 0 | 9.2135 | 9.0552 | 0 | 0 | 13.2371 | 0 | 0 | 10.9182 | 0 | 0 | 9.891 | 13.6597 | 0 | 0 | 0 | 0 | 11.1448 | 10.221 | 13.7581 | 0 | 11.3181 | 0 | 0 | 13.4602 | 0 | 0 | 0 | 14.9413 | 0 | 8.2039 | 14.0558 | 7.0433 | 8.4586 | 11.9754 | 0 | 0 | 0 | 10.8287 | 12.9065 | 10.2063 | 0 | 0 | 0 | 11.5438 | 0 | 0 | 0 | 0 | 8.466 | 0 | 0 | 11.8388 | 14.9645 | 11.7383 | 10.8381 | 11.8973 | 0 | 12.2098 | 0 | 9.4099 | 0 | 10.8076 | 11.1943 | 0 | 13.4917 | 12.3742 | 0 | 0 | 8.1139 | 0 | 0 | 8.9567 | 9.1815 | 0 | 14.5749 | 0 | 0 | 0 | 8.7042 | 13.7849 | 11.3082 | 0 | 0 | 8.8137 | 0 | 12.9473 | 13.2342 | 14.5171 | 0 | 12.6936 | 0 | 0 | 10.1694 | 0 | 0 | 9.8671 | 0 | 12.0835 | 11.0242 | 0 | 9.8451 | 0 | 12.4144 | 8.7509 | 12.1233 | 0 | 0 | 0 | 11.9792 | 14.7509 | 8.663 | 11.5726 | 0 | 8.8703 | 0 | 10.7467 | 0 | 12.0264 | 10.5796 | 13.5578 | 0 | 13.2487 | 0 | 14.7372 | 0 | 11.5718 | 12.0428 | 8.5317 | 0 | 9.1331 | 10.1331 | 0 | 0 | 0 | 10.0489 | 0 | 0 | 10.4096 | 0 | 7.9863 | 0 | 14.2249 | 0 | 9.6398 | 0 | 13.827 | 0 | 11.4029 | 14.0083 | 0 | 14.6295 | 8.3977 | 12.2431 | 0 | 0 | 12.8994 | 10.1701 | 0 | 10.9856 | 11.899 | 0 | 0 | 0 | 13.1117 | 8.3342 | 0 | 0 | 13.8109 | 0 | 11.5187 | 13.7718 | 12.5456 | 10.3398 | 9.9146 | 0 | 7.9518 | 11.9958 | 5.7566 | 10.2311 | 9.9919 | 0 | 8.6331 | 8.0005 | 13.6031 | 0 | 14.022 | 0 | 10.8023 | 0 | 14.0977 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4265 | 0 | 11.3544 | 0 | 10.6052 | 0 | 14.1907 | 0 | 0 | 9.9713 | 0 | 0 | 8.7297 | 9.8064 | 0 | 14.6096 | 13.1198 | 0 | 0 | 8.8559 | 5.5724 | 0 | 11.6231 | 13.473 | 9.9634 | 0 | 8.4067 | 11.453 | 0 | 13.1256 | 0 | 14.9479 | 14.2911 | 0 | 13.894 | 9.5465 | 0 | 0 | 14.8658 | 14.2499 | 0 | 8.2715 | 0 | 13.1085
#NAME? |  |  | 1303997.3635 | 1303997.3635 |  |  | 56 | 0 | 0 |  |  | 4.c |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4756 | 8.6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.98 | 0 | 8.5442 | 8.464 | 0 | 8.2556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6529 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 0 | 8.53 | 0 | 8.4482 | 0 | 0 | 0 | 0 | 0 | 4.9989 | 0 | 0 | 7.3885 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8516 | 7.5403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6195 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9385 | 8.3483 | 8.6275 | 0 | 0 | 0 | 0 | 0 | 8.3666 | 0 | 0 | 0 | 0 | 0 | 8.8665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6537 | 7.5044 | 0 | 0 | 0 | 0 | 0 | 8.0226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3337 | 0 | 7.7693 | 0 | 0 | 7.5813 | 0 | 0 | 0 | 0 | 0 | 8.1798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8116 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4846 | 6.5157 | 0 | 0 | 0 | 8.6365 | 7.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7398 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4554 | 0 | 8.1684 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1736 | 8.9677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2873 | 8.8092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5257 | 0 | 7.8489 | 0 | 0 | 0 | 0 | 8.7538 | 0 | 0 | 0 | 8.2999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6589 | 0 | 0 | 0 | 0 | 8.4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3927 | 0 | 0 | 0 | 0 | 6.7962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2055 | 0 | 0 | 0 | 7.852 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2726 | 0 | 8.1057 | 0 | 8.2488 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2741 | 0 | 7.7172 | 0 | 0 | 0 | 0 | 8.2873 | 0 | 0 | 0 | 0 | 0 | 7.8925 | 0 | 0 | 8.8844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4733 | 0
#NAME? |  |  | 224555.2443 | 224555.2443 |  |  | 57 | 0 | 0 |  |  | 5.a |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.808 | 0 | 13.5077 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5201 | 0 | 14.4542 | 12.2993 | 14.9165 | 0 | 11.9758 | 0 | 13.4985 | 0 | 0 | 0 | 13.6908 | 0 | 0 | 0 | 15.4329 | 15.2256 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8091 | 0 | 0 | 0 | 15.7769 | 13.8499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6603 | 0 | 0 | 0 | 0 | 0 | 15.4529 | 0 | 0 | 0 | 0 | 0 | 11.2805 | 14.0985 | 13.5444 | 0 | 0 | 0 | 0 | 0 | 0 | 13.1881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.3193 | 11.4002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2205 | 0 | 0 | 15.0012 | 0 | 0 | 0 | 0 | 12.9447 | 0 | 0 | 0 | 0 | 0 | 11.6193 | 0 | 0 | 15.8626 | 0 | 14.5774 | 0 | 0 | 0 | 0 | 15.3201 | 12.2839 | 0 | 0 | 13.7085 | 0 | 13.9974 | 12.9673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7256 | 0 | 0 | 0 | 0 | 14.9581 | 0 | 15.7163 | 0 | 0 | 0 | 0 | 0 | 14.7453 | 0 | 0 | 0 | 0 | 15.9159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0107 | 0 | 0 | 0 | 0 | 0 | 14.2564 | 15.9617 | 0 | 0 | 14.6892 | 0 | 0 | 0 | 0 | 0 | 13.3926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9152 | 0 | 0 | 0 | 0 | 11.5357 | 0 | 11.5818 | 0 | 0 | 14.3149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.0814 | 0 | 13.5914 | 13.5731 | 0 | 12.6548 | 0 | 0 | 0 | 0 | 0 | 11.9823 | 0 | 14.8258 | 0 | 0 | 13.7373 | 0 | 0 | 0 | 0 | 14.7798 | 13.8192 | 0 | 15.8632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.1438 | 0 | 0 | 12.0144 | 15.4283 | 13.7541 | 0 | 11.5192 | 0 | 0 | 0 | 13.8047 | 0 | 0 | 0 | 0 | 14.2014 | 0 | 13.2716 | 0 | 0 | 0 | 0 | 13.5682 | 0 | 0 | 0 | 0 | 0 | 15.6343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4219 | 15.8933 | 0 | 0 | 0 | 12.8867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.133 | 0 | 14.1473 | 0 | 13.5269 | 0 | 0 | 0 | 14.7313 | 15.5105 | 0 | 0 | 15.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1569 | 13.0586 | 0 | 0 | 0 | 12.2542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.9 | 0 | 0 | 0 | 15.8981 | 0 | 0 | 0 | 12.218 | 0 | 0 | 0 | 14.9283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0397 | 15.8744 | 0 | 0 | 0 | 0 | 0 | 15.8091 | 0 | 15.5016 | 0 | 0 | 13.0204 | 0 | 0 | 0 | 0 | 0 | 15.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5552 | 0 | 15.1706 | 0 | 0 | 11.1194 | 14.4842 | 13.6332 | 0 | 14.3973 | 0 | 0 | 14.7691 | 14.815 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0367 | 0 | 13.7706 | 0 | 0 | 0 | 14.8931 | 0 | 0 | 14.0189 | 14.8861 | 0 | 15.9177 | 0 | 0 | 0 | 0 | 12.5554 | 0 | 0 | 0 | 15.4209 | 0 | 0 | 15.3365 | 0 | 11.7847 | 0 | 0 | 13.6589 | 13.2098 | 0 | 12.4076 | 0 | 0 | 0 | 14.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4705 | 11.351 | 0 | 11.7348 | 0 | 15.8721 | 0 | 15.1857 | 0 | 14.1278 | 11.609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6916 | 0 | 0 | 0 | 0 | 14.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.0177 | 0 | 0 | 0 | 13.9813 | 14.1722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6363 | 0 | 14.2333 | 0 | 0 | 15.9276 | 0 | 0 | 14.3092 | 0 | 0 | 0 | 12.7234 | 0 | 12.6433 | 0 | 0 | 0 | 15.1072 | 0 | 13.4767 | 0 | 15.7147 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6289 | 0 | 14.3839 | 15.0241 | 0 | 0 | 0 | 13.2568 | 0 | 0 | 0 | 0 | 0 | 13.2831 | 0 | 14.1604 | 0 | 14.5247 | 13.95 | 14.8997 | 11.1809 | 0 | 12.3661 | 0 | 0 | 12.9503 | 0 | 13.6026 | 0 | 15.551 | 0 | 0 | 0 | 0 | 15.3484 | 0 | 15.2383 | 0 | 14.6441 | 0 | 0 | 0 | 13.6745 | 0 | 0 | 0 | 13.6138 | 0 | 0 | 0 | 12.6248 | 0 | 0 | 15.2459 | 0 | 0 | 0 | 14.5495 | 15.1472 | 11.6352 | 0 | 0 | 0 | 12.3071 | 0 | 0 | 0 | 13.8348 | 0 | 0 | 15.5502 | 0 | 0 | 0 | 14.5029 | 0 | 0 | 15.787 | 0 | 15.8657 | 0 | 0 | 0 | 0 | 14.9164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.7446 | 0 | 13.3816 | 0 | 0 | 14.1957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3286 | 0 | 15.7733 | 11.8914 | 0 | 11.5015 | 0 | 0 | 0 | 13.0504 | 0 | 0 | 0 | 15.2853 | 14.5864 | 11.4526 | 0 | 0 | 0 | 15.8289 | 0 | 0 | 0 | 13.5844 | 11.1866 | 13.3432 | 0 | 0 | 15.2027 | 0 | 0 | 11.4479 | 0 | 11.9919 | 0 | 0 | 0 | 15.4903 | 0 | 0 | 13.1903 | 0 | 0 | 0 | 0 | 0 | 15.6888 | 0 | 0 | 0 | 13.4453 | 12.5981 | 0 | 0 | 13.7681 | 0 | 0 | 15.6045 | 0 | 0 | 11.5911 | 13.8624 | 15.0693 | 0 | 0 | 0 | 0 | 11.8782 | 0 | 14.3081 | 14.5634 | 0 | 11.4479 | 0 | 0 | 0 | 11.081 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4385 | 0 | 0 | 0 | 0 | 13.0027 | 0 | 0 | 0 | 12.0565 | 0 | 12.1042 | 0 | 0 | 13.9074 | 12.5199 | 0 | 0 | 0 | 0 | 0 | 13.5623 | 0 | 12.9879 | 0 | 15.1452 | 0 | 0 | 14.6939 | 0 | 0 | 14.7759 | 0 | 0 | 12.356 | 0 | 0 | 0 | 15.7544 | 0 | 15.1828 | 15.8443 | 0 | 0 | 0 | 0 | 0 | 15.4505 | 0 | 13.8389 | 0 | 0 | 0 | 14.6767 | 0 | 0 | 15.9885 | 0 | 14.4144 | 0 | 0 | 12.3829 | 0 | 0 | 0 | 0 | 11.9067 | 0 | 0 | 0 | 15.8986 | 12.8952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.8383 | 0 | 0 | 0 | 13.0827 | 0 | 14.9021 | 0 | 0 | 0 | 0 | 0 | 14.5143 | 0 | 0 | 0 | 12.7083 | 14.4727 | 0 | 0 | 14.7746 | 0 | 15.9824 | 0 | 14.2759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9523 | 0 | 0 | 0 | 0 | 11.4245 | 0 | 0 | 14.1457 | 0 | 0 | 13.2418 | 14.8419 | 0 | 0 | 0 | 0 | 14.0606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.2434 | 0 | 0 | 0 | 0 | 14.5894 | 12.7306 | 12.2602 | 14.7732 | 0 | 0 | 0 | 0 | 14.4315 | 0 | 0 | 0 | 0 | 0 | 0 | 15.8074 | 13.8197 | 0 | 0 | 15.3869 | 0 | 0 | 15.0972 | 15.6725 | 0 | 0 | 15.1486 | 0 | 0 | 0 | 13.1096 | 0 | 0 | 13.8492 | 0 | 15.161 | 0 | 0 | 0 | 0 | 0 | 15.3051 | 0 | 0 | 0 | 14.7817 | 0 | 0 | 0
#NAME? |  |  | 710918.4391 | 710918.4391 |  |  | 58 | 0 | 0 |  |  | 5.b |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 |  |  | 59 | 0 | 0 |  |  | 6.a |  |  | 12.7407 | 11.2075 | 11.3951 | 6.7099 | 7.0031 | 11.9208 | 11.4804 | 0 | 0 | 0 | 10.3025 | 13.0136 | 11.8675 | 8.8857 | 9.8112 | 14.9228 | 0 | 7.0411 | 0 | 0 | 0 | 10.1863 | 0 | 9.324 | 0 | 8.6383 | 14.8049 | 10.6196 | 0 | 11.8188 | 14.4977 | 11.2168 | 0 | 0 | 0 | 8.0693 | 7.4368 | 10.8088 | 6.4476 | 12.0438 | 0 | 8.9013 | 10.6981 | 0 | 0 | 0 | 8.7627 | 11.8951 | 0 | 10 | 9.5259 | 10.5574 | 10.9664 | 9.2064 | 12.9147 | 11.8542 | 7.7087 | 9.1987 | 14.1119 | 0 | 9.1235 | 0 | 0 | 0 | 0 | 7.9037 | 0 | 0 | 12.3575 | 0 | 10.5773 | 11.0159 | 0 | 0 | 0 | 0 | 8.7244 | 11.191 | 0 | 0 | 13.6753 | 10.4138 | 0 | 0 | 8.2781 | 8.829 | 7.3897 | 13.1408 | 4.8445 | 12.1129 | 0 | 0 | 0 | 11.8913 | 5.6747 | 0 | 7.214 | 12.2798 | 6.2732 | 9.0732 | 11.2881 | 11.6433 | 11.4848 | 12.9911 | 11.3391 | 0 | 14.801 | 0 | 14.655 | 0 | 0 | 9.7063 | 13.1997 | 14.344 | 13.8169 | 0 | 12.9254 | 13.5075 | 0 | 12.795 | 13.0761 | 0 | 13.5495 | 13.4794 | 0 | 7.0033 | 0 | 12.4419 | 0 | 0 | 8.471 | 0 | 0 | 12.0513 | 9.7196 | 0 | 13.6849 | 0 | 0 | 10.5582 | 9.3134 | 13.9013 | 11.304 | 8.6491 | 14.9705 | 11.9206 | 9.6369 | 0 | 6.6194 | 11.813 | 14.8306 | 10.0332 | 0 | 9.8435 | 0 | 6.4256 | 9.3208 | 13.0007 | 9.8626 | 14.981 | 0 | 5.8899 | 7.5786 | 10.5098 | 8.3211 | 0 | 8.737 | 12.9095 | 0 | 13.8705 | 12.531 | 14.206 | 10.7105 | 13.1885 | 9.934 | 0 | 13.1126 | 11.2877 | 14.5641 | 14.1846 | 12.3822 | 0 | 0 | 7.0938 | 14.0704 | 0 | 12.0839 | 0 | 0 | 14.7235 | 10.8005 | 0 | 10.7957 | 14.4332 | 10.5083 | 8.4318 | 0 | 0 | 7.3968 | 0 | 9.7472 | 0 | 9.3504 | 5.7894 | 0 | 11.3803 | 0 | 11.2694 | 5.221 | 0 | 10.4082 | 13.8553 | 14.805 | 9.2201 | 12.4383 | 12.7929 | 0 | 11.704 | 12.3373 | 12.1552 | 0 | 11.6361 | 0 | 6.2076 | 0 | 0 | 10.3023 | 0 | 14.7334 | 5.9716 | 0 | 0 | 0 | 0 | 14.3231 | 0 | 6.7482 | 9.9995 | 0 | 13.8826 | 11.632 | 7.7822 | 10.5595 | 0 | 0 | 0 | 0 | 14.8136 | 0 | 4.8203 | 10.1872 | 12.094 | 9.4705 | 14.0607 | 0 | 12.0379 | 7.1952 | 0 | 0 | 0 | 8.7574 | 0 | 0 | 0 | 0 | 0 | 12.5577 | 11.0227 | 10.3693 | 0 | 13.528 | 10.1601 | 14.9056 | 8.6917 | 0 | 11.5391 | 0 | 12.2274 | 11.3943 | 7.1547 | 13.9673 | 0 | 5.203 | 8.2392 | 14.6805 | 12.0846 | 10.1787 | 0 | 9.8367 | 8.0634 | 10.967 | 14.4024 | 10.5364 | 0 | 7.1362 | 12.0795 | 14.8358 | 0 | 0 | 7.6495 | 12.5845 | 0 | 0 | 0 | 0 | 10.0028 | 12.0483 | 11.0334 | 11.1229 | 0 | 0 | 0 | 11.3749 | 12.4875 | 0 | 9.6235 | 0 | 13.6034 | 11.044 | 0 | 0 | 0 | 8.3366 | 0 | 0 | 10.2493 | 0 | 0 | 0 | 0 | 8.1878 | 0 | 0 | 11.3894 | 13.2308 | 0 | 11.5214 | 12.8102 | 12.8299 | 7.7504 | 7.2346 | 10.3469 | 13.3413 | 9.3056 | 5.8858 | 0 | 10.3472 | 9.4301 | 12.0512 | 14.176 | 14.8073 | 0 | 8.1174 | 11.5303 | 0 | 0 | 14.9638 | 14.5951 | 8.3155 | 0 | 12.9281 | 10.0904 | 13.3692 | 14.8847 | 7.5307 | 10.7295 | 14.4166 | 0 | 10.8945 | 13.249 | 0 | 13.8534 | 0 | 7.6497 | 9.1177 | 12.1717 | 10.528 | 14.6081 | 8.9095 | 12.4413 | 0 | 14.2561 | 9.5324 | 0 | 0 | 12.7309 | 0 | 11.5174 | 0 | 0 | 0 | 10.543 | 0 | 8.3576 | 11.3621 | 12.7939 | 8.5945 | 12.2997 | 0 | 0 | 14.3171 | 0 | 0 | 13.1608 | 14.4812 | 0 | 8.1091 | 9.5743 | 0 | 9.5729 | 0 | 4.9157 | 11.4862 | 0 | 12.3909 | 11.7986 | 10.0876 | 0 | 0 | 0 | 11.5608 | 13.1782 | 0 | 14.1365 | 7.8909 | 0 | 9.1874 | 9.6026 | 8.3063 | 0 | 11.5511 | 0 | 12.4271 | 8.0891 | 0 | 0 | 0 | 8.0528 | 0 | 12.5704 | 6.901 | 0 | 0 | 12.1365 | 13.0658 | 11.6588 | 13.725 | 13.2159 | 0 | 0 | 5.6364 | 0 | 8.2282 | 7.6366 | 14.7184 | 0 | 8.7418 | 8.0461 | 0 | 0 | 9.3685 | 0 | 0 | 8.9296 | 9.8683 | 0 | 0 | 14.2764 | 11.2865 | 11.3954 | 0 | 13.9336 | 10.989 | 0 | 0 | 0 | 8.2448 | 9.8967 | 0 | 0 | 13.913 | 0 | 11.7403 | 11.9463 | 0 | 0 | 11.8639 | 14.6029 | 0 | 7.4643 | 12.5019 | 0 | 10.6928 | 9.6498 | 10.572 | 13.567 | 11.4219 | 8.4485 | 0 | 0 | 8.1924 | 0 | 6.123 | 0 | 7.8636 | 0 | 9.3851 | 0 | 0 | 9.4434 | 12.0253 | 9.1153 | 12.795 | 11.6903 | 10.9799 | 12.7644 | 0 | 14.8238 | 7.3249 | 12.2471 | 12.7777 | 12.8668 | 10.4326 | 13.18 | 14.244 | 0 | 10.7986 | 0 | 14.2144 | 8.4849 | 14.8747 | 14.971 | 0 | 8.8133 | 13.3075 | 0 | 0 | 0 | 14.4555 | 10.652 | 0 | 7.8149 | 9.2967 | 8.4645 | 12.9385 | 11.0027 | 0 | 9.4071 | 14.665 | 13.501 | 0 | 0 | 6.9286 | 11.1444 | 11.483 | 8.6545 | 7.2257 | 9.0218 | 7.5566 | 0 | 14.26 | 0 | 0 | 14.0057 | 0 | 12.5139 | 10.371 | 0 | 12.7407 | 12.9301 | 13.564 | 0 | 10.1065 | 0 | 14.0907 | 8.5012 | 9.5842 | 0 | 14.7224 | 0 | 12.5726 | 0 | 10.7797 | 13.7981 | 10.7543 | 0 | 13.5031 | 12.7639 | 0 | 10.4628 | 0 | 0 | 10.7815 | 13.6656 | 0 | 0 | 0 | 13.2133 | 9.6806 | 0 | 11.254 | 0 | 14.5201 | 0 | 11.8457 | 0 | 0 | 0 | 0 | 13.4064 | 0 | 9.031 | 12.3664 | 0 | 13.9925 | 0 | 9.7336 | 0 | 11.8522 | 13.2061 | 10.8004 | 9.6696 | 0 | 8.167 | 0 | 5.722 | 0 | 8.0119 | 8.8213 | 10.6002 | 0 | 0 | 13.5696 | 10.2424 | 0 | 11.3375 | 0 | 6.6926 | 0 | 10.4511 | 12.8057 | 0 | 13.5853 | 13.286 | 8.4602 | 0 | 0 | 0 | 11.5218 | 13.9436 | 0 | 0 | 14.8987 | 14.8204 | 8.2649 | 0 | 5.2887 | 13.1596 | 0 | 9.1495 | 8.3074 | 14.8341 | 0 | 0 | 13.573 | 0 | 0 | 0 | 14.4153 | 13.765 | 7.5613 | 14.7229 | 0 | 6.6731 | 5.9503 | 12.62 | 0 | 13.0838 | 11.4868 | 11.4853 | 8.2652 | 8.4237 | 0 | 8.5907 | 13.4488 | 0 | 8.9955 | 0 | 13.318 | 14.6375 | 0 | 9.5152 | 0 | 7.0392 | 12.6599 | 10.2352 | 0 | 13.2589 | 12.0057 | 0 | 13.2693 | 0 | 14.14 | 7.1412 | 0 | 0 | 9.9394 | 14.4438 | 12.1997 | 9.8097 | 9.5901 | 12.2384 | 12.9823 | 0 | 12.1145 | 0 | 0 | 12.8324 | 0 | 9.372 | 10.169 | 9.421 | 0 | 12.6701 | 13.3471 | 9.7362 | 0 | 0 | 0 | 14.6893 | 0 | 8.609 | 0 | 6.1126 | 13.9517 | 0 | 0 | 0 | 0 | 10.9507 | 12.8697 | 0 | 9.875 | 0 | 0 | 11.4368 | 0 | 12.6738 | 0 | 12.013 | 0 | 14.327 | 12.1251 | 0 | 9.2367 | 13.2761 | 0 | 0 | 13.6791 | 0 | 12.916 | 13.0704 | 10.6203 | 0 | 0 | 7.8861 | 12.2662 | 0 | 8.4805 | 11.2573 | 0 | 13.8438 | 8.5489 | 0 | 0 | 0 | 9.1859 | 13.3133 | 12.99 | 0 | 0 | 14.2466 | 0 | 0 | 8.0491 | 0 | 10.8123 | 14.5711 | 13.6527 | 0 | 10.0117 | 13.9233 | 7.6591 | 7.2548 | 0 | 10.455 | 0 | 13.4032 | 12.6944 | 14.9586 | 9.0674 | 0 | 10.4003 | 10.9842 | 5.1543 | 0 | 0 | 0 | 9.4507 | 11.6732 | 0 | 0 | 13.4059 | 6.1371 | 0 | 5.7779 | 12.3023 | 0 | 12.1182 | 0 | 11.978 | 0 | 0 | 4.755 | 0 | 8.3065 | 10.2933 | 0 | 11.0816 | 6.8916 | 0 | 11.5132 | 0 | 12.6319 | 0 | 12.2548 | 0 | 0 | 0 | 8.7991 | 0 | 14.5718 | 9.7447 | 0 | 11.2537 | 0 | 0 | 14.1326 | 0 | 0 | 0 | 13.444 | 0 | 13.6042 | 0 | 10.6792 | 13.9784 | 0 | 7.4702 | 0 | 7.0835 | 11.1762 | 0 | 9.799 | 11.3261 | 12.4278 | 0 | 0 | 10.4993 | 7.1014 | 10.4035 | 11.9724 | 11.1442 | 8.4009 | 10.7685 | 0 | 0 | 0 | 12.2532 | 5.8341 | 8.6791 | 0 | 0 | 0 | 6.4058 | 14.3186 | 10.3081 | 12.6069 | 7.5694 | 0 | 14.4981 | 11.8001 | 7.4394 | 0 | 0 | 10.6673 | 13.6472 | 0 | 6.0774 | 0 | 13.9481 | 0 | 11.6798 | 11.1188 | 6.7089 | 9.1197 | 12.9483 | 11.877 | 13.3555 | 12.757 | 0 | 14.4239 | 11.3517 | 12.885 | 14.9818 | 0 | 13.6701 | 14.6011 | 0 | 11.137 | 9.1813 | 0 | 0 | 0 | 11.8597 | 8.5488 | 0 | 0 | 6.7681 | 12.3206 | 8.1789 | 0 | 9.2795 | 6.6423 | 10.7908 | 0 | 0 | 7.6317 | 11.6541 | 8.5821 | 10.8596 | 14.8082 | 12.3679 | 11.2905 | 8.0562 | 14.7195 | 8.985 | 0 | 8.34 | 14.8371 | 0 | 7.1519 | 0 | 0 | 0 | 0 | 8.264 | 8.3564 | 8.6765 | 6.3884 | 0 | 14.0718 | 9.9935 | 14.063 | 10.697 | 0 | 8.6848 | 0 | 0 | 12.9719 | 11.7191 | 0 | 8.67 | 13.5357 | 0 | 0 | 14.7066 | 14.5409 | 0 | 9.3332 | 5.6497 | 9.7229 | 0 | 14.9365 | 6.6913 | 0 | 13.9309 | 0 | 13.2103 | 0 | 8.6192 | 13.3938 | 6.7463 | 0 | 12.5238 | 11.0316 | 4.9154 | 0 | 10.357 | 14.9136 | 11.9117
#NAME? |  |  | 3263202.7444 | 3263202.7444 |  |  | 60 | 0 | 0 |  |  | 6.b |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7316 | 0 | 0 | 0 | 0 | 7.2659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1214 | 0 | 0 | 5.1506 | 6.2498 | 6.9094 | 0 | 7.5742 | 0 | 0 | 8.7521 | 0 | 0 | 4.114 | 0 | 0 | 0 | 0 | 0 | 6.2182 | 7.7056 | 0 | 0 | 0 | 8.9864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7069 | 0 | 0 | 6.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4517 | 0 | 0 | 0 | 7.3445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8595 | 7.7383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.694 | 8.1784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6473 | 7.8388 | 0 | 0 | 0 | 6.8432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7793 | 0 | 0 | 0 | 7.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7197 | 8.9553 | 8.8389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9115 | 0 | 0 | 8.0628 | 0 | 0 | 0 | 0 | 0 | 7.3945 | 0 | 0 | 7.2072 | 0 | 8.2633 | 0 | 0 | 0 | 0 | 6.864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4086 | 0 | 8.1446 | 8.3912 | 0 | 0 | 0 | 0 | 8.2916 | 8.4486 | 0 | 0 | 0 | 8.1481 | 0 | 7.0625 | 0 | 0 | 0 | 8.9586 | 0 | 0 | 0 | 5.7329 | 0 | 8.9148 | 0 | 0 | 6.1532 | 0 | 0 | 8.0223 | 0 | 0 | 8.9617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5116 | 0 | 0 | 0 | 0 | 0 | 8.9986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2761 | 0 | 7.4519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0674 | 0 | 0 | 7.458 | 0 | 0 | 7.419 | 8.6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6037 | 8.6297 | 0 | 0 | 0 | 0 | 0 | 8.5686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6332 | 7.0792 | 0 | 0 | 0 | 6.6831 | 0 | 0 | 7.1472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8312 | 0 | 0 | 8.1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3073 | 0 | 0 | 0 | 6.1843 | 0 | 0 | 8.1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.961 | 0 | 8.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3018 | 6.7106 | 0 | 0 | 0 | 7.5908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0992 | 0 | 7.9321 | 0 | 0 | 8.3757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8378 | 0 | 0 | 0 | 0 | 4.9212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7241 | 0 | 0 | 8.7364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.18 | 0 | 0 | 0 | 0 | 0 | 7.4501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9121 | 0 | 0 | 0 | 8.0449 | 0 | 0 | 8.0029 | 0 | 8.385 | 0 | 0 | 0 | 7.4625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7774 | 0 | 0 | 0 | 0 | 7.6205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3205 | 0 | 0 | 0 | 0 | 7.9405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4575 | 0 | 0 | 0 | 0 | 0 | 6.8105 | 0 | 8.6369 | 0 | 0 | 0 | 0 | 0 | 6.1371 | 0 | 8.0138 | 0 | 6.8576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6556 | 5.7795 | 0 | 0 | 0 | 0 | 0 | 7.6124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0385 | 0 | 0 | 7.5828 | 0 | 0 | 0 | 0 | 6.7641 | 0 | 0 | 0 | 0 | 8.8337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 879364.4788 | 0 |  |  | 61 | 0 | 0 |  |  | 7.a |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.577 | 0 | 9.7609 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7183 | 0 | 7.6263 | 11.2286 | 7.6512 | 0 | 10.697 | 0 | 8.8728 | 0 | 0 | 0 | 7.8003 | 0 | 0 | 0 | 12.1104 | 5.8424 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6926 | 0 | 0 | 0 | 7.8575 | 12.3687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5789 | 0 | 0 | 0 | 0 | 0 | 6.6746 | 0 | 0 | 0 | 0 | 0 | 10.1454 | 11.8242 | 10.3397 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.337 | 8.8851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7314 | 0 | 0 | 5.9268 | 0 | 0 | 0 | 0 | 12.2752 | 0 | 0 | 0 | 0 | 0 | 11.3974 | 0 | 0 | 11.1412 | 0 | 6.3878 | 0 | 0 | 0 | 0 | 8.7417 | 12.4449 | 0 | 0 | 12.7839 | 0 | 12.7431 | 4.6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7205 | 0 | 0 | 0 | 0 | 11.2749 | 0 | 7.8638 | 0 | 0 | 0 | 0 | 0 | 12.527 | 0 | 0 | 0 | 0 | 9.7242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8962 | 0 | 0 | 0 | 0 | 0 | 8.1125 | 10.2126 | 0 | 0 | 8.0877 | 0 | 0 | 0 | 0 | 0 | 12.8102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.059 | 0 | 0 | 0 | 0 | 11.1924 | 0 | 10.6163 | 0 | 0 | 12.0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.6231 | 0 | 10.2504 | 10.0725 | 0 | 12.788 | 0 | 0 | 0 | 0 | 0 | 11.4176 | 0 | 6.6668 | 0 | 0 | 12.5822 | 0 | 0 | 0 | 0 | 7.2992 | 11.5571 | 0 | 12.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6634 | 0 | 0 | 7.161 | 8.2203 | 5.1848 | 0 | 11.7548 | 0 | 0 | 0 | 6.3418 | 0 | 0 | 0 | 0 | 12.128 | 0 | 12.2439 | 0 | 0 | 0 | 0 | 8.7009 | 0 | 0 | 0 | 0 | 0 | 11.8324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4701 | 10.7574 | 0 | 0 | 0 | 12.7204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.9385 | 0 | 11.4453 | 0 | 8.0884 | 0 | 0 | 0 | 4.9581 | 11.89 | 0 | 0 | 10.5434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8752 | 9.7406 | 0 | 0 | 0 | 11.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.088 | 0 | 0 | 0 | 6.7685 | 0 | 0 | 0 | 12.7818 | 0 | 0 | 0 | 11.287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8625 | 12.616 | 0 | 0 | 0 | 0 | 0 | 12.6969 | 0 | 11.1964 | 0 | 0 | 7.9157 | 0 | 0 | 0 | 0 | 0 | 7.3002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.962 | 0 | 11.7726 | 0 | 0 | 8.2838 | 8.4987 | 12.6986 | 0 | 11.4691 | 0 | 0 | 12.3862 | 5.9157 | 0 | 0 | 0 | 0 | 0 | 0 | 13.1176 | 0 | 10.7922 | 0 | 0 | 0 | 12.5921 | 0 | 0 | 10.2302 | 8.3431 | 0 | 7.6508 | 0 | 0 | 0 | 0 | 11.8306 | 0 | 0 | 0 | 12.5849 | 0 | 0 | 12.649 | 0 | 6.7388 | 0 | 0 | 12.6317 | 10.5641 | 0 | 11.3072 | 0 | 0 | 0 | 9.9786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8013 | 10.964 | 0 | 11.1386 | 0 | 12.3432 | 0 | 8.5756 | 0 | 9.8622 | 10.0166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8446 | 0 | 0 | 0 | 0 | 8.513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7489 | 0 | 0 | 0 | 11.0605 | 8.0272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7467 | 0 | 11.9938 | 0 | 0 | 8.1317 | 0 | 0 | 10.292 | 0 | 0 | 0 | 12.7012 | 0 | 11.7659 | 0 | 0 | 0 | 12.0108 | 0 | 11.2773 | 0 | 7.3161 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8281 | 0 | 8.0922 | 12.5502 | 0 | 0 | 0 | 12.2144 | 0 | 0 | 0 | 0 | 0 | 9.9461 | 0 | 5.736 | 0 | 9.1126 | 10.8454 | 10.6317 | 11.2589 | 0 | 8.8958 | 0 | 0 | 9.8116 | 0 | 8.5551 | 0 | 7.3676 | 0 | 0 | 0 | 0 | 13.4612 | 0 | 6.1303 | 0 | 6.0608 | 0 | 0 | 0 | 12.6718 | 0 | 0 | 0 | 6.9217 | 0 | 0 | 0 | 7.1358 | 0 | 0 | 11.4388 | 0 | 0 | 0 | 8.2278 | 11.6894 | 11.516 | 0 | 0 | 0 | 10.8031 | 0 | 0 | 0 | 9.8448 | 0 | 0 | 11.7264 | 0 | 0 | 0 | 7.2991 | 0 | 0 | 10.6994 | 0 | 6.7983 | 0 | 0 | 0 | 0 | 12.1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2405 | 0 | 6.0787 | 0 | 0 | 10.0306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0139 | 0 | 8.775 | 9.6729 | 0 | 11.2582 | 0 | 0 | 0 | 9.4297 | 0 | 0 | 0 | 9.8431 | 6.714 | 11.582 | 0 | 0 | 0 | 4.4528 | 0 | 0 | 0 | 11.0768 | 6.5778 | 12.1661 | 0 | 0 | 11.2697 | 0 | 0 | 11.0542 | 0 | 12.347 | 0 | 0 | 0 | 8.5611 | 0 | 0 | 10.8997 | 0 | 0 | 0 | 12.3099 | 0 | 12.0505 | 0 | 0 | 0 | 7.1139 | 9.427 | 0 | 0 | 6.1617 | 0 | 0 | 6.7198 | 0 | 0 | 11.6891 | 10.3311 | 11.5601 | 0 | 0 | 0 | 0 | 6.5373 | 0 | 12.6059 | 10.8357 | 0 | 7.2485 | 0 | 0 | 0 | 12.3715 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7663 | 0 | 0 | 0 | 0 | 11.1947 | 0 | 0 | 0 | 12.7094 | 0 | 5.4216 | 0 | 0 | 8.0174 | 10.903 | 0 | 0 | 0 | 0 | 0 | 7.4785 | 0 | 10.3763 | 0 | 10.1445 | 0 | 0 | 11.1895 | 0 | 0 | 10.4587 | 0 | 0 | 11.8667 | 0 | 0 | 0 | 11.4131 | 0 | 12.686 | 11.8161 | 0 | 0 | 0 | 0 | 0 | 12.1274 | 0 | 10.6499 | 0 | 0 | 0 | 7.3295 | 0 | 0 | 6.5623 | 0 | 6.2929 | 0 | 0 | 10.7934 | 0 | 0 | 0 | 0 | 12.9674 | 0 | 0 | 0 | 10.212 | 9.3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9294 | 0 | 0 | 0 | 10.6796 | 0 | 5.7139 | 0 | 0 | 0 | 0 | 0 | 12.8302 | 0 | 0 | 0 | 4.0844 | 10.1004 | 0 | 0 | 11.3984 | 0 | 12.4865 | 0 | 12.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.0871 | 0 | 0 | 0 | 0 | 11.9891 | 0 | 0 | 12.5351 | 0 | 0 | 12.3564 | 6.4195 | 0 | 0 | 0 | 0 | 12.057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9391 | 0 | 0 | 0 | 0 | 11.5949 | 11.1719 | 10.6277 | 11.6625 | 0 | 0 | 0 | 0 | 11.1376 | 0 | 0 | 0 | 0 | 0 | 0 | 6.834 | 12.3685 | 0 | 0 | 8.4577 | 0 | 0 | 12.099 | 9.1951 | 0 | 0 | 12.8964 | 0 | 0 | 0 | 11.6936 | 0 | 0 | 10.7316 | 0 | 11.9732 | 0 | 0 | 0 | 0 | 0 | 11.2078 | 0 | 0 | 0 | 4.6855 | 0 | 0 | 0
#NAME? |  |  | 793136.6887 | 423066.6522 |  |  | 62 | 0 | 0 |  |  | 8.a |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3696 | 0 | 10.2445 | 0 | 0 | 0 | 0 | 0 | 0 | 11.054 | 0 | 6.8649 | 6.4297 | 6.9244 | 0 | 9.2189 | 0 | 10.7049 | 0 | 0 | 0 | 8.3382 | 0 | 0 | 0 | 7.6824 | 7.2929 | 0 | 0 | 0 | 0 | 0 | 0 | 11.211 | 0 | 0 | 0 | 11.459 | 9.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4221 | 0 | 0 | 0 | 0 | 0 | 7.4216 | 0 | 0 | 0 | 0 | 0 | 10.2111 | 6.6437 | 8.1994 | 0 | 0 | 0 | 0 | 0 | 0 | 9.8344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5376 | 9.2762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9479 | 0 | 0 | 10.8807 | 0 | 0 | 0 | 0 | 11.1506 | 0 | 0 | 0 | 0 | 0 | 10.0936 | 0 | 0 | 5.7699 | 0 | 9.864 | 0 | 0 | 0 | 0 | 11.8325 | 9.1822 | 0 | 0 | 11.9223 | 0 | 11.4629 | 11.863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3075 | 0 | 0 | 0 | 0 | 8.7628 | 0 | 11.3486 | 0 | 0 | 0 | 0 | 0 | 4.2603 | 0 | 0 | 0 | 0 | 6.5923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0758 | 0 | 0 | 0 | 0 | 0 | 8.8993 | 7.7169 | 0 | 0 | 10.2141 | 0 | 0 | 0 | 0 | 0 | 5.5585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4128 | 0 | 0 | 0 | 0 | 11.8202 | 0 | 10.7599 | 0 | 0 | 6.122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0996 | 0 | 6.2873 | 8.4941 | 0 | 10.2652 | 0 | 0 | 0 | 0 | 0 | 11.1013 | 0 | 8.7895 | 0 | 0 | 9.0288 | 0 | 0 | 0 | 0 | 11.8336 | 5.3383 | 0 | 10.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.552 | 0 | 0 | 6.5463 | 9.0413 | 10.1075 | 0 | 8.7415 | 0 | 0 | 0 | 7.628 | 0 | 0 | 0 | 0 | 10.3604 | 0 | 10.6453 | 0 | 0 | 0 | 0 | 11.6035 | 0 | 0 | 0 | 0 | 0 | 5.6974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.586 | 11.5246 | 0 | 0 | 0 | 8.0283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5818 | 0 | 11.1837 | 0 | 11.4439 | 0 | 0 | 0 | 7.0645 | 11.6778 | 0 | 0 | 10.6933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.1235 | 9.8265 | 0 | 0 | 0 | 7.4559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2564 | 0 | 0 | 0 | 9.8711 | 0 | 0 | 0 | 9.4756 | 0 | 0 | 0 | 7.9831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2901 | 5.9917 | 0 | 0 | 0 | 0 | 0 | 10.1505 | 0 | 11.0941 | 0 | 0 | 10.6871 | 0 | 0 | 0 | 0 | 0 | 10.8153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0238 | 0 | 9.2634 | 0 | 0 | 9.5055 | 10.2925 | 10.886 | 0 | 5.842 | 0 | 0 | 9.9843 | 10.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3654 | 0 | 9.4598 | 0 | 0 | 0 | 10.9104 | 0 | 0 | 11.4236 | 10.8651 | 0 | 11.0615 | 0 | 0 | 0 | 0 | 7.3361 | 0 | 0 | 0 | 11.1415 | 0 | 0 | 6.4539 | 0 | 9.5702 | 0 | 0 | 5.5824 | 9.0367 | 0 | 8.7054 | 0 | 0 | 0 | 6.2809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.356 | 11.0031 | 0 | 9.0194 | 0 | 7.5864 | 0 | 8.8477 | 0 | 11.8178 | 8.1259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.3567 | 0 | 0 | 0 | 0 | 10.7008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3239 | 0 | 0 | 0 | 9.4573 | 11.4263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7252 | 0 | 9.9275 | 0 | 0 | 9.801 | 0 | 0 | 8.5191 | 0 | 0 | 0 | 10.7958 | 0 | 5.0199 | 0 | 0 | 0 | 7.4191 | 0 | 9.0593 | 0 | 9.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7658 | 0 | 8.7833 | 6.7292 | 0 | 0 | 0 | 6.2379 | 0 | 0 | 0 | 0 | 0 | 10.8795 | 0 | 11.7057 | 0 | 11.5607 | 11.5917 | 11.3107 | 4.2169 | 0 | 11.2775 | 0 | 0 | 10.9153 | 0 | 5.4046 | 0 | 10.2601 | 0 | 0 | 0 | 0 | 10.4683 | 0 | 10.9371 | 0 | 10.3055 | 0 | 0 | 0 | 8.0819 | 0 | 0 | 0 | 7.7674 | 0 | 0 | 0 | 9.9654 | 0 | 0 | 11.9801 | 0 | 0 | 0 | 8.2923 | 6.7344 | 11.8273 | 0 | 0 | 0 | 10.87 | 0 | 0 | 0 | 11.0949 | 0 | 0 | 10.6346 | 0 | 0 | 0 | 9.2456 | 0 | 0 | 9.1507 | 0 | 10.3118 | 0 | 0 | 0 | 0 | 11.0101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0801 | 0 | 11.6238 | 0 | 0 | 11.5336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.0582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9703 | 0 | 11.5155 | 8.761 | 0 | 11.8138 | 0 | 0 | 0 | 10.8404 | 0 | 0 | 0 | 6.6487 | 10.1486 | 10.8089 | 0 | 0 | 0 | 9.9199 | 0 | 0 | 0 | 5.874 | 8.473 | 8.3062 | 0 | 0 | 11.3707 | 0 | 0 | 11.3225 | 0 | 4.3256 | 0 | 0 | 0 | 7.6676 | 0 | 0 | 9.3864 | 0 | 0 | 0 | 5.5455 | 0 | 8.1819 | 0 | 0 | 0 | 8.8481 | 10.8757 | 0 | 0 | 10.725 | 0 | 0 | 6.3091 | 0 | 0 | 7.6124 | 5.2639 | 8.1962 | 0 | 0 | 0 | 0 | 6.9747 | 0 | 11.0183 | 10.6193 | 0 | 10.2289 | 0 | 0 | 0 | 10.2501 | 0 | 0 | 0 | 0 | 0 | 0 | 11.1016 | 0 | 0 | 0 | 0 | 10.0778 | 0 | 0 | 0 | 10.8342 | 0 | 10.4968 | 0 | 0 | 9.2871 | 7.5582 | 0 | 0 | 0 | 0 | 0 | 6.5896 | 0 | 7.7522 | 0 | 8.9416 | 0 | 0 | 11.2787 | 0 | 0 | 9.9773 | 0 | 0 | 10.9226 | 0 | 0 | 0 | 10.3765 | 0 | 9.1053 | 5.1173 | 0 | 0 | 0 | 0 | 0 | 6.8594 | 0 | 11.0576 | 0 | 0 | 0 | 11.4103 | 0 | 0 | 10.9829 | 0 | 9.8223 | 0 | 0 | 9.2936 | 0 | 0 | 0 | 0 | 5.8162 | 0 | 0 | 0 | 10.4911 | 8.5932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2809 | 0 | 0 | 0 | 10.4499 | 0 | 11.3086 | 0 | 0 | 0 | 0 | 0 | 7.621 | 0 | 0 | 0 | 10.8164 | 9.5867 | 0 | 0 | 10.4225 | 0 | 8.4914 | 0 | 11.4445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8511 | 0 | 0 | 0 | 0 | 11.0211 | 0 | 0 | 11.7056 | 0 | 0 | 8.4537 | 7.3729 | 0 | 0 | 0 | 0 | 11.3283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8739 | 0 | 0 | 0 | 0 | 11.1931 | 7.1925 | 9.3318 | 10.2965 | 0 | 0 | 0 | 0 | 7.5711 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7951 | 8.912 | 0 | 0 | 11.2901 | 0 | 0 | 4.7853 | 9.6997 | 0 | 0 | 9.0708 | 0 | 0 | 0 | 6.5024 | 0 | 0 | 10.8387 | 0 | 8.7288 | 0 | 0 | 0 | 0 | 0 | 11.854 | 0 | 0 | 0 | 10.7413 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 |  |  | 63 | 0 | 0 |  |  | 8.b |  |  | 4.1962 | 6.9931 | 7.3741 | 5.1202 | 7.762 | 7.0564 | 5.909 | 0 | 8.3382 | 0 | 7.2505 | 7.1261 | 5.2702 | 7.6451 | 4.8888 | 7.7835 | 0 | 8.3491 | 0 | 0 | 0 | 6.5429 | 0 | 4.3832 | 0 | 8.9458 | 7.3602 | 6.5619 | 0 | 6.9618 | 8.2415 | 8.3826 | 0 | 0 | 7.3046 | 4.7919 | 4.0368 | 8.9204 | 6.5593 | 4.2826 | 0 | 8.4212 | 5.4514 | 4.3995 | 0 | 0 | 8.3408 | 6.4028 | 8.4779 | 7.9708 | 5.5958 | 7.4951 | 5.2578 | 6.2428 | 5.4917 | 4.0235 | 8.6629 | 6.3609 | 7.0076 | 7.0905 | 7.463 | 0 | 7.2076 | 6.0837 | 8.3029 | 7.0632 | 6.7857 | 0 | 6.2914 | 6.3833 | 5.5388 | 6.9584 | 6.4447 | 0 | 0 | 0 | 6.3213 | 4.0224 | 7.4874 | 8.7713 | 5.2126 | 8.4485 | 0 | 7.6267 | 5.7488 | 6.3794 | 7.0513 | 8.9659 | 4.0965 | 6.9759 | 0 | 0 | 8.7428 | 8.8812 | 5.1481 | 6.0903 | 6.8179 | 7.7225 | 7.5587 | 6.351 | 7.6738 | 6.0458 | 6.3333 | 4.8348 | 8.2013 | 5.2248 | 8.7766 | 0 | 7.4396 | 7.309 | 0 | 7.6903 | 4.2413 | 7.6331 | 4.1393 | 0 | 8.4039 | 8.4624 | 5.4869 | 7.6321 | 8.6774 | 0 | 4.7797 | 8.3903 | 0 | 8.8629 | 0 | 8.0802 | 5.9696 | 7.4695 | 5.2873 | 0 | 0 | 6.5606 | 7.128 | 0 | 5.2823 | 0 | 0 | 5.7973 | 8.159 | 8.2297 | 7.0254 | 7.6499 | 5.5134 | 6.4599 | 6.615 | 0 | 8.0926 | 8.8566 | 8.4937 | 7.0742 | 0 | 8.7192 | 0 | 6.9777 | 8.5997 | 8.164 | 8.2514 | 8.3794 | 0 | 6.3423 | 5.4732 | 6.3912 | 4.6105 | 0 | 7.9913 | 8.442 | 6.2288 | 8.5936 | 5.1126 | 4.9371 | 6.0141 | 6.5667 | 7.7658 | 0 | 8.0732 | 8.7319 | 7.2487 | 5.9521 | 4.3817 | 0 | 0 | 6.739 | 4.6445 | 0 | 4.4703 | 8.242 | 5.4434 | 4.9229 | 4.0753 | 0 | 8.8035 | 4.0086 | 6.7887 | 7.9028 | 5.7261 | 5.7855 | 4.9257 | 0 | 7.205 | 6.8706 | 5.6876 | 8.929 | 0 | 8.8912 | 0 | 4.4959 | 4.2036 | 0 | 4.5044 | 8.3252 | 8.0639 | 8.0697 | 6.5509 | 4.1859 | 7.7213 | 7.8113 | 6.1549 | 7.1178 | 4.7566 | 7.6058 | 0 | 6.8406 | 0 | 0 | 4.252 | 0 | 4.0208 | 8.4489 | 8.4809 | 5.1293 | 4.3378 | 0 | 4.018 | 0 | 5.3722 | 6.7679 | 0 | 5.3273 | 5.1511 | 4.8019 | 5.4127 | 0 | 0 | 8.8322 | 0 | 6.4481 | 7.7957 | 8.2949 | 7.9338 | 7.7111 | 6.0819 | 7.9234 | 7.2967 | 8.657 | 5.7581 | 7.5179 | 0 | 6.3831 | 8.9479 | 0 | 0 | 0 | 8.3684 | 0 | 6.5919 | 8.4347 | 4.2677 | 0 | 6.402 | 8.6146 | 8.9023 | 6.8612 | 0 | 8.6042 | 0 | 8.7322 | 8.748 | 8.8376 | 5.9277 | 0 | 6.4533 | 8.4891 | 7.0357 | 6.5392 | 8.6734 | 0 | 6.2995 | 5.7512 | 4.1688 | 8.7227 | 8.9302 | 8.5193 | 7.1484 | 8.6465 | 4.868 | 0 | 0 | 8.7749 | 5.9369 | 4.6962 | 0 | 8.3635 | 8.9367 | 8.4639 | 5.2108 | 6.5816 | 8.3467 | 8.4943 | 4.8234 | 0 | 6.5583 | 5.4011 | 4.4525 | 4.9721 | 5.2057 | 7.2853 | 6.899 | 0 | 6.1097 | 0 | 8.7836 | 0 | 7.2019 | 7.1292 | 7.4006 | 0 | 0 | 8.1698 | 5.7271 | 0 | 5.9189 | 4.6574 | 7.3529 | 5.6762 | 8.3091 | 7.5792 | 7.5891 | 4.7448 | 4.6043 | 7.4059 | 5.3365 | 6.7305 | 4.8653 | 4.0915 | 6.3852 | 4.6299 | 8.2685 | 7.967 | 8.8759 | 6.4246 | 5.637 | 8.7259 | 0 | 0 | 7.7001 | 7.3406 | 4.5759 | 0 | 6.7242 | 5.3981 | 6.1317 | 8.8601 | 4.2755 | 5.6974 | 6.5254 | 0 | 8.4108 | 8.9845 | 6.9907 | 5.7554 | 5.3221 | 7.7594 | 5.23 | 7.5677 | 8.8976 | 4.4882 | 6.9325 | 5.213 | 0 | 4.499 | 6.9066 | 6.7112 | 0 | 5.1401 | 6.3704 | 8.8326 | 0 | 6.8857 | 6.9437 | 5.6939 | 0 | 6.6029 | 4.0745 | 7.0566 | 8.0224 | 5.0102 | 7.0177 | 6.9311 | 6.1646 | 0 | 0 | 5.8546 | 5.5031 | 5.7772 | 4.6342 | 6.8476 | 0 | 8.6325 | 0 | 7.7792 | 7.8367 | 0 | 7.9446 | 7.8591 | 8.497 | 8.5891 | 7.0301 | 0 | 7.4539 | 6.2061 | 8.1275 | 6.9401 | 6.1013 | 8.5203 | 4.4965 | 8.8745 | 6.5484 | 0 | 5.1395 | 0 | 7.3832 | 7.4147 | 0 | 0 | 0 | 7.6465 | 0 | 6.7299 | 5.6316 | 0 | 0 | 4.4064 | 5.1025 | 5.8672 | 6.6859 | 8.0767 | 7.4386 | 0 | 8.5969 | 0 | 8.0686 | 7.2765 | 5.4516 | 0 | 6.2121 | 4.3079 | 0 | 0 | 7.2576 | 0 | 5.7642 | 5.7028 | 5.7548 | 7.9379 | 0 | 7.4359 | 4.4273 | 4.8277 | 0 | 5.1689 | 7.7438 | 0 | 6.0974 | 0 | 7.3271 | 7.6379 | 0 | 0 | 6.8545 | 0 | 5.3701 | 7.8665 | 5.1025 | 0 | 5.2382 | 6.3037 | 7.472 | 7.958 | 8.2974 | 6.8226 | 6.2827 | 5.8105 | 8.1327 | 7.8154 | 6.7485 | 7.135 | 0 | 0 | 4.4856 | 0 | 7.6687 | 0 | 6.9042 | 0 | 8.1884 | 0 | 0 | 7.5358 | 7.5761 | 5.5862 | 8.0686 | 4.0957 | 5.2307 | 7.8697 | 6.7297 | 5.9238 | 6.8287 | 8.7649 | 7.3292 | 4.7806 | 7.7212 | 7.4883 | 7.9262 | 8.5614 | 4.8189 | 5.6491 | 5.8386 | 5.2944 | 6.6364 | 7.5436 | 0 | 8.6473 | 6.1386 | 8.1646 | 5.0824 | 0 | 6.9888 | 8.8418 | 5.7784 | 8.0441 | 5.9216 | 8.7859 | 6.7982 | 7.7912 | 0 | 4.411 | 4.4158 | 8.2354 | 0 | 0 | 8.1283 | 6.1355 | 7.1718 | 8.9693 | 6.125 | 5.3777 | 8.0166 | 0 | 8.3923 | 0 | 7.829 | 8.6555 | 0 | 7.0334 | 5.2836 | 0 | 4.1962 | 5.4686 | 6.6688 | 0 | 6.103 | 0 | 6.012 | 6.8172 | 5.7206 | 0 | 6.6348 | 0 | 5.7663 | 0 | 6.1416 | 5.383 | 4.4161 | 5.8802 | 4.0408 | 5.6028 | 0 | 6.0391 | 0 | 0 | 8.3857 | 4.2277 | 6.63 | 0 | 4.715 | 5.3179 | 4.786 | 8.5146 | 6.1859 | 0 | 5.7606 | 0 | 8.2512 | 0 | 0 | 0 | 0 | 5.7156 | 0 | 5.8991 | 8.9477 | 0 | 6.8202 | 0 | 4.1518 | 0 | 7.1544 | 7.6182 | 4.6206 | 4.5897 | 0 | 5.7065 | 0 | 8.5738 | 0 | 6.1156 | 8.2645 | 6.7311 | 0 | 7.1296 | 5.8241 | 5.681 | 0 | 5.434 | 4.2455 | 7.575 | 0 | 7.0103 | 5.7925 | 0 | 6.9343 | 4.6915 | 6.4119 | 0 | 0 | 0 | 8.1374 | 6.4392 | 8.3834 | 0 | 7.7317 | 5.2616 | 7.4156 | 0 | 7.5545 | 7.6131 | 0 | 4.6376 | 5.1347 | 6.5455 | 0 | 4.7887 | 5.7619 | 0 | 8.2427 | 0 | 4.9872 | 5.4629 | 8.3953 | 7.9793 | 0 | 6.216 | 6.7372 | 7.0684 | 7.0445 | 5.9325 | 5.9765 | 4.8335 | 7.2118 | 8.3844 | 5.2546 | 7.2796 | 8.9983 | 0 | 8.0059 | 0 | 5.3101 | 4.1877 | 0 | 7.4796 | 7.9519 | 4.8905 | 8.0335 | 7.0869 | 6.9074 | 5.1712 | 7.079 | 4.0171 | 4.3062 | 7.9177 | 8.389 | 7.9945 | 0 | 7 | 4.6736 | 8.3461 | 8.1281 | 4.4776 | 7.5079 | 5.5553 | 6.5775 | 0 | 6.7011 | 0 | 0 | 5.8676 | 0 | 6.2706 | 4.0675 | 5.1308 | 0 | 8.8479 | 7.3756 | 8.0078 | 0 | 0 | 0 | 7.7846 | 7.7895 | 5.1336 | 0 | 5.8997 | 5.1817 | 4.3679 | 0 | 0 | 0 | 4.2478 | 6.5178 | 0 | 8.9785 | 7.1637 | 0 | 5.618 | 0 | 6.2928 | 8.5914 | 8.9232 | 0 | 8.1129 | 6.778 | 0 | 6.0589 | 8.6325 | 8.5084 | 0 | 4.9339 | 0 | 7.637 | 5.6212 | 7.9649 | 0 | 0 | 4.6122 | 8.4609 | 0 | 5.7947 | 8.385 | 0 | 7.2597 | 4.5084 | 0 | 0 | 0 | 6.4272 | 4.3985 | 5.3285 | 4.6569 | 0 | 8.665 | 0 | 0 | 6.3759 | 0 | 6.5375 | 4.9525 | 4.3386 | 0 | 8.8572 | 7.9104 | 7.3222 | 7.1602 | 5.6471 | 8.2664 | 0 | 4.9901 | 4.6257 | 8.5034 | 5.9643 | 0 | 4.146 | 4.6976 | 5.9556 | 0 | 8.3822 | 0 | 7.8913 | 8.4776 | 0 | 0 | 5.5183 | 7.9713 | 4.6447 | 6.8302 | 6.4732 | 0 | 6.0105 | 0 | 6.4529 | 0 | 8.5017 | 8.4239 | 0 | 8.1908 | 5.2826 | 0 | 6.1142 | 7.2884 | 0 | 4.7914 | 8.8304 | 4.9028 | 0 | 7.2334 | 0 | 0 | 5.9688 | 8.8624 | 5.9189 | 8.5377 | 5.8509 | 0 | 7.8096 | 0 | 6.3909 | 6.8687 | 8.9337 | 0 | 5.3152 | 5.7828 | 0 | 5.2667 | 0 | 7.0872 | 4.6764 | 0 | 6.4084 | 8.6554 | 6.4883 | 4.2641 | 0 | 4.429 | 8.632 | 5.2865 | 0 | 0 | 8.5565 | 5.7834 | 4.766 | 7.3964 | 8.7172 | 7.5009 | 7.9973 | 7.7083 | 6.8576 | 0 | 6.707 | 4.95 | 7.2354 | 0 | 4.9882 | 0 | 8.3598 | 4.6198 | 8.394 | 7.4566 | 6.7566 | 0 | 6.1452 | 6.0467 | 5.5237 | 0 | 0 | 4.5017 | 4.5103 | 0 | 4.3891 | 0 | 8.0408 | 0 | 8.3685 | 6.6295 | 6.1301 | 7.3165 | 5.216 | 6.2874 | 8.6143 | 8.7266 | 0 | 8.7955 | 5.6097 | 4.2951 | 6.0483 | 0 | 8.6148 | 7.3575 | 0 | 7.5373 | 7.2162 | 0 | 0 | 5.1802 | 8.0762 | 8.479 | 7.0374 | 0 | 8.3849 | 7.0529 | 7.5595 | 7.7969 | 5.5194 | 5.4515 | 8.9189 | 0 | 4.6572 | 8.221 | 4.4501 | 6.1726 | 6.8371 | 4.1979 | 6.5086 | 8.4633 | 8.4752 | 7.7156 | 7.9712 | 0 | 5.0759 | 7.2432 | 6.4769 | 7.0979 | 0 | 0 | 0 | 0 | 4.7184 | 8.4272 | 5.9117 | 4.2199 | 0 | 4.6067 | 8.7745 | 8.6373 | 5.4706 | 8.8428 | 8.7012 | 0 | 0 | 7.1674 | 6.1857 | 0 | 5.5753 | 7.4413 | 0 | 0 | 7.5456 | 7.4696 | 0 | 5.9406 | 4.1038 | 7.0773 | 0 | 7.6502 | 5.8187 | 0 | 6.9222 | 0 | 5.2005 | 5.5993 | 6.6612 | 8.3445 | 4.6475 | 0 | 5.8505 | 4.2916 | 6.8267 | 0 | 4.8642 | 8.5765 | 8.3962
#NAME? |  |  | 255354.2237 | 0 | [7 empty] | 9.a |  |  | 5.8492 | 7.9965 | 5.9632 | 5.6107 | 4.5544 | 4.1188 | 6.5972 | 5.4651 | 4.3005 | 4.0158 | 4.6152 | 5.5174 | 5.0664 | 5.3487 | 6.2841 | 4.5104 | 5.1067 | 4.3078 | 6.1515 | 4.506 | 4.9196 | 7.8846 | 7.0248 | 5.9973 | 6.4923 | 7.0332 | 5.8669 | 6.1959 | 7.3397 | 7.4277 | 4.1046 | 7.4264 | 4.5142 | 7.6434 | 5.5116 | 4.8491 | 6.9531 | 7.5308 | 7.5489 | 6.7095 | 4.0972 | 5.4966 | 7.505 | 6.9366 | 4.0581 | 4.5253 | 5.2191 | 7.1121 | 4.3007 | 7.2424 | 6.1812 | 6.8901 | 6.0605 | 4.1476 | 5.9463 | 7.8397 | 7.1593 | 6.0853 | 7.5034 | 4.7771 | 5.9694 | 4.7618 | 5.3058 | 6.4313 | 5.4746 | 4.6508 | 7.0556 | 7.6108 | 7.1478 | 4.8342 | 5.9829 | 5.4563 | 7.6197 | 6.3854 | 7.3695 | 4.5418 | 6.7359 | 6.4918 | 4.5679 | 7.0756 | 5.2893 | 4.0466 | 4.3925 | 4.062 | 4.6265 | 4.8851 | 4.2209 | 7.7607 | 7.6459 | 6.7906 | 7.6886 | 6.3622 | 7.7365 | 6.6345 | 7.101 | 7.5734 | 7.9215 | 6.2531 | 5.5292 | 4.9583 | 6.9827 | 5.59 | 7.6258 | 7.2558 | 7.7651 | 6.2047 | 5.6543 | 4.2467 | 6.6371 | 4.0914 | 5.8583 | 5.2541 | 6.3792 | 5.1303 | 6.202 | 7.5711 | 4.7256 | 7.098 | 5.4472 | 7.2537 | 4.9778 | 7.9254 | 5.4507 | 4.7923 | 5.2599 | 4.1423 | 7.3197 | 5.044 | 7.0532 | 6.3932 | 4.193 | 7.3055 | 5.8234 | 7.5813 | 5.7348 | 7.2398 | 5.2726 | 4.1552 | 6.613 | 4.8056 | 7.7523 | 7.1671 | 4.4101 | 7.8901 | 4.377 | 4.9525 | 5.4332 | 5.6251 | 6.0446 | 4.046 | 6.834 | 5.7437 | 6.4381 | 4.0124 | 7.703 | 6.2039 | 6.9806 | 4.5226 | 4.8111 | 5.5477 | 5.5797 | 7.6119 | 4.9968 | 7.3213 | 5.7034 | 6.0242 | 6.6611 | 7.4243 | 5.9349 | 7.699 | 7.4528 | 6.7265 | 4.0397 | 7.0177 | 4.3526 | 4.3685 | 6.6906 | 6.4741 | 5.8237 | 7.5156 | 7.4807 | 5.1577 | 5.5879 | 6.7324 | 6.9879 | 7.0273 | 4.9314 | 5.077 | 6.2519 | 4.3053 | 7.7536 | 6.9088 | 4.4802 | 4.4802 | 5.2489 | 5.6641 | 4.5861 | 6.8767 | 5.2605 | 5.6271 | 6.9444 | 4.2171 | 5.0035 | 5.7727 | 7.3395 | 4.3968 | 6.7557 | 7.8528 | 5.9809 | 6.3326 | 5.5049 | 4.9156 | 7.7462 | 6.7432 | 7.5236 | 5.2293 | 7.073 | 6.7988 | 5.4219 | 5.6077 | 7.1649 | 4.9527 | 7.3353 | 7.7102 | 4.3464 | 6.4318 | 7.1682 | 4.056 | 7.3618 | 5.121 | 5.423 | 5.9405 | 7.2515 | 4.1596 | 5.3934 | 5.5925 | 7.2687 | 7.721 | 5.5871 | 4.6755 | 6.5018 | 7.177 | 7.595 | 7.3389 | 7.9923 | 4.6172 | 7.2349 | 5.2736 | 7.5591 | 7.2306 | 5.0456 | 6.5422 | 7.2034 | 4.0193 | 5.7641 | 7.7575 | 6.7237 | 6.2275 | 6.4727 | 5.4906 | 5.1164 | 7.8344 | 5.6911 | 6.7806 | 6.6493 | 4.0074 | 6.5863 | 5.1047 | 6.9116 | 4.6828 | 4.6587 | 7.1845 | 4.7338 | 6.7575 | 7.3673 | 5.0135 | 7.6426 | 7.4349 | 7.2485 | 6.2387 | 7.1698 | 5.5649 | 6.0655 | 7.8724 | 5.7477 | 5.6985 | 6.5871 | 6.34 | 7.5606 | 7.9218 | 4.2205 | 6.5917 | 4.4606 | 5.6421 | 4.1701 | 6.5357 | 5.6095 | 4.7715 | 7.9057 | 4.5642 | 7.0138 | 6.9264 | 7.2903 | 6.5723 | 4.6008 | 6.2881 | 4.433 | 4.4872 | 5.7606 | 4.4282 | 7.8439 | 5.4619 | 4.5948 | 4.7578 | 5.9665 | 4.8905 | 6.6827 | 7.3722 | 5.4871 | 4.5552 | 4.7176 | 6.9003 | 4.4151 | 7.4018 | 6.2707 | 7.5278 | 6.1638 | 7.1053 | 6.0187 | 4.1419 | 7.6963 | 5.2297 | 4.2167 | 6.005 | 5.2188 | 5.7456 | 6.1667 | 6.3775 | 6.0433 | 6.5622 | 4.9148 | 7.7131 | 5.5107 | 7.867 | 7.1413 | 6.9542 | 5.9063 | 6.9081 | 6.8627 | 4.3373 | 7.9742 | 7.6082 | 4.8688 | 5.778 | 6.5995 | 6.0235 | 4.81 | 4.7719 | 4.218 | 5.3041 | 7.3574 | 5.5556 | 7.3234 | 7.7004 | 7.4931 | 7.8503 | 5.2329 | 4.8193 | 7.3403 | 5.3046 | 6.4387 | 5.4614 | 5.2425 | 5.1744 | 4.1729 | 4.8119 | 6.027 | 7.0284 | 7.4748 | 5.8641 | 7.2422 | 6.1927 | 5.4068 | 6.3293 | 5.4383 | 4.8645 | 5.0492 | 6.3094 | 7.7356 | 7.8901 | 4.7697 | 7.469 | 4.5106 | 6.5923 | 6.6993 | 5.8762 | 4.0916 | 7.6046 | 6.0892 | 7.7338 | 6.2608 | 5.3142 | 4.743 | 5.8527 | 7.8536 | 5.6799 | 4.0844 | 7.7513 | 6.5202 | 6.7708 | 5.0751 | 7.8026 | 7.1543 | 6.4679 | 7.1991 | 6.3573 | 7.5422 | 6.5086 | 7.8153 | 4.0178 | 6.6662 | 7.5076 | 7.8469 | 4.1398 | 5.5218 | 7.2676 | 5.1567 | 5.6442 | 4.6399 | 7.4191 | 7.4709 | 7.8576 | 4.1882 | 4.9277 | 7.2585 | 4.3498 | 4.123 | 7.471 | 6.1946 | 6.7179 | 5.7916 | 6.4466 | 4.0884 | 4.1093 | 4.3719 | 5.7978 | 6.4309 | 4.1627 | 6.4916 | 4.8888 | 6.5768 | 7.4644 | 7.643 | 5.3909 | 7.9205 | 5.5609 | 4.2077 | 5.7565 | 4.858 | 7.5366 | 7.6982 | 5.48 | 7.8854 | 6.1489 | 4.823 | 4.4496 | 7.585 | 5.933 | 4.4512 | 7.4015 | 5.0984 | 4.1972 | 4.2743 | 7.3559 | 7.8782 | 7.7707 | 4.7313 | 5.8613 | 6.428 | 4.7277 | 4.9295 | 5.979 | 5.8358 | 5.5722 | 6.3018 | 5.3672 | 4.1381 | 6.2545 | 6.0676 | 5.8449 | 4.2139 | 4.5922 | 5.0753 | 6.1209 | 7.6399 | 6.7529 | 4.8034 | 5.8299 | 7.0102 | 6.4256 | 4.9641 | 7.2434 | 6.1271 | 6.8459 | 6.7663 | 7.602 | 4.3933 | 5.379 | 5.6195 | 4.9067 | 4.6754 | 4.1507 | 7.5655 | 5.5347 | 7.8072 | 6.1423 | 4.3633 | 5.1274 | 5.5968 | 7.8185 | 6.2532 | 5.8321 | 5.0864 | 7.7427 | 5.4846 | 7.5928 | 4.0499 | 4.2852 | 7.6727 | 4.4084 | 5.2199 | 7.631 | 5.7683 | 4.5566 | 4.9111 | 7.8339 | 6.1711 | 4.6746 | 4.8532 | 4.7647 | 6.0675 | 4.2455 | 4.8745 | 4.8277 | 4.998 | 5.4545 | 5.1058 | 5.1919 | 5.2913 | 4.9141 | 4.8383 | 4.0747 | 7.9084 | 5.4289 | 6.6747 | 4.5424 | 5.1476 | 7.4087 | 6.041 | 7.0242 | 7.7055 | 7.7522 | 7.0339 | 7.2519 | 7.0056 | 4.6984 | 5.2273 | 6.303 | 5.8492 | 5.3166 | 4.203 | 5.5722 | 6.0174 | 4.643 | 6.6466 | 5.0801 | 6.2836 | 4.3759 | 5.705 | 7.7556 | 4.344 | 7.711 | 5.1377 | 4.4052 | 4.3153 | 6.0461 | 6.2572 | 7.8101 | 7.7651 | 6.654 | 4.4159 | 6.075 | 5.7177 | 7.5046 | 7.5836 | 5.143 | 4.641 | 7.2323 | 5.9774 | 5.7952 | 6.3065 | 6.0108 | 5.2225 | 4.3213 | 6.6056 | 7.5517 | 5.9849 | 7.407 | 5.4496 | 7.5577 | 7.8707 | 4.1911 | 7.929 | 4.4936 | 7.0866 | 6.4636 | 5.9118 | 7.7606 | 7.5239 | 5.9649 | 7.8433 | 4.9262 | 5.9223 | 4.7802 | 6.0695 | 6.0682 | 6.8921 | 5.2785 | 6.86 | 7.6982 | 6.8104 | 4.8425 | 5.9932 | 6.6031 | 6.3635 | 4.3583 | 4.6285 | 7.3691 | 6.5875 | 5.6806 | 4.116 | 5.2813 | 7.5772 | 4.8648 | 4.5009 | 6.5585 | 4.8482 | 6.6658 | 4.4939 | 5.4227 | 7.8875 | 6.7337 | 6.1852 | 5.2973 | 5.3886 | 7.8892 | 5.9237 | 5.8866 | 7.3362 | 7.3666 | 6.9803 | 7.6058 | 5.017 | 5.5407 | 4.6659 | 7.7098 | 7.6663 | 7.7732 | 4.9344 | 6.1706 | 7.8738 | 4.332 | 6.0064 | 7.0512 | 4.5093 | 5.2045 | 6.3055 | 5.4252 | 5.8756 | 6.53 | 4.1413 | 6.7625 | 7.617 | 7.8972 | 6.3413 | 4.0643 | 4.9045 | 5.2002 | 5.1486 | 7.9524 | 6.5672 | 6.6404 | 5.306 | 7.8201 | 7.6971 | 6.0157 | 4.613 | 4.022 | 7.5779 | 6.5438 | 5.5493 | 7.4118 | 4.3006 | 4.2576 | 6.6957 | 5.6544 | 5.3855 | 7.6031 | 5.1521 | 7.4246 | 6.0173 | 6.8402 | 6.2945 | 5.3941 | 5.3071 | 6.7455 | 6.6618 | 4.4471 | 7.6244 | 6.5538 | 7.6682 | 4.7183 | 7.3841 | 5.1896 | 5.6336 | 4.0952 | 7.3211 | 6.1988 | 5.3327 | 6.6414 | 6.4498 | 5.9039 | 4.6793 | 5.547 | 7.3879 | 7.2268 | 7.4144 | 5.7401 | 7.8119 | 4.941 | 6.6015 | 5.6184 | 7.1738 | 5.71 | 5.7748 | 5.7639 | 4.5929 | 7.1746 | 7.3567 | 6.1609 | 6.6398 | 5.9122 | 7.1332 | 6.9102 | 6.1837 | 6.3577 | 7.2344 | 5.7278 | 7.1196 | 5.1488 | 5.2015 | 6.0949 | 7.5413 | 5.4967 | 7.3083 | 6.9269 | 7.6697 | 5.9826 | 5.2849 | 6.8614 | 5.9484 | 6.721 | 6.7988 | 7.8837 | 7.169 | 5.1067 | 6.5924 | 5.7203 | 5.6378 | 5.9886 | 5.7509 | 4.4861 | 5.9939 | 5.9424 | 4.9517 | 6.5597 | 5.3535 | 7.9645 | 7.8877 | 5.2006 | 6.6915 | 6.1648 | 7.9959 | 4.9172 | 5.0771 | 7.3717 | 6.2534 | 6.6109 | 5.578 | 6.6756 | 7.9853 | 4.2872 | 6.9001 | 4.1846 | 5.7784 | 7.9869 | 6.4583 | 4.1547 | 6.6347 | 4.7974 | 7.8278 | 4.2561 | 5.134 | 4.8434 | 5.1837 | 6.8057 | 6.8561 | 4.2042 | 6.6721 | 5.1563 | 4.375 | 5.8607 | 4.2526 | 4.4923 | 7.6753 | 7.0991 | 4.0217 | 7.9501 | 4.7794 | 4.6482 | 5.0887 | 6.9158 | 6.7176 | 7.724 | 7.0897 | 6.2844 | 6.7113 | 7.614 | 7.9439 | 7.81 | 6.5575 | 5.8882 | 7.9184 | 4.6286 | 7.33 | 6.4237 | 5.3391 | 5.1793 | 7.7199 | 7.227 | 7.146 | 4.4578 | 6.4134 | 4.5276 | 7.5871 | 4.2154 | 7.2142 | 5.4322 | 6.2932 | 7.5776 | 5.4136 | 6.1789 | 7.6684 | 7.3777 | 4.8689 | 5.6203 | 4.2842 | 5.2644 | 4.5637 | 7.4936 | 7.2207 | 7.868 | 7.8482 | 6.4387 | 4.9819 | 4.2212 | 7.543 | 4.8326 | 7.3334 | 7.9689 | 5.3041 | 7.1705 | 7.7275 | 4.822 | 4.9478 | 4.803 | 5.6701 | 5.9653 | 7.7329 | 6.8709 | 5.6229 | 6.5126 | 4.2375 | 7.8946 | 6.7866 | 4.8241 | 7.078 | 4.9547 | 7.4758 | 7.9676 | 7.6165 | 5.775 | 6.5816 | 7.9706 | 7.2233 | 4.0292 | 6.6786 | 6.476 | 6.8627 | 4.2446 | 6.7866 | 5.8954 | 7.723 | 4.0272 | 4.7847 | 5.0871 | 4.5478 | 7.9408 | 6.9167 | 7.2993 | 7.9499 | 5.0472 | 4.5051 | 4.9866 | 6.1788 | 6.925 | 6.7532 | 7.0013 | 4.9164 | 6.3869 | 7.8828 | 4.2538 | 6.7876 | 7.9039 | 6.1429 | 5.6783 | 7.5692 | 4.9574 | 5.4514 | 5.6548 | 4.1925 | 5.7436 | 7.8922 | 4.4818 | 7.3894 | 5.0662 | 7.2425 | 4.4525 | 4.5464 | 6.8475 | 4.3177 | 4.3551 | 6.7272 | 5.6215 | 5.7088 | 4.0528 | 6.166 | 5.0048 | 5.9224 | 7.0779 | 6.6872 | 5.1966 | 6.1644 | 7.3101 | 7.6239 | 7.7096 | 6.5266 | 7.3243 | 7.5727 | 4.2755 | 7.2345 | 4.4072 | 7.2374 | 6.7613 | 5.194 | 7.0254 | 7.3983 | 4.7137 | 7.7159 | 4.3144 | 6.4861 | 4.8781 | 5.2502 | 4.0036 | 5.201 | 7.1794 | 6.9826 | 6.8027 | 6.681 | 4.8518 | 6.4269 | 6.6851 | 4.9473 | 6.2647 | 6.5528 | 7.5484 | 7.0219 | 4.4489 | 7.0826 | 4.2368 | 4.3512
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 4425561.4313 | 154365.9198 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 5146413.4321 | 5146413.4321 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 216374.1306 | 216374.1306 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 3663071.7698 | 3663071.7698 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 2496259.6163 | 2496259.6163 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 4508547.2823 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 174286.9252 | 174286.9252 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 305647.8489 | 305647.8489 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 5561572.4862 | 5561572.4862 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 2616408.378 | 2382410.5682 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 501014.1584 | 501014.1584 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 923128.3738 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#NAME? |  |  | 211964.288 | 0
#NAME? |  |  | 180892.2613 | 0
#NAME? |  |  | 3439584.7696 | 3439584.7696
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1659649.6865 | 1659649.6865
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 774939.717 | 0
#NAME? |  |  | 202746.0915 | 0
#NAME? |  |  | 1983693.0686 | 133110.7284
#NAME? |  |  | 0 | 0
#NAME? |  |  | 290119.0744 | 290119.0744
#NAME? |  |  | 1184717.1939 | 1184717.1939
#NAME? |  |  | 176931.3915 | 0
#NAME? |  |  | 2007738.3049 | 0
#NAME? |  |  | 6302418.035 | 0
#NAME? |  |  | 243710.3599 | 243710.3599
#NAME? |  |  | 0 | 0
#NAME? |  |  | 543998.4601 | 286836.414
#NAME? |  |  | 0 | 0
#NAME? |  |  | 312796.7353 | 0
#NAME? |  |  | 94460.0925 | 94460.0925
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1267271.5773 | 1267271.5773
#NAME? |  |  | 1557606.6193 | 1287802.3387
#NAME? |  |  | 0 | 0
#NAME? |  |  | 11738276.0979 | 11738276.0979
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1663150.0423 | 1663150.0423
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4068629.4177 | 4068629.4177
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 279307.98 | 279307.98
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 412457.476 | 412457.476
#NAME? |  |  | 212170.9851 | 212170.9851
#NAME? |  |  | 2510295.0766 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 189037.3705 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3259722.1808 | 0
#NAME? |  |  | 841398.6995 | 841398.6995
#NAME? |  |  | 0 | 0
#NAME? |  |  | 180208.9246 | 180208.9246
#NAME? |  |  | 3952850.1653 | 666245.1196
#NAME? |  |  | 312939.9177 | 312939.9177
#NAME? |  |  | 121335.2705 | 121335.2705
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3047663.1131 | 195869.7842
#NAME? |  |  | 0 | 0
#NAME? |  |  | 319179.854 | 319179.854
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1764666.7401 | 1764666.7401
#NAME? |  |  | 204584.0974 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 289829.5148 | 289829.5148
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 178798.7006 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 222066.6358 | 222066.6358
#NAME? |  |  | 3345744.3614 | 3345744.3614
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2064235.4397 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 186716.5327 | 186716.5327
#NAME? |  |  | 812052.1867 | 812052.1867
#NAME? |  |  | 0 | 0
#NAME? |  |  | 155461.0943 | 155461.0943
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 418543.9431 | 418543.9431
#NAME? |  |  | 0 | 0
#NAME? |  |  | 239117.7106 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 17170038.8112 | 11321388.3475
#NAME? |  |  | 208619.5878 | 0
#NAME? |  |  | 2137051.6132 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3723034.1605 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 935522.6889 | 935522.6889
#NAME? |  |  | 0 | 0
#NAME? |  |  | 154088.1769 | 154088.1769
#NAME? |  |  | 0 | 0
#NAME? |  |  | 222839.8058 | 222839.8058
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3394700.2689 | 3394700.2689
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 21830544.7028 | 0
#NAME? |  |  | 164210.8419 | 164210.8419
#NAME? |  |  | 269183.5341 | 269183.5341
#NAME? |  |  | 3364604.9215 | 3364604.9215
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4007064.9281 | 4007064.9281
#NAME? |  |  | 5161988.6567 | 0
#NAME? |  |  | 3089538.0005 | 3089538.0005
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3961013.9887 | 0
#NAME? |  |  | 313338.9274 | 313338.9274
#NAME? |  |  | 9173824.1284 | 0
#NAME? |  |  | 4577714.807 | 0
#NAME? |  |  | 1713215.7044 | 0
#NAME? |  |  | 1916438.1819 | 1916438.1819
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1435805.5371 | 1435805.5371
#NAME? |  |  | 2532706.6317 | 2532706.6317
#NAME? |  |  | 493016.5243 | 295640.4613
#NAME? |  |  | 2599820.1402 | 0
#NAME? |  |  | 211594.9333 | 211594.9333
#NAME? |  |  | 1307492.7144 | 1307492.7144
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3095506.7158 | 2884666.5203
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 288569.9083 | 288569.9083
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 9927230.0836 | 9927230.0836
#NAME? |  |  | 797410.6388 | 504548.3575
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 279013.8681 | 0
#NAME? |  |  | 4298841.8575 | 0
#NAME? |  |  | 1945176.3149 | 1945176.3149
#NAME? |  |  | 3474865.1034 | 3474865.1034
#NAME? |  |  | 2725691.674 | 2725691.674
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3100372.3009 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 332086.0004 | 332086.0004
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 738564.0926 | 424482.2541
#NAME? |  |  | 3621430.0089 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 777555.4347 | 605318.262
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1761129.742 | 533275.3946
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1054029.9572 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3078827.7101 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 872730.3683 | 872730.3683
#NAME? |  |  | 0 | 0
#NAME? |  |  | 199960.5549 | 0
#NAME? |  |  | 217061.8853 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 154393.1166 | 0
#NAME? |  |  | 294191.0065 | 294191.0065
#NAME? |  |  | 0 | 0
#NAME? |  |  | 206751.7509 | 206751.7509
#NAME? |  |  | 269730.0613 | 269730.0613
#NAME? |  |  | 8382284.4681 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4096794.5456 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 782430.0766 | 782430.0766
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 333450.6245 | 333450.6245
#NAME? |  |  | 260618.1383 | 260618.1383
#NAME? |  |  | 659604.5254 | 0
#NAME? |  |  | 1739957.7379 | 369653.2056
#NAME? |  |  | 254648.1208 | 254648.1208
#NAME? |  |  | 167010.8212 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1376443.2519 | 402145.4793
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 164215.3576 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 797342.1381 | 797342.1381
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 847591.2633 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 289366.6592 | 289366.6592
#NAME? |  |  | 129643.8366 | 129643.8366
#NAME? |  |  | 0 | 0
#NAME? |  |  | 681946.7524 | 681946.7524
#NAME? |  |  | 0 | 0
#NAME? |  |  | 163914.9744 | 163914.9744
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 220221.1691 | 220221.1691
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5495735.0462 | 0
#NAME? |  |  | 2179381.3689 | 2179381.3689
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3721540.7671 | 982463.2089
#NAME? |  |  | 237737.047 | 237737.047
#NAME? |  |  | 4856462.7601 | 4856462.7601
#NAME? |  |  | 1396579.427 | 450358.5589
#NAME? |  |  | 1040638.7184 | 1040638.7184
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3780775.4238 | 3780775.4238
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1992327.5083 | 1992327.5083
#NAME? |  |  | 3383665.6645 | 0
#NAME? |  |  | 454538.1267 | 269108.7479
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2055096.7109 | 1389933.6303
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3820991.5421 | 3820991.5421
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 178927.038 | 0
#NAME? |  |  | 294682.2365 | 294682.2365
#NAME? |  |  | 5957816.8935 | 5957816.8935
#NAME? |  |  | 376571.3721 | 376571.3721
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2486517.2422 | 2486517.2422
#NAME? |  |  | 4619974.8521 | 306523.6154
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1174018.0807 | 0
#NAME? |  |  | 212206.8182 | 212206.8182
#NAME? |  |  | 202905.0565 | 202905.0565
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3166757.9464 | 3166757.9464
#NAME? |  |  | 276450.0844 | 276450.0844
#NAME? |  |  | 153011.0004 | 153011.0004
#NAME? |  |  | 0 | 0
#NAME? |  |  | 7952591.7289 | 711313.2019
#NAME? |  |  | 228269.8221 | 0
#NAME? |  |  | 443473.3212 | 443473.3212
#NAME? |  |  | 515183.2553 | 515183.2553
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 6496388.5315 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2406044.2357 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1496895.8044 | 1496895.8044
#NAME? |  |  | 2889471.3214 | 414118.8276
#NAME? |  |  | 4340103.5148 | 4340103.5148
#NAME? |  |  | 243047.7738 | 0
#NAME? |  |  | 271092.2171 | 271092.2171
#NAME? |  |  | 3838305.6987 | 3838305.6987
#NAME? |  |  | 229209.6988 | 229209.6988
#NAME? |  |  | 3165252.1956 | 3165252.1956
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 232761.9097 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3298441.1634 | 352795.1868
#NAME? |  |  | 698274.5836 | 698274.5836
#NAME? |  |  | 2751826.2233 | 0
#NAME? |  |  | 3921636.0889 | 0
#NAME? |  |  | 13681816.3095 | 13681816.3095
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 600743.6241 | 600743.6241
#NAME? |  |  | 0 | 0
#NAME? |  |  | 279205.6696 | 279205.6696
#NAME? |  |  | 4995915.8917 | 4995915.8917
#NAME? |  |  | 398904.0098 | 398904.0098
#NAME? |  |  | 200549.5495 | 0
#NAME? |  |  | 1166675.2382 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5821747.7103 | 5821747.7103
#NAME? |  |  | 370240.8924 | 370240.8924
#NAME? |  |  | 236767.9294 | 236767.9294
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 197914.6877 | 0
#NAME? |  |  | 36243308.7773 | 192544.679
#NAME? |  |  | 3747363.7807 | 3747363.7807
#NAME? |  |  | 352804.5638 | 352804.5638
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4422938.7806 | 0
#NAME? |  |  | 3500733.5237 | 639799.2636
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 10938591.8444 | 8985096.791
#NAME? |  |  | 2806068.5207 | 0
#NAME? |  |  | 5359056.9588 | 5359056.9588
#NAME? |  |  | 170549.0667 | 170549.0667
#NAME? |  |  | 223396.7189 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3082477.8127 | 3082477.8127
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3408869.8489 | 3408869.8489
#NAME? |  |  | 3763034.3815 | 3575237.8929
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5233080.5152 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 144761.7594 | 144761.7594
#NAME? |  |  | 0 | 0
#NAME? |  |  | 264815.3411 | 264815.3411
#NAME? |  |  | 2087761.4239 | 1796340.0954
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4130865.0144 | 191061.8037
#NAME? |  |  | 3343482.6874 | 3343482.6874
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 421935.5564 | 421935.5564
#NAME? |  |  | 0 | 0
#NAME? |  |  | 438067.0188 | 438067.0188
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1596056.3928 | 1596056.3928
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5984877.3046 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 6117645.5057 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2741307.4698 | 2741307.4698
#NAME? |  |  | 3528545.1311 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3881247.9401 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 206715.9379 | 206715.9379
#NAME? |  |  | 17953889.104 | 17953889.104
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 621417.2908 | 621417.2908
#NAME? |  |  | 452480.6492 | 452480.6492
#NAME? |  |  | 256442.3195 | 256442.3195
#NAME? |  |  | 2846135.8087 | 2846135.8087
#NAME? |  |  | 170039.1558 | 170039.1558
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 355941.9819 | 355941.9819
#NAME? |  |  | 0 | 0
#NAME? |  |  | 604214.9078 | 604214.9078
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3853791.8902 | 3853791.8902
#NAME? |  |  | 17142792.8863 | 244374.2322
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5103978.9833 | 5103978.9833
#NAME? |  |  | 0 | 0
#NAME? |  |  | 513632.6032 | 513632.6032
#NAME? |  |  | 2512168.2686 | 2512168.2686
#NAME? |  |  | 1484449.5274 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3495639.1638 | 184114.3724
#NAME? |  |  | 1351944.0666 | 1351944.0666
#NAME? |  |  | 282468.526 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3827584.3687 | 65243.4233
#NAME? |  |  | 1969393.4194 | 191052.1167
#NAME? |  |  | 0 | 0
#NAME? |  |  | 331898.79 | 331898.79
#NAME? |  |  | 0 | 0
#NAME? |  |  | 607832.6862 | 0
#NAME? |  |  | 3369854.3112 | 3369854.3112
#NAME? |  |  | 2560292.1191 | 509820.6592
#NAME? |  |  | 2755715.5008 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 564738.2192 | 564738.2192
#NAME? |  |  | 4224199.5935 | 0
#NAME? |  |  | 203729.231 | 0
#NAME? |  |  | 2299288.1075 | 2299288.1075
#NAME? |  |  | 146448.7825 | 146448.7825
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2170762.7496 | 2170762.7496
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 364712.7242 | 364712.7242
#NAME? |  |  | 724059.2844 | 724059.2844
#NAME? |  |  | 0 | 0
#NAME? |  |  | 233070.4582 | 233070.4582
#NAME? |  |  | 3004741.0957 | 3004741.0957
#NAME? |  |  | 464233.1296 | 315976.9228
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4885702.546 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1053379.4013 | 1053379.4013
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 564572.9248 | 564572.9248
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4393831.8712 | 98863.5097
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5229359.2634 | 0
#NAME? |  |  | 605324.6162 | 605324.6162
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3485975.4347 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5011585.5169 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4206515.3382 | 4206515.3382
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2889933.8655 | 354236.4508
#NAME? |  |  | 1607798.7581 | 742480.1633
#NAME? |  |  | 355096.8135 | 355096.8135
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2089005.1131 | 2089005.1131
#NAME? |  |  | 3693339.929 | 3163618.1658
#NAME? |  |  | 5637548.0925 | 0
#NAME? |  |  | 167947.5338 | 167947.5338
#NAME? |  |  | 290088.6503 | 0
#NAME? |  |  | 5737421.3066 | 2366306.7351
#NAME? |  |  | 0 | 0
#NAME? |  |  | 438896.1587 | 438896.1587
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2525743.5917 | 2298666.5727
#NAME? |  |  | 465872.0755 | 465872.0755
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2727917.4348 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 527811.1303 | 527811.1303
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4460541.2887 | 4460541.2887
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1443563.9474 | 1443563.9474
#NAME? |  |  | 0 | 0
#NAME? |  |  | 504817.8115 | 504817.8115
#NAME? |  |  | 3554122.0418 | 3554122.0418
#NAME? |  |  | 0 | 0
#NAME? |  |  | 153204.1047 | 153204.1047
#NAME? |  |  | 6812362.3622 | 3315937.3903
#NAME? |  |  | 294301.876 | 294301.876
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 241345.8361 | 241345.8361
#NAME? |  |  | 3767655.5263 | 3767655.5263
#NAME? |  |  | 2593422.1811 | 2593422.1811
#NAME? |  |  | 0 | 0
#NAME? |  |  | 212954.5625 | 212954.5625
#NAME? |  |  | 3191417.7392 | 0
#NAME? |  |  | 4518927.2924 | 4518927.2924
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 7327142.3844 | 6754320.8168
#NAME? |  |  | 0 | 0
#NAME? |  |  | 229396.3442 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 625830.7008 | 625830.7008
#NAME? |  |  | 10516237.5112 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1051595.1589 | 1051595.1589
#NAME? |  |  | 658182.6852 | 658182.6852
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1911364.6963 | 1911364.6963
#NAME? |  |  | 0 | 0
#NAME? |  |  | 115102.0083 | 115102.0083
#NAME? |  |  | 305479.57 | 305479.57
#NAME? |  |  | 129841.4164 | 129841.4164
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1974083.9578 | 0
#NAME? |  |  | 179755.0717 | 179755.0717
#NAME? |  |  | 3752352.8939 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3395761.1424 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 161906.6648 | 0
#NAME? |  |  | 301481.3633 | 301481.3633
#NAME? |  |  | 8958248.7448 | 8958248.7448
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1298244.8416 | 0
#NAME? |  |  | 236459.4909 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3070226.7495 | 2884917.5639
#NAME? |  |  | 7428402.3599 | 706161.045
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5597513.8313 | 3176779.9015
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4670496.6779 | 0
#NAME? |  |  | 727366.5583 | 727366.5583
#NAME? |  |  | 3292601.8767 | 3292601.8767
#NAME? |  |  | 0 | 0
#NAME? |  |  | 207750.5565 | 207750.5565
#NAME? |  |  | 0 | 0
#NAME? |  |  | 216683.539 | 0
#NAME? |  |  | 3004214.471 | 0
#NAME? |  |  | 224871.2913 | 0
#NAME? |  |  | 2371900.4322 | 2371900.4322
#NAME? |  |  | 240603.7772 | 240603.7772
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2181419.0304 | 0
#NAME? |  |  | 1460635.3959 | 0
#NAME? |  |  | 3414918.2798 | 170873.6675
#NAME? |  |  | 2258947.5734 | 0
#NAME? |  |  | 2392931.6668 | 2392931.6668
#NAME? |  |  | 0 | 0
#NAME? |  |  | 611507.5074 | 611507.5074
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 372736.393 | 372736.393
#NAME? |  |  | 3288099.8032 | 3288099.8032
#NAME? |  |  | 6612779.4309 | 207030.4767
#NAME? |  |  | 0 | 0
#NAME? |  |  | 181307.2611 | 181307.2611
#NAME? |  |  | 496841.4452 | 496841.4452
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2039260.107 | 2039260.107
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4957245.6851 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1252317.6028 | 1252317.6028
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 7056093.5503 | 7056093.5503
#NAME? |  |  | 180164.5089 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1870860.8468 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3282682.1264 | 3282682.1264
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2049373.2614 | 0
#NAME? |  |  | 5219646.2452 | 266614.1869
#NAME? |  |  | 5203097.6493 | 2276474.5277
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 594357.3524 | 594357.3524
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4839476.5196 | 4573032.5123
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3471848.9131 | 3471848.9131
#NAME? |  |  | 295481.0945 | 295481.0945
#NAME? |  |  | 924310.537 | 924310.537
#NAME? |  |  | 1354688.5973 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 7476208.7685 | 0
#NAME? |  |  | 198399.0793 | 198399.0793
#NAME? |  |  | 4873167.0874 | 0
#NAME? |  |  | 1510777.0109 | 0
#NAME? |  |  | 1147656.4495 | 1147656.4495
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 775088.695 | 775088.695
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2024887.8164 | 2024887.8164
#NAME? |  |  | 2076217.319 | 0
#NAME? |  |  | 19922887.8891 | 19718405.0374
#NAME? |  |  | 3639553.5702 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4341009.9537 | 4341009.9537
#NAME? |  |  | 208214.4971 | 0
#NAME? |  |  | 2212195.0519 | 2212195.0519
#NAME? |  |  | 0 | 0
#NAME? |  |  | 529662.1608 | 529662.1608
#NAME? |  |  | 657708.5048 | 657708.5048
#NAME? |  |  | 7560339.3682 | 0
#NAME? |  |  | 2304171.5322 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1572834.9538 | 1572834.9538
#NAME? |  |  | 0 | 0
#NAME? |  |  | 293319.4293 | 293319.4293
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 287932.2465 | 0
#NAME? |  |  | 7372636.0396 | 3184277.9305
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 208602.2125 | 0
#NAME? |  |  | 177184.2138 | 177184.2138
#NAME? |  |  | 360895.2351 | 360895.2351
#NAME? |  |  | 353353.827 | 353353.827
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3571034.6426 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 264125.8593 | 264125.8593
#NAME? |  |  | 0 | 0
#NAME? |  |  | 448683.7413 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 130357.0486 | 130357.0486
#NAME? |  |  | 267502.3555 | 267502.3555
#NAME? |  |  | 189803.3824 | 189803.3824
#NAME? |  |  | 416081.2585 | 416081.2585
#NAME? |  |  | 3754858.1587 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 840870.2241 | 840870.2241
#NAME? |  |  | 0 | 0
#NAME? |  |  | 6803296.405 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3143675.8816 | 525714.3067
#NAME? |  |  | 3354067.8752 | 411371.7929
#NAME? |  |  | 203620.2663 | 203620.2663
#NAME? |  |  | 1517713.9867 | 1517713.9867
#NAME? |  |  | 0 | 0
#NAME? |  |  | 627899.6026 | 303951.7634
#NAME? |  |  | 194880.298 | 194880.298
#NAME? |  |  | 3148646.0853 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1464282.2526 | 1464282.2526
#NAME? |  |  | 41176.1416 | 41176.1416
#NAME? |  |  | 59680645.6657 | 11535822.3036
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 300734.2313 | 300734.2313
#NAME? |  |  | 0 | 0
#NAME? |  |  | 632013.4425 | 0
#NAME? |  |  | 1075047.9419 | 1075047.9419
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2630494.0376 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2203778.4645 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2600309.7804 | 2600309.7804
#NAME? |  |  | 5296683.5149 | 5296683.5149
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 734924.1888 | 734924.1888
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 475912.5717 | 475912.5717
#NAME? |  |  | 392343.0776 | 392343.0776
#NAME? |  |  | 2263212.0416 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4352810.3247 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 294025.2523 | 294025.2523
#NAME? |  |  | 0 | 0
#NAME? |  |  | 167968.2636 | 167968.2636
#NAME? |  |  | 1987154.8869 | 1661894.4431
#NAME? |  |  | 219052.2477 | 219052.2477
#NAME? |  |  | 2662522.3995 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 465122.1608 | 465122.1608
#NAME? |  |  | 10059735.5316 | 208545.3318
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 713881.2256 | 424727.5378
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2364335.1347 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3723523.9705 | 3723523.9705
#NAME? |  |  | 1342843.6752 | 1342843.6752
#NAME? |  |  | 1129265.7902 | 1129265.7902
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4243113.0772 | 4243113.0772
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2783199.2353 | 249459.1429
#NAME? |  |  | 337789.9538 | 337789.9538
#NAME? |  |  | 2270226.3215 | 0
#NAME? |  |  | 213334.7116 | 213334.7116
#NAME? |  |  | 0 | 0
#NAME? |  |  | 130215.7351 | 130215.7351
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2332864.4222 | 0
#NAME? |  |  | 4659471.3409 | 4456521.6479
#NAME? |  |  | 0 | 0
#NAME? |  |  | 14353647.218 | 709184.3212
#NAME? |  |  | 2238642.2035 | 0
#NAME? |  |  | 875110.7882 | 875110.7882
#NAME? |  |  | 341732.5244 | 0
#NAME? |  |  | 234099.8639 | 234099.8639
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 847089.7893 | 847089.7893
#NAME? |  |  | 2556080.8058 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 324665.6234 | 324665.6234
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 302967.3252 | 302967.3252
#NAME? |  |  | 3613191.6559 | 3613191.6559
#NAME? |  |  | 432601.0228 | 432601.0228
#NAME? |  |  | 27023396.5379 | 1302644.042
#NAME? |  |  | 6305133.0414 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2273952.5567 | 0
#NAME? |  |  | 5481761.9557 | 3402680.5214
#NAME? |  |  | 445814.8452 | 0
#NAME? |  |  | 240918.5234 | 0
#NAME? |  |  | 195543.0707 | 195543.0707
#NAME? |  |  | 343203.8173 | 343203.8173
#NAME? |  |  | 705672.3799 | 705672.3799
#NAME? |  |  | 162820.0783 | 162820.0783
#NAME? |  |  | 439662.4264 | 0
#NAME? |  |  | 1096802.4176 | 1096802.4176
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1188571.019 | 1188571.019
#NAME? |  |  | 0 | 0
#NAME? |  |  | 249700.2063 | 249700.2063
#NAME? |  |  | 0 | 0
#NAME? |  |  | 164942.5286 | 164942.5286
#NAME? |  |  | 2230507.9643 | 2230507.9643
#NAME? |  |  | 0 | 0
#NAME? |  |  | 280141.8894 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2831934.7957 | 0
#NAME? |  |  | 8044484.2285 | 353420.9516
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1701398.3579 | 1701398.3579
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3534586.3403 | 3534586.3403
#NAME? |  |  | 4239264.2799 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 517204.3281 | 202036.2945
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 7139172.6738 | 0
#NAME? |  |  | 191439.1179 | 0
#NAME? |  |  | 973305.7709 | 973305.7709
#NAME? |  |  | 1494690.6082 | 1494690.6082
#NAME? |  |  | 1624142.2841 | 1624142.2841
#NAME? |  |  | 477184.508 | 0
#NAME? |  |  | 176875.3087 | 176875.3087
#NAME? |  |  | 2819236.8083 | 2819236.8083
#NAME? |  |  | 2937484.6856 | 2937484.6856
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5673603.4038 | 5673603.4038
#NAME? |  |  | 0 | 0
#NAME? |  |  | 2097524.4417 | 2097524.4417
#NAME? |  |  | 5537332.1467 | 5537332.1467
#NAME? |  |  | 0 | 0
#NAME? |  |  | 6285277.8435 | 2555421.0805
#NAME? |  |  | 1494932.2649 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 206852.7595 | 206852.7595
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 10066261.7404 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1314810.482 | 1314810.482
#NAME? |  |  | 0 | 0
#NAME? |  |  | 775434.6154 | 598653.9499
#NAME? |  |  | 0 | 0
#NAME? |  |  | 305042.807 | 305042.807
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 144761.0987 | 144761.0987
#NAME? |  |  | 1980738.9165 | 460030.2379
#NAME? |  |  | 291601.691 | 291601.691
#NAME? |  |  | 0 | 0
#NAME? |  |  | 150834.2159 | 150834.2159
#NAME? |  |  | 237956.1275 | 237956.1275
#NAME? |  |  | 2293437.4595 | 0
#NAME? |  |  | 914745.273 | 914745.273
#NAME? |  |  | 0 | 0
#NAME? |  |  | 322021.983 | 322021.983
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 365270.7335 | 365270.7335
#NAME? |  |  | 0 | 0
#NAME? |  |  | 5797233.8598 | 0
#NAME? |  |  | 8087668.4144 | 153962.7875
#NAME? |  |  | 253774.5019 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 12076993.1474 | 12076993.1474
#NAME? |  |  | 1573676.7433 | 1573676.7433
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1993962.7635 | 203240.4859
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4443988.7946 | 2763003.6753
#NAME? |  |  | 1670175.1524 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 9665907.6661 | 0
#NAME? |  |  | 7602451.8065 | 7602451.8065
#NAME? |  |  | 114077.4595 | 114077.4595
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 217707.7655 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 159768.7561 | 159768.7561
#NAME? |  |  | 175727.5033 | 175727.5033
#NAME? |  |  | 3356239.0715 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 102998.723 | 102998.723
#NAME? |  |  | 195463.7464 | 195463.7464
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 1059683.3145 | 1059683.3145
#NAME? |  |  | 0 | 0
#NAME? |  |  | 4238938.9478 | 4238938.9478
#NAME? |  |  | 3005703.1152 | 0
#NAME? |  |  | 2809305.0549 | 1756093.6204
#NAME? |  |  | 176209.622 | 176209.622
#NAME? |  |  | 1967821.8114 | 1608779.4827
#NAME? |  |  | 1486285.8671 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3597591.0948 | 0
#NAME? |  |  | 0 | 0
#NAME? |  |  | 13238338.2542 | 4500724.3788
#NAME? |  |  | 354642.2219 | 354642.2219
#NAME? |  |  | 0 | 0
#NAME? |  |  | 3518091.5721 | 3324733.8555

## Risk Register
Project Risk Register | [14 empty] | ← Expand for HDR PRNG
|  | Contact HDR to develop custom quantitative methods for your firm. |  | This risk register is nearly identical to the one included as part of the one-for-one substitution model spreadsheet except it also includes delays. It demonstrates how subjective expert input can be translated into fully quantitative risk analysis, replacing traditional heat maps with probabilistic modeling. While inputs still rely on expert estimates of likelihood and impact, this approach expresses those estimates in mathematically defined terms suitable for simulation. This enables risk aggregation across a portfolio and supports decision-making with more meaningful outputs. The register can be used for project-level risk management and enterprise risk analysis, helping organizations assess potential losses, prioritize controls, and allocate resources more effectively. Begin by entering risk-specific information in the “Input Values” section. The model will calculate both expected and simulated losses—before and after mitigation—along with related metrics such as return on control.
www.hubbardresearch.com
info@hubbardresearch.com
| Trial Slider Bar → |  | Trial ID: | 568
Input Values | [10 empty] | Output Values
| The "Risk Name" should be a short, unique identifier for the risk being considered. | Enter the "Risk Classification" that best matches. If the category needs explanation, please use the "Notes" column. | Estimate the likelihood of the event occurring at least once per year. | Estimate the total impact of the event, assuming it occurs, with a 90% confidence interval. That is, estimate a lower bound and upper bound such that you believe there is a 90% chance the actual impact will be between the bounds. Note that the lower bound must be greater than 0. |  |  |  | Choose the task that the risk impacts. | For the control being applied to the risk, provide an estimate of the cost of implementing the control. | Estimate the effectiveness of the controls being applied as a percent reduction in the likelihood of the event occurring. For example, if the risk has a 10% chance per year of occurring and a control is applied with 25% effectiveness, the mitigated likelihood of the event occurring would be 7.5%. | The expected value, or probability-weighted average, of the loss due to a risk. A lognormal distribution is assumed for impact. | Pseudo-random numbers between 0 and 1 are generated for each variable using a unique variable ID. These numbers are then used in other formulas to generate values for each scenario. |  |  | A random draw against the likelihood of the event determines if the event occurs. If it does occur, total losses are randomly drawn from the impact range. If the event does not occur, there is $0 simulated loss. | The expected value, or probability-weighted average, of the loss after applying controls. A lognormal distribution is assumed for impact. | The loss simulated in this trial, if there is one, after the implementation of the control. | Return on control is computed by comparing the monetized risk reduction (change in expected loss) to the total cost of controls. | The time delay simulated in this trial, if there is one.
Examples of Enterprise Risks |  |  |  | 90% Confidence Interval of Immediate Costs |  | 90% Confidence Interval of Delays (Weeks) | [5 empty] | 1 | 2 | 3
Risk ID | Risk Name | Risk Classification | Probability of event during project | Lower Bound | Upper Bound | Lower Bound | Upper Bound | Task Affected | Total Cost of Controls | Control Effectiveness | Expected Inherent Loss | Probability Rand | Impact Rand | Delay | Simulated Loss | Expected Residual Loss | Simulated Residual Loss | Return on Control | Simulated Delay
1 | Supplier A failure | Supply Chain | 6% | 500000 | 10000000 | 2 | 6.6 | 1.a | 150000 | 35% | 203099.0041 | 0.7471 | 0.43574 | 0.29073 | 0 | 132014.3527 | 0 | -52.61% | 0
2 | Supplier B failure | Supply Chain | 12% | 2000000 | 5000000 | 1 | 3.6 | 2.b | 125000 | 50% | 394482.3624 | 0.13656 | 0.68103 | 0.86814 | 0 | 197241.1812 | 0 | 57.79% | 0
3 | Hurricane on East Coast Site | Natural | 15% | 150000 | 300000 | 1 | 3 | 1.a | 25000 | 50% | 32534.0256 | 0.030627 | 0.72986 | 0.54335 | 241345.8361 | 16267.0128 | 241345.8361 | -34.93% | 1.7962
4 | Safety accident resulting in delays | Safety | 4% | 200000 | 500000 | 1 | 6 | 5.b | 10000 | 10% | 13149.4121 | 0.88527 | 0.30556 | 0.51152 | 0 | 11834.4709 | 0 | -86.85% | 0
5 | Exposure to a large lawsuit | Legal | 3% | 500000 | 2000000 | 0.4 | 1 | 1.b | 15000 | 30% | 32785.5449 | 0.55267 | 0.45024 | 0.18336 | 0 | 22949.8815 | 0 | -34.43% | 0
6 | Unknown underground conditions | Site conditions | 8% | 500000 | 10000000 | 0.6 | 3 | 2.c | 100000 | 70% | 270798.6722 | 0.9382 | 0.91669 | 0.32195 | 0 | 81239.6017 | 0 | 89.56% | 0
7 | Data breach | Cyber | 3.5% | 1000000 | 25000000 | 0.2 | 1 | 7.a | 150000 | 85% | 282445.5379 | 0.92731 | 0.41907 | 0.27257 | 0 | 42366.8307 | 0 | 60.05% | 0
8 | Material X shortage | Supply Chain | 15% | 100000 | 1000000 | 0.6 | 3 | 3.a | 0 | 0% | 60600.1676 | 0.98099 | 0.43313 | 0.14704 | 0 | 60600.1676 | 0 | 0% | 0
9 | [10 empty] | 0 | 0.80574 | 0.36366 | 0.61134 | 0 | 0 | 0 | 0% | 0
10 | [10 empty] | 0 | 0.45897 | 0.32486 | 0.46178 | 0 | 0 | 0 | 0% | 0
11 | [10 empty] | 0 | 0.13531 | 0.64749 | 0.50164 | 0 | 0 | 0 | 0% | 0
12 | [10 empty] | 0 | 0.32448 | 0.11496 | 0.62248 | 0 | 0 | 0 | 0% | 0
13 | [10 empty] | 0 | 0.15686 | 0.10627 | 0.78262 | 0 | 0 | 0 | 0% | 0
14 | [10 empty] | 0 | 0.33016 | 0.84234 | 0.88407 | 0 | 0 | 0 | 0% | 0
15 | [10 empty] | 0 | 0.79461 | 0.70246 | 0.60821 | 0 | 0 | 0 | 0% | 0
16 | [10 empty] | 0 | 0.54526 | 0.28351 | 0.48588 | 0 | 0 | 0 | 0% | 0
17 | [10 empty] | 0 | 0.9078 | 0.59772 | 0.45844 | 0 | 0 | 0 | 0% | 0
18 | [10 empty] | 0 | 0.4475 | 0.93637 | 0.82039 | 0 | 0 | 0 | 0% | 0
19 | [10 empty] | 0 | 0.039231 | 0.32568 | 0.039139 | 0 | 0 | 0 | 0% | 0
20 | [10 empty] | 0 | 0.4623 | 0.64939 | 0.43103 | 0 | 0 | 0 | 0% | 0