## Risk Register
One-for-One Substitution Model: Project Risk Register | [11 empty] | ← Expand for HDR PRNG
|  | Contact HDR to develop custom quantitative methods for your firm. |  | Introduction: This risk register demonstrates how subjective expert input can be translated into fully quantitative risk analysis, replacing traditional heat maps with probabilistic modeling. While inputs still rely on expert estimates of likelihood and impact, this approach expresses those estimates in mathematically defined terms suitable for simulation. This enables risk aggregation across a portfolio and supports decision-making with more meaningful outputs. The register can be used for project-level risk management and enterprise risk analysis, helping organizations assess potential losses, prioritize controls, and allocate resources more effectively. Begin by entering risk-specific information in the “Input Values” section. The model will calculate both expected and simulated losses—before and after mitigation—along with related metrics such as return on control. Recalculate the workbook after you update values. Press the F9 key or use "Calculate Now" in the Formulas Ribbon.
www.hubbardresearch.com
info@hubbardresearch.com
| Trial Slider Bar → |  | Trial ID: | 175
Input Values | [8 empty] | Output Values
| The "Risk Name" should be a short, unique identifier for the risk being considered. | Enter the "Risk Classification" that best matches. If the category needs explanation, please use the "Notes" column. | Estimate the likelihood of the event occurring at least once per year. | Estimate the total impact of the event, assuming it occurs, with a 90% confidence interval. That is, estimate a lower bound and upper bound, such that you believe there is a 90% chance the actual impact will be between the bounds. Note that the lower bound must be greater than 0. |  | Choose the task that the risk impacts. | For the control being applied to the risk, provide an estimate of the cost of implementing the control. | Estimate the effectiveness of the controls being applied as a percent reduction in the likelihood of the event occurring. For example, if the risk has a 10% chance per year of occurring and a control is reduces likelihood by 25%, the mitigated likelihood of the event occurring would be 7.5%. | The expected value, or probability-weighted average, of the loss due to a risk. A lognormal distribution is assumed for impact. | Pseudorandom numbers between 0 and 1 are generated for each variable using a unique variable ID. These numbers are then used in other formulas to calculate scenario values. |  | A random draw against the likelihood of the event determines if the event occurs. If it does occur, total losses are randomly drawn from the impact range. If the event does not occur, there is $0 simulated loss. | The expected value, or probability-weighted average, of the loss after applying controls. A lognormal distribution is assumed for impact. | The loss simulated in this trial, if there is one, after the implementation of the control. | Return on control is computed by comparing the monetized risk reduction (change in expected loss) to the total cost of controls.
| Examples of Enterprise Risks |  |  | 90% Confidence Interval of Immediate Costs | [5 empty] | 1 | 2
Risk ID | Risk Name | Risk Classification | Probability of event during project | Lower Bound | Upper Bound | Task Affected | Total Cost of Controls | Control Effectiveness | Expected Inherent Loss | Probability Rand | Impact Rand | Simulated Inherent Loss | Expected Residual Loss | Simulated Residual Loss | Return on Control
1 | Supplier A failure | Supply Chain | 6% | 500000 | 10000000 | 1.a | 150000 | 35% | 203099.0041 | 0.72288 | 0.84654 | 0 | 132014.3527 | 0 | -52.61%
2 | Supplier B failure | Supply Chain | 12% | 2000000 | 5000000 | 2.b | 125000 | 50% | 394482.3624 | 0.032267 | 0.97051 | 5350631.0908 | 197241.1812 | 5350631.0908 | 57.79%
3 | Hurricane on East Coast Site | Natural | 15% | 150000 | 300000 | 1.a | 25000 | 50% | 32534.0256 | 0.59407 | 0.85224 | 0 | 16267.0128 | 0 | -34.93%
4 | Safety accident resulting in delays | Safety | 4% | 200000 | 500000 | 5.b | 10000 | 10% | 13149.4121 | 0.00085182 | 0.073007 | 210941.3954 | 11834.4709 | 210941.3954 | -86.85%
5 | Exposure to a large lawsuit | Legal | 3% | 500000 | 2000000 | 1.b | 15000 | 30% | 32785.5449 | 0.053192 | 0.72998 | 0 | 22949.8815 | 0 | -34.43%
6 | Unknown underground conditions | Site conditions | 8% | 500000 | 10000000 | 2.c | 100000 | 70% | 270798.6722 | 0.11569 | 0.86752 | 0 | 81239.6017 | 0 | 89.56%
7 | Data breach | Cyber | 3.5% | 1000000 | 25000000 | 7.a | 150000 | 85% | 282445.5379 | 0.92822 | 0.18577 | 0 | 42366.8307 | 0 | 60.05%
8 | Material X shortage | Supply Chain | 15% | 100000 | 1000000 | 3.a | 0 | 0% | 60600.1676 | 0.24853 | 0.85897 | 0 | 60600.1676 | 0 | 0%
9 | [8 empty] | 0 | 0.69128 | 0.73759 | 0 | 0 | 0 | 0%
10 | [8 empty] | 0 | 0.71136 | 0.2132 | 0 | 0 | 0 | 0%
11 | [8 empty] | 0 | 0.5167 | 0.039062 | 0 | 0 | 0 | 0%
12 | [8 empty] | 0 | 0.93438 | 0.31827 | 0 | 0 | 0 | 0%
13 | [8 empty] | 0 | 0.574 | 0.32504 | 0 | 0 | 0 | 0%
14 | [8 empty] | 0 | 0.23643 | 0.62024 | 0 | 0 | 0 | 0%
15 | [8 empty] | 0 | 0.60892 | 0.99049 | 0 | 0 | 0 | 0%
16 | [8 empty] | 0 | 0.60762 | 0.48843 | 0 | 0 | 0 | 0%
17 | [8 empty] | 0 | 0.17619 | 0.12438 | 0 | 0 | 0 | 0%
18 | [8 empty] | 0 | 0.79146 | 0.11862 | 0 | 0 | 0 | 0%
19 | [8 empty] | 0 | 0.29027 | 0.55183 | 0 | 0 | 0 | 0%
20 | [8 empty] | 0 | 0.87625 | 0.58522 | 0 | 0 | 0 | 0%

## Loss Exceedance Curve
One-For-One Substitution Model: Loss Exceedance | [6 empty] | Expand for Residual Loss Data Table → |  |  |  | Expand for Residual Losses →
| Contact HDR to develop custom quantitative methods for your firm. |  |  | Introduction: This tab displays the results of the Monte Carlo simulation. Excel's What-If Data Tables are used to run 1,000 random trials based on the Risk Estimates provided, and a histogram shows how often total losses fall within specified bins. Expand the columns using “+” to display the residual risk curve on the Loss Exceedance Curve chart. Ensure that calculation mode is set to "Partial" (Formulas → Calculation Options) so that results update correctly.
www.hubbardresearch.com
info@hubbardresearch.com
| Trial ID: | 42
The loss exceedance curve displays the probability of exceeding a given loss in one year compared to your organization's willingness to accept that magnitude of a loss (your risk tolerance). Below the chart, the user can enter a loss in the gold cell and the probability of exceeding that loss will be shown. |  |  | Your organization's risk tolerance can be defined by estimating at least three points on this curve. One way to start with this is to leave the Acceptable Prob. Loss Exceeded where it is and adjust the Loss amounts to match your tolerance. Are you willing to accept a 99% chance of losing $1MM or more in a given year? If not, what about $500,000 or more? |  |  | This data table calculates the inherent loss that occurs in each trial. A total of 10,000 trials are calculated. Note that these are the losses that occur with no controls present. |  | This data table calculates the residual loss that occurs in each trial. A total of 10,000 trials are calculated. Note that these are the losses that occur after controls are applied. |  | This table calculates the probability of inherent and residual (if controls are included) losses in pre-defined intervals (e.g., the probability of a loss between $500,000 and $999,999). These values are used to plot the loss exceedance curve.
Inherent Risk, Residual Risk, and Risk Tolerance |  |  | Loss Exceedance Tolerance |  |  | Total Simulated Inherent Losses |  | Total Simulated Residual Losses |  | Chart Table
Recalculate the workbook to update the curve. Press the F9 key or use "Calculate Now" in the Formulas Ribbon. |  |  |  | Loss | Acceptable Probability Loss Exceeded | Trial | Loss | Trial | Loss | Loss | Inherent: % Loss or Greater | Residual: % Loss or Greater
[6 empty] | Current Trial → | 5561572.4862 | Current Trial → | 5561572.4862 | 0.0001 | 51.6% | 36.5%
|  |  |  | 100000 | 99% | 1 | 1053426.5169 | 1 | 1053426.5169 | 500000.0001 | 33.4% | 19.6%
|  |  |  | 2000000 | 15% | 2 | 0 | 2 | 0 | 1000000.0001 | 28.1% | 14.6%
|  |  |  | 10000000 | 2% | 3 | 3915036.6982 | 3 | 3915036.6982 | 1070000.0001 | 27.5% | 14.1%
|  |  |  | 50000000 | 0.5% | 4 | 0 | 4 | 0 | 1144900.0001 | 27.2% | 13.8%
[6 empty] | 5 | 0 | 5 | 0 | 1225043.0001 | 26.7% | 13.5%
[6 empty] | 6 | 0 | 6 | 0 | 1310796.0101 | 26.2% | 12.9%
|  |  | Expected Losses |  |  | 7 | 0 | 7 | 0 | 1402551.7308 | 25.6% | 12.5%
|  |  | Expected Inherent Loss |  | 1301297.6273 | 8 | 0 | 8 | 0 | 1500730.352 | 24.7% | 12%
[6 empty] | 9 | 0 | 9 | 0 | 1605781.4766 | 24.1% | 11.6%
|  |  | Expected Residual Loss |  | 537625.2037 | 10 | 4456414.2255 | 10 | 0 | 1718186.18 | 23.4% | 11%
[6 empty] | 11 | 0 | 11 | 0 | 1838459.2126 | 23.1% | 10.7%
[6 empty] | 12 | 1303997.3635 | 12 | 1303997.3635 | 1967151.3575 | 22.7% | 10.4%
[6 empty] | 13 | 224555.2443 | 13 | 224555.2443 | 2104851.9525 | 20.9% | 9.9%
[6 empty] | 14 | 710918.4391 | 14 | 710918.4391 | 2252191.5892 | 20.1% | 9.5%
[6 empty] | 15 | 0 | 15 | 0 | 2409845.0004 | 18.9% | 8.8%
[6 empty] | 16 | 3263202.7444 | 16 | 3263202.7444 | 2578534.1505 | 18.1% | 8.3%
[6 empty] | 17 | 879364.4788 | 17 | 0 | 2759031.541 | 17% | 7.9%
Probability of Inherent Loss Exceeding | 2000000 | is 9.6% |  |  |  | 18 | 793136.6887 | 18 | 423066.6522 | 2952163.7489 | 16.1% | 7.3%
[6 empty] | 19 | 0 | 19 | 0 | 3158815.2113 | 14.9% | 7%
[6 empty] | 20 | 255354.2237 | 20 | 0 | 3379932.2761 | 13.4% | 5.5%
[6 empty] | 21 | 0 | 21 | 0 | 3616527.5354 | 11.6% | 4.5%
[6 empty] | 22 | 0 | 22 | 0 | 3869684.4629 | 9.9% | 3.7%
[6 empty] | 23 | 0 | 23 | 0 | 4140562.3753 | 9% | 3.4%
[6 empty] | 24 | 4425561.4313 | 24 | 154365.9198 | 4430401.7415 | 7.8% | 2.9%
[6 empty] | 25 | 5146413.4321 | 25 | 5146413.4321 | 4740529.8635 | 6.9% | 2.4%
[6 empty] | 26 | 0 | 26 | 0 | 5072366.9539 | 6.2% | 2.2%
[6 empty] | 27 | 0 | 27 | 0 | 5427432.6407 | 5.3% | 1.8%
[6 empty] | 28 | 216374.1306 | 28 | 216374.1306 | 5807352.9255 | 4.4% | 1.5%
[6 empty] | 29 | 0 | 29 | 0 | 6213867.6303 | 4% | 1.3%
[6 empty] | 30 | 3663071.7698 | 30 | 3663071.7698 | 6648838.3644 | 3.5% | 1.3%
[6 empty] | 31 | 0 | 31 | 0 | 7114257.0499 | 3.2% | 1.1%
[6 empty] | 32 | 2496259.6163 | 32 | 2496259.6163 | 7612255.0434 | 2.5% | 1%
[6 empty] | 33 | 4508547.2823 | 33 | 0 | 8145112.8965 | 2.2% | 1%
[6 empty] | 34 | 0 | 34 | 0 | 8715270.7992 | 2.1% | 1%
[6 empty] | 35 | 0 | 35 | 0 | 9325339.7552 | 1.9% | 0.8%
[6 empty] | 36 | 0 | 36 | 0 | 9978113.538 | 1.7% | 0.7%
[6 empty] | 37 | 174286.9252 | 37 | 174286.9252 | 10676581.4857 | 1.4% | 0.7%
[6 empty] | 38 | 0 | 38 | 0 | 11423942.1897 | 1.3% | 0.6%
[6 empty] | 39 | 0 | 39 | 0 | 12223618.143 | 1.1% | 0.3%
[6 empty] | 40 | 0 | 40 | 0 | 13079271.413 | 1.1% | 0.3%
[6 empty] | 41 | 305647.8489 | 41 | 305647.8489 | 13994820.4119 | 0.9% | 0.2%
[6 empty] | 42 | 5561572.4862 | 42 | 5561572.4862 | 14974457.8407 | 0.8% | 0.2%
[6 empty] | 43 | 2616408.378 | 43 | 2382410.5682 | 16022669.8896 | 0.8% | 0.2%
[6 empty] | 44 | 501014.1584 | 44 | 501014.1584 | 17144256.7818 | 0.7% | 0.2%
[6 empty] | 45 | 0 | 45 | 0 | 18344354.7566 | 0.5% | 0.1%
[6 empty] | 46 | 0 | 46 | 0 | 19628459.5895 | 0.5% | 0.1%
[6 empty] | 47 | 0 | 47 | 0 | 21002451.7608 | 0.4% | 0%
[6 empty] | 48 | 923128.3738 | 48 | 0 | 22472623.384 | 0.3% | 0%
[6 empty] | 49 | 0 | 49 | 0 | 24045707.0209 | 0.3% | 0%
[6 empty] | 50 | 0 | 50 | 0 | 25728906.5124 | 0.3% | 0%
[6 empty] | 51 | 211964.288 | 51 | 0 | 27529929.9682 | 0.2% | 0%
[6 empty] | 52 | 180892.2613 | 52 | 0 | 29457025.066 | 0.2% | 0%
[6 empty] | 53 | 3439584.7696 | 53 | 3439584.7696 | 31519016.8206 | 0.2% | 0%
[6 empty] | 54 | 0 | 54 | 0 | 33725347.9981 | 0.2% | 0%
[6 empty] | 55 | 1659649.6865 | 55 | 1659649.6865 | 36086122.3579 | 0.2% | 0%
[6 empty] | 56 | 0 | 56 | 0 | 38612150.923 | 0.1% | 0%
[6 empty] | 57 | 0 | 57 | 0 | 41315001.4876 | 0.1% | 0%
[6 empty] | 58 | 774939.717 | 58 | 0 | 44207051.5917 | 0.1% | 0%
[6 empty] | 59 | 202746.0915 | 59 | 0 | 47301545.2032 | 0.1% | 0%
[6 empty] | 60 | 1983693.0686 | 60 | 133110.7284 | 50612653.3674 | 0.1% | 0%
[6 empty] | 61 | 0 | 61 | 0 | 54155539.1031 | 0.1% | 0%
[6 empty] | 62 | 290119.0744 | 62 | 290119.0744 | 57946426.8403 | 0.1% | 0%
[6 empty] | 63 | 1184717.1939 | 63 | 1184717.1939 | 62002676.7192 | 0% | 0%
[6 empty] | 64 | 176931.3915 | 64 | 0 | 66342864.0895 | 0% | 0%
[6 empty] | 65 | 2007738.3049 | 65 | 0 | 70986864.5758 | 0% | 0%
[6 empty] | 66 | 6302418.035 | 66 | 0 | 75955945.0961 | 0% | 0%
[6 empty] | 67 | 243710.3599 | 67 | 243710.3599 | 81272861.2528 | 0% | 0%
[6 empty] | 68 | 0 | 68 | 0 | 86961961.5405 | 0% | 0%
[6 empty] | 69 | 543998.4601 | 69 | 286836.414 | 93049298.8483 | 0% | 0%
[6 empty] | 70 | 0 | 70 | 0 | 99562749.7677 | 0% | 0%
[6 empty] | 71 | 312796.7353 | 71 | 0 | 106532142.2514 | 0% | 0%
[6 empty] | 72 | 94460.0925 | 72 | 94460.0925 | 113989392.209 | 0% | 0%
[6 empty] | 73 | 0 | 73 | 0 | 121968649.6637 | 0% | 0%
[6 empty] | 74 | 1267271.5773 | 74 | 1267271.5773 | 130506455.1401 | 0% | 0%
[6 empty] | 75 | 1557606.6193 | 75 | 1287802.3387 | 139641906.9999 | 0% | 0%
[6 empty] | 76 | 0 | 76 | 0 | 149416840.4899 | 0% | 0%
[6 empty] | 77 | 11738276.0979 | 77 | 11738276.0979 | 159876019.3242 | 0% | 0%
[6 empty] | 78 | 0 | 78 | 0 | 171067340.6769 | 0% | 0%
[6 empty] | 79 | 1663150.0423 | 79 | 1663150.0423 | 183042054.5243 | 0% | 0%
[6 empty] | 80 | 0 | 80 | 0 | 195854998.341 | 0% | 0%
[6 empty] | 81 | 4068629.4177 | 81 | 4068629.4177 | 209564848.2249 | 0% | 0%
[6 empty] | 82 | 0 | 82 | 0 | 224234387.6006 | 0% | 0%
[6 empty] | 83 | 0 | 83 | 0 | 239930794.7327 | 0% | 0%
[6 empty] | 84 | 279307.98 | 84 | 279307.98 | 256725950.3639 | 0% | 0%
[6 empty] | 85 | 0 | 85 | 0 | 274696766.8894 | 0% | 0%
[6 empty] | 86 | 0 | 86 | 0 | 293925540.5717 | 0% | 0%
[6 empty] | 87 | 412457.476 | 87 | 412457.476 | 314500328.4117 | 0% | 0%
[6 empty] | 88 | 212170.9851 | 88 | 212170.9851 | 336515351.4005 | 0% | 0%
[6 empty] | 89 | 2510295.0766 | 89 | 0 | 360071425.9985 | 0% | 0%
[6 empty] | 90 | 0 | 90 | 0 | 385276425.8184 | 0% | 0%
[6 empty] | 91 | 189037.3705 | 91 | 0 | 412245775.6257 | 0% | 0%
[6 empty] | 92 | 0 | 92 | 0 | 441102979.9195 | 0% | 0%
[6 empty] | 93 | 3259722.1808 | 93 | 0 | 471980188.5139 | 0% | 0%
[6 empty] | 94 | 841398.6995 | 94 | 841398.6995 | 505018801.7099 | 0% | 0%
[6 empty] | 95 | 0 | 95 | 0 | 540370117.8296 | 0% | 0%
[6 empty] | 96 | 180208.9246 | 96 | 180208.9246 | 578196026.0776 | 0% | 0%
[6 empty] | 97 | 3952850.1653 | 97 | 666245.1196 | 618669747.9031 | 0% | 0%
[6 empty] | 98 | 312939.9177 | 98 | 312939.9177 | 661976630.2563 | 0% | 0%
[6 empty] | 99 | 121335.2705 | 99 | 121335.2705 | 708314994.3742 | 0% | 0%
[6 empty] | 100 | 0 | 100 | 0 | 757897043.9804 | 0% | 0%
[6 empty] | 101 | 0 | 101 | 0 | 810949837.0591 | 0% | 0%
[6 empty] | 102 | 3047663.1131 | 102 | 195869.7842 | 867716325.6532 | 0% | 0%
[6 empty] | 103 | 0 | 103 | 0 | 928456468.4489 | 0% | 0%
[6 empty] | 104 | 319179.854 | 104 | 319179.854 | 993448421.2403 | 0% | 0%
[6 empty] | 105 | 0 | 105 | 0 | 1062989810.7272 | 0% | 0%
[6 empty] | 106 | 0 | 106 | 0 | 1137399097.4781 | 0% | 0%
[6 empty] | 107 | 1764666.7401 | 107 | 1764666.7401 | 1217017034.3015 | 0% | 0%
[6 empty] | 108 | 204584.0974 | 108 | 0 | 1302208226.7026 | 0% | 0%
[6 empty] | 109 | 0 | 109 | 0 | 1393362802.5718 | 0% | 0%
[6 empty] | 110 | 289829.5148 | 110 | 289829.5148 | 1490898198.7518 | 0% | 0%
[6 empty] | 111 | 0 | 111 | 0 | 1595261072.6645 | 0% | 0%
[6 empty] | 112 | 0 | 112 | 0 | 1706929347.751 | 0% | 0%
[6 empty] | 113 | 0 | 113 | 0 | 1826414402.0936 | 0% | 0%
[6 empty] | 114 | 0 | 114 | 0 | 1954263410.2401 | 0% | 0%
[6 empty] | 115 | 0 | 115 | 0 | 2091061848.9569 | 0% | 0%
[6 empty] | 116 | 0 | 116 | 0 | 2237436178.3839 | 0% | 0%
[6 empty] | 117 | 0 | 117 | 0 | 2394056710.8708 | 0% | 0%
[6 empty] | 118 | 0 | 118 | 0 | 2561640680.6317 | 0% | 0%
[6 empty] | 119 | 178798.7006 | 119 | 0 | 2740955528.2759 | 0% | 0%
[6 empty] | 120 | 0 | 120 | 0 | 2932822415.2553 | 0% | 0%
[6 empty] | 121 | 222066.6358 | 121 | 222066.6358
[6 empty] | 122 | 3345744.3614 | 122 | 3345744.3614
[6 empty] | 123 | 0 | 123 | 0
[6 empty] | 124 | 0 | 124 | 0
[6 empty] | 125 | 0 | 125 | 0
[6 empty] | 126 | 0 | 126 | 0
[6 empty] | 127 | 2064235.4397 | 127 | 0
[6 empty] | 128 | 0 | 128 | 0
[6 empty] | 129 | 0 | 129 | 0
[6 empty] | 130 | 186716.5327 | 130 | 186716.5327
[6 empty] | 131 | 812052.1867 | 131 | 812052.1867
[6 empty] | 132 | 0 | 132 | 0
[6 empty] | 133 | 155461.0943 | 133 | 155461.0943
[6 empty] | 134 | 0 | 134 | 0
[6 empty] | 135 | 0 | 135 | 0
[6 empty] | 136 | 418543.9431 | 136 | 418543.9431
[6 empty] | 137 | 0 | 137 | 0
[6 empty] | 138 | 239117.7106 | 138 | 0
[6 empty] | 139 | 0 | 139 | 0
[6 empty] | 140 | 17170038.8112 | 140 | 11321388.3475
[6 empty] | 141 | 208619.5878 | 141 | 0
[6 empty] | 142 | 2137051.6132 | 142 | 0
[6 empty] | 143 | 0 | 143 | 0
[6 empty] | 144 | 3723034.1605 | 144 | 0
[6 empty] | 145 | 0 | 145 | 0
[6 empty] | 146 | 935522.6889 | 146 | 935522.6889
[6 empty] | 147 | 0 | 147 | 0
[6 empty] | 148 | 154088.1769 | 148 | 154088.1769
[6 empty] | 149 | 0 | 149 | 0
[6 empty] | 150 | 222839.8058 | 150 | 222839.8058
[6 empty] | 151 | 0 | 151 | 0
[6 empty] | 152 | 0 | 152 | 0
[6 empty] | 153 | 0 | 153 | 0
[6 empty] | 154 | 0 | 154 | 0
[6 empty] | 155 | 0 | 155 | 0
[6 empty] | 156 | 3394700.2689 | 156 | 3394700.2689
[6 empty] | 157 | 0 | 157 | 0
[6 empty] | 158 | 0 | 158 | 0
[6 empty] | 159 | 21830544.7028 | 159 | 0
[6 empty] | 160 | 164210.8419 | 160 | 164210.8419
[6 empty] | 161 | 269183.5341 | 161 | 269183.5341
[6 empty] | 162 | 3364604.9215 | 162 | 3364604.9215
[6 empty] | 163 | 0 | 163 | 0
[6 empty] | 164 | 4007064.9281 | 164 | 4007064.9281
[6 empty] | 165 | 5161988.6567 | 165 | 0
[6 empty] | 166 | 3089538.0005 | 166 | 3089538.0005
[6 empty] | 167 | 0 | 167 | 0
[6 empty] | 168 | 3961013.9887 | 168 | 0
[6 empty] | 169 | 313338.9274 | 169 | 313338.9274
[6 empty] | 170 | 9173824.1284 | 170 | 0
[6 empty] | 171 | 4577714.807 | 171 | 0
[6 empty] | 172 | 1713215.7044 | 172 | 0
[6 empty] | 173 | 1916438.1819 | 173 | 1916438.1819
[6 empty] | 174 | 0 | 174 | 0
[6 empty] | 175 | 1435805.5371 | 175 | 1435805.5371
[6 empty] | 176 | 2532706.6317 | 176 | 2532706.6317
[6 empty] | 177 | 493016.5243 | 177 | 295640.4613
[6 empty] | 178 | 2599820.1402 | 178 | 0
[6 empty] | 179 | 211594.9333 | 179 | 211594.9333
[6 empty] | 180 | 1307492.7144 | 180 | 1307492.7144
[6 empty] | 181 | 0 | 181 | 0
[6 empty] | 182 | 0 | 182 | 0
[6 empty] | 183 | 0 | 183 | 0
[6 empty] | 184 | 0 | 184 | 0
[6 empty] | 185 | 3095506.7158 | 185 | 2884666.5203
[6 empty] | 186 | 0 | 186 | 0
[6 empty] | 187 | 0 | 187 | 0
[6 empty] | 188 | 0 | 188 | 0
[6 empty] | 189 | 0 | 189 | 0
[6 empty] | 190 | 288569.9083 | 190 | 288569.9083
[6 empty] | 191 | 0 | 191 | 0
[6 empty] | 192 | 0 | 192 | 0
[6 empty] | 193 | 0 | 193 | 0
[6 empty] | 194 | 9927230.0836 | 194 | 9927230.0836
[6 empty] | 195 | 797410.6388 | 195 | 504548.3575
[6 empty] | 196 | 0 | 196 | 0
[6 empty] | 197 | 0 | 197 | 0
[6 empty] | 198 | 0 | 198 | 0
[6 empty] | 199 | 0 | 199 | 0
[6 empty] | 200 | 279013.8681 | 200 | 0
[6 empty] | 201 | 4298841.8575 | 201 | 0
[6 empty] | 202 | 1945176.3149 | 202 | 1945176.3149
[6 empty] | 203 | 3474865.1034 | 203 | 3474865.1034
[6 empty] | 204 | 2725691.674 | 204 | 2725691.674
[6 empty] | 205 | 0 | 205 | 0
[6 empty] | 206 | 3100372.3009 | 206 | 0
[6 empty] | 207 | 0 | 207 | 0
[6 empty] | 208 | 0 | 208 | 0
[6 empty] | 209 | 0 | 209 | 0
[6 empty] | 210 | 332086.0004 | 210 | 332086.0004
[6 empty] | 211 | 0 | 211 | 0
[6 empty] | 212 | 0 | 212 | 0
[6 empty] | 213 | 0 | 213 | 0
[6 empty] | 214 | 0 | 214 | 0
[6 empty] | 215 | 738564.0926 | 215 | 424482.2541
[6 empty] | 216 | 3621430.0089 | 216 | 0
[6 empty] | 217 | 0 | 217 | 0
[6 empty] | 218 | 777555.4347 | 218 | 605318.262
[6 empty] | 219 | 0 | 219 | 0
[6 empty] | 220 | 0 | 220 | 0
[6 empty] | 221 | 0 | 221 | 0
[6 empty] | 222 | 0 | 222 | 0
[6 empty] | 223 | 1761129.742 | 223 | 533275.3946
[6 empty] | 224 | 0 | 224 | 0
[6 empty] | 225 | 0 | 225 | 0
[6 empty] | 226 | 0 | 226 | 0
[6 empty] | 227 | 0 | 227 | 0
[6 empty] | 228 | 0 | 228 | 0
[6 empty] | 229 | 1054029.9572 | 229 | 0
[6 empty] | 230 | 0 | 230 | 0
[6 empty] | 231 | 3078827.7101 | 231 | 0
[6 empty] | 232 | 0 | 232 | 0
[6 empty] | 233 | 0 | 233 | 0
[6 empty] | 234 | 0 | 234 | 0
[6 empty] | 235 | 872730.3683 | 235 | 872730.3683
[6 empty] | 236 | 0 | 236 | 0
[6 empty] | 237 | 199960.5549 | 237 | 0
[6 empty] | 238 | 217061.8853 | 238 | 0
[6 empty] | 239 | 0 | 239 | 0
[6 empty] | 240 | 154393.1166 | 240 | 0
[6 empty] | 241 | 294191.0065 | 241 | 294191.0065
[6 empty] | 242 | 0 | 242 | 0
[6 empty] | 243 | 206751.7509 | 243 | 206751.7509
[6 empty] | 244 | 269730.0613 | 244 | 269730.0613
[6 empty] | 245 | 8382284.4681 | 245 | 0
[6 empty] | 246 | 0 | 246 | 0
[6 empty] | 247 | 4096794.5456 | 247 | 0
[6 empty] | 248 | 0 | 248 | 0
[6 empty] | 249 | 0 | 249 | 0
[6 empty] | 250 | 782430.0766 | 250 | 782430.0766
[6 empty] | 251 | 0 | 251 | 0
[6 empty] | 252 | 0 | 252 | 0
[6 empty] | 253 | 333450.6245 | 253 | 333450.6245
[6 empty] | 254 | 260618.1383 | 254 | 260618.1383
[6 empty] | 255 | 659604.5254 | 255 | 0
[6 empty] | 256 | 1739957.7379 | 256 | 369653.2056
[6 empty] | 257 | 254648.1208 | 257 | 254648.1208
[6 empty] | 258 | 167010.8212 | 258 | 0
[6 empty] | 259 | 0 | 259 | 0
[6 empty] | 260 | 1376443.2519 | 260 | 402145.4793
[6 empty] | 261 | 0 | 261 | 0
[6 empty] | 262 | 0 | 262 | 0
[6 empty] | 263 | 164215.3576 | 263 | 0
[6 empty] | 264 | 0 | 264 | 0
[6 empty] | 265 | 797342.1381 | 265 | 797342.1381
[6 empty] | 266 | 0 | 266 | 0
[6 empty] | 267 | 0 | 267 | 0
[6 empty] | 268 | 847591.2633 | 268 | 0
[6 empty] | 269 | 0 | 269 | 0
[6 empty] | 270 | 0 | 270 | 0
[6 empty] | 271 | 289366.6592 | 271 | 289366.6592
[6 empty] | 272 | 129643.8366 | 272 | 129643.8366
[6 empty] | 273 | 0 | 273 | 0
[6 empty] | 274 | 681946.7524 | 274 | 681946.7524
[6 empty] | 275 | 0 | 275 | 0
[6 empty] | 276 | 163914.9744 | 276 | 163914.9744
[6 empty] | 277 | 0 | 277 | 0
[6 empty] | 278 | 0 | 278 | 0
[6 empty] | 279 | 220221.1691 | 279 | 220221.1691
[6 empty] | 280 | 0 | 280 | 0
[6 empty] | 281 | 5495735.0462 | 281 | 0
[6 empty] | 282 | 2179381.3689 | 282 | 2179381.3689
[6 empty] | 283 | 0 | 283 | 0
[6 empty] | 284 | 3721540.7671 | 284 | 982463.2089
[6 empty] | 285 | 237737.047 | 285 | 237737.047
[6 empty] | 286 | 4856462.7601 | 286 | 4856462.7601
[6 empty] | 287 | 1396579.427 | 287 | 450358.5589
[6 empty] | 288 | 1040638.7184 | 288 | 1040638.7184
[6 empty] | 289 | 0 | 289 | 0
[6 empty] | 290 | 3780775.4238 | 290 | 3780775.4238
[6 empty] | 291 | 0 | 291 | 0
[6 empty] | 292 | 1992327.5083 | 292 | 1992327.5083
[6 empty] | 293 | 3383665.6645 | 293 | 0
[6 empty] | 294 | 454538.1267 | 294 | 269108.7479
[6 empty] | 295 | 0 | 295 | 0
[6 empty] | 296 | 2055096.7109 | 296 | 1389933.6303
[6 empty] | 297 | 0 | 297 | 0
[6 empty] | 298 | 3820991.5421 | 298 | 3820991.5421
[6 empty] | 299 | 0 | 299 | 0
[6 empty] | 300 | 0 | 300 | 0
[6 empty] | 301 | 178927.038 | 301 | 0
[6 empty] | 302 | 294682.2365 | 302 | 294682.2365
[6 empty] | 303 | 5957816.8935 | 303 | 5957816.8935
[6 empty] | 304 | 376571.3721 | 304 | 376571.3721
[6 empty] | 305 | 0 | 305 | 0
[6 empty] | 306 | 0 | 306 | 0
[6 empty] | 307 | 0 | 307 | 0
[6 empty] | 308 | 0 | 308 | 0
[6 empty] | 309 | 0 | 309 | 0
[6 empty] | 310 | 0 | 310 | 0
[6 empty] | 311 | 0 | 311 | 0
[6 empty] | 312 | 2486517.2422 | 312 | 2486517.2422
[6 empty] | 313 | 4619974.8521 | 313 | 306523.6154
[6 empty] | 314 | 0 | 314 | 0
[6 empty] | 315 | 1174018.0807 | 315 | 0
[6 empty] | 316 | 212206.8182 | 316 | 212206.8182
[6 empty] | 317 | 202905.0565 | 317 | 202905.0565
[6 empty] | 318 | 0 | 318 | 0
[6 empty] | 319 | 3166757.9464 | 319 | 3166757.9464
[6 empty] | 320 | 276450.0844 | 320 | 276450.0844
[6 empty] | 321 | 153011.0004 | 321 | 153011.0004
[6 empty] | 322 | 0 | 322 | 0
[6 empty] | 323 | 7952591.7289 | 323 | 711313.2019
[6 empty] | 324 | 228269.8221 | 324 | 0
[6 empty] | 325 | 443473.3212 | 325 | 443473.3212
[6 empty] | 326 | 515183.2553 | 326 | 515183.2553
[6 empty] | 327 | 0 | 327 | 0
[6 empty] | 328 | 0 | 328 | 0
[6 empty] | 329 | 0 | 329 | 0
[6 empty] | 330 | 6496388.5315 | 330 | 0
[6 empty] | 331 | 0 | 331 | 0
[6 empty] | 332 | 2406044.2357 | 332 | 0
[6 empty] | 333 | 0 | 333 | 0
[6 empty] | 334 | 1496895.8044 | 334 | 1496895.8044
[6 empty] | 335 | 2889471.3214 | 335 | 414118.8276
[6 empty] | 336 | 4340103.5148 | 336 | 4340103.5148
[6 empty] | 337 | 243047.7738 | 337 | 0
[6 empty] | 338 | 271092.2171 | 338 | 271092.2171
[6 empty] | 339 | 3838305.6987 | 339 | 3838305.6987
[6 empty] | 340 | 229209.6988 | 340 | 229209.6988
[6 empty] | 341 | 3165252.1956 | 341 | 3165252.1956
[6 empty] | 342 | 0 | 342 | 0
[6 empty] | 343 | 0 | 343 | 0
[6 empty] | 344 | 232761.9097 | 344 | 0
[6 empty] | 345 | 0 | 345 | 0
[6 empty] | 346 | 0 | 346 | 0
[6 empty] | 347 | 0 | 347 | 0
[6 empty] | 348 | 0 | 348 | 0
[6 empty] | 349 | 0 | 349 | 0
[6 empty] | 350 | 3298441.1634 | 350 | 352795.1868
[6 empty] | 351 | 698274.5836 | 351 | 698274.5836
[6 empty] | 352 | 2751826.2233 | 352 | 0
[6 empty] | 353 | 3921636.0889 | 353 | 0
[6 empty] | 354 | 13681816.3095 | 354 | 13681816.3095
[6 empty] | 355 | 0 | 355 | 0
[6 empty] | 356 | 0 | 356 | 0
[6 empty] | 357 | 600743.6241 | 357 | 600743.6241
[6 empty] | 358 | 0 | 358 | 0
[6 empty] | 359 | 279205.6696 | 359 | 279205.6696
[6 empty] | 360 | 4995915.8917 | 360 | 4995915.8917
[6 empty] | 361 | 398904.0098 | 361 | 398904.0098
[6 empty] | 362 | 200549.5495 | 362 | 0
[6 empty] | 363 | 1166675.2382 | 363 | 0
[6 empty] | 364 | 0 | 364 | 0
[6 empty] | 365 | 0 | 365 | 0
[6 empty] | 366 | 5821747.7103 | 366 | 5821747.7103
[6 empty] | 367 | 370240.8924 | 367 | 370240.8924
[6 empty] | 368 | 236767.9294 | 368 | 236767.9294
[6 empty] | 369 | 0 | 369 | 0
[6 empty] | 370 | 0 | 370 | 0
[6 empty] | 371 | 197914.6877 | 371 | 0
[6 empty] | 372 | 36243308.7773 | 372 | 192544.679
[6 empty] | 373 | 3747363.7807 | 373 | 3747363.7807
[6 empty] | 374 | 352804.5638 | 374 | 352804.5638
[6 empty] | 375 | 0 | 375 | 0
[6 empty] | 376 | 4422938.7806 | 376 | 0
[6 empty] | 377 | 3500733.5237 | 377 | 639799.2636
[6 empty] | 378 | 0 | 378 | 0
[6 empty] | 379 | 0 | 379 | 0
[6 empty] | 380 | 10938591.8444 | 380 | 8985096.791
[6 empty] | 381 | 2806068.5207 | 381 | 0
[6 empty] | 382 | 5359056.9588 | 382 | 5359056.9588
[6 empty] | 383 | 170549.0667 | 383 | 170549.0667
[6 empty] | 384 | 223396.7189 | 384 | 0
[6 empty] | 385 | 0 | 385 | 0
[6 empty] | 386 | 3082477.8127 | 386 | 3082477.8127
[6 empty] | 387 | 0 | 387 | 0
[6 empty] | 388 | 0 | 388 | 0
[6 empty] | 389 | 0 | 389 | 0
[6 empty] | 390 | 0 | 390 | 0
[6 empty] | 391 | 0 | 391 | 0
[6 empty] | 392 | 0 | 392 | 0
[6 empty] | 393 | 0 | 393 | 0
[6 empty] | 394 | 3408869.8489 | 394 | 3408869.8489
[6 empty] | 395 | 3763034.3815 | 395 | 3575237.8929
[6 empty] | 396 | 0 | 396 | 0
[6 empty] | 397 | 0 | 397 | 0
[6 empty] | 398 | 5233080.5152 | 398 | 0
[6 empty] | 399 | 0 | 399 | 0
[6 empty] | 400 | 144761.7594 | 400 | 144761.7594
[6 empty] | 401 | 0 | 401 | 0
[6 empty] | 402 | 264815.3411 | 402 | 264815.3411
[6 empty] | 403 | 2087761.4239 | 403 | 1796340.0954
[6 empty] | 404 | 0 | 404 | 0
[6 empty] | 405 | 0 | 405 | 0
[6 empty] | 406 | 0 | 406 | 0
[6 empty] | 407 | 4130865.0144 | 407 | 191061.8037
[6 empty] | 408 | 3343482.6874 | 408 | 3343482.6874
[6 empty] | 409 | 0 | 409 | 0
[6 empty] | 410 | 0 | 410 | 0
[6 empty] | 411 | 0 | 411 | 0
[6 empty] | 412 | 0 | 412 | 0
[6 empty] | 413 | 0 | 413 | 0
[6 empty] | 414 | 421935.5564 | 414 | 421935.5564
[6 empty] | 415 | 0 | 415 | 0
[6 empty] | 416 | 438067.0188 | 416 | 438067.0188
[6 empty] | 417 | 0 | 417 | 0
[6 empty] | 418 | 1596056.3928 | 418 | 1596056.3928
[6 empty] | 419 | 0 | 419 | 0
[6 empty] | 420 | 0 | 420 | 0
[6 empty] | 421 | 5984877.3046 | 421 | 0
[6 empty] | 422 | 0 | 422 | 0
[6 empty] | 423 | 0 | 423 | 0
[6 empty] | 424 | 6117645.5057 | 424 | 0
[6 empty] | 425 | 0 | 425 | 0
[6 empty] | 426 | 2741307.4698 | 426 | 2741307.4698
[6 empty] | 427 | 3528545.1311 | 427 | 0
[6 empty] | 428 | 0 | 428 | 0
[6 empty] | 429 | 3881247.9401 | 429 | 0
[6 empty] | 430 | 0 | 430 | 0
[6 empty] | 431 | 0 | 431 | 0
[6 empty] | 432 | 0 | 432 | 0
[6 empty] | 433 | 206715.9379 | 433 | 206715.9379
[6 empty] | 434 | 17953889.104 | 434 | 17953889.104
[6 empty] | 435 | 0 | 435 | 0
[6 empty] | 436 | 0 | 436 | 0
[6 empty] | 437 | 621417.2908 | 437 | 621417.2908
[6 empty] | 438 | 452480.6492 | 438 | 452480.6492
[6 empty] | 439 | 256442.3195 | 439 | 256442.3195
[6 empty] | 440 | 2846135.8087 | 440 | 2846135.8087
[6 empty] | 441 | 170039.1558 | 441 | 170039.1558
[6 empty] | 442 | 0 | 442 | 0
[6 empty] | 443 | 0 | 443 | 0
[6 empty] | 444 | 355941.9819 | 444 | 355941.9819
[6 empty] | 445 | 0 | 445 | 0
[6 empty] | 446 | 604214.9078 | 446 | 604214.9078
[6 empty] | 447 | 0 | 447 | 0
[6 empty] | 448 | 3853791.8902 | 448 | 3853791.8902
[6 empty] | 449 | 17142792.8863 | 449 | 244374.2322
[6 empty] | 450 | 0 | 450 | 0
[6 empty] | 451 | 0 | 451 | 0
[6 empty] | 452 | 5103978.9833 | 452 | 5103978.9833
[6 empty] | 453 | 0 | 453 | 0
[6 empty] | 454 | 513632.6032 | 454 | 513632.6032
[6 empty] | 455 | 2512168.2686 | 455 | 2512168.2686
[6 empty] | 456 | 1484449.5274 | 456 | 0
[6 empty] | 457 | 0 | 457 | 0
[6 empty] | 458 | 0 | 458 | 0
[6 empty] | 459 | 3495639.1638 | 459 | 184114.3724
[6 empty] | 460 | 1351944.0666 | 460 | 1351944.0666
[6 empty] | 461 | 282468.526 | 461 | 0
[6 empty] | 462 | 0 | 462 | 0
[6 empty] | 463 | 3827584.3687 | 463 | 65243.4233
[6 empty] | 464 | 1969393.4194 | 464 | 191052.1167
[6 empty] | 465 | 0 | 465 | 0
[6 empty] | 466 | 331898.79 | 466 | 331898.79
[6 empty] | 467 | 0 | 467 | 0
[6 empty] | 468 | 607832.6862 | 468 | 0
[6 empty] | 469 | 3369854.3112 | 469 | 3369854.3112
[6 empty] | 470 | 2560292.1191 | 470 | 509820.6592
[6 empty] | 471 | 2755715.5008 | 471 | 0
[6 empty] | 472 | 0 | 472 | 0
[6 empty] | 473 | 0 | 473 | 0
[6 empty] | 474 | 0 | 474 | 0
[6 empty] | 475 | 0 | 475 | 0
[6 empty] | 476 | 0 | 476 | 0
[6 empty] | 477 | 0 | 477 | 0
[6 empty] | 478 | 564738.2192 | 478 | 564738.2192
[6 empty] | 479 | 4224199.5935 | 479 | 0
[6 empty] | 480 | 203729.231 | 480 | 0
[6 empty] | 481 | 2299288.1075 | 481 | 2299288.1075
[6 empty] | 482 | 146448.7825 | 482 | 146448.7825
[6 empty] | 483 | 0 | 483 | 0
[6 empty] | 484 | 2170762.7496 | 484 | 2170762.7496
[6 empty] | 485 | 0 | 485 | 0
[6 empty] | 486 | 0 | 486 | 0
[6 empty] | 487 | 0 | 487 | 0
[6 empty] | 488 | 364712.7242 | 488 | 364712.7242
[6 empty] | 489 | 724059.2844 | 489 | 724059.2844
[6 empty] | 490 | 0 | 490 | 0
[6 empty] | 491 | 233070.4582 | 491 | 233070.4582
[6 empty] | 492 | 3004741.0957 | 492 | 3004741.0957
[6 empty] | 493 | 464233.1296 | 493 | 315976.9228
[6 empty] | 494 | 0 | 494 | 0
[6 empty] | 495 | 0 | 495 | 0
[6 empty] | 496 | 4885702.546 | 496 | 0
[6 empty] | 497 | 0 | 497 | 0
[6 empty] | 498 | 0 | 498 | 0
[6 empty] | 499 | 1053379.4013 | 499 | 1053379.4013
[6 empty] | 500 | 0 | 500 | 0
[6 empty] | 501 | 0 | 501 | 0
[6 empty] | 502 | 564572.9248 | 502 | 564572.9248
[6 empty] | 503 | 0 | 503 | 0
[6 empty] | 504 | 0 | 504 | 0
[6 empty] | 505 | 0 | 505 | 0
[6 empty] | 506 | 0 | 506 | 0
[6 empty] | 507 | 4393831.8712 | 507 | 98863.5097
[6 empty] | 508 | 0 | 508 | 0
[6 empty] | 509 | 5229359.2634 | 509 | 0
[6 empty] | 510 | 605324.6162 | 510 | 605324.6162
[6 empty] | 511 | 0 | 511 | 0
[6 empty] | 512 | 0 | 512 | 0
[6 empty] | 513 | 0 | 513 | 0
[6 empty] | 514 | 3485975.4347 | 514 | 0
[6 empty] | 515 | 0 | 515 | 0
[6 empty] | 516 | 0 | 516 | 0
[6 empty] | 517 | 5011585.5169 | 517 | 0
[6 empty] | 518 | 0 | 518 | 0
[6 empty] | 519 | 0 | 519 | 0
[6 empty] | 520 | 0 | 520 | 0
[6 empty] | 521 | 0 | 521 | 0
[6 empty] | 522 | 4206515.3382 | 522 | 4206515.3382
[6 empty] | 523 | 0 | 523 | 0
[6 empty] | 524 | 0 | 524 | 0
[6 empty] | 525 | 0 | 525 | 0
[6 empty] | 526 | 0 | 526 | 0
[6 empty] | 527 | 0 | 527 | 0
[6 empty] | 528 | 0 | 528 | 0
[6 empty] | 529 | 0 | 529 | 0
[6 empty] | 530 | 0 | 530 | 0
[6 empty] | 531 | 2889933.8655 | 531 | 354236.4508
[6 empty] | 532 | 1607798.7581 | 532 | 742480.1633
[6 empty] | 533 | 355096.8135 | 533 | 355096.8135
[6 empty] | 534 | 0 | 534 | 0
[6 empty] | 535 | 2089005.1131 | 535 | 2089005.1131
[6 empty] | 536 | 3693339.929 | 536 | 3163618.1658
[6 empty] | 537 | 5637548.0925 | 537 | 0
[6 empty] | 538 | 167947.5338 | 538 | 167947.5338
[6 empty] | 539 | 290088.6503 | 539 | 0
[6 empty] | 540 | 5737421.3066 | 540 | 2366306.7351
[6 empty] | 541 | 0 | 541 | 0
[6 empty] | 542 | 438896.1587 | 542 | 438896.1587
[6 empty] | 543 | 0 | 543 | 0
[6 empty] | 544 | 2525743.5917 | 544 | 2298666.5727
[6 empty] | 545 | 465872.0755 | 545 | 465872.0755
[6 empty] | 546 | 0 | 546 | 0
[6 empty] | 547 | 2727917.4348 | 547 | 0
[6 empty] | 548 | 0 | 548 | 0
[6 empty] | 549 | 0 | 549 | 0
[6 empty] | 550 | 0 | 550 | 0
[6 empty] | 551 | 527811.1303 | 551 | 527811.1303
[6 empty] | 552 | 0 | 552 | 0
[6 empty] | 553 | 0 | 553 | 0
[6 empty] | 554 | 0 | 554 | 0
[6 empty] | 555 | 0 | 555 | 0
[6 empty] | 556 | 4460541.2887 | 556 | 4460541.2887
[6 empty] | 557 | 0 | 557 | 0
[6 empty] | 558 | 1443563.9474 | 558 | 1443563.9474
[6 empty] | 559 | 0 | 559 | 0
[6 empty] | 560 | 504817.8115 | 560 | 504817.8115
[6 empty] | 561 | 3554122.0418 | 561 | 3554122.0418
[6 empty] | 562 | 0 | 562 | 0
[6 empty] | 563 | 153204.1047 | 563 | 153204.1047
[6 empty] | 564 | 6812362.3622 | 564 | 3315937.3903
[6 empty] | 565 | 294301.876 | 565 | 294301.876
[6 empty] | 566 | 0 | 566 | 0
[6 empty] | 567 | 0 | 567 | 0
[6 empty] | 568 | 241345.8361 | 568 | 241345.8361
[6 empty] | 569 | 3767655.5263 | 569 | 3767655.5263
[6 empty] | 570 | 2593422.1811 | 570 | 2593422.1811
[6 empty] | 571 | 0 | 571 | 0
[6 empty] | 572 | 212954.5625 | 572 | 212954.5625
[6 empty] | 573 | 3191417.7392 | 573 | 0
[6 empty] | 574 | 4518927.2924 | 574 | 4518927.2924
[6 empty] | 575 | 0 | 575 | 0
[6 empty] | 576 | 0 | 576 | 0
[6 empty] | 577 | 0 | 577 | 0
[6 empty] | 578 | 7327142.3844 | 578 | 6754320.8168
[6 empty] | 579 | 0 | 579 | 0
[6 empty] | 580 | 229396.3442 | 580 | 0
[6 empty] | 581 | 0 | 581 | 0
[6 empty] | 582 | 625830.7008 | 582 | 625830.7008
[6 empty] | 583 | 10516237.5112 | 583 | 0
[6 empty] | 584 | 0 | 584 | 0
[6 empty] | 585 | 0 | 585 | 0
[6 empty] | 586 | 0 | 586 | 0
[6 empty] | 587 | 1051595.1589 | 587 | 1051595.1589
[6 empty] | 588 | 658182.6852 | 588 | 658182.6852
[6 empty] | 589 | 0 | 589 | 0
[6 empty] | 590 | 0 | 590 | 0
[6 empty] | 591 | 1911364.6963 | 591 | 1911364.6963
[6 empty] | 592 | 0 | 592 | 0
[6 empty] | 593 | 115102.0083 | 593 | 115102.0083
[6 empty] | 594 | 305479.57 | 594 | 305479.57
[6 empty] | 595 | 129841.4164 | 595 | 129841.4164
[6 empty] | 596 | 0 | 596 | 0
[6 empty] | 597 | 1974083.9578 | 597 | 0
[6 empty] | 598 | 179755.0717 | 598 | 179755.0717
[6 empty] | 599 | 3752352.8939 | 599 | 0
[6 empty] | 600 | 0 | 600 | 0
[6 empty] | 601 | 0 | 601 | 0
[6 empty] | 602 | 3395761.1424 | 602 | 0
[6 empty] | 603 | 0 | 603 | 0
[6 empty] | 604 | 0 | 604 | 0
[6 empty] | 605 | 0 | 605 | 0
[6 empty] | 606 | 0 | 606 | 0
[6 empty] | 607 | 161906.6648 | 607 | 0
[6 empty] | 608 | 301481.3633 | 608 | 301481.3633
[6 empty] | 609 | 8958248.7448 | 609 | 8958248.7448
[6 empty] | 610 | 0 | 610 | 0
[6 empty] | 611 | 0 | 611 | 0
[6 empty] | 612 | 1298244.8416 | 612 | 0
[6 empty] | 613 | 236459.4909 | 613 | 0
[6 empty] | 614 | 0 | 614 | 0
[6 empty] | 615 | 0 | 615 | 0
[6 empty] | 616 | 0 | 616 | 0
[6 empty] | 617 | 0 | 617 | 0
[6 empty] | 618 | 3070226.7495 | 618 | 2884917.5639
[6 empty] | 619 | 7428402.3599 | 619 | 706161.045
[6 empty] | 620 | 0 | 620 | 0
[6 empty] | 621 | 0 | 621 | 0
[6 empty] | 622 | 5597513.8313 | 622 | 3176779.9015
[6 empty] | 623 | 0 | 623 | 0
[6 empty] | 624 | 0 | 624 | 0
[6 empty] | 625 | 4670496.6779 | 625 | 0
[6 empty] | 626 | 727366.5583 | 626 | 727366.5583
[6 empty] | 627 | 3292601.8767 | 627 | 3292601.8767
[6 empty] | 628 | 0 | 628 | 0
[6 empty] | 629 | 207750.5565 | 629 | 207750.5565
[6 empty] | 630 | 0 | 630 | 0
[6 empty] | 631 | 216683.539 | 631 | 0
[6 empty] | 632 | 3004214.471 | 632 | 0
[6 empty] | 633 | 224871.2913 | 633 | 0
[6 empty] | 634 | 2371900.4322 | 634 | 2371900.4322
[6 empty] | 635 | 240603.7772 | 635 | 240603.7772
[6 empty] | 636 | 0 | 636 | 0
[6 empty] | 637 | 0 | 637 | 0
[6 empty] | 638 | 2181419.0304 | 638 | 0
[6 empty] | 639 | 1460635.3959 | 639 | 0
[6 empty] | 640 | 3414918.2798 | 640 | 170873.6675
[6 empty] | 641 | 2258947.5734 | 641 | 0
[6 empty] | 642 | 2392931.6668 | 642 | 2392931.6668
[6 empty] | 643 | 0 | 643 | 0
[6 empty] | 644 | 611507.5074 | 644 | 611507.5074
[6 empty] | 645 | 0 | 645 | 0
[6 empty] | 646 | 0 | 646 | 0
[6 empty] | 647 | 372736.393 | 647 | 372736.393
[6 empty] | 648 | 3288099.8032 | 648 | 3288099.8032
[6 empty] | 649 | 6612779.4309 | 649 | 207030.4767
[6 empty] | 650 | 0 | 650 | 0
[6 empty] | 651 | 181307.2611 | 651 | 181307.2611
[6 empty] | 652 | 496841.4452 | 652 | 496841.4452
[6 empty] | 653 | 0 | 653 | 0
[6 empty] | 654 | 2039260.107 | 654 | 2039260.107
[6 empty] | 655 | 0 | 655 | 0
[6 empty] | 656 | 0 | 656 | 0
[6 empty] | 657 | 4957245.6851 | 657 | 0
[6 empty] | 658 | 0 | 658 | 0
[6 empty] | 659 | 0 | 659 | 0
[6 empty] | 660 | 0 | 660 | 0
[6 empty] | 661 | 1252317.6028 | 661 | 1252317.6028
[6 empty] | 662 | 0 | 662 | 0
[6 empty] | 663 | 0 | 663 | 0
[6 empty] | 664 | 0 | 664 | 0
[6 empty] | 665 | 7056093.5503 | 665 | 7056093.5503
[6 empty] | 666 | 180164.5089 | 666 | 0
[6 empty] | 667 | 0 | 667 | 0
[6 empty] | 668 | 1870860.8468 | 668 | 0
[6 empty] | 669 | 0 | 669 | 0
[6 empty] | 670 | 3282682.1264 | 670 | 3282682.1264
[6 empty] | 671 | 0 | 671 | 0
[6 empty] | 672 | 2049373.2614 | 672 | 0
[6 empty] | 673 | 5219646.2452 | 673 | 266614.1869
[6 empty] | 674 | 5203097.6493 | 674 | 2276474.5277
[6 empty] | 675 | 0 | 675 | 0
[6 empty] | 676 | 0 | 676 | 0
[6 empty] | 677 | 0 | 677 | 0
[6 empty] | 678 | 0 | 678 | 0
[6 empty] | 679 | 0 | 679 | 0
[6 empty] | 680 | 0 | 680 | 0
[6 empty] | 681 | 0 | 681 | 0
[6 empty] | 682 | 0 | 682 | 0
[6 empty] | 683 | 0 | 683 | 0
[6 empty] | 684 | 0 | 684 | 0
[6 empty] | 685 | 594357.3524 | 685 | 594357.3524
[6 empty] | 686 | 0 | 686 | 0
[6 empty] | 687 | 4839476.5196 | 687 | 4573032.5123
[6 empty] | 688 | 0 | 688 | 0
[6 empty] | 689 | 0 | 689 | 0
[6 empty] | 690 | 0 | 690 | 0
[6 empty] | 691 | 0 | 691 | 0
[6 empty] | 692 | 3471848.9131 | 692 | 3471848.9131
[6 empty] | 693 | 295481.0945 | 693 | 295481.0945
[6 empty] | 694 | 924310.537 | 694 | 924310.537
[6 empty] | 695 | 1354688.5973 | 695 | 0
[6 empty] | 696 | 0 | 696 | 0
[6 empty] | 697 | 7476208.7685 | 697 | 0
[6 empty] | 698 | 198399.0793 | 698 | 198399.0793
[6 empty] | 699 | 4873167.0874 | 699 | 0
[6 empty] | 700 | 1510777.0109 | 700 | 0
[6 empty] | 701 | 1147656.4495 | 701 | 1147656.4495
[6 empty] | 702 | 0 | 702 | 0
[6 empty] | 703 | 0 | 703 | 0
[6 empty] | 704 | 775088.695 | 704 | 775088.695
[6 empty] | 705 | 0 | 705 | 0
[6 empty] | 706 | 0 | 706 | 0
[6 empty] | 707 | 0 | 707 | 0
[6 empty] | 708 | 0 | 708 | 0
[6 empty] | 709 | 0 | 709 | 0
[6 empty] | 710 | 2024887.8164 | 710 | 2024887.8164
[6 empty] | 711 | 2076217.319 | 711 | 0
[6 empty] | 712 | 19922887.8891 | 712 | 19718405.0374
[6 empty] | 713 | 3639553.5702 | 713 | 0
[6 empty] | 714 | 0 | 714 | 0
[6 empty] | 715 | 0 | 715 | 0
[6 empty] | 716 | 4341009.9537 | 716 | 4341009.9537
[6 empty] | 717 | 208214.4971 | 717 | 0
[6 empty] | 718 | 2212195.0519 | 718 | 2212195.0519
[6 empty] | 719 | 0 | 719 | 0
[6 empty] | 720 | 529662.1608 | 720 | 529662.1608
[6 empty] | 721 | 657708.5048 | 721 | 657708.5048
[6 empty] | 722 | 7560339.3682 | 722 | 0
[6 empty] | 723 | 2304171.5322 | 723 | 0
[6 empty] | 724 | 0 | 724 | 0
[6 empty] | 725 | 1572834.9538 | 725 | 1572834.9538
[6 empty] | 726 | 0 | 726 | 0
[6 empty] | 727 | 293319.4293 | 727 | 293319.4293
[6 empty] | 728 | 0 | 728 | 0
[6 empty] | 729 | 0 | 729 | 0
[6 empty] | 730 | 0 | 730 | 0
[6 empty] | 731 | 0 | 731 | 0
[6 empty] | 732 | 0 | 732 | 0
[6 empty] | 733 | 0 | 733 | 0
[6 empty] | 734 | 0 | 734 | 0
[6 empty] | 735 | 0 | 735 | 0
[6 empty] | 736 | 287932.2465 | 736 | 0
[6 empty] | 737 | 7372636.0396 | 737 | 3184277.9305
[6 empty] | 738 | 0 | 738 | 0
[6 empty] | 739 | 0 | 739 | 0
[6 empty] | 740 | 0 | 740 | 0
[6 empty] | 741 | 0 | 741 | 0
[6 empty] | 742 | 0 | 742 | 0
[6 empty] | 743 | 0 | 743 | 0
[6 empty] | 744 | 0 | 744 | 0
[6 empty] | 745 | 208602.2125 | 745 | 0
[6 empty] | 746 | 177184.2138 | 746 | 177184.2138
[6 empty] | 747 | 360895.2351 | 747 | 360895.2351
[6 empty] | 748 | 353353.827 | 748 | 353353.827
[6 empty] | 749 | 0 | 749 | 0
[6 empty] | 750 | 0 | 750 | 0
[6 empty] | 751 | 0 | 751 | 0
[6 empty] | 752 | 0 | 752 | 0
[6 empty] | 753 | 3571034.6426 | 753 | 0
[6 empty] | 754 | 0 | 754 | 0
[6 empty] | 755 | 264125.8593 | 755 | 264125.8593
[6 empty] | 756 | 0 | 756 | 0
[6 empty] | 757 | 448683.7413 | 757 | 0
[6 empty] | 758 | 0 | 758 | 0
[6 empty] | 759 | 0 | 759 | 0
[6 empty] | 760 | 130357.0486 | 760 | 130357.0486
[6 empty] | 761 | 267502.3555 | 761 | 267502.3555
[6 empty] | 762 | 189803.3824 | 762 | 189803.3824
[6 empty] | 763 | 416081.2585 | 763 | 416081.2585
[6 empty] | 764 | 3754858.1587 | 764 | 0
[6 empty] | 765 | 0 | 765 | 0
[6 empty] | 766 | 0 | 766 | 0
[6 empty] | 767 | 0 | 767 | 0
[6 empty] | 768 | 840870.2241 | 768 | 840870.2241
[6 empty] | 769 | 0 | 769 | 0
[6 empty] | 770 | 6803296.405 | 770 | 0
[6 empty] | 771 | 0 | 771 | 0
[6 empty] | 772 | 0 | 772 | 0
[6 empty] | 773 | 3143675.8816 | 773 | 525714.3067
[6 empty] | 774 | 3354067.8752 | 774 | 411371.7929
[6 empty] | 775 | 203620.2663 | 775 | 203620.2663
[6 empty] | 776 | 1517713.9867 | 776 | 1517713.9867
[6 empty] | 777 | 0 | 777 | 0
[6 empty] | 778 | 627899.6026 | 778 | 303951.7634
[6 empty] | 779 | 194880.298 | 779 | 194880.298
[6 empty] | 780 | 3148646.0853 | 780 | 0
[6 empty] | 781 | 0 | 781 | 0
[6 empty] | 782 | 0 | 782 | 0
[6 empty] | 783 | 1464282.2526 | 783 | 1464282.2526
[6 empty] | 784 | 41176.1416 | 784 | 41176.1416
[6 empty] | 785 | 59680645.6657 | 785 | 11535822.3036
[6 empty] | 786 | 0 | 786 | 0
[6 empty] | 787 | 0 | 787 | 0
[6 empty] | 788 | 300734.2313 | 788 | 300734.2313
[6 empty] | 789 | 0 | 789 | 0
[6 empty] | 790 | 632013.4425 | 790 | 0
[6 empty] | 791 | 1075047.9419 | 791 | 1075047.9419
[6 empty] | 792 | 0 | 792 | 0
[6 empty] | 793 | 2630494.0376 | 793 | 0
[6 empty] | 794 | 0 | 794 | 0
[6 empty] | 795 | 0 | 795 | 0
[6 empty] | 796 | 2203778.4645 | 796 | 0
[6 empty] | 797 | 0 | 797 | 0
[6 empty] | 798 | 2600309.7804 | 798 | 2600309.7804
[6 empty] | 799 | 5296683.5149 | 799 | 5296683.5149
[6 empty] | 800 | 0 | 800 | 0
[6 empty] | 801 | 0 | 801 | 0
[6 empty] | 802 | 0 | 802 | 0
[6 empty] | 803 | 0 | 803 | 0
[6 empty] | 804 | 734924.1888 | 804 | 734924.1888
[6 empty] | 805 | 0 | 805 | 0
[6 empty] | 806 | 0 | 806 | 0
[6 empty] | 807 | 0 | 807 | 0
[6 empty] | 808 | 475912.5717 | 808 | 475912.5717
[6 empty] | 809 | 392343.0776 | 809 | 392343.0776
[6 empty] | 810 | 2263212.0416 | 810 | 0
[6 empty] | 811 | 0 | 811 | 0
[6 empty] | 812 | 0 | 812 | 0
[6 empty] | 813 | 0 | 813 | 0
[6 empty] | 814 | 0 | 814 | 0
[6 empty] | 815 | 0 | 815 | 0
[6 empty] | 816 | 0 | 816 | 0
[6 empty] | 817 | 4352810.3247 | 817 | 0
[6 empty] | 818 | 0 | 818 | 0
[6 empty] | 819 | 294025.2523 | 819 | 294025.2523
[6 empty] | 820 | 0 | 820 | 0
[6 empty] | 821 | 167968.2636 | 821 | 167968.2636
[6 empty] | 822 | 1987154.8869 | 822 | 1661894.4431
[6 empty] | 823 | 219052.2477 | 823 | 219052.2477
[6 empty] | 824 | 2662522.3995 | 824 | 0
[6 empty] | 825 | 0 | 825 | 0
[6 empty] | 826 | 465122.1608 | 826 | 465122.1608
[6 empty] | 827 | 10059735.5316 | 827 | 208545.3318
[6 empty] | 828 | 0 | 828 | 0
[6 empty] | 829 | 0 | 829 | 0
[6 empty] | 830 | 713881.2256 | 830 | 424727.5378
[6 empty] | 831 | 0 | 831 | 0
[6 empty] | 832 | 2364335.1347 | 832 | 0
[6 empty] | 833 | 0 | 833 | 0
[6 empty] | 834 | 0 | 834 | 0
[6 empty] | 835 | 3723523.9705 | 835 | 3723523.9705
[6 empty] | 836 | 1342843.6752 | 836 | 1342843.6752
[6 empty] | 837 | 1129265.7902 | 837 | 1129265.7902
[6 empty] | 838 | 0 | 838 | 0
[6 empty] | 839 | 4243113.0772 | 839 | 4243113.0772
[6 empty] | 840 | 0 | 840 | 0
[6 empty] | 841 | 2783199.2353 | 841 | 249459.1429
[6 empty] | 842 | 337789.9538 | 842 | 337789.9538
[6 empty] | 843 | 2270226.3215 | 843 | 0
[6 empty] | 844 | 213334.7116 | 844 | 213334.7116
[6 empty] | 845 | 0 | 845 | 0
[6 empty] | 846 | 130215.7351 | 846 | 130215.7351
[6 empty] | 847 | 0 | 847 | 0
[6 empty] | 848 | 2332864.4222 | 848 | 0
[6 empty] | 849 | 4659471.3409 | 849 | 4456521.6479
[6 empty] | 850 | 0 | 850 | 0
[6 empty] | 851 | 14353647.218 | 851 | 709184.3212
[6 empty] | 852 | 2238642.2035 | 852 | 0
[6 empty] | 853 | 875110.7882 | 853 | 875110.7882
[6 empty] | 854 | 341732.5244 | 854 | 0
[6 empty] | 855 | 234099.8639 | 855 | 234099.8639
[6 empty] | 856 | 0 | 856 | 0
[6 empty] | 857 | 0 | 857 | 0
[6 empty] | 858 | 847089.7893 | 858 | 847089.7893
[6 empty] | 859 | 2556080.8058 | 859 | 0
[6 empty] | 860 | 0 | 860 | 0
[6 empty] | 861 | 324665.6234 | 861 | 324665.6234
[6 empty] | 862 | 0 | 862 | 0
[6 empty] | 863 | 0 | 863 | 0
[6 empty] | 864 | 302967.3252 | 864 | 302967.3252
[6 empty] | 865 | 3613191.6559 | 865 | 3613191.6559
[6 empty] | 866 | 432601.0228 | 866 | 432601.0228
[6 empty] | 867 | 27023396.5379 | 867 | 1302644.042
[6 empty] | 868 | 6305133.0414 | 868 | 0
[6 empty] | 869 | 0 | 869 | 0
[6 empty] | 870 | 0 | 870 | 0
[6 empty] | 871 | 2273952.5567 | 871 | 0
[6 empty] | 872 | 5481761.9557 | 872 | 3402680.5214
[6 empty] | 873 | 445814.8452 | 873 | 0
[6 empty] | 874 | 240918.5234 | 874 | 0
[6 empty] | 875 | 195543.0707 | 875 | 195543.0707
[6 empty] | 876 | 343203.8173 | 876 | 343203.8173
[6 empty] | 877 | 705672.3799 | 877 | 705672.3799
[6 empty] | 878 | 162820.0783 | 878 | 162820.0783
[6 empty] | 879 | 439662.4264 | 879 | 0
[6 empty] | 880 | 1096802.4176 | 880 | 1096802.4176
[6 empty] | 881 | 0 | 881 | 0
[6 empty] | 882 | 1188571.019 | 882 | 1188571.019
[6 empty] | 883 | 0 | 883 | 0
[6 empty] | 884 | 249700.2063 | 884 | 249700.2063
[6 empty] | 885 | 0 | 885 | 0
[6 empty] | 886 | 164942.5286 | 886 | 164942.5286
[6 empty] | 887 | 2230507.9643 | 887 | 2230507.9643
[6 empty] | 888 | 0 | 888 | 0
[6 empty] | 889 | 280141.8894 | 889 | 0
[6 empty] | 890 | 0 | 890 | 0
[6 empty] | 891 | 0 | 891 | 0
[6 empty] | 892 | 2831934.7957 | 892 | 0
[6 empty] | 893 | 8044484.2285 | 893 | 353420.9516
[6 empty] | 894 | 0 | 894 | 0
[6 empty] | 895 | 1701398.3579 | 895 | 1701398.3579
[6 empty] | 896 | 0 | 896 | 0
[6 empty] | 897 | 0 | 897 | 0
[6 empty] | 898 | 0 | 898 | 0
[6 empty] | 899 | 0 | 899 | 0
[6 empty] | 900 | 3534586.3403 | 900 | 3534586.3403
[6 empty] | 901 | 4239264.2799 | 901 | 0
[6 empty] | 902 | 0 | 902 | 0
[6 empty] | 903 | 517204.3281 | 903 | 202036.2945
[6 empty] | 904 | 0 | 904 | 0
[6 empty] | 905 | 0 | 905 | 0
[6 empty] | 906 | 0 | 906 | 0
[6 empty] | 907 | 7139172.6738 | 907 | 0
[6 empty] | 908 | 191439.1179 | 908 | 0
[6 empty] | 909 | 973305.7709 | 909 | 973305.7709
[6 empty] | 910 | 1494690.6082 | 910 | 1494690.6082
[6 empty] | 911 | 1624142.2841 | 911 | 1624142.2841
[6 empty] | 912 | 477184.508 | 912 | 0
[6 empty] | 913 | 176875.3087 | 913 | 176875.3087
[6 empty] | 914 | 2819236.8083 | 914 | 2819236.8083
[6 empty] | 915 | 2937484.6856 | 915 | 2937484.6856
[6 empty] | 916 | 0 | 916 | 0
[6 empty] | 917 | 0 | 917 | 0
[6 empty] | 918 | 5673603.4038 | 918 | 5673603.4038
[6 empty] | 919 | 0 | 919 | 0
[6 empty] | 920 | 2097524.4417 | 920 | 2097524.4417
[6 empty] | 921 | 5537332.1467 | 921 | 5537332.1467
[6 empty] | 922 | 0 | 922 | 0
[6 empty] | 923 | 6285277.8435 | 923 | 2555421.0805
[6 empty] | 924 | 1494932.2649 | 924 | 0
[6 empty] | 925 | 0 | 925 | 0
[6 empty] | 926 | 206852.7595 | 926 | 206852.7595
[6 empty] | 927 | 0 | 927 | 0
[6 empty] | 928 | 0 | 928 | 0
[6 empty] | 929 | 10066261.7404 | 929 | 0
[6 empty] | 930 | 0 | 930 | 0
[6 empty] | 931 | 1314810.482 | 931 | 1314810.482
[6 empty] | 932 | 0 | 932 | 0
[6 empty] | 933 | 775434.6154 | 933 | 598653.9499
[6 empty] | 934 | 0 | 934 | 0
[6 empty] | 935 | 305042.807 | 935 | 305042.807
[6 empty] | 936 | 0 | 936 | 0
[6 empty] | 937 | 0 | 937 | 0
[6 empty] | 938 | 144761.0987 | 938 | 144761.0987
[6 empty] | 939 | 1980738.9165 | 939 | 460030.2379
[6 empty] | 940 | 291601.691 | 940 | 291601.691
[6 empty] | 941 | 0 | 941 | 0
[6 empty] | 942 | 150834.2159 | 942 | 150834.2159
[6 empty] | 943 | 237956.1275 | 943 | 237956.1275
[6 empty] | 944 | 2293437.4595 | 944 | 0
[6 empty] | 945 | 914745.273 | 945 | 914745.273
[6 empty] | 946 | 0 | 946 | 0
[6 empty] | 947 | 322021.983 | 947 | 322021.983
[6 empty] | 948 | 0 | 948 | 0
[6 empty] | 949 | 0 | 949 | 0
[6 empty] | 950 | 365270.7335 | 950 | 365270.7335
[6 empty] | 951 | 0 | 951 | 0
[6 empty] | 952 | 5797233.8598 | 952 | 0
[6 empty] | 953 | 8087668.4144 | 953 | 153962.7875
[6 empty] | 954 | 253774.5019 | 954 | 0
[6 empty] | 955 | 0 | 955 | 0
[6 empty] | 956 | 12076993.1474 | 956 | 12076993.1474
[6 empty] | 957 | 1573676.7433 | 957 | 1573676.7433
[6 empty] | 958 | 0 | 958 | 0
[6 empty] | 959 | 1993962.7635 | 959 | 203240.4859
[6 empty] | 960 | 0 | 960 | 0
[6 empty] | 961 | 4443988.7946 | 961 | 2763003.6753
[6 empty] | 962 | 1670175.1524 | 962 | 0
[6 empty] | 963 | 0 | 963 | 0
[6 empty] | 964 | 9665907.6661 | 964 | 0
[6 empty] | 965 | 7602451.8065 | 965 | 7602451.8065
[6 empty] | 966 | 114077.4595 | 966 | 114077.4595
[6 empty] | 967 | 0 | 967 | 0
[6 empty] | 968 | 0 | 968 | 0
[6 empty] | 969 | 0 | 969 | 0
[6 empty] | 970 | 0 | 970 | 0
[6 empty] | 971 | 0 | 971 | 0
[6 empty] | 972 | 217707.7655 | 972 | 0
[6 empty] | 973 | 0 | 973 | 0
[6 empty] | 974 | 0 | 974 | 0
[6 empty] | 975 | 0 | 975 | 0
[6 empty] | 976 | 159768.7561 | 976 | 159768.7561
[6 empty] | 977 | 175727.5033 | 977 | 175727.5033
[6 empty] | 978 | 3356239.0715 | 978 | 0
[6 empty] | 979 | 0 | 979 | 0
[6 empty] | 980 | 102998.723 | 980 | 102998.723
[6 empty] | 981 | 195463.7464 | 981 | 195463.7464
[6 empty] | 982 | 0 | 982 | 0
[6 empty] | 983 | 0 | 983 | 0
[6 empty] | 984 | 0 | 984 | 0
[6 empty] | 985 | 1059683.3145 | 985 | 1059683.3145
[6 empty] | 986 | 0 | 986 | 0
[6 empty] | 987 | 4238938.9478 | 987 | 4238938.9478
[6 empty] | 988 | 3005703.1152 | 988 | 0
[6 empty] | 989 | 2809305.0549 | 989 | 1756093.6204
[6 empty] | 990 | 176209.622 | 990 | 176209.622
[6 empty] | 991 | 1967821.8114 | 991 | 1608779.4827
[6 empty] | 992 | 1486285.8671 | 992 | 0
[6 empty] | 993 | 0 | 993 | 0
[6 empty] | 994 | 0 | 994 | 0
[6 empty] | 995 | 3597591.0948 | 995 | 0
[6 empty] | 996 | 0 | 996 | 0
[6 empty] | 997 | 13238338.2542 | 997 | 4500724.3788
[6 empty] | 998 | 354642.2219 | 998 | 354642.2219
[6 empty] | 999 | 0 | 999 | 0
[6 empty] | 1000 | 3518091.5721 | 1000 | 3324733.8555
[6 empty] | 1001 | 0 | 1001 | 0
[6 empty] | 1002 | 0 | 1002 | 0
[6 empty] | 1003 | 0 | 1003 | 0
[6 empty] | 1004 | 2304945.6392 | 1004 | 0
[6 empty] | 1005 | 593036.1287 | 1005 | 593036.1287
[6 empty] | 1006 | 0 | 1006 | 0
[6 empty] | 1007 | 3726136.4677 | 1007 | 3726136.4677
[6 empty] | 1008 | 1773925.0962 | 1008 | 0
[6 empty] | 1009 | 703026.5078 | 1009 | 703026.5078
[6 empty] | 1010 | 2517947.1948 | 1010 | 0
[6 empty] | 1011 | 0 | 1011 | 0
[6 empty] | 1012 | 0 | 1012 | 0
[6 empty] | 1013 | 208630.5594 | 1013 | 208630.5594
[6 empty] | 1014 | 0 | 1014 | 0
[6 empty] | 1015 | 313197.0967 | 1015 | 313197.0967
[6 empty] | 1016 | 0 | 1016 | 0
[6 empty] | 1017 | 0 | 1017 | 0
[6 empty] | 1018 | 0 | 1018 | 0
[6 empty] | 1019 | 0 | 1019 | 0
[6 empty] | 1020 | 0 | 1020 | 0
[6 empty] | 1021 | 305751.8445 | 1021 | 0
[6 empty] | 1022 | 0 | 1022 | 0
[6 empty] | 1023 | 226380.8561 | 1023 | 226380.8561
[6 empty] | 1024 | 202596.2794 | 1024 | 0
[6 empty] | 1025 | 0 | 1025 | 0
[6 empty] | 1026 | 0 | 1026 | 0
[6 empty] | 1027 | 0 | 1027 | 0
[6 empty] | 1028 | 0 | 1028 | 0
[6 empty] | 1029 | 0 | 1029 | 0
[6 empty] | 1030 | 0 | 1030 | 0
[6 empty] | 1031 | 0 | 1031 | 0
[6 empty] | 1032 | 569223.6231 | 1032 | 328364.4924
[6 empty] | 1033 | 300390.8741 | 1033 | 300390.8741
[6 empty] | 1034 | 3091884.1665 | 1034 | 3091884.1665
[6 empty] | 1035 | 3946360.2377 | 1035 | 0
[6 empty] | 1036 | 214247.7448 | 1036 | 0
[6 empty] | 1037 | 0 | 1037 | 0
[6 empty] | 1038 | 440537.6308 | 1038 | 440537.6308
[6 empty] | 1039 | 300847.8435 | 1039 | 0
[6 empty] | 1040 | 0 | 1040 | 0
[6 empty] | 1041 | 0 | 1041 | 0
[6 empty] | 1042 | 0 | 1042 | 0
[6 empty] | 1043 | 10337690.7795 | 1043 | 0
[6 empty] | 1044 | 3152403.7798 | 1044 | 2918152.0432
[6 empty] | 1045 | 4137259.7797 | 1045 | 0
[6 empty] | 1046 | 0 | 1046 | 0
[6 empty] | 1047 | 0 | 1047 | 0
[6 empty] | 1048 | 0 | 1048 | 0
[6 empty] | 1049 | 0 | 1049 | 0
[6 empty] | 1050 | 3545097.3878 | 1050 | 3545097.3878
[6 empty] | 1051 | 1149280.8431 | 1051 | 1149280.8431
[6 empty] | 1052 | 0 | 1052 | 0
[6 empty] | 1053 | 204254.0649 | 1053 | 204254.0649
[6 empty] | 1054 | 239132.6005 | 1054 | 0
[6 empty] | 1055 | 130401.5058 | 1055 | 0
[6 empty] | 1056 | 0 | 1056 | 0
[6 empty] | 1057 | 0 | 1057 | 0
[6 empty] | 1058 | 0 | 1058 | 0
[6 empty] | 1059 | 1954373.3662 | 1059 | 0
[6 empty] | 1060 | 0 | 1060 | 0
[6 empty] | 1061 | 471659.762 | 1061 | 169539.2081
[6 empty] | 1062 | 177170.8673 | 1062 | 0
[6 empty] | 1063 | 0 | 1063 | 0
[6 empty] | 1064 | 2775122.722 | 1064 | 2775122.722
[6 empty] | 1065 | 0 | 1065 | 0
[6 empty] | 1066 | 0 | 1066 | 0
[6 empty] | 1067 | 159968.0204 | 1067 | 159968.0204
[6 empty] | 1068 | 6392630.7716 | 1068 | 3263981.9933
[6 empty] | 1069 | 0 | 1069 | 0
[6 empty] | 1070 | 0 | 1070 | 0
[6 empty] | 1071 | 0 | 1071 | 0
[6 empty] | 1072 | 910379.3329 | 1072 | 681398.6401
[6 empty] | 1073 | 2988535.29 | 1073 | 179207.5229
[6 empty] | 1074 | 562004.3198 | 1074 | 0
[6 empty] | 1075 | 6272424.6527 | 1075 | 189228.1306
[6 empty] | 1076 | 425603.1079 | 1076 | 425603.1079
[6 empty] | 1077 | 3186014.8566 | 1077 | 0
[6 empty] | 1078 | 0 | 1078 | 0
[6 empty] | 1079 | 3303228.0407 | 1079 | 3303228.0407
[6 empty] | 1080 | 26504525.4914 | 1080 | 2448446.3548
[6 empty] | 1081 | 0 | 1081 | 0
[6 empty] | 1082 | 0 | 1082 | 0
[6 empty] | 1083 | 177539.3636 | 1083 | 0
[6 empty] | 1084 | 0 | 1084 | 0
[6 empty] | 1085 | 2593899.2392 | 1085 | 2593899.2392
[6 empty] | 1086 | 0 | 1086 | 0
[6 empty] | 1087 | 0 | 1087 | 0
[6 empty] | 1088 | 0 | 1088 | 0
[6 empty] | 1089 | 0 | 1089 | 0
[6 empty] | 1090 | 0 | 1090 | 0
[6 empty] | 1091 | 0 | 1091 | 0
[6 empty] | 1092 | 830345.3476 | 1092 | 830345.3476
[6 empty] | 1093 | 4568520.7438 | 1093 | 4568520.7438
[6 empty] | 1094 | 0 | 1094 | 0
[6 empty] | 1095 | 5121880.3519 | 1095 | 0
[6 empty] | 1096 | 558028.9719 | 1096 | 0
[6 empty] | 1097 | 5653234.998 | 1097 | 929538.0838
[6 empty] | 1098 | 0 | 1098 | 0
[6 empty] | 1099 | 335257.4737 | 1099 | 335257.4737
[6 empty] | 1100 | 0 | 1100 | 0
[6 empty] | 1101 | 685498.2085 | 1101 | 0
[6 empty] | 1102 | 0 | 1102 | 0
[6 empty] | 1103 | 634311.6551 | 1103 | 634311.6551
[6 empty] | 1104 | 6028152.9717 | 1104 | 0
[6 empty] | 1105 | 0 | 1105 | 0
[6 empty] | 1106 | 243158.7366 | 1106 | 243158.7366
[6 empty] | 1107 | 165272.679 | 1107 | 0
[6 empty] | 1108 | 3273330.3981 | 1108 | 3273330.3981
[6 empty] | 1109 | 365226.0446 | 1109 | 365226.0446
[6 empty] | 1110 | 0 | 1110 | 0
[6 empty] | 1111 | 265549.5082 | 1111 | 265549.5082
[6 empty] | 1112 | 0 | 1112 | 0
[6 empty] | 1113 | 129293.0493 | 1113 | 0
[6 empty] | 1114 | 0 | 1114 | 0
[6 empty] | 1115 | 1101877.7669 | 1115 | 1101877.7669
[6 empty] | 1116 | 185136.2211 | 1116 | 0
[6 empty] | 1117 | 0 | 1117 | 0
[6 empty] | 1118 | 1351391.4918 | 1118 | 0
[6 empty] | 1119 | 0 | 1119 | 0
[6 empty] | 1120 | 4576192.502 | 1120 | 4576192.502
[6 empty] | 1121 | 0 | 1121 | 0
[6 empty] | 1122 | 155594.198 | 1122 | 0
[6 empty] | 1123 | 3189857.7672 | 1123 | 0
[6 empty] | 1124 | 6389772.0928 | 1124 | 0
[6 empty] | 1125 | 0 | 1125 | 0
[6 empty] | 1126 | 181925.2006 | 1126 | 181925.2006
[6 empty] | 1127 | 13018809.7005 | 1127 | 0
[6 empty] | 1128 | 0 | 1128 | 0
[6 empty] | 1129 | 4164333.7571 | 1129 | 1806953.2089
[6 empty] | 1130 | 0 | 1130 | 0
[6 empty] | 1131 | 1953633.8108 | 1131 | 0
[6 empty] | 1132 | 0 | 1132 | 0
[6 empty] | 1133 | 4203799.9511 | 1133 | 0
[6 empty] | 1134 | 0 | 1134 | 0
[6 empty] | 1135 | 0 | 1135 | 0
[6 empty] | 1136 | 0 | 1136 | 0
[6 empty] | 1137 | 0 | 1137 | 0
[6 empty] | 1138 | 0 | 1138 | 0
[6 empty] | 1139 | 231036.8806 | 1139 | 0
[6 empty] | 1140 | 15867859.4479 | 1140 | 0
[6 empty] | 1141 | 723382.9796 | 1141 | 723382.9796
[6 empty] | 1142 | 0 | 1142 | 0
[6 empty] | 1143 | 7267637.5109 | 1143 | 7267637.5109
[6 empty] | 1144 | 950516.1313 | 1144 | 821104.57
[6 empty] | 1145 | 0 | 1145 | 0
[6 empty] | 1146 | 1443338.4537 | 1146 | 1443338.4537
[6 empty] | 1147 | 0 | 1147 | 0
[6 empty] | 1148 | 141966.0078 | 1148 | 141966.0078
[6 empty] | 1149 | 1433629.984 | 1149 | 0
[6 empty] | 1150 | 2213919.3294 | 1150 | 0
[6 empty] | 1151 | 0 | 1151 | 0
[6 empty] | 1152 | 1016532.0313 | 1152 | 1016532.0313
[6 empty] | 1153 | 3110903.5395 | 1153 | 3110903.5395
[6 empty] | 1154 | 0 | 1154 | 0
[6 empty] | 1155 | 0 | 1155 | 0
[6 empty] | 1156 | 0 | 1156 | 0
[6 empty] | 1157 | 4040131.9472 | 1157 | 0
[6 empty] | 1158 | 0 | 1158 | 0
[6 empty] | 1159 | 2428201.354 | 1159 | 2428201.354
[6 empty] | 1160 | 0 | 1160 | 0
[6 empty] | 1161 | 0 | 1161 | 0
[6 empty] | 1162 | 0 | 1162 | 0
[6 empty] | 1163 | 0 | 1163 | 0
[6 empty] | 1164 | 2770436.977 | 1164 | 2770436.977
[6 empty] | 1165 | 3086791.113 | 1165 | 2918330.5674
[6 empty] | 1166 | 182316.4939 | 1166 | 0
[6 empty] | 1167 | 0 | 1167 | 0
[6 empty] | 1168 | 5011084.4273 | 1168 | 0
[6 empty] | 1169 | 335271.1362 | 1169 | 0
[6 empty] | 1170 | 142075.3817 | 1170 | 142075.3817
[6 empty] | 1171 | 0 | 1171 | 0
[6 empty] | 1172 | 196406.9773 | 1172 | 196406.9773
[6 empty] | 1173 | 195109.9102 | 1173 | 0
[6 empty] | 1174 | 1176264.4927 | 1174 | 1176264.4927
[6 empty] | 1175 | 5446757.4993 | 1175 | 0
[6 empty] | 1176 | 604899.0216 | 1176 | 604899.0216
[6 empty] | 1177 | 11199989.9298 | 1177 | 0
[6 empty] | 1178 | 0 | 1178 | 0
[6 empty] | 1179 | 8150661.9649 | 1179 | 0
[6 empty] | 1180 | 0 | 1180 | 0
[6 empty] | 1181 | 0 | 1181 | 0
[6 empty] | 1182 | 2052111.1986 | 1182 | 2052111.1986
[6 empty] | 1183 | 2342147.0238 | 1183 | 0
[6 empty] | 1184 | 172832.2456 | 1184 | 0
[6 empty] | 1185 | 0 | 1185 | 0
[6 empty] | 1186 | 3738087.5946 | 1186 | 924803.3363
[6 empty] | 1187 | 0 | 1187 | 0
[6 empty] | 1188 | 0 | 1188 | 0
[6 empty] | 1189 | 3706113.812 | 1189 | 3706113.812
[6 empty] | 1190 | 0 | 1190 | 0
[6 empty] | 1191 | 321408.1427 | 1191 | 321408.1427
[6 empty] | 1192 | 0 | 1192 | 0
[6 empty] | 1193 | 0 | 1193 | 0
[6 empty] | 1194 | 696741.6112 | 1194 | 496293.9819
[6 empty] | 1195 | 0 | 1195 | 0
[6 empty] | 1196 | 523144.0296 | 1196 | 523144.0296
[6 empty] | 1197 | 0 | 1197 | 0
[6 empty] | 1198 | 380220.9879 | 1198 | 380220.9879
[6 empty] | 1199 | 1501946.4036 | 1199 | 1501946.4036
[6 empty] | 1200 | 1653852.9436 | 1200 | 1653852.9436
[6 empty] | 1201 | 1050791.4811 | 1201 | 0
[6 empty] | 1202 | 2632087.872 | 1202 | 0
[6 empty] | 1203 | 224701.5845 | 1203 | 224701.5845
[6 empty] | 1204 | 0 | 1204 | 0
[6 empty] | 1205 | 0 | 1205 | 0
[6 empty] | 1206 | 0 | 1206 | 0
[6 empty] | 1207 | 2719311.8698 | 1207 | 0
[6 empty] | 1208 | 3793248.4386 | 1208 | 3793248.4386
[6 empty] | 1209 | 0 | 1209 | 0
[6 empty] | 1210 | 2083111.609 | 1210 | 0
[6 empty] | 1211 | 3234205.6589 | 1211 | 0
[6 empty] | 1212 | 894429.1716 | 1212 | 894429.1716
[6 empty] | 1213 | 0 | 1213 | 0
[6 empty] | 1214 | 251980.6632 | 1214 | 251980.6632
[6 empty] | 1215 | 0 | 1215 | 0
[6 empty] | 1216 | 0 | 1216 | 0
[6 empty] | 1217 | 0 | 1217 | 0
[6 empty] | 1218 | 319680.5549 | 1218 | 319680.5549
[6 empty] | 1219 | 4835054.4477 | 1219 | 0
[6 empty] | 1220 | 265279.6182 | 1220 | 265279.6182
[6 empty] | 1221 | 0 | 1221 | 0
[6 empty] | 1222 | 5216835.516 | 1222 | 3669496.1289
[6 empty] | 1223 | 0 | 1223 | 0
[6 empty] | 1224 | 3996317.942 | 1224 | 0
[6 empty] | 1225 | 0 | 1225 | 0
[6 empty] | 1226 | 0 | 1226 | 0
[6 empty] | 1227 | 2002213.3861 | 1227 | 0
[6 empty] | 1228 | 0 | 1228 | 0
[6 empty] | 1229 | 0 | 1229 | 0
[6 empty] | 1230 | 0 | 1230 | 0
[6 empty] | 1231 | 285079.0549 | 1231 | 285079.0549
[6 empty] | 1232 | 260343.2207 | 1232 | 0
[6 empty] | 1233 | 229407.0181 | 1233 | 0
[6 empty] | 1234 | 249120.3799 | 1234 | 249120.3799
[6 empty] | 1235 | 0 | 1235 | 0
[6 empty] | 1236 | 191213.1831 | 1236 | 191213.1831
[6 empty] | 1237 | 1120495.3498 | 1237 | 0
[6 empty] | 1238 | 163067.9266 | 1238 | 163067.9266
[6 empty] | 1239 | 0 | 1239 | 0
[6 empty] | 1240 | 0 | 1240 | 0
[6 empty] | 1241 | 269239.2078 | 1241 | 269239.2078
[6 empty] | 1242 | 138017.2211 | 1242 | 138017.2211
[6 empty] | 1243 | 201098.5096 | 1243 | 0
[6 empty] | 1244 | 15099440.3462 | 1244 | 0
[6 empty] | 1245 | 0 | 1245 | 0
[6 empty] | 1246 | 0 | 1246 | 0
[6 empty] | 1247 | 0 | 1247 | 0
[6 empty] | 1248 | 0 | 1248 | 0
[6 empty] | 1249 | 0 | 1249 | 0
[6 empty] | 1250 | 0 | 1250 | 0
[6 empty] | 1251 | 3497546.168 | 1251 | 3497546.168
[6 empty] | 1252 | 0 | 1252 | 0
[6 empty] | 1253 | 493337.273 | 1253 | 493337.273
[6 empty] | 1254 | 1159946.491 | 1254 | 1159946.491
[6 empty] | 1255 | 0 | 1255 | 0
[6 empty] | 1256 | 190926.673 | 1256 | 0
[6 empty] | 1257 | 1943380.1262 | 1257 | 1943380.1262
[6 empty] | 1258 | 290578.2397 | 1258 | 290578.2397
[6 empty] | 1259 | 0 | 1259 | 0
[6 empty] | 1260 | 1804057.404 | 1260 | 0
[6 empty] | 1261 | 486452.1072 | 1261 | 486452.1072
[6 empty] | 1262 | 1828999.5364 | 1262 | 0
[6 empty] | 1263 | 208498.3464 | 1263 | 0
[6 empty] | 1264 | 412786.855 | 1264 | 412786.855
[6 empty] | 1265 | 0 | 1265 | 0
[6 empty] | 1266 | 249140.8971 | 1266 | 0
[6 empty] | 1267 | 2917488.0618 | 1267 | 0
[6 empty] | 1268 | 1704195.786 | 1268 | 0
[6 empty] | 1269 | 2342089.1598 | 1269 | 2342089.1598
[6 empty] | 1270 | 1797369.4187 | 1270 | 0
[6 empty] | 1271 | 0 | 1271 | 0
[6 empty] | 1272 | 0 | 1272 | 0
[6 empty] | 1273 | 0 | 1273 | 0
[6 empty] | 1274 | 0 | 1274 | 0
[6 empty] | 1275 | 0 | 1275 | 0
[6 empty] | 1276 | 0 | 1276 | 0
[6 empty] | 1277 | 0 | 1277 | 0
[6 empty] | 1278 | 0 | 1278 | 0
[6 empty] | 1279 | 0 | 1279 | 0
[6 empty] | 1280 | 250027.8913 | 1280 | 250027.8913
[6 empty] | 1281 | 0 | 1281 | 0
[6 empty] | 1282 | 232429.6315 | 1282 | 232429.6315
[6 empty] | 1283 | 0 | 1283 | 0
[6 empty] | 1284 | 0 | 1284 | 0
[6 empty] | 1285 | 0 | 1285 | 0
[6 empty] | 1286 | 0 | 1286 | 0
[6 empty] | 1287 | 0 | 1287 | 0
[6 empty] | 1288 | 367874.4475 | 1288 | 367874.4475
[6 empty] | 1289 | 0 | 1289 | 0
[6 empty] | 1290 | 0 | 1290 | 0
[6 empty] | 1291 | 0 | 1291 | 0
[6 empty] | 1292 | 1048983.1941 | 1292 | 1048983.1941
[6 empty] | 1293 | 4611556.679 | 1293 | 4611556.679
[6 empty] | 1294 | 896833.845 | 1294 | 0
[6 empty] | 1295 | 5375760.2318 | 1295 | 0
[6 empty] | 1296 | 672357.5725 | 1296 | 672357.5725
[6 empty] | 1297 | 3273930.7925 | 1297 | 3273930.7925
[6 empty] | 1298 | 0 | 1298 | 0
[6 empty] | 1299 | 932238.0868 | 1299 | 0
[6 empty] | 1300 | 1132313.8579 | 1300 | 1132313.8579
[6 empty] | 1301 | 3267779.3131 | 1301 | 0
[6 empty] | 1302 | 1910266.7849 | 1302 | 1910266.7849
[6 empty] | 1303 | 339534.2324 | 1303 | 183938.3478
[6 empty] | 1304 | 435086.2646 | 1304 | 435086.2646
[6 empty] | 1305 | 0 | 1305 | 0
[6 empty] | 1306 | 0 | 1306 | 0
[6 empty] | 1307 | 411453.8411 | 1307 | 0
[6 empty] | 1308 | 0 | 1308 | 0
[6 empty] | 1309 | 165609.1848 | 1309 | 165609.1848
[6 empty] | 1310 | 0 | 1310 | 0
[6 empty] | 1311 | 2346190.9569 | 1311 | 635846.4016
[6 empty] | 1312 | 156027.9361 | 1312 | 156027.9361
[6 empty] | 1313 | 0 | 1313 | 0
[6 empty] | 1314 | 187966.1145 | 1314 | 0
[6 empty] | 1315 | 0 | 1315 | 0
[6 empty] | 1316 | 1117959.2589 | 1316 | 1117959.2589
[6 empty] | 1317 | 0 | 1317 | 0
[6 empty] | 1318 | 0 | 1318 | 0
[6 empty] | 1319 | 0 | 1319 | 0
[6 empty] | 1320 | 222510.3094 | 1320 | 0
[6 empty] | 1321 | 0 | 1321 | 0
[6 empty] | 1322 | 6948462.0743 | 1322 | 266931.8272
[6 empty] | 1323 | 0 | 1323 | 0
[6 empty] | 1324 | 10394184.0318 | 1324 | 216297.7843
[6 empty] | 1325 | 0 | 1325 | 0
[6 empty] | 1326 | 0 | 1326 | 0
[6 empty] | 1327 | 440957.9001 | 1327 | 440957.9001
[6 empty] | 1328 | 246414.5769 | 1328 | 246414.5769
[6 empty] | 1329 | 0 | 1329 | 0
[6 empty] | 1330 | 255497.0384 | 1330 | 0
[6 empty] | 1331 | 202435.3796 | 1331 | 202435.3796
[6 empty] | 1332 | 159853.0327 | 1332 | 159853.0327
[6 empty] | 1333 | 0 | 1333 | 0
[6 empty] | 1334 | 0 | 1334 | 0
[6 empty] | 1335 | 18098449.4595 | 1335 | 0
[6 empty] | 1336 | 0 | 1336 | 0
[6 empty] | 1337 | 995685.1705 | 1337 | 619559.2828
[6 empty] | 1338 | 0 | 1338 | 0
[6 empty] | 1339 | 883787.9258 | 1339 | 747367.6867
[6 empty] | 1340 | 0 | 1340 | 0
[6 empty] | 1341 | 0 | 1341 | 0
[6 empty] | 1342 | 1158807.3733 | 1342 | 1158807.3733
[6 empty] | 1343 | 1052497.529 | 1343 | 0
[6 empty] | 1344 | 1195925.7563 | 1344 | 0
[6 empty] | 1345 | 4237993.3017 | 1345 | 1323109.4008
[6 empty] | 1346 | 1007729.2893 | 1346 | 305599.1561
[6 empty] | 1347 | 0 | 1347 | 0
[6 empty] | 1348 | 0 | 1348 | 0
[6 empty] | 1349 | 0 | 1349 | 0
[6 empty] | 1350 | 2491365.4681 | 1350 | 2491365.4681
[6 empty] | 1351 | 614979.8754 | 1351 | 614979.8754
[6 empty] | 1352 | 192806.474 | 1352 | 192806.474
[6 empty] | 1353 | 0 | 1353 | 0
[6 empty] | 1354 | 0 | 1354 | 0
[6 empty] | 1355 | 887675.1422 | 1355 | 0
[6 empty] | 1356 | 0 | 1356 | 0
[6 empty] | 1357 | 0 | 1357 | 0
[6 empty] | 1358 | 3084068.7511 | 1358 | 0
[6 empty] | 1359 | 502240.8173 | 1359 | 502240.8173
[6 empty] | 1360 | 234054.7255 | 1360 | 234054.7255
[6 empty] | 1361 | 242193.4766 | 1361 | 0
[6 empty] | 1362 | 0 | 1362 | 0
[6 empty] | 1363 | 0 | 1363 | 0
[6 empty] | 1364 | 0 | 1364 | 0
[6 empty] | 1365 | 9679171.7002 | 1365 | 9679171.7002
[6 empty] | 1366 | 0 | 1366 | 0
[6 empty] | 1367 | 495121.1765 | 1367 | 495121.1765
[6 empty] | 1368 | 0 | 1368 | 0
[6 empty] | 1369 | 0 | 1369 | 0
[6 empty] | 1370 | 0 | 1370 | 0
[6 empty] | 1371 | 0 | 1371 | 0
[6 empty] | 1372 | 236431.1434 | 1372 | 236431.1434
[6 empty] | 1373 | 807782.3026 | 1373 | 0
[6 empty] | 1374 | 2715712.7042 | 1374 | 0
[6 empty] | 1375 | 449059.8269 | 1375 | 449059.8269
[6 empty] | 1376 | 0 | 1376 | 0
[6 empty] | 1377 | 467604.5611 | 1377 | 467604.5611
[6 empty] | 1378 | 0 | 1378 | 0
[6 empty] | 1379 | 3557464.7166 | 1379 | 3338890.7611
[6 empty] | 1380 | 6113106.7811 | 1380 | 0
[6 empty] | 1381 | 0 | 1381 | 0
[6 empty] | 1382 | 0 | 1382 | 0
[6 empty] | 1383 | 0 | 1383 | 0
[6 empty] | 1384 | 0 | 1384 | 0
[6 empty] | 1385 | 0 | 1385 | 0
[6 empty] | 1386 | 0 | 1386 | 0
[6 empty] | 1387 | 0 | 1387 | 0
[6 empty] | 1388 | 457571.2048 | 1388 | 457571.2048
[6 empty] | 1389 | 5834555.9324 | 1389 | 5834555.9324
[6 empty] | 1390 | 4162966.1201 | 1390 | 0
[6 empty] | 1391 | 4950375.3904 | 1391 | 973150.2238
[6 empty] | 1392 | 1098238.3059 | 1392 | 1098238.3059
[6 empty] | 1393 | 2166697.9913 | 1393 | 0
[6 empty] | 1394 | 4024445.9103 | 1394 | 0
[6 empty] | 1395 | 0 | 1395 | 0
[6 empty] | 1396 | 1571259.2302 | 1396 | 1571259.2302
[6 empty] | 1397 | 2175650.0757 | 1397 | 2175650.0757
[6 empty] | 1398 | 284817.8574 | 1398 | 0
[6 empty] | 1399 | 196543.0286 | 1399 | 0
[6 empty] | 1400 | 4080768.5349 | 1400 | 4080768.5349
[6 empty] | 1401 | 385953.6067 | 1401 | 385953.6067
[6 empty] | 1402 | 0 | 1402 | 0
[6 empty] | 1403 | 0 | 1403 | 0
[6 empty] | 1404 | 0 | 1404 | 0
[6 empty] | 1405 | 0 | 1405 | 0
[6 empty] | 1406 | 0 | 1406 | 0
[6 empty] | 1407 | 0 | 1407 | 0
[6 empty] | 1408 | 0 | 1408 | 0
[6 empty] | 1409 | 212259.305 | 1409 | 0
[6 empty] | 1410 | 1647913.2641 | 1410 | 1647913.2641
[6 empty] | 1411 | 4827659.3386 | 1411 | 4827659.3386
[6 empty] | 1412 | 8109501.8713 | 1412 | 5211591.7698
[6 empty] | 1413 | 0 | 1413 | 0
[6 empty] | 1414 | 0 | 1414 | 0
[6 empty] | 1415 | 0 | 1415 | 0
[6 empty] | 1416 | 2176838.6539 | 1416 | 2176838.6539
[6 empty] | 1417 | 0 | 1417 | 0
[6 empty] | 1418 | 2738664.3671 | 1418 | 2738664.3671
[6 empty] | 1419 | 2997464.7577 | 1419 | 369426.2597
[6 empty] | 1420 | 203495.9685 | 1420 | 203495.9685
[6 empty] | 1421 | 4578319.9685 | 1421 | 4578319.9685
[6 empty] | 1422 | 203462.6036 | 1422 | 203462.6036
[6 empty] | 1423 | 0 | 1423 | 0
[6 empty] | 1424 | 2208450.9213 | 1424 | 0
[6 empty] | 1425 | 0 | 1425 | 0
[6 empty] | 1426 | 158097.9544 | 1426 | 0
[6 empty] | 1427 | 123949.4739 | 1427 | 123949.4739
[6 empty] | 1428 | 340987.4697 | 1428 | 0
[6 empty] | 1429 | 1286153.1213 | 1429 | 1286153.1213
[6 empty] | 1430 | 0 | 1430 | 0
[6 empty] | 1431 | 446901.5505 | 1431 | 446901.5505
[6 empty] | 1432 | 0 | 1432 | 0
[6 empty] | 1433 | 7868573.0063 | 1433 | 3292827.4952
[6 empty] | 1434 | 0 | 1434 | 0
[6 empty] | 1435 | 0 | 1435 | 0
[6 empty] | 1436 | 216267.1008 | 1436 | 216267.1008
[6 empty] | 1437 | 375750.1556 | 1437 | 375750.1556
[6 empty] | 1438 | 0 | 1438 | 0
[6 empty] | 1439 | 0 | 1439 | 0
[6 empty] | 1440 | 14689900.4264 | 1440 | 0
[6 empty] | 1441 | 0 | 1441 | 0
[6 empty] | 1442 | 0 | 1442 | 0
[6 empty] | 1443 | 0 | 1443 | 0
[6 empty] | 1444 | 3208578.1024 | 1444 | 3208578.1024
[6 empty] | 1445 | 218790.9042 | 1445 | 218790.9042
[6 empty] | 1446 | 0 | 1446 | 0
[6 empty] | 1447 | 0 | 1447 | 0
[6 empty] | 1448 | 432230.5519 | 1448 | 432230.5519
[6 empty] | 1449 | 0 | 1449 | 0
[6 empty] | 1450 | 163580.9332 | 1450 | 163580.9332
[6 empty] | 1451 | 0 | 1451 | 0
[6 empty] | 1452 | 0 | 1452 | 0
[6 empty] | 1453 | 3420683.7699 | 1453 | 216146.1242
[6 empty] | 1454 | 0 | 1454 | 0
[6 empty] | 1455 | 0 | 1455 | 0
[6 empty] | 1456 | 0 | 1456 | 0
[6 empty] | 1457 | 576830.5074 | 1457 | 0
[6 empty] | 1458 | 0 | 1458 | 0
[6 empty] | 1459 | 3528637.1093 | 1459 | 3528637.1093
[6 empty] | 1460 | 0 | 1460 | 0
[6 empty] | 1461 | 0 | 1461 | 0
[6 empty] | 1462 | 0 | 1462 | 0
[6 empty] | 1463 | 14531693.5202 | 1463 | 14531693.5202
[6 empty] | 1464 | 0 | 1464 | 0
[6 empty] | 1465 | 0 | 1465 | 0
[6 empty] | 1466 | 219505.7058 | 1466 | 0
[6 empty] | 1467 | 7881785.8778 | 1467 | 0
[6 empty] | 1468 | 2432320.317 | 1468 | 0
[6 empty] | 1469 | 220963.4531 | 1469 | 220963.4531
[6 empty] | 1470 | 0 | 1470 | 0
[6 empty] | 1471 | 0 | 1471 | 0
[6 empty] | 1472 | 69598888.9213 | 1472 | 247727.4855
[6 empty] | 1473 | 0 | 1473 | 0
[6 empty] | 1474 | 0 | 1474 | 0
[6 empty] | 1475 | 0 | 1475 | 0
[6 empty] | 1476 | 1337306.1379 | 1476 | 1185915.8318
[6 empty] | 1477 | 0 | 1477 | 0
[6 empty] | 1478 | 0 | 1478 | 0
[6 empty] | 1479 | 70534.9071 | 1479 | 70534.9071
[6 empty] | 1480 | 0 | 1480 | 0
[6 empty] | 1481 | 208548.6681 | 1481 | 208548.6681
[6 empty] | 1482 | 12142995.6109 | 1482 | 393540.6337
[6 empty] | 1483 | 4276653.4967 | 1483 | 246231.0826
[6 empty] | 1484 | 0 | 1484 | 0
[6 empty] | 1485 | 0 | 1485 | 0
[6 empty] | 1486 | 0 | 1486 | 0
[6 empty] | 1487 | 0 | 1487 | 0
[6 empty] | 1488 | 0 | 1488 | 0
[6 empty] | 1489 | 0 | 1489 | 0
[6 empty] | 1490 | 0 | 1490 | 0
[6 empty] | 1491 | 0 | 1491 | 0
[6 empty] | 1492 | 0 | 1492 | 0
[6 empty] | 1493 | 124928.9522 | 1493 | 124928.9522
[6 empty] | 1494 | 0 | 1494 | 0
[6 empty] | 1495 | 0 | 1495 | 0
[6 empty] | 1496 | 2153728.1813 | 1496 | 2153728.1813
[6 empty] | 1497 | 291283.8976 | 1497 | 291283.8976
[6 empty] | 1498 | 0 | 1498 | 0
[6 empty] | 1499 | 229712.5177 | 1499 | 229712.5177
[6 empty] | 1500 | 0 | 1500 | 0
[6 empty] | 1501 | 0 | 1501 | 0
[6 empty] | 1502 | 341711.1005 | 1502 | 341711.1005
[6 empty] | 1503 | 0 | 1503 | 0
[6 empty] | 1504 | 0 | 1504 | 0
[6 empty] | 1505 | 1419062.0482 | 1505 | 0
[6 empty] | 1506 | 0 | 1506 | 0
[6 empty] | 1507 | 0 | 1507 | 0
[6 empty] | 1508 | 0 | 1508 | 0
[6 empty] | 1509 | 0 | 1509 | 0
[6 empty] | 1510 | 803956.4349 | 1510 | 803956.4349
[6 empty] | 1511 | 386088.2634 | 1511 | 386088.2634
[6 empty] | 1512 | 0 | 1512 | 0
[6 empty] | 1513 | 22494207.8123 | 1513 | 0
[6 empty] | 1514 | 1112412.0721 | 1514 | 1112412.0721
[6 empty] | 1515 | 4135815.3566 | 1515 | 4135815.3566
[6 empty] | 1516 | 2496718.8957 | 1516 | 0
[6 empty] | 1517 | 0 | 1517 | 0
[6 empty] | 1518 | 720944.9646 | 1518 | 0
[6 empty] | 1519 | 0 | 1519 | 0
[6 empty] | 1520 | 230952.1049 | 1520 | 230952.1049
[6 empty] | 1521 | 318370.4851 | 1521 | 0
[6 empty] | 1522 | 0 | 1522 | 0
[6 empty] | 1523 | 2338358.7161 | 1523 | 172744.7466
[6 empty] | 1524 | 2460482.9672 | 1524 | 0
[6 empty] | 1525 | 433076.192 | 1525 | 433076.192
[6 empty] | 1526 | 7253498.649 | 1526 | 7253498.649
[6 empty] | 1527 | 4734504.9724 | 1527 | 4734504.9724
[6 empty] | 1528 | 0 | 1528 | 0
[6 empty] | 1529 | 0 | 1529 | 0
[6 empty] | 1530 | 1532784.8788 | 1530 | 1532784.8788
[6 empty] | 1531 | 0 | 1531 | 0
[6 empty] | 1532 | 0 | 1532 | 0
[6 empty] | 1533 | 2178568.7109 | 1533 | 2178568.7109
[6 empty] | 1534 | 6347606.3067 | 1534 | 0
[6 empty] | 1535 | 396008.0069 | 1535 | 396008.0069
[6 empty] | 1536 | 263280.3339 | 1536 | 263280.3339
[6 empty] | 1537 | 0 | 1537 | 0
[6 empty] | 1538 | 182348.6707 | 1538 | 0
[6 empty] | 1539 | 257187.2651 | 1539 | 0
[6 empty] | 1540 | 0 | 1540 | 0
[6 empty] | 1541 | 1984329.1455 | 1541 | 0
[6 empty] | 1542 | 8890731.5306 | 1542 | 0
[6 empty] | 1543 | 13472034.9052 | 1543 | 3498129.7871
[6 empty] | 1544 | 0 | 1544 | 0
[6 empty] | 1545 | 0 | 1545 | 0
[6 empty] | 1546 | 1270403.7641 | 1546 | 1270403.7641
[6 empty] | 1547 | 3520201.6737 | 1547 | 3520201.6737
[6 empty] | 1548 | 252402.3934 | 1548 | 252402.3934
[6 empty] | 1549 | 0 | 1549 | 0
[6 empty] | 1550 | 3207769.4359 | 1550 | 3207769.4359
[6 empty] | 1551 | 0 | 1551 | 0
[6 empty] | 1552 | 4609771.9646 | 1552 | 4609771.9646
[6 empty] | 1553 | 0 | 1553 | 0
[6 empty] | 1554 | 0 | 1554 | 0
[6 empty] | 1555 | 0 | 1555 | 0
[6 empty] | 1556 | 235825.0965 | 1556 | 235825.0965
[6 empty] | 1557 | 3625017.6132 | 1557 | 3625017.6132
[6 empty] | 1558 | 5533577.8345 | 1558 | 5284742.7333
[6 empty] | 1559 | 0 | 1559 | 0
[6 empty] | 1560 | 2996758.3958 | 1560 | 0
[6 empty] | 1561 | 730621.2271 | 1561 | 730621.2271
[6 empty] | 1562 | 0 | 1562 | 0
[6 empty] | 1563 | 286608.3151 | 1563 | 0
[6 empty] | 1564 | 1094600.369 | 1564 | 1094600.369
[6 empty] | 1565 | 0 | 1565 | 0
[6 empty] | 1566 | 0 | 1566 | 0
[6 empty] | 1567 | 2729285.6762 | 1567 | 305168.8501
[6 empty] | 1568 | 0 | 1568 | 0
[6 empty] | 1569 | 0 | 1569 | 0
[6 empty] | 1570 | 0 | 1570 | 0
[6 empty] | 1571 | 0 | 1571 | 0
[6 empty] | 1572 | 0 | 1572 | 0
[6 empty] | 1573 | 304017.1845 | 1573 | 304017.1845
[6 empty] | 1574 | 360204.9174 | 1574 | 360204.9174
[6 empty] | 1575 | 0 | 1575 | 0
[6 empty] | 1576 | 2614541.6243 | 1576 | 2614541.6243
[6 empty] | 1577 | 0 | 1577 | 0
[6 empty] | 1578 | 2644345.6011 | 1578 | 2644345.6011
[6 empty] | 1579 | 0 | 1579 | 0
[6 empty] | 1580 | 0 | 1580 | 0
[6 empty] | 1581 | 0 | 1581 | 0
[6 empty] | 1582 | 5238914.2125 | 1582 | 5238914.2125
[6 empty] | 1583 | 6327314.9244 | 1583 | 6327314.9244
[6 empty] | 1584 | 6948107.7283 | 1584 | 0
[6 empty] | 1585 | 579870.2639 | 1585 | 0
[6 empty] | 1586 | 0 | 1586 | 0
[6 empty] | 1587 | 171309.5858 | 1587 | 171309.5858
[6 empty] | 1588 | 633638.6541 | 1588 | 633638.6541
[6 empty] | 1589 | 0 | 1589 | 0
[6 empty] | 1590 | 0 | 1590 | 0
[6 empty] | 1591 | 1486982.7893 | 1591 | 0
[6 empty] | 1592 | 176270.4966 | 1592 | 176270.4966
[6 empty] | 1593 | 4376568.0025 | 1593 | 4376568.0025
[6 empty] | 1594 | 414960.0135 | 1594 | 414960.0135
[6 empty] | 1595 | 5572589.4371 | 1595 | 0
[6 empty] | 1596 | 4362345.6278 | 1596 | 4362345.6278
[6 empty] | 1597 | 0 | 1597 | 0
[6 empty] | 1598 | 4392828.3116 | 1598 | 2318843.3914
[6 empty] | 1599 | 284417.2935 | 1599 | 284417.2935
[6 empty] | 1600 | 2490169.2067 | 1600 | 0
[6 empty] | 1601 | 0 | 1601 | 0
[6 empty] | 1602 | 6531143.5565 | 1602 | 4799951.3124
[6 empty] | 1603 | 2694767.5338 | 1603 | 2694767.5338
[6 empty] | 1604 | 0 | 1604 | 0
[6 empty] | 1605 | 0 | 1605 | 0
[6 empty] | 1606 | 508287.6975 | 1606 | 508287.6975
[6 empty] | 1607 | 0 | 1607 | 0
[6 empty] | 1608 | 197723.3778 | 1608 | 0
[6 empty] | 1609 | 0 | 1609 | 0
[6 empty] | 1610 | 482211.6199 | 1610 | 482211.6199
[6 empty] | 1611 | 0 | 1611 | 0
[6 empty] | 1612 | 0 | 1612 | 0
[6 empty] | 1613 | 194100.686 | 1613 | 194100.686
[6 empty] | 1614 | 0 | 1614 | 0
[6 empty] | 1615 | 0 | 1615 | 0
[6 empty] | 1616 | 412826.4735 | 1616 | 412826.4735
[6 empty] | 1617 | 0 | 1617 | 0
[6 empty] | 1618 | 2498064.7431 | 1618 | 2498064.7431
[6 empty] | 1619 | 3204578.1886 | 1619 | 3204578.1886
[6 empty] | 1620 | 0 | 1620 | 0
[6 empty] | 1621 | 0 | 1621 | 0
[6 empty] | 1622 | 0 | 1622 | 0
[6 empty] | 1623 | 0 | 1623 | 0
[6 empty] | 1624 | 0 | 1624 | 0
[6 empty] | 1625 | 0 | 1625 | 0
[6 empty] | 1626 | 296642.5488 | 1626 | 296642.5488
[6 empty] | 1627 | 0 | 1627 | 0
[6 empty] | 1628 | 179189.5034 | 1628 | 179189.5034
[6 empty] | 1629 | 0 | 1629 | 0
[6 empty] | 1630 | 242433.7945 | 1630 | 242433.7945
[6 empty] | 1631 | 0 | 1631 | 0
[6 empty] | 1632 | 17795386.5224 | 1632 | 143382.6789
[6 empty] | 1633 | 0 | 1633 | 0
[6 empty] | 1634 | 0 | 1634 | 0
[6 empty] | 1635 | 774951.4531 | 1635 | 774951.4531
[6 empty] | 1636 | 162296.947 | 1636 | 162296.947
[6 empty] | 1637 | 16489571.8206 | 1637 | 16489571.8206
[6 empty] | 1638 | 0 | 1638 | 0
[6 empty] | 1639 | 1497239.6711 | 1639 | 0
[6 empty] | 1640 | 209914.3796 | 1640 | 209914.3796
[6 empty] | 1641 | 0 | 1641 | 0
[6 empty] | 1642 | 0 | 1642 | 0
[6 empty] | 1643 | 0 | 1643 | 0
[6 empty] | 1644 | 3097634.6226 | 1644 | 0
[6 empty] | 1645 | 0 | 1645 | 0
[6 empty] | 1646 | 0 | 1646 | 0
[6 empty] | 1647 | 2842129.0407 | 1647 | 222057.093
[6 empty] | 1648 | 0 | 1648 | 0
[6 empty] | 1649 | 0 | 1649 | 0
[6 empty] | 1650 | 0 | 1650 | 0
[6 empty] | 1651 | 0 | 1651 | 0
[6 empty] | 1652 | 0 | 1652 | 0
[6 empty] | 1653 | 0 | 1653 | 0
[6 empty] | 1654 | 10408354.836 | 1654 | 0
[6 empty] | 1655 | 4221775.5565 | 1655 | 0
[6 empty] | 1656 | 0 | 1656 | 0
[6 empty] | 1657 | 4947598.0701 | 1657 | 4529885.6409
[6 empty] | 1658 | 5057628.0052 | 1658 | 0
[6 empty] | 1659 | 607284.7848 | 1659 | 607284.7848
[6 empty] | 1660 | 226815.3598 | 1660 | 0
[6 empty] | 1661 | 4891576.1515 | 1661 | 4738882.9648
[6 empty] | 1662 | 0 | 1662 | 0
[6 empty] | 1663 | 0 | 1663 | 0
[6 empty] | 1664 | 0 | 1664 | 0
[6 empty] | 1665 | 0 | 1665 | 0
[6 empty] | 1666 | 325491.7457 | 1666 | 325491.7457
[6 empty] | 1667 | 0 | 1667 | 0
[6 empty] | 1668 | 296409.1321 | 1668 | 296409.1321
[6 empty] | 1669 | 443647.6041 | 1669 | 443647.6041
[6 empty] | 1670 | 64353.6687 | 1670 | 64353.6687
[6 empty] | 1671 | 246852.1542 | 1671 | 246852.1542
[6 empty] | 1672 | 475886.3907 | 1672 | 475886.3907
[6 empty] | 1673 | 46021245.3627 | 1673 | 166649.6663
[6 empty] | 1674 | 79919.5252 | 1674 | 79919.5252
[6 empty] | 1675 | 0 | 1675 | 0
[6 empty] | 1676 | 0 | 1676 | 0
[6 empty] | 1677 | 509414.976 | 1677 | 509414.976
[6 empty] | 1678 | 0 | 1678 | 0
[6 empty] | 1679 | 547242.0067 | 1679 | 547242.0067
[6 empty] | 1680 | 3705635.9605 | 1680 | 0
[6 empty] | 1681 | 0 | 1681 | 0
[6 empty] | 1682 | 0 | 1682 | 0
[6 empty] | 1683 | 0 | 1683 | 0
[6 empty] | 1684 | 0 | 1684 | 0
[6 empty] | 1685 | 0 | 1685 | 0
[6 empty] | 1686 | 561455.0975 | 1686 | 229855.3094
[6 empty] | 1687 | 4417411.8128 | 1687 | 4417411.8128
[6 empty] | 1688 | 0 | 1688 | 0
[6 empty] | 1689 | 148480.7856 | 1689 | 148480.7856
[6 empty] | 1690 | 8873379.6393 | 1690 | 0
[6 empty] | 1691 | 0 | 1691 | 0
[6 empty] | 1692 | 15037056.528 | 1692 | 0
[6 empty] | 1693 | 0 | 1693 | 0
[6 empty] | 1694 | 0 | 1694 | 0
[6 empty] | 1695 | 0 | 1695 | 0
[6 empty] | 1696 | 0 | 1696 | 0
[6 empty] | 1697 | 0 | 1697 | 0
[6 empty] | 1698 | 0 | 1698 | 0
[6 empty] | 1699 | 0 | 1699 | 0
[6 empty] | 1700 | 0 | 1700 | 0
[6 empty] | 1701 | 1605654.5259 | 1701 | 0
[6 empty] | 1702 | 0 | 1702 | 0
[6 empty] | 1703 | 5401328.3625 | 1703 | 3233694.6336
[6 empty] | 1704 | 630525.4088 | 1704 | 630525.4088
[6 empty] | 1705 | 22536318.2862 | 1705 | 5132365.8976
[6 empty] | 1706 | 0 | 1706 | 0
[6 empty] | 1707 | 0 | 1707 | 0
[6 empty] | 1708 | 0 | 1708 | 0
[6 empty] | 1709 | 0 | 1709 | 0
[6 empty] | 1710 | 650244.2388 | 1710 | 650244.2388
[6 empty] | 1711 | 272167.4401 | 1711 | 0
[6 empty] | 1712 | 0 | 1712 | 0
[6 empty] | 1713 | 0 | 1713 | 0
[6 empty] | 1714 | 6845457.7949 | 1714 | 6845457.7949
[6 empty] | 1715 | 186434.947 | 1715 | 186434.947
[6 empty] | 1716 | 284506.0081 | 1716 | 284506.0081
[6 empty] | 1717 | 0 | 1717 | 0
[6 empty] | 1718 | 0 | 1718 | 0
[6 empty] | 1719 | 0 | 1719 | 0
[6 empty] | 1720 | 3721113.2007 | 1720 | 3552283.902
[6 empty] | 1721 | 0 | 1721 | 0
[6 empty] | 1722 | 0 | 1722 | 0
[6 empty] | 1723 | 0 | 1723 | 0
[6 empty] | 1724 | 880163.6486 | 1724 | 0
[6 empty] | 1725 | 4550437.8215 | 1725 | 4550437.8215
[6 empty] | 1726 | 0 | 1726 | 0
[6 empty] | 1727 | 2268975.1324 | 1727 | 0
[6 empty] | 1728 | 0 | 1728 | 0
[6 empty] | 1729 | 5038040.3069 | 1729 | 0
[6 empty] | 1730 | 0 | 1730 | 0
[6 empty] | 1731 | 274871.5842 | 1731 | 274871.5842
[6 empty] | 1732 | 695725.7901 | 1732 | 695725.7901
[6 empty] | 1733 | 0 | 1733 | 0
[6 empty] | 1734 | 5747594.1985 | 1734 | 206170.427
[6 empty] | 1735 | 0 | 1735 | 0
[6 empty] | 1736 | 0 | 1736 | 0
[6 empty] | 1737 | 637752.1915 | 1737 | 637752.1915
[6 empty] | 1738 | 4014224.0964 | 1738 | 4014224.0964
[6 empty] | 1739 | 359297.5686 | 1739 | 359297.5686
[6 empty] | 1740 | 0 | 1740 | 0
[6 empty] | 1741 | 290321.7009 | 1741 | 290321.7009
[6 empty] | 1742 | 578438.6892 | 1742 | 578438.6892
[6 empty] | 1743 | 0 | 1743 | 0
[6 empty] | 1744 | 1564429.4351 | 1744 | 1564429.4351
[6 empty] | 1745 | 5076698.398 | 1745 | 0
[6 empty] | 1746 | 252598.2966 | 1746 | 252598.2966
[6 empty] | 1747 | 236431.1394 | 1747 | 0
[6 empty] | 1748 | 316896.4492 | 1748 | 316896.4492
[6 empty] | 1749 | 897266.3172 | 1749 | 0
[6 empty] | 1750 | 1582781.6041 | 1750 | 0
[6 empty] | 1751 | 3234312.1138 | 1751 | 3234312.1138
[6 empty] | 1752 | 19852772.1807 | 1752 | 0
[6 empty] | 1753 | 199636.9142 | 1753 | 199636.9142
[6 empty] | 1754 | 3022466.8046 | 1754 | 0
[6 empty] | 1755 | 4111538.4571 | 1755 | 0
[6 empty] | 1756 | 0 | 1756 | 0
[6 empty] | 1757 | 151862.4077 | 1757 | 151862.4077
[6 empty] | 1758 | 0 | 1758 | 0
[6 empty] | 1759 | 0 | 1759 | 0
[6 empty] | 1760 | 644816.5645 | 1760 | 644816.5645
[6 empty] | 1761 | 0 | 1761 | 0
[6 empty] | 1762 | 0 | 1762 | 0
[6 empty] | 1763 | 0 | 1763 | 0
[6 empty] | 1764 | 213078.2977 | 1764 | 0
[6 empty] | 1765 | 0 | 1765 | 0
[6 empty] | 1766 | 725043.0157 | 1766 | 725043.0157
[6 empty] | 1767 | 0 | 1767 | 0
[6 empty] | 1768 | 4367364.7734 | 1768 | 4367364.7734
[6 empty] | 1769 | 14774018.6133 | 1769 | 0
[6 empty] | 1770 | 361508.2097 | 1770 | 361508.2097
[6 empty] | 1771 | 222054.8076 | 1771 | 0
[6 empty] | 1772 | 0 | 1772 | 0
[6 empty] | 1773 | 0 | 1773 | 0
[6 empty] | 1774 | 3821858.1818 | 1774 | 3821858.1818
[6 empty] | 1775 | 776405.2073 | 1775 | 776405.2073
[6 empty] | 1776 | 6681730.62 | 1776 | 6681730.62
[6 empty] | 1777 | 0 | 1777 | 0
[6 empty] | 1778 | 4643750.3083 | 1778 | 721809.5297
[6 empty] | 1779 | 47761414.3414 | 1779 | 181080.7296
[6 empty] | 1780 | 3501393.4617 | 1780 | 3501393.4617
[6 empty] | 1781 | 0 | 1781 | 0
[6 empty] | 1782 | 327439.8492 | 1782 | 327439.8492
[6 empty] | 1783 | 241100.2433 | 1783 | 241100.2433
[6 empty] | 1784 | 3734027.7889 | 1784 | 3734027.7889
[6 empty] | 1785 | 8849502.5186 | 1785 | 8849502.5186
[6 empty] | 1786 | 2805576.277 | 1786 | 2805576.277
[6 empty] | 1787 | 1434058.5873 | 1787 | 97458.7518
[6 empty] | 1788 | 4824254.6627 | 1788 | 4824254.6627
[6 empty] | 1789 | 0 | 1789 | 0
[6 empty] | 1790 | 0 | 1790 | 0
[6 empty] | 1791 | 3546365.3078 | 1791 | 3546365.3078
[6 empty] | 1792 | 2127146.6742 | 1792 | 0
[6 empty] | 1793 | 1312324.7401 | 1793 | 1312324.7401
[6 empty] | 1794 | 0 | 1794 | 0
[6 empty] | 1795 | 991039.3691 | 1795 | 0
[6 empty] | 1796 | 0 | 1796 | 0
[6 empty] | 1797 | 0 | 1797 | 0
[6 empty] | 1798 | 0 | 1798 | 0
[6 empty] | 1799 | 0 | 1799 | 0
[6 empty] | 1800 | 212245.0101 | 1800 | 212245.0101
[6 empty] | 1801 | 447304.0397 | 1801 | 447304.0397
[6 empty] | 1802 | 504880.4701 | 1802 | 504880.4701
[6 empty] | 1803 | 988541.3094 | 1803 | 988541.3094
[6 empty] | 1804 | 0 | 1804 | 0
[6 empty] | 1805 | 0 | 1805 | 0
[6 empty] | 1806 | 0 | 1806 | 0
[6 empty] | 1807 | 2037992.6651 | 1807 | 2037992.6651
[6 empty] | 1808 | 1727573.6595 | 1808 | 0
[6 empty] | 1809 | 21996313.6802 | 1809 | 0
[6 empty] | 1810 | 0 | 1810 | 0
[6 empty] | 1811 | 460143.869 | 1811 | 460143.869
[6 empty] | 1812 | 0 | 1812 | 0
[6 empty] | 1813 | 3369531.3292 | 1813 | 705147.3946
[6 empty] | 1814 | 0 | 1814 | 0
[6 empty] | 1815 | 818860.8654 | 1815 | 0
[6 empty] | 1816 | 5146413.4654 | 1816 | 4842465.6864
[6 empty] | 1817 | 87837.6784 | 1817 | 87837.6784
[6 empty] | 1818 | 4039815.0789 | 1818 | 2689784.7036
[6 empty] | 1819 | 0 | 1819 | 0
[6 empty] | 1820 | 215198.7212 | 1820 | 215198.7212
[6 empty] | 1821 | 0 | 1821 | 0
[6 empty] | 1822 | 2084542.0432 | 1822 | 0
[6 empty] | 1823 | 300578.7031 | 1823 | 300578.7031
[6 empty] | 1824 | 0 | 1824 | 0
[6 empty] | 1825 | 419294.1335 | 1825 | 419294.1335
[6 empty] | 1826 | 7103540.4372 | 1826 | 0
[6 empty] | 1827 | 0 | 1827 | 0
[6 empty] | 1828 | 0 | 1828 | 0
[6 empty] | 1829 | 4895621.1664 | 1829 | 4895621.1664
[6 empty] | 1830 | 452782.4825 | 1830 | 452782.4825
[6 empty] | 1831 | 1198346.7971 | 1831 | 0
[6 empty] | 1832 | 0 | 1832 | 0
[6 empty] | 1833 | 734663.7224 | 1833 | 0
[6 empty] | 1834 | 0 | 1834 | 0
[6 empty] | 1835 | 0 | 1835 | 0
[6 empty] | 1836 | 1591209.8471 | 1836 | 0
[6 empty] | 1837 | 0 | 1837 | 0
[6 empty] | 1838 | 0 | 1838 | 0
[6 empty] | 1839 | 243455.9236 | 1839 | 243455.9236
[6 empty] | 1840 | 0 | 1840 | 0
[6 empty] | 1841 | 0 | 1841 | 0
[6 empty] | 1842 | 0 | 1842 | 0
[6 empty] | 1843 | 4205456.5805 | 1843 | 4205456.5805
[6 empty] | 1844 | 0 | 1844 | 0
[6 empty] | 1845 | 0 | 1845 | 0
[6 empty] | 1846 | 190662.3353 | 1846 | 190662.3353
[6 empty] | 1847 | 1026293.033 | 1847 | 1026293.033
[6 empty] | 1848 | 537202.5511 | 1848 | 537202.5511
[6 empty] | 1849 | 0 | 1849 | 0
[6 empty] | 1850 | 0 | 1850 | 0
[6 empty] | 1851 | 420571.952 | 1851 | 420571.952
[6 empty] | 1852 | 2859335.6671 | 1852 | 2859335.6671
[6 empty] | 1853 | 0 | 1853 | 0
[6 empty] | 1854 | 9170019.349 | 1854 | 0
[6 empty] | 1855 | 518165.4101 | 1855 | 518165.4101
[6 empty] | 1856 | 0 | 1856 | 0
[6 empty] | 1857 | 0 | 1857 | 0
[6 empty] | 1858 | 0 | 1858 | 0
[6 empty] | 1859 | 0 | 1859 | 0
[6 empty] | 1860 | 794648.7852 | 1860 | 0
[6 empty] | 1861 | 0 | 1861 | 0
[6 empty] | 1862 | 0 | 1862 | 0
[6 empty] | 1863 | 0 | 1863 | 0
[6 empty] | 1864 | 537628.4715 | 1864 | 537628.4715
[6 empty] | 1865 | 0 | 1865 | 0
[6 empty] | 1866 | 175532.2046 | 1866 | 175532.2046
[6 empty] | 1867 | 164137.4447 | 1867 | 0
[6 empty] | 1868 | 0 | 1868 | 0
[6 empty] | 1869 | 0 | 1869 | 0
[6 empty] | 1870 | 205113.1007 | 1870 | 205113.1007
[6 empty] | 1871 | 0 | 1871 | 0
[6 empty] | 1872 | 820592.5234 | 1872 | 0
[6 empty] | 1873 | 0 | 1873 | 0
[6 empty] | 1874 | 694427.6728 | 1874 | 694427.6728
[6 empty] | 1875 | 0 | 1875 | 0
[6 empty] | 1876 | 4386422.9215 | 1876 | 0
[6 empty] | 1877 | 0 | 1877 | 0
[6 empty] | 1878 | 0 | 1878 | 0
[6 empty] | 1879 | 0 | 1879 | 0
[6 empty] | 1880 | 347556.2411 | 1880 | 347556.2411
[6 empty] | 1881 | 75102.9461 | 1881 | 75102.9461
[6 empty] | 1882 | 0 | 1882 | 0
[6 empty] | 1883 | 0 | 1883 | 0
[6 empty] | 1884 | 4603914.9041 | 1884 | 4603914.9041
[6 empty] | 1885 | 287157.5466 | 1885 | 287157.5466
[6 empty] | 1886 | 287972.0464 | 1886 | 287972.0464
[6 empty] | 1887 | 83661.9373 | 1887 | 83661.9373
[6 empty] | 1888 | 3553750.0548 | 1888 | 210155.0545
[6 empty] | 1889 | 4650047.6868 | 1889 | 796535.7121
[6 empty] | 1890 | 173632.7598 | 1890 | 173632.7598
[6 empty] | 1891 | 4021838.8989 | 1891 | 4021838.8989
[6 empty] | 1892 | 4325864.4697 | 1892 | 287906.1367
[6 empty] | 1893 | 189975.4343 | 1893 | 0
[6 empty] | 1894 | 519404.7399 | 1894 | 519404.7399
[6 empty] | 1895 | 3224785.9893 | 1895 | 3224785.9893
[6 empty] | 1896 | 0 | 1896 | 0
[6 empty] | 1897 | 2162991.6182 | 1897 | 2162991.6182
[6 empty] | 1898 | 0 | 1898 | 0
[6 empty] | 1899 | 9982018.3687 | 1899 | 9982018.3687
[6 empty] | 1900 | 221922.1741 | 1900 | 0
[6 empty] | 1901 | 0 | 1901 | 0
[6 empty] | 1902 | 0 | 1902 | 0
[6 empty] | 1903 | 3183731.7794 | 1903 | 1141987.9973
[6 empty] | 1904 | 150904.0822 | 1904 | 0
[6 empty] | 1905 | 0 | 1905 | 0
[6 empty] | 1906 | 4381727.0212 | 1906 | 0
[6 empty] | 1907 | 4044718.2038 | 1907 | 0
[6 empty] | 1908 | 296346.475 | 1908 | 296346.475
[6 empty] | 1909 | 11058152.2173 | 1909 | 0
[6 empty] | 1910 | 0 | 1910 | 0
[6 empty] | 1911 | 314962.8376 | 1911 | 0
[6 empty] | 1912 | 0 | 1912 | 0
[6 empty] | 1913 | 170302.0905 | 1913 | 170302.0905
[6 empty] | 1914 | 0 | 1914 | 0
[6 empty] | 1915 | 0 | 1915 | 0
[6 empty] | 1916 | 236953.5333 | 1916 | 236953.5333
[6 empty] | 1917 | 0 | 1917 | 0
[6 empty] | 1918 | 0 | 1918 | 0
[6 empty] | 1919 | 513102.905 | 1919 | 513102.905
[6 empty] | 1920 | 3006510.0676 | 1920 | 0
[6 empty] | 1921 | 71876.8478 | 1921 | 71876.8478
[6 empty] | 1922 | 205114.8166 | 1922 | 0
[6 empty] | 1923 | 2868676.2711 | 1923 | 0
[6 empty] | 1924 | 0 | 1924 | 0
[6 empty] | 1925 | 2250676.6611 | 1925 | 0
[6 empty] | 1926 | 0 | 1926 | 0
[6 empty] | 1927 | 2144791.4373 | 1927 | 208916.7837
[6 empty] | 1928 | 4107035.5341 | 1928 | 4107035.5341
[6 empty] | 1929 | 0 | 1929 | 0
[6 empty] | 1930 | 0 | 1930 | 0
[6 empty] | 1931 | 0 | 1931 | 0
[6 empty] | 1932 | 0 | 1932 | 0
[6 empty] | 1933 | 0 | 1933 | 0
[6 empty] | 1934 | 0 | 1934 | 0
[6 empty] | 1935 | 0 | 1935 | 0
[6 empty] | 1936 | 179389.5397 | 1936 | 179389.5397
[6 empty] | 1937 | 0 | 1937 | 0
[6 empty] | 1938 | 1888680.2242 | 1938 | 0
[6 empty] | 1939 | 0 | 1939 | 0
[6 empty] | 1940 | 10108426.3493 | 1940 | 6163749.3606
[6 empty] | 1941 | 0 | 1941 | 0
[6 empty] | 1942 | 0 | 1942 | 0
[6 empty] | 1943 | 0 | 1943 | 0
[6 empty] | 1944 | 218899.1099 | 1944 | 218899.1099
[6 empty] | 1945 | 0 | 1945 | 0
[6 empty] | 1946 | 3732635.7295 | 1946 | 242189.1976
[6 empty] | 1947 | 0 | 1947 | 0
[6 empty] | 1948 | 0 | 1948 | 0
[6 empty] | 1949 | 0 | 1949 | 0
[6 empty] | 1950 | 432868.1328 | 1950 | 432868.1328
[6 empty] | 1951 | 0 | 1951 | 0
[6 empty] | 1952 | 0 | 1952 | 0
[6 empty] | 1953 | 0 | 1953 | 0
[6 empty] | 1954 | 0 | 1954 | 0
[6 empty] | 1955 | 8468787.8927 | 1955 | 0
[6 empty] | 1956 | 1246097.982 | 1956 | 0
[6 empty] | 1957 | 3009900.1694 | 1957 | 3009900.1694
[6 empty] | 1958 | 0 | 1958 | 0
[6 empty] | 1959 | 4073579.0866 | 1959 | 0
[6 empty] | 1960 | 1282863.6772 | 1960 | 0
[6 empty] | 1961 | 0 | 1961 | 0
[6 empty] | 1962 | 4725390.9663 | 1962 | 371000.6203
[6 empty] | 1963 | 128103.2435 | 1963 | 128103.2435
[6 empty] | 1964 | 1103588.5914 | 1964 | 911912.2026
[6 empty] | 1965 | 545379.7958 | 1965 | 545379.7958
[6 empty] | 1966 | 0 | 1966 | 0
[6 empty] | 1967 | 5910542.4203 | 1967 | 5910542.4203
[6 empty] | 1968 | 0 | 1968 | 0
[6 empty] | 1969 | 264654.5152 | 1969 | 264654.5152
[6 empty] | 1970 | 232244.3722 | 1970 | 232244.3722
[6 empty] | 1971 | 0 | 1971 | 0
[6 empty] | 1972 | 0 | 1972 | 0
[6 empty] | 1973 | 288807.5938 | 1973 | 288807.5938
[6 empty] | 1974 | 216907.8636 | 1974 | 0
[6 empty] | 1975 | 0 | 1975 | 0
[6 empty] | 1976 | 175654.2961 | 1976 | 175654.2961
[6 empty] | 1977 | 2361044.3492 | 1977 | 0
[6 empty] | 1978 | 3612798.5466 | 1978 | 3612798.5466
[6 empty] | 1979 | 0 | 1979 | 0
[6 empty] | 1980 | 6850778.4638 | 1980 | 4514132.5576
[6 empty] | 1981 | 0 | 1981 | 0
[6 empty] | 1982 | 0 | 1982 | 0
[6 empty] | 1983 | 0 | 1983 | 0
[6 empty] | 1984 | 0 | 1984 | 0
[6 empty] | 1985 | 1119666.3277 | 1985 | 0
[6 empty] | 1986 | 226216.1991 | 1986 | 226216.1991
[6 empty] | 1987 | 0 | 1987 | 0
[6 empty] | 1988 | 3810665.9437 | 1988 | 3810665.9437
[6 empty] | 1989 | 0 | 1989 | 0
[6 empty] | 1990 | 346112.5206 | 1990 | 346112.5206
[6 empty] | 1991 | 0 | 1991 | 0
[6 empty] | 1992 | 3017452.3471 | 1992 | 0
[6 empty] | 1993 | 0 | 1993 | 0
[6 empty] | 1994 | 6811885.9176 | 1994 | 6811885.9176
[6 empty] | 1995 | 0 | 1995 | 0
[6 empty] | 1996 | 0 | 1996 | 0
[6 empty] | 1997 | 0 | 1997 | 0
[6 empty] | 1998 | 58812.084 | 1998 | 58812.084
[6 empty] | 1999 | 0 | 1999 | 0
[6 empty] | 2000 | 566987.4725 | 2000 | 566987.4725
[6 empty] | 2001 | 167928.8245 | 2001 | 0
[6 empty] | 2002 | 0 | 2002 | 0
[6 empty] | 2003 | 311720.7952 | 2003 | 0
[6 empty] | 2004 | 0 | 2004 | 0
[6 empty] | 2005 | 0 | 2005 | 0
[6 empty] | 2006 | 488312.1381 | 2006 | 488312.1381
[6 empty] | 2007 | 0 | 2007 | 0
[6 empty] | 2008 | 1532462.6099 | 2008 | 251661.7716
[6 empty] | 2009 | 0 | 2009 | 0
[6 empty] | 2010 | 0 | 2010 | 0
[6 empty] | 2011 | 4353531.4099 | 2011 | 4128445.9637
[6 empty] | 2012 | 0 | 2012 | 0
[6 empty] | 2013 | 4636122.766 | 2013 | 0
[6 empty] | 2014 | 0 | 2014 | 0
[6 empty] | 2015 | 0 | 2015 | 0
[6 empty] | 2016 | 0 | 2016 | 0
[6 empty] | 2017 | 205581.7957 | 2017 | 205581.7957
[6 empty] | 2018 | 0 | 2018 | 0
[6 empty] | 2019 | 250998.0119 | 2019 | 0
[6 empty] | 2020 | 0 | 2020 | 0
[6 empty] | 2021 | 0 | 2021 | 0
[6 empty] | 2022 | 229697.2053 | 2022 | 229697.2053
[6 empty] | 2023 | 517432.5652 | 2023 | 0
[6 empty] | 2024 | 221970.6039 | 2024 | 221970.6039
[6 empty] | 2025 | 2743032.5826 | 2025 | 0
[6 empty] | 2026 | 0 | 2026 | 0
[6 empty] | 2027 | 0 | 2027 | 0
[6 empty] | 2028 | 1019759.9484 | 2028 | 0
[6 empty] | 2029 | 0 | 2029 | 0
[6 empty] | 2030 | 189689.2202 | 2030 | 189689.2202
[6 empty] | 2031 | 580551.0335 | 2031 | 580551.0335
[6 empty] | 2032 | 185771.5108 | 2032 | 185771.5108
[6 empty] | 2033 | 1183933.439 | 2033 | 1183933.439
[6 empty] | 2034 | 267708.933 | 2034 | 0
[6 empty] | 2035 | 0 | 2035 | 0
[6 empty] | 2036 | 1727902.5399 | 2036 | 0
[6 empty] | 2037 | 3326825.211 | 2037 | 3326825.211
[6 empty] | 2038 | 0 | 2038 | 0
[6 empty] | 2039 | 3963706.0533 | 2039 | 3963706.0533
[6 empty] | 2040 | 249839.972 | 2040 | 249839.972
[6 empty] | 2041 | 0 | 2041 | 0
[6 empty] | 2042 | 0 | 2042 | 0
[6 empty] | 2043 | 273693.8583 | 2043 | 273693.8583
[6 empty] | 2044 | 233374.4993 | 2044 | 0
[6 empty] | 2045 | 2750310.2691 | 2045 | 2750310.2691
[6 empty] | 2046 | 0 | 2046 | 0
[6 empty] | 2047 | 0 | 2047 | 0
[6 empty] | 2048 | 0 | 2048 | 0
[6 empty] | 2049 | 4149843.7526 | 2049 | 0
[6 empty] | 2050 | 0 | 2050 | 0
[6 empty] | 2051 | 0 | 2051 | 0
[6 empty] | 2052 | 401852.182 | 2052 | 401852.182
[6 empty] | 2053 | 1756875.7905 | 2053 | 191870.1408
[6 empty] | 2054 | 243961.627 | 2054 | 0
[6 empty] | 2055 | 225725.3721 | 2055 | 225725.3721
[6 empty] | 2056 | 2282438.4259 | 2056 | 0
[6 empty] | 2057 | 0 | 2057 | 0
[6 empty] | 2058 | 0 | 2058 | 0
[6 empty] | 2059 | 0 | 2059 | 0
[6 empty] | 2060 | 0 | 2060 | 0
[6 empty] | 2061 | 0 | 2061 | 0
[6 empty] | 2062 | 0 | 2062 | 0
[6 empty] | 2063 | 0 | 2063 | 0
[6 empty] | 2064 | 4583365.0989 | 2064 | 4583365.0989
[6 empty] | 2065 | 101592.1005 | 2065 | 101592.1005
[6 empty] | 2066 | 0 | 2066 | 0
[6 empty] | 2067 | 0 | 2067 | 0
[6 empty] | 2068 | 1106603.3398 | 2068 | 1106603.3398
[6 empty] | 2069 | 219132.3671 | 2069 | 0
[6 empty] | 2070 | 0 | 2070 | 0
[6 empty] | 2071 | 1399156.7949 | 2071 | 373840.8563
[6 empty] | 2072 | 0 | 2072 | 0
[6 empty] | 2073 | 0 | 2073 | 0
[6 empty] | 2074 | 0 | 2074 | 0
[6 empty] | 2075 | 0 | 2075 | 0
[6 empty] | 2076 | 6445860.433 | 2076 | 6445860.433
[6 empty] | 2077 | 3483456.3518 | 2077 | 3483456.3518
[6 empty] | 2078 | 827665.4664 | 2078 | 827665.4664
[6 empty] | 2079 | 1714486.753 | 2079 | 0
[6 empty] | 2080 | 4584516.8747 | 2080 | 0
[6 empty] | 2081 | 219353.8794 | 2081 | 219353.8794
[6 empty] | 2082 | 3817399.0118 | 2082 | 3563230.7861
[6 empty] | 2083 | 0 | 2083 | 0
[6 empty] | 2084 | 0 | 2084 | 0
[6 empty] | 2085 | 2762373.9957 | 2085 | 2762373.9957
[6 empty] | 2086 | 5891631.354 | 2086 | 5891631.354
[6 empty] | 2087 | 0 | 2087 | 0
[6 empty] | 2088 | 0 | 2088 | 0
[6 empty] | 2089 | 0 | 2089 | 0
[6 empty] | 2090 | 0 | 2090 | 0
[6 empty] | 2091 | 170564.5762 | 2091 | 0
[6 empty] | 2092 | 0 | 2092 | 0
[6 empty] | 2093 | 0 | 2093 | 0
[6 empty] | 2094 | 0 | 2094 | 0
[6 empty] | 2095 | 0 | 2095 | 0
[6 empty] | 2096 | 0 | 2096 | 0
[6 empty] | 2097 | 0 | 2097 | 0
[6 empty] | 2098 | 0 | 2098 | 0
[6 empty] | 2099 | 0 | 2099 | 0
[6 empty] | 2100 | 0 | 2100 | 0
[6 empty] | 2101 | 0 | 2101 | 0
[6 empty] | 2102 | 224632.4026 | 2102 | 224632.4026
[6 empty] | 2103 | 873059.457 | 2103 | 873059.457
[6 empty] | 2104 | 5067883.4003 | 2104 | 5067883.4003
[6 empty] | 2105 | 0 | 2105 | 0
[6 empty] | 2106 | 0 | 2106 | 0
[6 empty] | 2107 | 3329936.8787 | 2107 | 0
[6 empty] | 2108 | 3155389.1929 | 2108 | 124012.3009
[6 empty] | 2109 | 0 | 2109 | 0
[6 empty] | 2110 | 0 | 2110 | 0
[6 empty] | 2111 | 0 | 2111 | 0
[6 empty] | 2112 | 0 | 2112 | 0
[6 empty] | 2113 | 308318.8486 | 2113 | 308318.8486
[6 empty] | 2114 | 526144.7041 | 2114 | 526144.7041
[6 empty] | 2115 | 7840582.3814 | 2115 | 3434384.6722
[6 empty] | 2116 | 448327.4953 | 2116 | 448327.4953
[6 empty] | 2117 | 938856.9864 | 2117 | 0
[6 empty] | 2118 | 0 | 2118 | 0
[6 empty] | 2119 | 0 | 2119 | 0
[6 empty] | 2120 | 0 | 2120 | 0
[6 empty] | 2121 | 0 | 2121 | 0
[6 empty] | 2122 | 0 | 2122 | 0
[6 empty] | 2123 | 0 | 2123 | 0
[6 empty] | 2124 | 3806904.967 | 2124 | 2059277.9391
[6 empty] | 2125 | 414273.5919 | 2125 | 414273.5919
[6 empty] | 2126 | 8132589.95 | 2126 | 936607.4615
[6 empty] | 2127 | 0 | 2127 | 0
[6 empty] | 2128 | 8161822.7559 | 2128 | 8161822.7559
[6 empty] | 2129 | 153428.2278 | 2129 | 153428.2278
[6 empty] | 2130 | 0 | 2130 | 0
[6 empty] | 2131 | 0 | 2131 | 0
[6 empty] | 2132 | 0 | 2132 | 0
[6 empty] | 2133 | 0 | 2133 | 0
[6 empty] | 2134 | 0 | 2134 | 0
[6 empty] | 2135 | 0 | 2135 | 0
[6 empty] | 2136 | 1320730.1216 | 2136 | 1320730.1216
[6 empty] | 2137 | 0 | 2137 | 0
[6 empty] | 2138 | 0 | 2138 | 0
[6 empty] | 2139 | 119560.8027 | 2139 | 119560.8027
[6 empty] | 2140 | 0 | 2140 | 0
[6 empty] | 2141 | 6971731.5817 | 2141 | 3603612.2197
[6 empty] | 2142 | 250208.7239 | 2142 | 250208.7239
[6 empty] | 2143 | 0 | 2143 | 0
[6 empty] | 2144 | 562523.5759 | 2144 | 562523.5759
[6 empty] | 2145 | 174549.5353 | 2145 | 174549.5353
[6 empty] | 2146 | 3188771.6104 | 2146 | 2936244.3505
[6 empty] | 2147 | 3239731.6759 | 2147 | 0
[6 empty] | 2148 | 0 | 2148 | 0
[6 empty] | 2149 | 217160.632 | 2149 | 0
[6 empty] | 2150 | 799655.3186 | 2150 | 0
[6 empty] | 2151 | 2721675.6104 | 2151 | 0
[6 empty] | 2152 | 254240.7941 | 2152 | 254240.7941
[6 empty] | 2153 | 3092265.1 | 2153 | 252324.7572
[6 empty] | 2154 | 0 | 2154 | 0
[6 empty] | 2155 | 0 | 2155 | 0
[6 empty] | 2156 | 158614.448 | 2156 | 158614.448
[6 empty] | 2157 | 0 | 2157 | 0
[6 empty] | 2158 | 1569935.0291 | 2158 | 1569935.0291
[6 empty] | 2159 | 0 | 2159 | 0
[6 empty] | 2160 | 1168356.6135 | 2160 | 0
[6 empty] | 2161 | 0 | 2161 | 0
[6 empty] | 2162 | 5435591.8396 | 2162 | 0
[6 empty] | 2163 | 0 | 2163 | 0
[6 empty] | 2164 | 263989.1859 | 2164 | 0
[6 empty] | 2165 | 0 | 2165 | 0
[6 empty] | 2166 | 1045909.7963 | 2166 | 1045909.7963
[6 empty] | 2167 | 131943.8397 | 2167 | 131943.8397
[6 empty] | 2168 | 1378047.0689 | 2168 | 0
[6 empty] | 2169 | 862615.0819 | 2169 | 0
[6 empty] | 2170 | 225835.6531 | 2170 | 0
[6 empty] | 2171 | 3849395.2212 | 2171 | 3849395.2212
[6 empty] | 2172 | 0 | 2172 | 0
[6 empty] | 2173 | 0 | 2173 | 0
[6 empty] | 2174 | 629198.0628 | 2174 | 629198.0628
[6 empty] | 2175 | 197926.4193 | 2175 | 197926.4193
[6 empty] | 2176 | 3858631.1975 | 2176 | 3858631.1975
[6 empty] | 2177 | 211870.4423 | 2177 | 0
[6 empty] | 2178 | 0 | 2178 | 0
[6 empty] | 2179 | 0 | 2179 | 0
[6 empty] | 2180 | 338268.0697 | 2180 | 338268.0697
[6 empty] | 2181 | 0 | 2181 | 0
[6 empty] | 2182 | 0 | 2182 | 0
[6 empty] | 2183 | 0 | 2183 | 0
[6 empty] | 2184 | 0 | 2184 | 0
[6 empty] | 2185 | 0 | 2185 | 0
[6 empty] | 2186 | 0 | 2186 | 0
[6 empty] | 2187 | 4971145.4342 | 2187 | 233777.3765
[6 empty] | 2188 | 306991.2404 | 2188 | 306991.2404
[6 empty] | 2189 | 231755.0233 | 2189 | 231755.0233
[6 empty] | 2190 | 0 | 2190 | 0
[6 empty] | 2191 | 3972737.3481 | 2191 | 0
[6 empty] | 2192 | 5185873.4174 | 2192 | 0
[6 empty] | 2193 | 13653666.1481 | 2193 | 1361758.2165
[6 empty] | 2194 | 811198.3545 | 2194 | 811198.3545
[6 empty] | 2195 | 580748.0314 | 2195 | 0
[6 empty] | 2196 | 0 | 2196 | 0
[6 empty] | 2197 | 412757.0547 | 2197 | 224408.4506
[6 empty] | 2198 | 6318342.4999 | 2198 | 0
[6 empty] | 2199 | 356283.9867 | 2199 | 0
[6 empty] | 2200 | 0 | 2200 | 0
[6 empty] | 2201 | 0 | 2201 | 0
[6 empty] | 2202 | 0 | 2202 | 0
[6 empty] | 2203 | 4098724.02 | 2203 | 230411.3511
[6 empty] | 2204 | 0 | 2204 | 0
[6 empty] | 2205 | 697429.3011 | 2205 | 455032.7623
[6 empty] | 2206 | 20670467.555 | 2206 | 0
[6 empty] | 2207 | 2205780.1173 | 2207 | 0
[6 empty] | 2208 | 0 | 2208 | 0
[6 empty] | 2209 | 0 | 2209 | 0
[6 empty] | 2210 | 1762274.942 | 2210 | 1762274.942
[6 empty] | 2211 | 2456292.691 | 2211 | 144241.7274
[6 empty] | 2212 | 0 | 2212 | 0
[6 empty] | 2213 | 0 | 2213 | 0
[6 empty] | 2214 | 0 | 2214 | 0
[6 empty] | 2215 | 286827.3935 | 2215 | 286827.3935
[6 empty] | 2216 | 0 | 2216 | 0
[6 empty] | 2217 | 0 | 2217 | 0
[6 empty] | 2218 | 237639.6393 | 2218 | 237639.6393
[6 empty] | 2219 | 5381776.5357 | 2219 | 5381776.5357
[6 empty] | 2220 | 0 | 2220 | 0
[6 empty] | 2221 | 0 | 2221 | 0
[6 empty] | 2222 | 0 | 2222 | 0
[6 empty] | 2223 | 0 | 2223 | 0
[6 empty] | 2224 | 312643.1332 | 2224 | 312643.1332
[6 empty] | 2225 | 215229.759 | 2225 | 0
[6 empty] | 2226 | 0 | 2226 | 0
[6 empty] | 2227 | 0 | 2227 | 0
[6 empty] | 2228 | 231042.712 | 2228 | 0
[6 empty] | 2229 | 0 | 2229 | 0
[6 empty] | 2230 | 581358.8907 | 2230 | 581358.8907
[6 empty] | 2231 | 0 | 2231 | 0
[6 empty] | 2232 | 419490.003 | 2232 | 419490.003
[6 empty] | 2233 | 2362234.2717 | 2233 | 2362234.2717
[6 empty] | 2234 | 0 | 2234 | 0
[6 empty] | 2235 | 0 | 2235 | 0
[6 empty] | 2236 | 0 | 2236 | 0
[6 empty] | 2237 | 0 | 2237 | 0
[6 empty] | 2238 | 6124840.8112 | 2238 | 881960.5069
[6 empty] | 2239 | 3034293.4772 | 2239 | 3034293.4772
[6 empty] | 2240 | 5045103.2073 | 2240 | 1066275.1423
[6 empty] | 2241 | 6830893.4843 | 2241 | 6672673.8252
[6 empty] | 2242 | 12237551.2019 | 2242 | 0
[6 empty] | 2243 | 0 | 2243 | 0
[6 empty] | 2244 | 0 | 2244 | 0
[6 empty] | 2245 | 0 | 2245 | 0
[6 empty] | 2246 | 400860.7789 | 2246 | 400860.7789
[6 empty] | 2247 | 0 | 2247 | 0
[6 empty] | 2248 | 6835982.6612 | 2248 | 2880458.7122
[6 empty] | 2249 | 0 | 2249 | 0
[6 empty] | 2250 | 3023813.1498 | 2250 | 0
[6 empty] | 2251 | 0 | 2251 | 0
[6 empty] | 2252 | 401239.6489 | 2252 | 401239.6489
[6 empty] | 2253 | 0 | 2253 | 0
[6 empty] | 2254 | 0 | 2254 | 0
[6 empty] | 2255 | 0 | 2255 | 0
[6 empty] | 2256 | 199276.9615 | 2256 | 199276.9615
[6 empty] | 2257 | 0 | 2257 | 0
[6 empty] | 2258 | 266829.4545 | 2258 | 266829.4545
[6 empty] | 2259 | 1942792.8253 | 2259 | 0
[6 empty] | 2260 | 145882.9988 | 2260 | 145882.9988
[6 empty] | 2261 | 4218579.7665 | 2261 | 4218579.7665
[6 empty] | 2262 | 0 | 2262 | 0
[6 empty] | 2263 | 230285.5085 | 2263 | 0
[6 empty] | 2264 | 0 | 2264 | 0
[6 empty] | 2265 | 0 | 2265 | 0
[6 empty] | 2266 | 0 | 2266 | 0
[6 empty] | 2267 | 0 | 2267 | 0
[6 empty] | 2268 | 3476867.6691 | 2268 | 0
[6 empty] | 2269 | 7571711.8404 | 2269 | 0
[6 empty] | 2270 | 4426682.9971 | 2270 | 0
[6 empty] | 2271 | 0 | 2271 | 0
[6 empty] | 2272 | 0 | 2272 | 0
[6 empty] | 2273 | 0 | 2273 | 0
[6 empty] | 2274 | 224016.2361 | 2274 | 224016.2361
[6 empty] | 2275 | 0 | 2275 | 0
[6 empty] | 2276 | 0 | 2276 | 0
[6 empty] | 2277 | 0 | 2277 | 0
[6 empty] | 2278 | 207425.7019 | 2278 | 207425.7019
[6 empty] | 2279 | 0 | 2279 | 0
[6 empty] | 2280 | 8089601.7179 | 2280 | 3422877.3294
[6 empty] | 2281 | 8919888.3959 | 2281 | 8919888.3959
[6 empty] | 2282 | 0 | 2282 | 0
[6 empty] | 2283 | 195161.0978 | 2283 | 195161.0978
[6 empty] | 2284 | 0 | 2284 | 0
[6 empty] | 2285 | 6485118.9598 | 2285 | 333950.888
[6 empty] | 2286 | 0 | 2286 | 0
[6 empty] | 2287 | 0 | 2287 | 0
[6 empty] | 2288 | 0 | 2288 | 0
[6 empty] | 2289 | 0 | 2289 | 0
[6 empty] | 2290 | 0 | 2290 | 0
[6 empty] | 2291 | 228510.9381 | 2291 | 228510.9381
[6 empty] | 2292 | 0 | 2292 | 0
[6 empty] | 2293 | 0 | 2293 | 0
[6 empty] | 2294 | 0 | 2294 | 0
[6 empty] | 2295 | 0 | 2295 | 0
[6 empty] | 2296 | 8571989.3313 | 2296 | 0
[6 empty] | 2297 | 0 | 2297 | 0
[6 empty] | 2298 | 465883.7523 | 2298 | 465883.7523
[6 empty] | 2299 | 3516764.3433 | 2299 | 189121.3326
[6 empty] | 2300 | 0 | 2300 | 0
[6 empty] | 2301 | 0 | 2301 | 0
[6 empty] | 2302 | 3863967.049 | 2302 | 3863967.049
[6 empty] | 2303 | 0 | 2303 | 0
[6 empty] | 2304 | 0 | 2304 | 0
[6 empty] | 2305 | 0 | 2305 | 0
[6 empty] | 2306 | 0 | 2306 | 0
[6 empty] | 2307 | 0 | 2307 | 0
[6 empty] | 2308 | 0 | 2308 | 0
[6 empty] | 2309 | 0 | 2309 | 0
[6 empty] | 2310 | 68657.6856 | 2310 | 68657.6856
[6 empty] | 2311 | 308575.5877 | 2311 | 308575.5877
[6 empty] | 2312 | 184714.9213 | 2312 | 184714.9213
[6 empty] | 2313 | 14342335.8935 | 2313 | 0
[6 empty] | 2314 | 3790624.6891 | 2314 | 3790624.6891
[6 empty] | 2315 | 324716.4224 | 2315 | 324716.4224
[6 empty] | 2316 | 0 | 2316 | 0
[6 empty] | 2317 | 0 | 2317 | 0
[6 empty] | 2318 | 1682463.0768 | 2318 | 1682463.0768
[6 empty] | 2319 | 0 | 2319 | 0
[6 empty] | 2320 | 0 | 2320 | 0
[6 empty] | 2321 | 0 | 2321 | 0
[6 empty] | 2322 | 0 | 2322 | 0
[6 empty] | 2323 | 0 | 2323 | 0
[6 empty] | 2324 | 3060698.1455 | 2324 | 3060698.1455
[6 empty] | 2325 | 2771451.2564 | 2325 | 2771451.2564
[6 empty] | 2326 | 1648687.8659 | 2326 | 1648687.8659
[6 empty] | 2327 | 0 | 2327 | 0
[6 empty] | 2328 | 3077941.7271 | 2328 | 3077941.7271
[6 empty] | 2329 | 254044.7318 | 2329 | 254044.7318
[6 empty] | 2330 | 0 | 2330 | 0
[6 empty] | 2331 | 228408.7738 | 2331 | 228408.7738
[6 empty] | 2332 | 0 | 2332 | 0
[6 empty] | 2333 | 2807065.1628 | 2333 | 0
[6 empty] | 2334 | 0 | 2334 | 0
[6 empty] | 2335 | 0 | 2335 | 0
[6 empty] | 2336 | 0 | 2336 | 0
[6 empty] | 2337 | 3598168.1931 | 2337 | 0
[6 empty] | 2338 | 3090704.3067 | 2338 | 0
[6 empty] | 2339 | 8201544.374 | 2339 | 8201544.374
[6 empty] | 2340 | 0 | 2340 | 0
[6 empty] | 2341 | 6174467.7947 | 2341 | 2918457.9263
[6 empty] | 2342 | 179915.3121 | 2342 | 0
[6 empty] | 2343 | 953226.2956 | 2343 | 274256.9151
[6 empty] | 2344 | 8177615.5106 | 2344 | 0
[6 empty] | 2345 | 10276839.2829 | 2345 | 159757.9691
[6 empty] | 2346 | 0 | 2346 | 0
[6 empty] | 2347 | 0 | 2347 | 0
[6 empty] | 2348 | 0 | 2348 | 0
[6 empty] | 2349 | 4666068.296 | 2349 | 333404.0257
[6 empty] | 2350 | 95424.7687 | 2350 | 95424.7687
[6 empty] | 2351 | 0 | 2351 | 0
[6 empty] | 2352 | 291952.2718 | 2352 | 291952.2718
[6 empty] | 2353 | 2431470.5923 | 2353 | 0
[6 empty] | 2354 | 4114144.5307 | 2354 | 4114144.5307
[6 empty] | 2355 | 0 | 2355 | 0
[6 empty] | 2356 | 0 | 2356 | 0
[6 empty] | 2357 | 756415.5383 | 2357 | 756415.5383
[6 empty] | 2358 | 2644538.2605 | 2358 | 0
[6 empty] | 2359 | 130470.3723 | 2359 | 130470.3723
[6 empty] | 2360 | 187344.4848 | 2360 | 187344.4848
[6 empty] | 2361 | 0 | 2361 | 0
[6 empty] | 2362 | 0 | 2362 | 0
[6 empty] | 2363 | 0 | 2363 | 0
[6 empty] | 2364 | 1157638.5396 | 2364 | 1157638.5396
[6 empty] | 2365 | 0 | 2365 | 0
[6 empty] | 2366 | 0 | 2366 | 0
[6 empty] | 2367 | 8930185.0207 | 2367 | 0
[6 empty] | 2368 | 0 | 2368 | 0
[6 empty] | 2369 | 177556.1282 | 2369 | 177556.1282
[6 empty] | 2370 | 0 | 2370 | 0
[6 empty] | 2371 | 323156.1033 | 2371 | 323156.1033
[6 empty] | 2372 | 0 | 2372 | 0
[6 empty] | 2373 | 0 | 2373 | 0
[6 empty] | 2374 | 0 | 2374 | 0
[6 empty] | 2375 | 161125.5674 | 2375 | 0
[6 empty] | 2376 | 0 | 2376 | 0
[6 empty] | 2377 | 2093398.46 | 2377 | 2093398.46
[6 empty] | 2378 | 0 | 2378 | 0
[6 empty] | 2379 | 0 | 2379 | 0
[6 empty] | 2380 | 168401.902 | 2380 | 0
[6 empty] | 2381 | 0 | 2381 | 0
[6 empty] | 2382 | 6386588.79 | 2382 | 0
[6 empty] | 2383 | 3228220.8666 | 2383 | 3228220.8666
[6 empty] | 2384 | 0 | 2384 | 0
[6 empty] | 2385 | 0 | 2385 | 0
[6 empty] | 2386 | 203464.4879 | 2386 | 0
[6 empty] | 2387 | 1557117.2269 | 2387 | 1557117.2269
[6 empty] | 2388 | 0 | 2388 | 0
[6 empty] | 2389 | 1647608.9728 | 2389 | 1647608.9728
[6 empty] | 2390 | 37812672.1627 | 2390 | 37812672.1627
[6 empty] | 2391 | 436669.3322 | 2391 | 436669.3322
[6 empty] | 2392 | 0 | 2392 | 0
[6 empty] | 2393 | 5545277.7019 | 2393 | 5545277.7019
[6 empty] | 2394 | 4504305.0845 | 2394 | 4504305.0845
[6 empty] | 2395 | 0 | 2395 | 0
[6 empty] | 2396 | 207931.6582 | 2396 | 207931.6582
[6 empty] | 2397 | 3090397.3113 | 2397 | 0
[6 empty] | 2398 | 0 | 2398 | 0
[6 empty] | 2399 | 0 | 2399 | 0
[6 empty] | 2400 | 0 | 2400 | 0
[6 empty] | 2401 | 3014768.9013 | 2401 | 0
[6 empty] | 2402 | 8439786.993 | 2402 | 0
[6 empty] | 2403 | 2181283.6424 | 2403 | 2181283.6424
[6 empty] | 2404 | 0 | 2404 | 0
[6 empty] | 2405 | 13731747.6081 | 2405 | 0
[6 empty] | 2406 | 467369.4954 | 2406 | 467369.4954
[6 empty] | 2407 | 0 | 2407 | 0
[6 empty] | 2408 | 2631148.4889 | 2408 | 2631148.4889
[6 empty] | 2409 | 0 | 2409 | 0
[6 empty] | 2410 | 0 | 2410 | 0
[6 empty] | 2411 | 0 | 2411 | 0
[6 empty] | 2412 | 0 | 2412 | 0
[6 empty] | 2413 | 2529596.8286 | 2413 | 2529596.8286
[6 empty] | 2414 | 0 | 2414 | 0
[6 empty] | 2415 | 2271732.3776 | 2415 | 2271732.3776
[6 empty] | 2416 | 0 | 2416 | 0
[6 empty] | 2417 | 0 | 2417 | 0
[6 empty] | 2418 | 622592.8404 | 2418 | 622592.8404
[6 empty] | 2419 | 257872.2199 | 2419 | 257872.2199
[6 empty] | 2420 | 0 | 2420 | 0
[6 empty] | 2421 | 0 | 2421 | 0
[6 empty] | 2422 | 0 | 2422 | 0
[6 empty] | 2423 | 4227782.9387 | 2423 | 0
[6 empty] | 2424 | 193189.3344 | 2424 | 193189.3344
[6 empty] | 2425 | 276958.562 | 2425 | 276958.562
[6 empty] | 2426 | 0 | 2426 | 0
[6 empty] | 2427 | 85121.0638 | 2427 | 85121.0638
[6 empty] | 2428 | 0 | 2428 | 0
[6 empty] | 2429 | 0 | 2429 | 0
[6 empty] | 2430 | 275444.7663 | 2430 | 275444.7663
[6 empty] | 2431 | 0 | 2431 | 0
[6 empty] | 2432 | 448545.1008 | 2432 | 225888.0002
[6 empty] | 2433 | 0 | 2433 | 0
[6 empty] | 2434 | 0 | 2434 | 0
[6 empty] | 2435 | 0 | 2435 | 0
[6 empty] | 2436 | 880614.8687 | 2436 | 880614.8687
[6 empty] | 2437 | 0 | 2437 | 0
[6 empty] | 2438 | 4759056.5291 | 2438 | 0
[6 empty] | 2439 | 10559027.22 | 2439 | 10559027.22
[6 empty] | 2440 | 0 | 2440 | 0
[6 empty] | 2441 | 0 | 2441 | 0
[6 empty] | 2442 | 795352.472 | 2442 | 795352.472
[6 empty] | 2443 | 6530922.7493 | 2443 | 0
[6 empty] | 2444 | 0 | 2444 | 0
[6 empty] | 2445 | 0 | 2445 | 0
[6 empty] | 2446 | 4710429.1734 | 2446 | 4710429.1734
[6 empty] | 2447 | 0 | 2447 | 0
[6 empty] | 2448 | 0 | 2448 | 0
[6 empty] | 2449 | 0 | 2449 | 0
[6 empty] | 2450 | 8496138.408 | 2450 | 188100.6411
[6 empty] | 2451 | 8118148.3146 | 2451 | 187378.1201
[6 empty] | 2452 | 0 | 2452 | 0
[6 empty] | 2453 | 1071973.5213 | 2453 | 1071973.5213
[6 empty] | 2454 | 0 | 2454 | 0
[6 empty] | 2455 | 2896555.4087 | 2455 | 0
[6 empty] | 2456 | 0 | 2456 | 0
[6 empty] | 2457 | 0 | 2457 | 0
[6 empty] | 2458 | 246483.017 | 2458 | 246483.017
[6 empty] | 2459 | 241673.9006 | 2459 | 0
[6 empty] | 2460 | 0 | 2460 | 0
[6 empty] | 2461 | 0 | 2461 | 0
[6 empty] | 2462 | 725301.7225 | 2462 | 725301.7225
[6 empty] | 2463 | 0 | 2463 | 0
[6 empty] | 2464 | 0 | 2464 | 0
[6 empty] | 2465 | 562280.5914 | 2465 | 562280.5914
[6 empty] | 2466 | 0 | 2466 | 0
[6 empty] | 2467 | 0 | 2467 | 0
[6 empty] | 2468 | 0 | 2468 | 0
[6 empty] | 2469 | 2589645.0898 | 2469 | 0
[6 empty] | 2470 | 7494704.0905 | 2470 | 0
[6 empty] | 2471 | 0 | 2471 | 0
[6 empty] | 2472 | 0 | 2472 | 0
[6 empty] | 2473 | 3475250.4113 | 2473 | 0
[6 empty] | 2474 | 0 | 2474 | 0
[6 empty] | 2475 | 3150389.7403 | 2475 | 0
[6 empty] | 2476 | 807672.9738 | 2476 | 0
[6 empty] | 2477 | 295407.5462 | 2477 | 295407.5462
[6 empty] | 2478 | 0 | 2478 | 0
[6 empty] | 2479 | 0 | 2479 | 0
[6 empty] | 2480 | 655452.6221 | 2480 | 427768.1112
[6 empty] | 2481 | 1544647.8841 | 2481 | 523450.8986
[6 empty] | 2482 | 0 | 2482 | 0
[6 empty] | 2483 | 427254.4184 | 2483 | 219864.7865
[6 empty] | 2484 | 0 | 2484 | 0
[6 empty] | 2485 | 0 | 2485 | 0
[6 empty] | 2486 | 13189395.6505 | 2486 | 0
[6 empty] | 2487 | 0 | 2487 | 0
[6 empty] | 2488 | 0 | 2488 | 0
[6 empty] | 2489 | 0 | 2489 | 0
[6 empty] | 2490 | 2475188.3394 | 2490 | 2475188.3394
[6 empty] | 2491 | 0 | 2491 | 0
[6 empty] | 2492 | 0 | 2492 | 0
[6 empty] | 2493 | 0 | 2493 | 0
[6 empty] | 2494 | 2591313.4322 | 2494 | 0
[6 empty] | 2495 | 0 | 2495 | 0
[6 empty] | 2496 | 2764609.9552 | 2496 | 201588.9721
[6 empty] | 2497 | 0 | 2497 | 0
[6 empty] | 2498 | 360508.8606 | 2498 | 0
[6 empty] | 2499 | 0 | 2499 | 0
[6 empty] | 2500 | 0 | 2500 | 0
[6 empty] | 2501 | 2355604.4939 | 2501 | 509441.7423
[6 empty] | 2502 | 0 | 2502 | 0
[6 empty] | 2503 | 0 | 2503 | 0
[6 empty] | 2504 | 3083756.2236 | 2504 | 3083756.2236
[6 empty] | 2505 | 4246322.806 | 2505 | 0
[6 empty] | 2506 | 601153.6833 | 2506 | 601153.6833
[6 empty] | 2507 | 3364174.8023 | 2507 | 0
[6 empty] | 2508 | 0 | 2508 | 0
[6 empty] | 2509 | 0 | 2509 | 0
[6 empty] | 2510 | 0 | 2510 | 0
[6 empty] | 2511 | 17320781.4936 | 2511 | 17320781.4936
[6 empty] | 2512 | 348298.9612 | 2512 | 348298.9612
[6 empty] | 2513 | 0 | 2513 | 0
[6 empty] | 2514 | 748285.3951 | 2514 | 748285.3951
[6 empty] | 2515 | 2365881.372 | 2515 | 2147469.5263
[6 empty] | 2516 | 2081857.7863 | 2516 | 0
[6 empty] | 2517 | 0 | 2517 | 0
[6 empty] | 2518 | 3747288.2546 | 2518 | 3747288.2546
[6 empty] | 2519 | 196316.1003 | 2519 | 0
[6 empty] | 2520 | 0 | 2520 | 0
[6 empty] | 2521 | 12483629.9452 | 2521 | 0
[6 empty] | 2522 | 4424551.9144 | 2522 | 4424551.9144
[6 empty] | 2523 | 0 | 2523 | 0
[6 empty] | 2524 | 190506.0811 | 2524 | 0
[6 empty] | 2525 | 0 | 2525 | 0
[6 empty] | 2526 | 0 | 2526 | 0
[6 empty] | 2527 | 604244.9208 | 2527 | 604244.9208
[6 empty] | 2528 | 0 | 2528 | 0
[6 empty] | 2529 | 0 | 2529 | 0
[6 empty] | 2530 | 244148.3773 | 2530 | 244148.3773
[6 empty] | 2531 | 2822113.6851 | 2531 | 0
[6 empty] | 2532 | 370326.5867 | 2532 | 370326.5867
[6 empty] | 2533 | 0 | 2533 | 0
[6 empty] | 2534 | 3237409.1494 | 2534 | 3237409.1494
[6 empty] | 2535 | 170771.5581 | 2535 | 0
[6 empty] | 2536 | 1359738.1985 | 2536 | 1359738.1985
[6 empty] | 2537 | 0 | 2537 | 0
[6 empty] | 2538 | 176697.706 | 2538 | 176697.706
[6 empty] | 2539 | 0 | 2539 | 0
[6 empty] | 2540 | 65752.3114 | 2540 | 65752.3114
[6 empty] | 2541 | 0 | 2541 | 0
[6 empty] | 2542 | 7880461.6553 | 2542 | 7880461.6553
[6 empty] | 2543 | 0 | 2543 | 0
[6 empty] | 2544 | 181985.9203 | 2544 | 181985.9203
[6 empty] | 2545 | 8296212.1879 | 2545 | 0
[6 empty] | 2546 | 0 | 2546 | 0
[6 empty] | 2547 | 0 | 2547 | 0
[6 empty] | 2548 | 681939.7795 | 2548 | 0
[6 empty] | 2549 | 0 | 2549 | 0
[6 empty] | 2550 | 479084.4722 | 2550 | 479084.4722
[6 empty] | 2551 | 0 | 2551 | 0
[6 empty] | 2552 | 0 | 2552 | 0
[6 empty] | 2553 | 0 | 2553 | 0
[6 empty] | 2554 | 810387.8075 | 2554 | 640063.348
[6 empty] | 2555 | 3118506.8693 | 2555 | 3118506.8693
[6 empty] | 2556 | 15717395.6873 | 2556 | 0
[6 empty] | 2557 | 5729888.0076 | 2557 | 0
[6 empty] | 2558 | 248362.9634 | 2558 | 248362.9634
[6 empty] | 2559 | 40015761.8529 | 2559 | 0
[6 empty] | 2560 | 0 | 2560 | 0
[6 empty] | 2561 | 0 | 2561 | 0
[6 empty] | 2562 | 2829018.7743 | 2562 | 0
[6 empty] | 2563 | 0 | 2563 | 0
[6 empty] | 2564 | 89984.4574 | 2564 | 89984.4574
[6 empty] | 2565 | 0 | 2565 | 0
[6 empty] | 2566 | 224494.8364 | 2566 | 224494.8364
[6 empty] | 2567 | 0 | 2567 | 0
[6 empty] | 2568 | 0 | 2568 | 0
[6 empty] | 2569 | 2314642.0966 | 2569 | 0
[6 empty] | 2570 | 0 | 2570 | 0
[6 empty] | 2571 | 370750.1778 | 2571 | 370750.1778
[6 empty] | 2572 | 4895672.666 | 2572 | 0
[6 empty] | 2573 | 0 | 2573 | 0
[6 empty] | 2574 | 244270.7961 | 2574 | 244270.7961
[6 empty] | 2575 | 405965.1746 | 2575 | 405965.1746
[6 empty] | 2576 | 0 | 2576 | 0
[6 empty] | 2577 | 2131250.8695 | 2577 | 2131250.8695
[6 empty] | 2578 | 0 | 2578 | 0
[6 empty] | 2579 | 4466382.2794 | 2579 | 0
[6 empty] | 2580 | 3781939.4067 | 2580 | 3781939.4067
[6 empty] | 2581 | 4164810.4398 | 2581 | 0
[6 empty] | 2582 | 0 | 2582 | 0
[6 empty] | 2583 | 4189041.8337 | 2583 | 4189041.8337
[6 empty] | 2584 | 0 | 2584 | 0
[6 empty] | 2585 | 0 | 2585 | 0
[6 empty] | 2586 | 0 | 2586 | 0
[6 empty] | 2587 | 6563132.8023 | 2587 | 6563132.8023
[6 empty] | 2588 | 0 | 2588 | 0
[6 empty] | 2589 | 2815814.2684 | 2589 | 2815814.2684
[6 empty] | 2590 | 2947073.0805 | 2590 | 2947073.0805
[6 empty] | 2591 | 3451247.8532 | 2591 | 3451247.8532
[6 empty] | 2592 | 180771.4467 | 2592 | 180771.4467
[6 empty] | 2593 | 371209.5897 | 2593 | 371209.5897
[6 empty] | 2594 | 0 | 2594 | 0
[6 empty] | 2595 | 6316137.0691 | 2595 | 6316137.0691
[6 empty] | 2596 | 0 | 2596 | 0
[6 empty] | 2597 | 0 | 2597 | 0
[6 empty] | 2598 | 0 | 2598 | 0
[6 empty] | 2599 | 2726387.9414 | 2599 | 2001678.6486
[6 empty] | 2600 | 0 | 2600 | 0
[6 empty] | 2601 | 0 | 2601 | 0
[6 empty] | 2602 | 2627177.4639 | 2602 | 0
[6 empty] | 2603 | 478466.3889 | 2603 | 478466.3889
[6 empty] | 2604 | 1623666.9932 | 2604 | 1623666.9932
[6 empty] | 2605 | 245809.548 | 2605 | 245809.548
[6 empty] | 2606 | 0 | 2606 | 0
[6 empty] | 2607 | 0 | 2607 | 0
[6 empty] | 2608 | 0 | 2608 | 0
[6 empty] | 2609 | 0 | 2609 | 0
[6 empty] | 2610 | 165192.1159 | 2610 | 165192.1159
[6 empty] | 2611 | 0 | 2611 | 0
[6 empty] | 2612 | 0 | 2612 | 0
[6 empty] | 2613 | 0 | 2613 | 0
[6 empty] | 2614 | 0 | 2614 | 0
[6 empty] | 2615 | 0 | 2615 | 0
[6 empty] | 2616 | 2782142.2184 | 2616 | 2782142.2184
[6 empty] | 2617 | 386507.4846 | 2617 | 386507.4846
[6 empty] | 2618 | 229149.7984 | 2618 | 229149.7984
[6 empty] | 2619 | 0 | 2619 | 0
[6 empty] | 2620 | 0 | 2620 | 0
[6 empty] | 2621 | 0 | 2621 | 0
[6 empty] | 2622 | 0 | 2622 | 0
[6 empty] | 2623 | 1428286.1425 | 2623 | 0
[6 empty] | 2624 | 222059.4853 | 2624 | 0
[6 empty] | 2625 | 0 | 2625 | 0
[6 empty] | 2626 | 169016.3287 | 2626 | 169016.3287
[6 empty] | 2627 | 0 | 2627 | 0
[6 empty] | 2628 | 0 | 2628 | 0
[6 empty] | 2629 | 0 | 2629 | 0
[6 empty] | 2630 | 0 | 2630 | 0
[6 empty] | 2631 | 8628101.1821 | 2631 | 0
[6 empty] | 2632 | 0 | 2632 | 0
[6 empty] | 2633 | 0 | 2633 | 0
[6 empty] | 2634 | 4694102.6978 | 2634 | 4694102.6978
[6 empty] | 2635 | 191305.6085 | 2635 | 191305.6085
[6 empty] | 2636 | 1593612.2702 | 2636 | 0
[6 empty] | 2637 | 0 | 2637 | 0
[6 empty] | 2638 | 359949.9013 | 2638 | 359949.9013
[6 empty] | 2639 | 3216598.3731 | 2639 | 446075.4324
[6 empty] | 2640 | 325617.2346 | 2640 | 325617.2346
[6 empty] | 2641 | 0 | 2641 | 0
[6 empty] | 2642 | 241205.5353 | 2642 | 241205.5353
[6 empty] | 2643 | 2872039.2827 | 2643 | 2872039.2827
[6 empty] | 2644 | 853631.194 | 2644 | 393835.493
[6 empty] | 2645 | 512030.5295 | 2645 | 318644.4488
[6 empty] | 2646 | 2910945.5718 | 2646 | 596827.626
[6 empty] | 2647 | 0 | 2647 | 0
[6 empty] | 2648 | 141135.9776 | 2648 | 141135.9776
[6 empty] | 2649 | 0 | 2649 | 0
[6 empty] | 2650 | 3298325.8317 | 2650 | 744717.0884
[6 empty] | 2651 | 0 | 2651 | 0
[6 empty] | 2652 | 0 | 2652 | 0
[6 empty] | 2653 | 0 | 2653 | 0
[6 empty] | 2654 | 204514.9883 | 2654 | 204514.9883
[6 empty] | 2655 | 0 | 2655 | 0
[6 empty] | 2656 | 0 | 2656 | 0
[6 empty] | 2657 | 536870.3043 | 2657 | 292541.5768
[6 empty] | 2658 | 2607232.8856 | 2658 | 0
[6 empty] | 2659 | 226327.5524 | 2659 | 226327.5524
[6 empty] | 2660 | 1776540.3055 | 2660 | 1776540.3055
[6 empty] | 2661 | 0 | 2661 | 0
[6 empty] | 2662 | 166224.0588 | 2662 | 166224.0588
[6 empty] | 2663 | 0 | 2663 | 0
[6 empty] | 2664 | 2650607.2035 | 2664 | 211890.1017
[6 empty] | 2665 | 10211596.5769 | 2665 | 10211596.5769
[6 empty] | 2666 | 0 | 2666 | 0
[6 empty] | 2667 | 138865.332 | 2667 | 0
[6 empty] | 2668 | 0 | 2668 | 0
[6 empty] | 2669 | 1150684.0553 | 2669 | 0
[6 empty] | 2670 | 0 | 2670 | 0
[6 empty] | 2671 | 1615846.3677 | 2671 | 0
[6 empty] | 2672 | 682218.9201 | 2672 | 682218.9201
[6 empty] | 2673 | 146787.7175 | 2673 | 146787.7175
[6 empty] | 2674 | 0 | 2674 | 0
[6 empty] | 2675 | 0 | 2675 | 0
[6 empty] | 2676 | 0 | 2676 | 0
[6 empty] | 2677 | 0 | 2677 | 0
[6 empty] | 2678 | 0 | 2678 | 0
[6 empty] | 2679 | 0 | 2679 | 0
[6 empty] | 2680 | 228643.8078 | 2680 | 0
[6 empty] | 2681 | 3026151.5616 | 2681 | 3026151.5616
[6 empty] | 2682 | 0 | 2682 | 0
[6 empty] | 2683 | 1854094.9365 | 2683 | 0
[6 empty] | 2684 | 4425627.8629 | 2684 | 4425627.8629
[6 empty] | 2685 | 4141889.6129 | 2685 | 4141889.6129
[6 empty] | 2686 | 0 | 2686 | 0
[6 empty] | 2687 | 0 | 2687 | 0
[6 empty] | 2688 | 274442.6709 | 2688 | 0
[6 empty] | 2689 | 0 | 2689 | 0
[6 empty] | 2690 | 0 | 2690 | 0
[6 empty] | 2691 | 254524.6676 | 2691 | 254524.6676
[6 empty] | 2692 | 139313.564 | 2692 | 139313.564
[6 empty] | 2693 | 5792244.0019 | 2693 | 0
[6 empty] | 2694 | 0 | 2694 | 0
[6 empty] | 2695 | 15348411.6945 | 2695 | 203832.7246
[6 empty] | 2696 | 0 | 2696 | 0
[6 empty] | 2697 | 0 | 2697 | 0
[6 empty] | 2698 | 1602251.6955 | 2698 | 465845.6092
[6 empty] | 2699 | 0 | 2699 | 0
[6 empty] | 2700 | 2566249.2891 | 2700 | 0
[6 empty] | 2701 | 0 | 2701 | 0
[6 empty] | 2702 | 1320500.9709 | 2702 | 0
[6 empty] | 2703 | 0 | 2703 | 0
[6 empty] | 2704 | 0 | 2704 | 0
[6 empty] | 2705 | 0 | 2705 | 0
[6 empty] | 2706 | 342495.6267 | 2706 | 342495.6267
[6 empty] | 2707 | 5970530.2917 | 2707 | 0
[6 empty] | 2708 | 0 | 2708 | 0
[6 empty] | 2709 | 586356.6888 | 2709 | 586356.6888
[6 empty] | 2710 | 236868.1363 | 2710 | 236868.1363
[6 empty] | 2711 | 0 | 2711 | 0
[6 empty] | 2712 | 0 | 2712 | 0
[6 empty] | 2713 | 221849.2618 | 2713 | 221849.2618
[6 empty] | 2714 | 0 | 2714 | 0
[6 empty] | 2715 | 0 | 2715 | 0
[6 empty] | 2716 | 762952.7097 | 2716 | 372390.9822
[6 empty] | 2717 | 255188.9026 | 2717 | 0
[6 empty] | 2718 | 0 | 2718 | 0
[6 empty] | 2719 | 4802301.0138 | 2719 | 247270.9002
[6 empty] | 2720 | 0 | 2720 | 0
[6 empty] | 2721 | 2131439.6428 | 2721 | 0
[6 empty] | 2722 | 0 | 2722 | 0
[6 empty] | 2723 | 0 | 2723 | 0
[6 empty] | 2724 | 0 | 2724 | 0
[6 empty] | 2725 | 399375.7547 | 2725 | 399375.7547
[6 empty] | 2726 | 0 | 2726 | 0
[6 empty] | 2727 | 2819292.6472 | 2727 | 0
[6 empty] | 2728 | 0 | 2728 | 0
[6 empty] | 2729 | 0 | 2729 | 0
[6 empty] | 2730 | 151264.9035 | 2730 | 0
[6 empty] | 2731 | 8129412.1882 | 2731 | 8129412.1882
[6 empty] | 2732 | 0 | 2732 | 0
[6 empty] | 2733 | 1702284.2141 | 2733 | 0
[6 empty] | 2734 | 0 | 2734 | 0
[6 empty] | 2735 | 639754.0285 | 2735 | 639754.0285
[6 empty] | 2736 | 295111.4534 | 2736 | 295111.4534
[6 empty] | 2737 | 217355.8247 | 2737 | 217355.8247
[6 empty] | 2738 | 173145.4644 | 2738 | 173145.4644
[6 empty] | 2739 | 0 | 2739 | 0
[6 empty] | 2740 | 0 | 2740 | 0
[6 empty] | 2741 | 743381.2926 | 2741 | 0
[6 empty] | 2742 | 0 | 2742 | 0
[6 empty] | 2743 | 0 | 2743 | 0
[6 empty] | 2744 | 3046360.4158 | 2744 | 3046360.4158
[6 empty] | 2745 | 208558.1212 | 2745 | 208558.1212
[6 empty] | 2746 | 961632.6778 | 2746 | 961632.6778
[6 empty] | 2747 | 0 | 2747 | 0
[6 empty] | 2748 | 265747.9809 | 2748 | 0
[6 empty] | 2749 | 500994.057 | 2749 | 500994.057
[6 empty] | 2750 | 2141831.4462 | 2750 | 0
[6 empty] | 2751 | 2919547.7805 | 2751 | 2919547.7805
[6 empty] | 2752 | 219116.5194 | 2752 | 219116.5194
[6 empty] | 2753 | 0 | 2753 | 0
[6 empty] | 2754 | 4289470.0074 | 2754 | 4289470.0074
[6 empty] | 2755 | 0 | 2755 | 0
[6 empty] | 2756 | 326175.9582 | 2756 | 326175.9582
[6 empty] | 2757 | 168436.7887 | 2757 | 168436.7887
[6 empty] | 2758 | 0 | 2758 | 0
[6 empty] | 2759 | 5827908.2043 | 2759 | 5827908.2043
[6 empty] | 2760 | 2292971.1367 | 2760 | 2292971.1367
[6 empty] | 2761 | 264249.0139 | 2761 | 264249.0139
[6 empty] | 2762 | 229095.8511 | 2762 | 229095.8511
[6 empty] | 2763 | 5427682.8805 | 2763 | 0
[6 empty] | 2764 | 0 | 2764 | 0
[6 empty] | 2765 | 0 | 2765 | 0
[6 empty] | 2766 | 375222.3982 | 2766 | 375222.3982
[6 empty] | 2767 | 629429.6562 | 2767 | 629429.6562
[6 empty] | 2768 | 240456.487 | 2768 | 0
[6 empty] | 2769 | 1797957.3984 | 2769 | 1797957.3984
[6 empty] | 2770 | 6597332.9084 | 2770 | 0
[6 empty] | 2771 | 0 | 2771 | 0
[6 empty] | 2772 | 0 | 2772 | 0
[6 empty] | 2773 | 3247545.5298 | 2773 | 3247545.5298
[6 empty] | 2774 | 0 | 2774 | 0
[6 empty] | 2775 | 0 | 2775 | 0
[6 empty] | 2776 | 0 | 2776 | 0
[6 empty] | 2777 | 0 | 2777 | 0
[6 empty] | 2778 | 0 | 2778 | 0
[6 empty] | 2779 | 231151.9334 | 2779 | 0
[6 empty] | 2780 | 0 | 2780 | 0
[6 empty] | 2781 | 3400373.2148 | 2781 | 3400373.2148
[6 empty] | 2782 | 190995.768 | 2782 | 190995.768
[6 empty] | 2783 | 196609.3019 | 2783 | 0
[6 empty] | 2784 | 0 | 2784 | 0
[6 empty] | 2785 | 0 | 2785 | 0
[6 empty] | 2786 | 0 | 2786 | 0
[6 empty] | 2787 | 0 | 2787 | 0
[6 empty] | 2788 | 0 | 2788 | 0
[6 empty] | 2789 | 223225.4137 | 2789 | 223225.4137
[6 empty] | 2790 | 0 | 2790 | 0
[6 empty] | 2791 | 0 | 2791 | 0
[6 empty] | 2792 | 0 | 2792 | 0
[6 empty] | 2793 | 231166.7017 | 2793 | 0
[6 empty] | 2794 | 0 | 2794 | 0
[6 empty] | 2795 | 333376.7764 | 2795 | 333376.7764
[6 empty] | 2796 | 223363.4298 | 2796 | 223363.4298
[6 empty] | 2797 | 0 | 2797 | 0
[6 empty] | 2798 | 185596.3426 | 2798 | 0
[6 empty] | 2799 | 0 | 2799 | 0
[6 empty] | 2800 | 289547.4876 | 2800 | 0
[6 empty] | 2801 | 9610665.0889 | 2801 | 0
[6 empty] | 2802 | 0 | 2802 | 0
[6 empty] | 2803 | 0 | 2803 | 0
[6 empty] | 2804 | 0 | 2804 | 0
[6 empty] | 2805 | 0 | 2805 | 0
[6 empty] | 2806 | 0 | 2806 | 0
[6 empty] | 2807 | 544694.0562 | 2807 | 544694.0562
[6 empty] | 2808 | 945606.2472 | 2808 | 945606.2472
[6 empty] | 2809 | 0 | 2809 | 0
[6 empty] | 2810 | 237069.0331 | 2810 | 0
[6 empty] | 2811 | 0 | 2811 | 0
[6 empty] | 2812 | 0 | 2812 | 0
[6 empty] | 2813 | 3691541.9348 | 2813 | 3691541.9348
[6 empty] | 2814 | 309549.7481 | 2814 | 309549.7481
[6 empty] | 2815 | 229116.1222 | 2815 | 229116.1222
[6 empty] | 2816 | 152974.7168 | 2816 | 0
[6 empty] | 2817 | 320731.8598 | 2817 | 320731.8598
[6 empty] | 2818 | 0 | 2818 | 0
[6 empty] | 2819 | 0 | 2819 | 0
[6 empty] | 2820 | 286702.1966 | 2820 | 286702.1966
[6 empty] | 2821 | 0 | 2821 | 0
[6 empty] | 2822 | 138692.0289 | 2822 | 0
[6 empty] | 2823 | 0 | 2823 | 0
[6 empty] | 2824 | 0 | 2824 | 0
[6 empty] | 2825 | 4127849.7073 | 2825 | 4127849.7073
[6 empty] | 2826 | 2031088.025 | 2826 | 2031088.025
[6 empty] | 2827 | 0 | 2827 | 0
[6 empty] | 2828 | 4415914.14 | 2828 | 494082.2424
[6 empty] | 2829 | 496202.4856 | 2829 | 496202.4856
[6 empty] | 2830 | 0 | 2830 | 0
[6 empty] | 2831 | 0 | 2831 | 0
[6 empty] | 2832 | 182285.389 | 2832 | 0
[6 empty] | 2833 | 162887.8196 | 2833 | 0
[6 empty] | 2834 | 148992.4247 | 2834 | 148992.4247
[6 empty] | 2835 | 0 | 2835 | 0
[6 empty] | 2836 | 0 | 2836 | 0
[6 empty] | 2837 | 0 | 2837 | 0
[6 empty] | 2838 | 0 | 2838 | 0
[6 empty] | 2839 | 0 | 2839 | 0
[6 empty] | 2840 | 0 | 2840 | 0
[6 empty] | 2841 | 0 | 2841 | 0
[6 empty] | 2842 | 18638101.2298 | 2842 | 0
[6 empty] | 2843 | 2355374.9651 | 2843 | 2355374.9651
[6 empty] | 2844 | 0 | 2844 | 0
[6 empty] | 2845 | 271278.935 | 2845 | 0
[6 empty] | 2846 | 0 | 2846 | 0
[6 empty] | 2847 | 235937.0025 | 2847 | 0
[6 empty] | 2848 | 292692.6294 | 2848 | 0
[6 empty] | 2849 | 0 | 2849 | 0
[6 empty] | 2850 | 235205.7285 | 2850 | 0
[6 empty] | 2851 | 0 | 2851 | 0
[6 empty] | 2852 | 230910.2378 | 2852 | 230910.2378
[6 empty] | 2853 | 290153.2453 | 2853 | 290153.2453
[6 empty] | 2854 | 351924.5214 | 2854 | 351924.5214
[6 empty] | 2855 | 285890.8602 | 2855 | 285890.8602
[6 empty] | 2856 | 202057.6004 | 2856 | 202057.6004
[6 empty] | 2857 | 0 | 2857 | 0
[6 empty] | 2858 | 0 | 2858 | 0
[6 empty] | 2859 | 0 | 2859 | 0
[6 empty] | 2860 | 4792353.2539 | 2860 | 1607756.3757
[6 empty] | 2861 | 0 | 2861 | 0
[6 empty] | 2862 | 0 | 2862 | 0
[6 empty] | 2863 | 0 | 2863 | 0
[6 empty] | 2864 | 297905.0275 | 2864 | 297905.0275
[6 empty] | 2865 | 0 | 2865 | 0
[6 empty] | 2866 | 10571152.7185 | 2866 | 10571152.7185
[6 empty] | 2867 | 0 | 2867 | 0
[6 empty] | 2868 | 0 | 2868 | 0
[6 empty] | 2869 | 464422.0462 | 2869 | 464422.0462
[6 empty] | 2870 | 464776.9897 | 2870 | 464776.9897
[6 empty] | 2871 | 0 | 2871 | 0
[6 empty] | 2872 | 0 | 2872 | 0
[6 empty] | 2873 | 0 | 2873 | 0
[6 empty] | 2874 | 137323.3867 | 2874 | 137323.3867
[6 empty] | 2875 | 0 | 2875 | 0
[6 empty] | 2876 | 0 | 2876 | 0
[6 empty] | 2877 | 2089153.1453 | 2877 | 2089153.1453
[6 empty] | 2878 | 103838.9715 | 2878 | 103838.9715
[6 empty] | 2879 | 2421414.458 | 2879 | 0
[6 empty] | 2880 | 0 | 2880 | 0
[6 empty] | 2881 | 5443873.5158 | 2881 | 0
[6 empty] | 2882 | 921557.3501 | 2882 | 0
[6 empty] | 2883 | 0 | 2883 | 0
[6 empty] | 2884 | 3333197.369 | 2884 | 188123.8982
[6 empty] | 2885 | 0 | 2885 | 0
[6 empty] | 2886 | 202175.1443 | 2886 | 0
[6 empty] | 2887 | 0 | 2887 | 0
[6 empty] | 2888 | 541880.6946 | 2888 | 541880.6946
[6 empty] | 2889 | 4378811.2401 | 2889 | 3516418.7185
[6 empty] | 2890 | 252258.1286 | 2890 | 43609.5444
[6 empty] | 2891 | 10548304.3656 | 2891 | 295589.5453
[6 empty] | 2892 | 0 | 2892 | 0
[6 empty] | 2893 | 0 | 2893 | 0
[6 empty] | 2894 | 0 | 2894 | 0
[6 empty] | 2895 | 0 | 2895 | 0
[6 empty] | 2896 | 0 | 2896 | 0
[6 empty] | 2897 | 1475358.8127 | 2897 | 1475358.8127
[6 empty] | 2898 | 2555906.0195 | 2898 | 2242358.4522
[6 empty] | 2899 | 0 | 2899 | 0
[6 empty] | 2900 | 0 | 2900 | 0
[6 empty] | 2901 | 0 | 2901 | 0
[6 empty] | 2902 | 0 | 2902 | 0
[6 empty] | 2903 | 1206296.2119 | 2903 | 0
[6 empty] | 2904 | 5314099.5308 | 2904 | 0
[6 empty] | 2905 | 202953.2096 | 2905 | 202953.2096
[6 empty] | 2906 | 0 | 2906 | 0
[6 empty] | 2907 | 323059.6035 | 2907 | 323059.6035
[6 empty] | 2908 | 3960771.423 | 2908 | 188038.2916
[6 empty] | 2909 | 0 | 2909 | 0
[6 empty] | 2910 | 0 | 2910 | 0
[6 empty] | 2911 | 0 | 2911 | 0
[6 empty] | 2912 | 2211428.3874 | 2912 | 0
[6 empty] | 2913 | 324684.2695 | 2913 | 0
[6 empty] | 2914 | 1026342.9145 | 2914 | 1026342.9145
[6 empty] | 2915 | 160988.1097 | 2915 | 160988.1097
[6 empty] | 2916 | 0 | 2916 | 0
[6 empty] | 2917 | 1281353.4599 | 2917 | 0
[6 empty] | 2918 | 3453465.8329 | 2918 | 174620.1493
[6 empty] | 2919 | 0 | 2919 | 0
[6 empty] | 2920 | 2738784.5821 | 2920 | 2738784.5821
[6 empty] | 2921 | 0 | 2921 | 0
[6 empty] | 2922 | 2720211.8909 | 2922 | 2720211.8909
[6 empty] | 2923 | 192541.2303 | 2923 | 192541.2303
[6 empty] | 2924 | 0 | 2924 | 0
[6 empty] | 2925 | 360215.1512 | 2925 | 217164.5133
[6 empty] | 2926 | 0 | 2926 | 0
[6 empty] | 2927 | 2813195.2528 | 2927 | 2813195.2528
[6 empty] | 2928 | 0 | 2928 | 0
[6 empty] | 2929 | 93243.438 | 2929 | 93243.438
[6 empty] | 2930 | 198598.1234 | 2930 | 198598.1234
[6 empty] | 2931 | 0 | 2931 | 0
[6 empty] | 2932 | 0 | 2932 | 0
[6 empty] | 2933 | 0 | 2933 | 0
[6 empty] | 2934 | 158530.9763 | 2934 | 158530.9763
[6 empty] | 2935 | 0 | 2935 | 0
[6 empty] | 2936 | 213552.5061 | 2936 | 213552.5061
[6 empty] | 2937 | 1441114.2349 | 2937 | 0
[6 empty] | 2938 | 1712639.5982 | 2938 | 1712639.5982
[6 empty] | 2939 | 197601.648 | 2939 | 0
[6 empty] | 2940 | 348966.8078 | 2940 | 348966.8078
[6 empty] | 2941 | 156737.5503 | 2941 | 156737.5503
[6 empty] | 2942 | 0 | 2942 | 0
[6 empty] | 2943 | 0 | 2943 | 0
[6 empty] | 2944 | 3643863.9148 | 2944 | 0
[6 empty] | 2945 | 0 | 2945 | 0
[6 empty] | 2946 | 0 | 2946 | 0
[6 empty] | 2947 | 268495.6439 | 2947 | 0
[6 empty] | 2948 | 0 | 2948 | 0
[6 empty] | 2949 | 0 | 2949 | 0
[6 empty] | 2950 | 267670.3247 | 2950 | 267670.3247
[6 empty] | 2951 | 156080.8622 | 2951 | 0
[6 empty] | 2952 | 0 | 2952 | 0
[6 empty] | 2953 | 0 | 2953 | 0
[6 empty] | 2954 | 199574.2284 | 2954 | 0
[6 empty] | 2955 | 9677842.0086 | 2955 | 339024.4215
[6 empty] | 2956 | 1812546.6127 | 2956 | 1812546.6127
[6 empty] | 2957 | 244693.2899 | 2957 | 244693.2899
[6 empty] | 2958 | 0 | 2958 | 0
[6 empty] | 2959 | 0 | 2959 | 0
[6 empty] | 2960 | 0 | 2960 | 0
[6 empty] | 2961 | 0 | 2961 | 0
[6 empty] | 2962 | 3609396.3682 | 2962 | 3609396.3682
[6 empty] | 2963 | 200030.6198 | 2963 | 200030.6198
[6 empty] | 2964 | 2070125.98 | 2964 | 0
[6 empty] | 2965 | 0 | 2965 | 0
[6 empty] | 2966 | 0 | 2966 | 0
[6 empty] | 2967 | 0 | 2967 | 0
[6 empty] | 2968 | 2333590.9058 | 2968 | 0
[6 empty] | 2969 | 0 | 2969 | 0
[6 empty] | 2970 | 0 | 2970 | 0
[6 empty] | 2971 | 0 | 2971 | 0
[6 empty] | 2972 | 247072.3979 | 2972 | 0
[6 empty] | 2973 | 3617522.7545 | 2973 | 0
[6 empty] | 2974 | 189244.5961 | 2974 | 189244.5961
[6 empty] | 2975 | 2416427.2356 | 2975 | 0
[6 empty] | 2976 | 175605.2145 | 2976 | 0
[6 empty] | 2977 | 188091.6343 | 2977 | 188091.6343
[6 empty] | 2978 | 3955474.2599 | 2978 | 0
[6 empty] | 2979 | 2669385.3451 | 2979 | 2669385.3451
[6 empty] | 2980 | 1352785.4783 | 2980 | 0
[6 empty] | 2981 | 200448.6028 | 2981 | 200448.6028
[6 empty] | 2982 | 0 | 2982 | 0
[6 empty] | 2983 | 5078790.7573 | 2983 | 0
[6 empty] | 2984 | 0 | 2984 | 0
[6 empty] | 2985 | 0 | 2985 | 0
[6 empty] | 2986 | 0 | 2986 | 0
[6 empty] | 2987 | 3529098.1128 | 2987 | 3529098.1128
[6 empty] | 2988 | 0 | 2988 | 0
[6 empty] | 2989 | 241615.8626 | 2989 | 0
[6 empty] | 2990 | 4718191.0521 | 2990 | 0
[6 empty] | 2991 | 0 | 2991 | 0
[6 empty] | 2992 | 0 | 2992 | 0
[6 empty] | 2993 | 0 | 2993 | 0
[6 empty] | 2994 | 0 | 2994 | 0
[6 empty] | 2995 | 402399.988 | 2995 | 402399.988
[6 empty] | 2996 | 244569.1057 | 2996 | 244569.1057
[6 empty] | 2997 | 20247774.5854 | 2997 | 5992658.6379
[6 empty] | 2998 | 0 | 2998 | 0
[6 empty] | 2999 | 0 | 2999 | 0
[6 empty] | 3000 | 393480.5884 | 3000 | 393480.5884
[6 empty] | 3001 | 643946.7519 | 3001 | 0
[6 empty] | 3002 | 0 | 3002 | 0
[6 empty] | 3003 | 4027752.0358 | 3003 | 4027752.0358
[6 empty] | 3004 | 0 | 3004 | 0
[6 empty] | 3005 | 187229.7299 | 3005 | 187229.7299
[6 empty] | 3006 | 321963.8037 | 3006 | 321963.8037
[6 empty] | 3007 | 0 | 3007 | 0
[6 empty] | 3008 | 0 | 3008 | 0
[6 empty] | 3009 | 6964350.3478 | 3009 | 6964350.3478
[6 empty] | 3010 | 0 | 3010 | 0
[6 empty] | 3011 | 0 | 3011 | 0
[6 empty] | 3012 | 0 | 3012 | 0
[6 empty] | 3013 | 7233776.9885 | 3013 | 7233776.9885
[6 empty] | 3014 | 2050298.4957 | 3014 | 0
[6 empty] | 3015 | 0 | 3015 | 0
[6 empty] | 3016 | 5118627.6074 | 3016 | 2832489.4851
[6 empty] | 3017 | 0 | 3017 | 0
[6 empty] | 3018 | 2967785.1522 | 3018 | 2967785.1522
[6 empty] | 3019 | 479059.271 | 3019 | 479059.271
[6 empty] | 3020 | 0 | 3020 | 0
[6 empty] | 3021 | 0 | 3021 | 0
[6 empty] | 3022 | 198289.0853 | 3022 | 198289.0853
[6 empty] | 3023 | 0 | 3023 | 0
[6 empty] | 3024 | 5773163.7248 | 3024 | 2113977.3364
[6 empty] | 3025 | 0 | 3025 | 0
[6 empty] | 3026 | 0 | 3026 | 0
[6 empty] | 3027 | 102217.1742 | 3027 | 102217.1742
[6 empty] | 3028 | 4559465.2164 | 3028 | 4559465.2164
[6 empty] | 3029 | 3171025.1232 | 3029 | 0
[6 empty] | 3030 | 422683.135 | 3030 | 422683.135
[6 empty] | 3031 | 0 | 3031 | 0
[6 empty] | 3032 | 0 | 3032 | 0
[6 empty] | 3033 | 204171.4741 | 3033 | 204171.4741
[6 empty] | 3034 | 0 | 3034 | 0
[6 empty] | 3035 | 1904871.9735 | 3035 | 273670.666
[6 empty] | 3036 | 5657128.1189 | 3036 | 5657128.1189
[6 empty] | 3037 | 0 | 3037 | 0
[6 empty] | 3038 | 251016.7716 | 3038 | 251016.7716
[6 empty] | 3039 | 0 | 3039 | 0
[6 empty] | 3040 | 0 | 3040 | 0
[6 empty] | 3041 | 3014908.195 | 3041 | 3014908.195
[6 empty] | 3042 | 0 | 3042 | 0
[6 empty] | 3043 | 2663719.2103 | 3043 | 2663719.2103
[6 empty] | 3044 | 4521637.7105 | 3044 | 4521637.7105
[6 empty] | 3045 | 233492.2489 | 3045 | 233492.2489
[6 empty] | 3046 | 463509.7759 | 3046 | 463509.7759
[6 empty] | 3047 | 424659.226 | 3047 | 424659.226
[6 empty] | 3048 | 0 | 3048 | 0
[6 empty] | 3049 | 1466531.7752 | 3049 | 1466531.7752
[6 empty] | 3050 | 0 | 3050 | 0
[6 empty] | 3051 | 1140717.6757 | 3051 | 468091.9509
[6 empty] | 3052 | 0 | 3052 | 0
[6 empty] | 3053 | 645757.869 | 3053 | 645757.869
[6 empty] | 3054 | 5142935.5266 | 3054 | 5142935.5266
[6 empty] | 3055 | 232387.7426 | 3055 | 232387.7426
[6 empty] | 3056 | 0 | 3056 | 0
[6 empty] | 3057 | 970413.5712 | 3057 | 970413.5712
[6 empty] | 3058 | 2588551.9412 | 3058 | 2588551.9412
[6 empty] | 3059 | 1262610.8163 | 3059 | 0
[6 empty] | 3060 | 0 | 3060 | 0
[6 empty] | 3061 | 448157.1934 | 3061 | 448157.1934
[6 empty] | 3062 | 0 | 3062 | 0
[6 empty] | 3063 | 707125.9255 | 3063 | 209589.3553
[6 empty] | 3064 | 200974.6214 | 3064 | 0
[6 empty] | 3065 | 324630.1523 | 3065 | 324630.1523
[6 empty] | 3066 | 3816960.7781 | 3066 | 0
[6 empty] | 3067 | 1262337.5659 | 3067 | 1262337.5659
[6 empty] | 3068 | 0 | 3068 | 0
[6 empty] | 3069 | 0 | 3069 | 0
[6 empty] | 3070 | 357984.0542 | 3070 | 357984.0542
[6 empty] | 3071 | 8878833.6618 | 3071 | 8878833.6618
[6 empty] | 3072 | 591919.6021 | 3072 | 591919.6021
[6 empty] | 3073 | 0 | 3073 | 0
[6 empty] | 3074 | 0 | 3074 | 0
[6 empty] | 3075 | 177761.8626 | 3075 | 177761.8626
[6 empty] | 3076 | 0 | 3076 | 0
[6 empty] | 3077 | 545287.2287 | 3077 | 0
[6 empty] | 3078 | 3477076.6773 | 3078 | 3477076.6773
[6 empty] | 3079 | 297629.4793 | 3079 | 297629.4793
[6 empty] | 3080 | 364188.1088 | 3080 | 364188.1088
[6 empty] | 3081 | 0 | 3081 | 0
[6 empty] | 3082 | 256949.0398 | 3082 | 0
[6 empty] | 3083 | 259955.4247 | 3083 | 259955.4247
[6 empty] | 3084 | 0 | 3084 | 0
[6 empty] | 3085 | 0 | 3085 | 0
[6 empty] | 3086 | 277227.7165 | 3086 | 277227.7165
[6 empty] | 3087 | 3572075.0488 | 3087 | 0
[6 empty] | 3088 | 166304.365 | 3088 | 0
[6 empty] | 3089 | 309570.9974 | 3089 | 309570.9974
[6 empty] | 3090 | 0 | 3090 | 0
[6 empty] | 3091 | 1237569.6026 | 3091 | 170663.4926
[6 empty] | 3092 | 0 | 3092 | 0
[6 empty] | 3093 | 188092.3376 | 3093 | 188092.3376
[6 empty] | 3094 | 0 | 3094 | 0
[6 empty] | 3095 | 255827.2632 | 3095 | 0
[6 empty] | 3096 | 665048.9026 | 3096 | 665048.9026
[6 empty] | 3097 | 2728983.8481 | 3097 | 183676.2565
[6 empty] | 3098 | 0 | 3098 | 0
[6 empty] | 3099 | 11417197.5743 | 3099 | 0
[6 empty] | 3100 | 0 | 3100 | 0
[6 empty] | 3101 | 0 | 3101 | 0
[6 empty] | 3102 | 0 | 3102 | 0
[6 empty] | 3103 | 3145818.1288 | 3103 | 0
[6 empty] | 3104 | 503162.8057 | 3104 | 503162.8057
[6 empty] | 3105 | 379002.6078 | 3105 | 379002.6078
[6 empty] | 3106 | 0 | 3106 | 0
[6 empty] | 3107 | 1120575.3454 | 3107 | 1120575.3454
[6 empty] | 3108 | 1036609.747 | 3108 | 0
[6 empty] | 3109 | 2286277.4259 | 3109 | 2066286.3005
[6 empty] | 3110 | 5165739.5359 | 3110 | 2904889.7804
[6 empty] | 3111 | 0 | 3111 | 0
[6 empty] | 3112 | 4688511.8209 | 3112 | 4688511.8209
[6 empty] | 3113 | 0 | 3113 | 0
[6 empty] | 3114 | 0 | 3114 | 0
[6 empty] | 3115 | 0 | 3115 | 0
[6 empty] | 3116 | 3811829.1464 | 3116 | 0
[6 empty] | 3117 | 0 | 3117 | 0
[6 empty] | 3118 | 230536.0201 | 3118 | 230536.0201
[6 empty] | 3119 | 197738.8009 | 3119 | 197738.8009
[6 empty] | 3120 | 0 | 3120 | 0
[6 empty] | 3121 | 0 | 3121 | 0
[6 empty] | 3122 | 262547.4014 | 3122 | 262547.4014
[6 empty] | 3123 | 662870.7185 | 3123 | 662870.7185
[6 empty] | 3124 | 1920939.6926 | 3124 | 876361.27
[6 empty] | 3125 | 3104255.4151 | 3125 | 3104255.4151
[6 empty] | 3126 | 0 | 3126 | 0
[6 empty] | 3127 | 0 | 3127 | 0
[6 empty] | 3128 | 0 | 3128 | 0
[6 empty] | 3129 | 0 | 3129 | 0
[6 empty] | 3130 | 2709044.5197 | 3130 | 2709044.5197
[6 empty] | 3131 | 0 | 3131 | 0
[6 empty] | 3132 | 6537312.6634 | 3132 | 6537312.6634
[6 empty] | 3133 | 3825069.1 | 3133 | 0
[6 empty] | 3134 | 369780.3512 | 3134 | 184217.3179
[6 empty] | 3135 | 3858982.0745 | 3135 | 3858982.0745
[6 empty] | 3136 | 6788775.5607 | 3136 | 0
[6 empty] | 3137 | 0 | 3137 | 0
[6 empty] | 3138 | 0 | 3138 | 0
[6 empty] | 3139 | 427843.1777 | 3139 | 427843.1777
[6 empty] | 3140 | 29135335.3907 | 3140 | 0
[6 empty] | 3141 | 388646.3262 | 3141 | 198406.8138
[6 empty] | 3142 | 0 | 3142 | 0
[6 empty] | 3143 | 0 | 3143 | 0
[6 empty] | 3144 | 0 | 3144 | 0
[6 empty] | 3145 | 213497.9723 | 3145 | 213497.9723
[6 empty] | 3146 | 561959.9234 | 3146 | 561959.9234
[6 empty] | 3147 | 285905.2758 | 3147 | 285905.2758
[6 empty] | 3148 | 0 | 3148 | 0
[6 empty] | 3149 | 0 | 3149 | 0
[6 empty] | 3150 | 783256.6675 | 3150 | 368669.2103
[6 empty] | 3151 | 2748028.4653 | 3151 | 0
[6 empty] | 3152 | 843261.142 | 3152 | 843261.142
[6 empty] | 3153 | 0 | 3153 | 0
[6 empty] | 3154 | 0 | 3154 | 0
[6 empty] | 3155 | 355318.3387 | 3155 | 355318.3387
[6 empty] | 3156 | 0 | 3156 | 0
[6 empty] | 3157 | 0 | 3157 | 0
[6 empty] | 3158 | 820248.9437 | 3158 | 0
[6 empty] | 3159 | 1280024.8211 | 3159 | 0
[6 empty] | 3160 | 0 | 3160 | 0
[6 empty] | 3161 | 0 | 3161 | 0
[6 empty] | 3162 | 2570559.6033 | 3162 | 0
[6 empty] | 3163 | 520420.1325 | 3163 | 520420.1325
[6 empty] | 3164 | 1265119.2399 | 3164 | 1023086.4578
[6 empty] | 3165 | 0 | 3165 | 0
[6 empty] | 3166 | 0 | 3166 | 0
[6 empty] | 3167 | 0 | 3167 | 0
[6 empty] | 3168 | 0 | 3168 | 0
[6 empty] | 3169 | 165820.8418 | 3169 | 165820.8418
[6 empty] | 3170 | 0 | 3170 | 0
[6 empty] | 3171 | 2934600.6185 | 3171 | 2934600.6185
[6 empty] | 3172 | 875198.9934 | 3172 | 875198.9934
[6 empty] | 3173 | 0 | 3173 | 0
[6 empty] | 3174 | 124568.9686 | 3174 | 124568.9686
[6 empty] | 3175 | 3188959.9527 | 3175 | 3188959.9527
[6 empty] | 3176 | 416645.9779 | 3176 | 416645.9779
[6 empty] | 3177 | 0 | 3177 | 0
[6 empty] | 3178 | 0 | 3178 | 0
[6 empty] | 3179 | 0 | 3179 | 0
[6 empty] | 3180 | 2201022.7518 | 3180 | 0
[6 empty] | 3181 | 816908.6076 | 3181 | 816908.6076
[6 empty] | 3182 | 266522.4016 | 3182 | 266522.4016
[6 empty] | 3183 | 0 | 3183 | 0
[6 empty] | 3184 | 4069496.1919 | 3184 | 2376496.9132
[6 empty] | 3185 | 0 | 3185 | 0
[6 empty] | 3186 | 3160678.1057 | 3186 | 0
[6 empty] | 3187 | 0 | 3187 | 0
[6 empty] | 3188 | 919658.229 | 3188 | 919658.229
[6 empty] | 3189 | 4920097.5676 | 3189 | 235038.3576
[6 empty] | 3190 | 820392.4233 | 3190 | 0
[6 empty] | 3191 | 0 | 3191 | 0
[6 empty] | 3192 | 0 | 3192 | 0
[6 empty] | 3193 | 2917102.7432 | 3193 | 0
[6 empty] | 3194 | 223827.0087 | 3194 | 0
[6 empty] | 3195 | 0 | 3195 | 0
[6 empty] | 3196 | 0 | 3196 | 0
[6 empty] | 3197 | 0 | 3197 | 0
[6 empty] | 3198 | 238047.5003 | 3198 | 238047.5003
[6 empty] | 3199 | 203210.7065 | 3199 | 203210.7065
[6 empty] | 3200 | 231615.2777 | 3200 | 0
[6 empty] | 3201 | 3125140.9154 | 3201 | 0
[6 empty] | 3202 | 0 | 3202 | 0
[6 empty] | 3203 | 0 | 3203 | 0
[6 empty] | 3204 | 135808.1273 | 3204 | 135808.1273
[6 empty] | 3205 | 0 | 3205 | 0
[6 empty] | 3206 | 173511.2055 | 3206 | 173511.2055
[6 empty] | 3207 | 0 | 3207 | 0
[6 empty] | 3208 | 167846.5312 | 3208 | 0
[6 empty] | 3209 | 161313.8624 | 3209 | 161313.8624
[6 empty] | 3210 | 280125.3493 | 3210 | 280125.3493
[6 empty] | 3211 | 0 | 3211 | 0
[6 empty] | 3212 | 0 | 3212 | 0
[6 empty] | 3213 | 0 | 3213 | 0
[6 empty] | 3214 | 12183252.3851 | 3214 | 7939537.6713
[6 empty] | 3215 | 0 | 3215 | 0
[6 empty] | 3216 | 896470.7149 | 3216 | 896470.7149
[6 empty] | 3217 | 0 | 3217 | 0
[6 empty] | 3218 | 285645.0122 | 3218 | 0
[6 empty] | 3219 | 0 | 3219 | 0
[6 empty] | 3220 | 0 | 3220 | 0
[6 empty] | 3221 | 0 | 3221 | 0
[6 empty] | 3222 | 0 | 3222 | 0
[6 empty] | 3223 | 640885.1353 | 3223 | 640885.1353
[6 empty] | 3224 | 0 | 3224 | 0
[6 empty] | 3225 | 2952515.1518 | 3225 | 1494434.4471
[6 empty] | 3226 | 2478038.5698 | 3226 | 2478038.5698
[6 empty] | 3227 | 0 | 3227 | 0
[6 empty] | 3228 | 522156.2179 | 3228 | 522156.2179
[6 empty] | 3229 | 0 | 3229 | 0
[6 empty] | 3230 | 3856416.391 | 3230 | 0
[6 empty] | 3231 | 1713782.2859 | 3231 | 1713782.2859
[6 empty] | 3232 | 252568.1392 | 3232 | 0
[6 empty] | 3233 | 4874475.1165 | 3233 | 3660315.0738
[6 empty] | 3234 | 2746354.2716 | 3234 | 2746354.2716
[6 empty] | 3235 | 1895360.6673 | 3235 | 249299.9175
[6 empty] | 3236 | 3654929.9097 | 3236 | 3654929.9097
[6 empty] | 3237 | 155167.3688 | 3237 | 155167.3688
[6 empty] | 3238 | 2554464.1377 | 3238 | 2554464.1377
[6 empty] | 3239 | 3685221.8277 | 3239 | 0
[6 empty] | 3240 | 225636.7366 | 3240 | 225636.7366
[6 empty] | 3241 | 0 | 3241 | 0
[6 empty] | 3242 | 3303488.7416 | 3242 | 0
[6 empty] | 3243 | 13387071.2223 | 3243 | 0
[6 empty] | 3244 | 817142.5624 | 3244 | 817142.5624
[6 empty] | 3245 | 7022968.4011 | 3245 | 7022968.4011
[6 empty] | 3246 | 0 | 3246 | 0
[6 empty] | 3247 | 0 | 3247 | 0
[6 empty] | 3248 | 2394038.1811 | 3248 | 0
[6 empty] | 3249 | 4253050.4338 | 3249 | 4253050.4338
[6 empty] | 3250 | 0 | 3250 | 0
[6 empty] | 3251 | 0 | 3251 | 0
[6 empty] | 3252 | 367056.2695 | 3252 | 367056.2695
[6 empty] | 3253 | 3268783.7688 | 3253 | 0
[6 empty] | 3254 | 0 | 3254 | 0
[6 empty] | 3255 | 0 | 3255 | 0
[6 empty] | 3256 | 2335969.7496 | 3256 | 0
[6 empty] | 3257 | 1916123.0959 | 3257 | 0
[6 empty] | 3258 | 0 | 3258 | 0
[6 empty] | 3259 | 0 | 3259 | 0
[6 empty] | 3260 | 0 | 3260 | 0
[6 empty] | 3261 | 0 | 3261 | 0
[6 empty] | 3262 | 187731.5669 | 3262 | 0
[6 empty] | 3263 | 0 | 3263 | 0
[6 empty] | 3264 | 245616.3165 | 3264 | 245616.3165
[6 empty] | 3265 | 0 | 3265 | 0
[6 empty] | 3266 | 0 | 3266 | 0
[6 empty] | 3267 | 0 | 3267 | 0
[6 empty] | 3268 | 0 | 3268 | 0
[6 empty] | 3269 | 0 | 3269 | 0
[6 empty] | 3270 | 0 | 3270 | 0
[6 empty] | 3271 | 11522220.5435 | 3271 | 11522220.5435
[6 empty] | 3272 | 75426.6713 | 3272 | 75426.6713
[6 empty] | 3273 | 207296.6039 | 3273 | 207296.6039
[6 empty] | 3274 | 3325885.5949 | 3274 | 3079769.4172
[6 empty] | 3275 | 0 | 3275 | 0
[6 empty] | 3276 | 0 | 3276 | 0
[6 empty] | 3277 | 264899.0122 | 3277 | 264899.0122
[6 empty] | 3278 | 261391.4385 | 3278 | 261391.4385
[6 empty] | 3279 | 2699823.6294 | 3279 | 0
[6 empty] | 3280 | 714584.9698 | 3280 | 714584.9698
[6 empty] | 3281 | 3725196.6754 | 3281 | 0
[6 empty] | 3282 | 0 | 3282 | 0
[6 empty] | 3283 | 0 | 3283 | 0
[6 empty] | 3284 | 1697830.5744 | 3284 | 1697830.5744
[6 empty] | 3285 | 0 | 3285 | 0
[6 empty] | 3286 | 0 | 3286 | 0
[6 empty] | 3287 | 254892.4278 | 3287 | 0
[6 empty] | 3288 | 0 | 3288 | 0
[6 empty] | 3289 | 0 | 3289 | 0
[6 empty] | 3290 | 0 | 3290 | 0
[6 empty] | 3291 | 0 | 3291 | 0
[6 empty] | 3292 | 0 | 3292 | 0
[6 empty] | 3293 | 0 | 3293 | 0
[6 empty] | 3294 | 0 | 3294 | 0
[6 empty] | 3295 | 10269124.7523 | 3295 | 8502857.7236
[6 empty] | 3296 | 0 | 3296 | 0
[6 empty] | 3297 | 4246832.1087 | 3297 | 4000072.8374
[6 empty] | 3298 | 1244987.9596 | 3298 | 0
[6 empty] | 3299 | 5683593.6211 | 3299 | 5683593.6211
[6 empty] | 3300 | 0 | 3300 | 0
[6 empty] | 3301 | 0 | 3301 | 0
[6 empty] | 3302 | 2699593.632 | 3302 | 0
[6 empty] | 3303 | 0 | 3303 | 0
[6 empty] | 3304 | 0 | 3304 | 0
[6 empty] | 3305 | 269387.4764 | 3305 | 269387.4764
[6 empty] | 3306 | 5466587.8937 | 3306 | 5466587.8937
[6 empty] | 3307 | 410097.3889 | 3307 | 410097.3889
[6 empty] | 3308 | 0 | 3308 | 0
[6 empty] | 3309 | 154030.7325 | 3309 | 154030.7325
[6 empty] | 3310 | 0 | 3310 | 0
[6 empty] | 3311 | 0 | 3311 | 0
[6 empty] | 3312 | 0 | 3312 | 0
[6 empty] | 3313 | 7018935.6925 | 3313 | 0
[6 empty] | 3314 | 5590872.4155 | 3314 | 0
[6 empty] | 3315 | 0 | 3315 | 0
[6 empty] | 3316 | 0 | 3316 | 0
[6 empty] | 3317 | 0 | 3317 | 0
[6 empty] | 3318 | 0 | 3318 | 0
[6 empty] | 3319 | 467932.3251 | 3319 | 467932.3251
[6 empty] | 3320 | 0 | 3320 | 0
[6 empty] | 3321 | 252060.108 | 3321 | 252060.108
[6 empty] | 3322 | 4203845.738 | 3322 | 4203845.738
[6 empty] | 3323 | 0 | 3323 | 0
[6 empty] | 3324 | 0 | 3324 | 0
[6 empty] | 3325 | 0 | 3325 | 0
[6 empty] | 3326 | 0 | 3326 | 0
[6 empty] | 3327 | 127651.6829 | 3327 | 127651.6829
[6 empty] | 3328 | 290933.2567 | 3328 | 290933.2567
[6 empty] | 3329 | 247287.0861 | 3329 | 247287.0861
[6 empty] | 3330 | 139904.5664 | 3330 | 0
[6 empty] | 3331 | 567377.8683 | 3331 | 567377.8683
[6 empty] | 3332 | 0 | 3332 | 0
[6 empty] | 3333 | 297598.968 | 3333 | 297598.968
[6 empty] | 3334 | 0 | 3334 | 0
[6 empty] | 3335 | 4745165.3546 | 3335 | 4745165.3546
[6 empty] | 3336 | 5928571.3099 | 3336 | 5928571.3099
[6 empty] | 3337 | 807622.9166 | 3337 | 0
[6 empty] | 3338 | 0 | 3338 | 0
[6 empty] | 3339 | 121487.0841 | 3339 | 121487.0841
[6 empty] | 3340 | 10092996.8479 | 3340 | 9809764.8916
[6 empty] | 3341 | 195420.6935 | 3341 | 0
[6 empty] | 3342 | 0 | 3342 | 0
[6 empty] | 3343 | 0 | 3343 | 0
[6 empty] | 3344 | 921876.6495 | 3344 | 921876.6495
[6 empty] | 3345 | 0 | 3345 | 0
[6 empty] | 3346 | 209347.6761 | 3346 | 0
[6 empty] | 3347 | 0 | 3347 | 0
[6 empty] | 3348 | 0 | 3348 | 0
[6 empty] | 3349 | 3055188.1849 | 3349 | 3055188.1849
[6 empty] | 3350 | 3256525.1174 | 3350 | 3256525.1174
[6 empty] | 3351 | 5679615.2667 | 3351 | 0
[6 empty] | 3352 | 0 | 3352 | 0
[6 empty] | 3353 | 0 | 3353 | 0
[6 empty] | 3354 | 285778.9578 | 3354 | 0
[6 empty] | 3355 | 0 | 3355 | 0
[6 empty] | 3356 | 0 | 3356 | 0
[6 empty] | 3357 | 4576089.1233 | 3357 | 0
[6 empty] | 3358 | 0 | 3358 | 0
[6 empty] | 3359 | 4039339.5564 | 3359 | 0
[6 empty] | 3360 | 0 | 3360 | 0
[6 empty] | 3361 | 4289020.791 | 3361 | 4289020.791
[6 empty] | 3362 | 2913651.4006 | 3362 | 216027.6573
[6 empty] | 3363 | 2778574.8931 | 3363 | 0
[6 empty] | 3364 | 304323.3287 | 3364 | 304323.3287
[6 empty] | 3365 | 0 | 3365 | 0
[6 empty] | 3366 | 0 | 3366 | 0
[6 empty] | 3367 | 3289119.2805 | 3367 | 0
[6 empty] | 3368 | 513830.2798 | 3368 | 513830.2798
[6 empty] | 3369 | 0 | 3369 | 0
[6 empty] | 3370 | 0 | 3370 | 0
[6 empty] | 3371 | 209289.1829 | 3371 | 0
[6 empty] | 3372 | 1210579.7566 | 3372 | 0
[6 empty] | 3373 | 183786.7893 | 3373 | 183786.7893
[6 empty] | 3374 | 0 | 3374 | 0
[6 empty] | 3375 | 295333.8194 | 3375 | 295333.8194
[6 empty] | 3376 | 2958718.7657 | 3376 | 0
[6 empty] | 3377 | 0 | 3377 | 0
[6 empty] | 3378 | 1306900.4538 | 3378 | 0
[6 empty] | 3379 | 0 | 3379 | 0
[6 empty] | 3380 | 0 | 3380 | 0
[6 empty] | 3381 | 0 | 3381 | 0
[6 empty] | 3382 | 4852773.6652 | 3382 | 4852773.6652
[6 empty] | 3383 | 0 | 3383 | 0
[6 empty] | 3384 | 4063380.4141 | 3384 | 4063380.4141
[6 empty] | 3385 | 0 | 3385 | 0
[6 empty] | 3386 | 0 | 3386 | 0
[6 empty] | 3387 | 0 | 3387 | 0
[6 empty] | 3388 | 248924.1219 | 3388 | 248924.1219
[6 empty] | 3389 | 0 | 3389 | 0
[6 empty] | 3390 | 60447.8051 | 3390 | 60447.8051
[6 empty] | 3391 | 0 | 3391 | 0
[6 empty] | 3392 | 641687.6339 | 3392 | 473030.0913
[6 empty] | 3393 | 2473826.9094 | 3393 | 0
[6 empty] | 3394 | 98816.3711 | 3394 | 98816.3711
[6 empty] | 3395 | 0 | 3395 | 0
[6 empty] | 3396 | 0 | 3396 | 0
[6 empty] | 3397 | 0 | 3397 | 0
[6 empty] | 3398 | 0 | 3398 | 0
[6 empty] | 3399 | 204624.2873 | 3399 | 204624.2873
[6 empty] | 3400 | 399829.9389 | 3400 | 399829.9389
[6 empty] | 3401 | 0 | 3401 | 0
[6 empty] | 3402 | 332220.6488 | 3402 | 0
[6 empty] | 3403 | 199881.4452 | 3403 | 199881.4452
[6 empty] | 3404 | 0 | 3404 | 0
[6 empty] | 3405 | 2211588.2694 | 3405 | 0
[6 empty] | 3406 | 6316426.187 | 3406 | 6316426.187
[6 empty] | 3407 | 0 | 3407 | 0
[6 empty] | 3408 | 0 | 3408 | 0
[6 empty] | 3409 | 1375558.9378 | 3409 | 0
[6 empty] | 3410 | 0 | 3410 | 0
[6 empty] | 3411 | 180337.9598 | 3411 | 180337.9598
[6 empty] | 3412 | 355609.7311 | 3412 | 355609.7311
[6 empty] | 3413 | 2217039.1906 | 3413 | 2217039.1906
[6 empty] | 3414 | 754932.0443 | 3414 | 174330.4171
[6 empty] | 3415 | 0 | 3415 | 0
[6 empty] | 3416 | 9098079.2714 | 3416 | 5181272.2259
[6 empty] | 3417 | 0 | 3417 | 0
[6 empty] | 3418 | 1766988.0026 | 3418 | 0
[6 empty] | 3419 | 0 | 3419 | 0
[6 empty] | 3420 | 154948.3693 | 3420 | 0
[6 empty] | 3421 | 26045185.8296 | 3421 | 0
[6 empty] | 3422 | 1593870.233 | 3422 | 0
[6 empty] | 3423 | 1977867.2672 | 3423 | 0
[6 empty] | 3424 | 0 | 3424 | 0
[6 empty] | 3425 | 872882.2449 | 3425 | 872882.2449
[6 empty] | 3426 | 2249304.0877 | 3426 | 0
[6 empty] | 3427 | 232536.7737 | 3427 | 232536.7737
[6 empty] | 3428 | 3960759.9068 | 3428 | 0
[6 empty] | 3429 | 171924.8051 | 3429 | 171924.8051
[6 empty] | 3430 | 0 | 3430 | 0
[6 empty] | 3431 | 0 | 3431 | 0
[6 empty] | 3432 | 0 | 3432 | 0
[6 empty] | 3433 | 989693.6374 | 3433 | 989693.6374
[6 empty] | 3434 | 325885.7284 | 3434 | 157920.2515
[6 empty] | 3435 | 4260058.2374 | 3435 | 0
[6 empty] | 3436 | 0 | 3436 | 0
[6 empty] | 3437 | 0 | 3437 | 0
[6 empty] | 3438 | 0 | 3438 | 0
[6 empty] | 3439 | 374959.8151 | 3439 | 374959.8151
[6 empty] | 3440 | 292669.9251 | 3440 | 292669.9251
[6 empty] | 3441 | 0 | 3441 | 0
[6 empty] | 3442 | 240880.7738 | 3442 | 240880.7738
[6 empty] | 3443 | 142076.0363 | 3443 | 142076.0363
[6 empty] | 3444 | 0 | 3444 | 0
[6 empty] | 3445 | 0 | 3445 | 0
[6 empty] | 3446 | 392192.8663 | 3446 | 231755.5888
[6 empty] | 3447 | 3482008.9309 | 3447 | 0
[6 empty] | 3448 | 1836294.8722 | 3448 | 1836294.8722
[6 empty] | 3449 | 2554253.7617 | 3449 | 0
[6 empty] | 3450 | 0 | 3450 | 0
[6 empty] | 3451 | 0 | 3451 | 0
[6 empty] | 3452 | 0 | 3452 | 0
[6 empty] | 3453 | 0 | 3453 | 0
[6 empty] | 3454 | 1085141.4112 | 3454 | 1085141.4112
[6 empty] | 3455 | 0 | 3455 | 0
[6 empty] | 3456 | 0 | 3456 | 0
[6 empty] | 3457 | 0 | 3457 | 0
[6 empty] | 3458 | 0 | 3458 | 0
[6 empty] | 3459 | 295654.5075 | 3459 | 132267.9741
[6 empty] | 3460 | 0 | 3460 | 0
[6 empty] | 3461 | 0 | 3461 | 0
[6 empty] | 3462 | 133143.7508 | 3462 | 0
[6 empty] | 3463 | 0 | 3463 | 0
[6 empty] | 3464 | 206514.4765 | 3464 | 0
[6 empty] | 3465 | 0 | 3465 | 0
[6 empty] | 3466 | 267034.083 | 3466 | 267034.083
[6 empty] | 3467 | 514589.8478 | 3467 | 514589.8478
[6 empty] | 3468 | 0 | 3468 | 0
[6 empty] | 3469 | 234911.979 | 3469 | 234911.979
[6 empty] | 3470 | 2296971.1756 | 3470 | 0
[6 empty] | 3471 | 4608890.6543 | 3471 | 4608890.6543
[6 empty] | 3472 | 0 | 3472 | 0
[6 empty] | 3473 | 232729.6048 | 3473 | 232729.6048
[6 empty] | 3474 | 258153.3385 | 3474 | 0
[6 empty] | 3475 | 2807930.3282 | 3475 | 0
[6 empty] | 3476 | 2258318.5738 | 3476 | 0
[6 empty] | 3477 | 294362.2111 | 3477 | 294362.2111
[6 empty] | 3478 | 0 | 3478 | 0
[6 empty] | 3479 | 0 | 3479 | 0
[6 empty] | 3480 | 2584192.4942 | 3480 | 0
[6 empty] | 3481 | 280115.4282 | 3481 | 280115.4282
[6 empty] | 3482 | 0 | 3482 | 0
[6 empty] | 3483 | 1254035.4663 | 3483 | 0
[6 empty] | 3484 | 0 | 3484 | 0
[6 empty] | 3485 | 0 | 3485 | 0
[6 empty] | 3486 | 0 | 3486 | 0
[6 empty] | 3487 | 189193.3527 | 3487 | 0
[6 empty] | 3488 | 366415.4891 | 3488 | 366415.4891
[6 empty] | 3489 | 4004027.3481 | 3489 | 4004027.3481
[6 empty] | 3490 | 341560.3331 | 3490 | 341560.3331
[6 empty] | 3491 | 1533465.7421 | 3491 | 1533465.7421
[6 empty] | 3492 | 0 | 3492 | 0
[6 empty] | 3493 | 189966.8262 | 3493 | 0
[6 empty] | 3494 | 3368278.4386 | 3494 | 0
[6 empty] | 3495 | 0 | 3495 | 0
[6 empty] | 3496 | 0 | 3496 | 0
[6 empty] | 3497 | 0 | 3497 | 0
[6 empty] | 3498 | 0 | 3498 | 0
[6 empty] | 3499 | 1544681.4517 | 3499 | 0
[6 empty] | 3500 | 0 | 3500 | 0
[6 empty] | 3501 | 0 | 3501 | 0
[6 empty] | 3502 | 98748.2391 | 3502 | 98748.2391
[6 empty] | 3503 | 8138789.9731 | 3503 | 0
[6 empty] | 3504 | 0 | 3504 | 0
[6 empty] | 3505 | 967709.1593 | 3505 | 967709.1593
[6 empty] | 3506 | 0 | 3506 | 0
[6 empty] | 3507 | 204496.5929 | 3507 | 204496.5929
[6 empty] | 3508 | 0 | 3508 | 0
[6 empty] | 3509 | 3430976.4122 | 3509 | 0
[6 empty] | 3510 | 0 | 3510 | 0
[6 empty] | 3511 | 0 | 3511 | 0
[6 empty] | 3512 | 2984538.247 | 3512 | 2984538.247
[6 empty] | 3513 | 0 | 3513 | 0
[6 empty] | 3514 | 0 | 3514 | 0
[6 empty] | 3515 | 0 | 3515 | 0
[6 empty] | 3516 | 0 | 3516 | 0
[6 empty] | 3517 | 2463816.12 | 3517 | 0
[6 empty] | 3518 | 0 | 3518 | 0
[6 empty] | 3519 | 507896.2021 | 3519 | 507896.2021
[6 empty] | 3520 | 6247687.2408 | 3520 | 6247687.2408
[6 empty] | 3521 | 311786.6811 | 3521 | 311786.6811
[6 empty] | 3522 | 334464.7164 | 3522 | 334464.7164
[6 empty] | 3523 | 0 | 3523 | 0
[6 empty] | 3524 | 0 | 3524 | 0
[6 empty] | 3525 | 640776.2157 | 3525 | 640776.2157
[6 empty] | 3526 | 3837142.6737 | 3526 | 0
[6 empty] | 3527 | 390202.0193 | 3527 | 390202.0193
[6 empty] | 3528 | 1913635.3248 | 3528 | 1913635.3248
[6 empty] | 3529 | 8994795.9556 | 3529 | 0
[6 empty] | 3530 | 0 | 3530 | 0
[6 empty] | 3531 | 930585.0603 | 3531 | 930585.0603
[6 empty] | 3532 | 1714876.2618 | 3532 | 0
[6 empty] | 3533 | 0 | 3533 | 0
[6 empty] | 3534 | 0 | 3534 | 0
[6 empty] | 3535 | 0 | 3535 | 0
[6 empty] | 3536 | 3804871.792 | 3536 | 3804871.792
[6 empty] | 3537 | 0 | 3537 | 0
[6 empty] | 3538 | 9900116.3477 | 3538 | 400162.9322
[6 empty] | 3539 | 416758.1663 | 3539 | 0
[6 empty] | 3540 | 0 | 3540 | 0
[6 empty] | 3541 | 0 | 3541 | 0
[6 empty] | 3542 | 0 | 3542 | 0
[6 empty] | 3543 | 2626114.5535 | 3543 | 2626114.5535
[6 empty] | 3544 | 4752234.0036 | 3544 | 2732711.4853
[6 empty] | 3545 | 0 | 3545 | 0
[6 empty] | 3546 | 0 | 3546 | 0
[6 empty] | 3547 | 3153642.1147 | 3547 | 1625126.5917
[6 empty] | 3548 | 0 | 3548 | 0
[6 empty] | 3549 | 3121273.5085 | 3549 | 2274274.6955
[6 empty] | 3550 | 6385964.6817 | 3550 | 4970794.6695
[6 empty] | 3551 | 2915389.8954 | 3551 | 2915389.8954
[6 empty] | 3552 | 225345.7392 | 3552 | 0
[6 empty] | 3553 | 0 | 3553 | 0
[6 empty] | 3554 | 2485526.7331 | 3554 | 0
[6 empty] | 3555 | 386192.1578 | 3555 | 386192.1578
[6 empty] | 3556 | 0 | 3556 | 0
[6 empty] | 3557 | 442674.8243 | 3557 | 442674.8243
[6 empty] | 3558 | 0 | 3558 | 0
[6 empty] | 3559 | 205794.4323 | 3559 | 205794.4323
[6 empty] | 3560 | 13222550.8016 | 3560 | 0
[6 empty] | 3561 | 76971.5603 | 3561 | 76971.5603
[6 empty] | 3562 | 0 | 3562 | 0
[6 empty] | 3563 | 216901.0865 | 3563 | 0
[6 empty] | 3564 | 3234288.0459 | 3564 | 3234288.0459
[6 empty] | 3565 | 0 | 3565 | 0
[6 empty] | 3566 | 0 | 3566 | 0
[6 empty] | 3567 | 36321869.0257 | 3567 | 124531.6376
[6 empty] | 3568 | 488651.5641 | 3568 | 488651.5641
[6 empty] | 3569 | 148906.724 | 3569 | 148906.724
[6 empty] | 3570 | 415692.0774 | 3570 | 415692.0774
[6 empty] | 3571 | 0 | 3571 | 0
[6 empty] | 3572 | 201320.8569 | 3572 | 201320.8569
[6 empty] | 3573 | 0 | 3573 | 0
[6 empty] | 3574 | 3931780.3247 | 3574 | 3931780.3247
[6 empty] | 3575 | 985116.7428 | 3575 | 985116.7428
[6 empty] | 3576 | 0 | 3576 | 0
[6 empty] | 3577 | 0 | 3577 | 0
[6 empty] | 3578 | 0 | 3578 | 0
[6 empty] | 3579 | 0 | 3579 | 0
[6 empty] | 3580 | 0 | 3580 | 0
[6 empty] | 3581 | 5698877.3668 | 3581 | 5698877.3668
[6 empty] | 3582 | 204871.4753 | 3582 | 0
[6 empty] | 3583 | 3445014.519 | 3583 | 3445014.519
[6 empty] | 3584 | 602169.5636 | 3584 | 602169.5636
[6 empty] | 3585 | 0 | 3585 | 0
[6 empty] | 3586 | 0 | 3586 | 0
[6 empty] | 3587 | 0 | 3587 | 0
[6 empty] | 3588 | 479438.3459 | 3588 | 479438.3459
[6 empty] | 3589 | 885961.5588 | 3589 | 885961.5588
[6 empty] | 3590 | 2016020.1064 | 3590 | 190980.9735
[6 empty] | 3591 | 6393694.9493 | 3591 | 0
[6 empty] | 3592 | 0 | 3592 | 0
[6 empty] | 3593 | 4153258.7377 | 3593 | 4153258.7377
[6 empty] | 3594 | 0 | 3594 | 0
[6 empty] | 3595 | 3468547.7417 | 3595 | 3468547.7417
[6 empty] | 3596 | 1130884.5966 | 3596 | 905251.2563
[6 empty] | 3597 | 0 | 3597 | 0
[6 empty] | 3598 | 1270080.0307 | 3598 | 1270080.0307
[6 empty] | 3599 | 1619681.5702 | 3599 | 1619681.5702
[6 empty] | 3600 | 0 | 3600 | 0
[6 empty] | 3601 | 1162411.1154 | 3601 | 979671.4181
[6 empty] | 3602 | 1134490.2559 | 3602 | 1134490.2559
[6 empty] | 3603 | 0 | 3603 | 0
[6 empty] | 3604 | 0 | 3604 | 0
[6 empty] | 3605 | 312443.7434 | 3605 | 312443.7434
[6 empty] | 3606 | 0 | 3606 | 0
[6 empty] | 3607 | 322232.1996 | 3607 | 322232.1996
[6 empty] | 3608 | 1642181.7672 | 3608 | 1642181.7672
[6 empty] | 3609 | 0 | 3609 | 0
[6 empty] | 3610 | 0 | 3610 | 0
[6 empty] | 3611 | 3689611.3264 | 3611 | 3689611.3264
[6 empty] | 3612 | 1451974.7783 | 3612 | 820410.9135
[6 empty] | 3613 | 677681.9514 | 3613 | 677681.9514
[6 empty] | 3614 | 0 | 3614 | 0
[6 empty] | 3615 | 0 | 3615 | 0
[6 empty] | 3616 | 0 | 3616 | 0
[6 empty] | 3617 | 0 | 3617 | 0
[6 empty] | 3618 | 0 | 3618 | 0
[6 empty] | 3619 | 0 | 3619 | 0
[6 empty] | 3620 | 0 | 3620 | 0
[6 empty] | 3621 | 2078141.5564 | 3621 | 252634.5072
[6 empty] | 3622 | 298555.6355 | 3622 | 298555.6355
[6 empty] | 3623 | 493913.7105 | 3623 | 493913.7105
[6 empty] | 3624 | 0 | 3624 | 0
[6 empty] | 3625 | 11532674.5354 | 3625 | 0
[6 empty] | 3626 | 4002522.9952 | 3626 | 583981.2081
[6 empty] | 3627 | 3890938.5078 | 3627 | 222971.7109
[6 empty] | 3628 | 0 | 3628 | 0
[6 empty] | 3629 | 197885.7669 | 3629 | 197885.7669
[6 empty] | 3630 | 216125.8636 | 3630 | 216125.8636
[6 empty] | 3631 | 3457307.07 | 3631 | 0
[6 empty] | 3632 | 0 | 3632 | 0
[6 empty] | 3633 | 222795.9763 | 3633 | 222795.9763
[6 empty] | 3634 | 487349.9883 | 3634 | 487349.9883
[6 empty] | 3635 | 1063048.8422 | 3635 | 1063048.8422
[6 empty] | 3636 | 0 | 3636 | 0
[6 empty] | 3637 | 0 | 3637 | 0
[6 empty] | 3638 | 317867.04 | 3638 | 0
[6 empty] | 3639 | 3008323.2152 | 3639 | 171950.0327
[6 empty] | 3640 | 2350950.9829 | 3640 | 2350950.9829
[6 empty] | 3641 | 1529540.5794 | 3641 | 1529540.5794
[6 empty] | 3642 | 225384.0922 | 3642 | 225384.0922
[6 empty] | 3643 | 324414.2298 | 3643 | 324414.2298
[6 empty] | 3644 | 4504990.7645 | 3644 | 94191.1152
[6 empty] | 3645 | 3188899.662 | 3645 | 0
[6 empty] | 3646 | 0 | 3646 | 0
[6 empty] | 3647 | 629765.7401 | 3647 | 629765.7401
[6 empty] | 3648 | 0 | 3648 | 0
[6 empty] | 3649 | 16569729.7763 | 3649 | 0
[6 empty] | 3650 | 0 | 3650 | 0
[6 empty] | 3651 | 0 | 3651 | 0
[6 empty] | 3652 | 227498.989 | 3652 | 0
[6 empty] | 3653 | 0 | 3653 | 0
[6 empty] | 3654 | 211613.3678 | 3654 | 0
[6 empty] | 3655 | 0 | 3655 | 0
[6 empty] | 3656 | 3330129.8288 | 3656 | 2938249.0045
[6 empty] | 3657 | 0 | 3657 | 0
[6 empty] | 3658 | 171115.3903 | 3658 | 171115.3903
[6 empty] | 3659 | 0 | 3659 | 0
[6 empty] | 3660 | 0 | 3660 | 0
[6 empty] | 3661 | 0 | 3661 | 0
[6 empty] | 3662 | 216266.7884 | 3662 | 216266.7884
[6 empty] | 3663 | 181765.1855 | 3663 | 0
[6 empty] | 3664 | 0 | 3664 | 0
[6 empty] | 3665 | 226308.1185 | 3665 | 226308.1185
[6 empty] | 3666 | 0 | 3666 | 0
[6 empty] | 3667 | 286355.8639 | 3667 | 286355.8639
[6 empty] | 3668 | 0 | 3668 | 0
[6 empty] | 3669 | 0 | 3669 | 0
[6 empty] | 3670 | 3041365.0095 | 3670 | 3041365.0095
[6 empty] | 3671 | 3962499.5065 | 3671 | 3962499.5065
[6 empty] | 3672 | 294918.0239 | 3672 | 294918.0239
[6 empty] | 3673 | 0 | 3673 | 0
[6 empty] | 3674 | 7160876.8055 | 3674 | 184461.9329
[6 empty] | 3675 | 3239782.1658 | 3675 | 3239782.1658
[6 empty] | 3676 | 3023489.4381 | 3676 | 305891.0854
[6 empty] | 3677 | 497211.6665 | 3677 | 497211.6665
[6 empty] | 3678 | 0 | 3678 | 0
[6 empty] | 3679 | 1515697.6622 | 3679 | 0
[6 empty] | 3680 | 0 | 3680 | 0
[6 empty] | 3681 | 312914.3048 | 3681 | 312914.3048
[6 empty] | 3682 | 0 | 3682 | 0
[6 empty] | 3683 | 3280917.2147 | 3683 | 3280917.2147
[6 empty] | 3684 | 0 | 3684 | 0
[6 empty] | 3685 | 21758749.4377 | 3685 | 0
[6 empty] | 3686 | 862503.4531 | 3686 | 678064.1278
[6 empty] | 3687 | 1816240.2935 | 3687 | 1816240.2935
[6 empty] | 3688 | 0 | 3688 | 0
[6 empty] | 3689 | 0 | 3689 | 0
[6 empty] | 3690 | 5473629.2947 | 3690 | 849158.3163
[6 empty] | 3691 | 144486.9375 | 3691 | 144486.9375
[6 empty] | 3692 | 30616788.2562 | 3692 | 0
[6 empty] | 3693 | 0 | 3693 | 0
[6 empty] | 3694 | 0 | 3694 | 0
[6 empty] | 3695 | 356511.5036 | 3695 | 356511.5036
[6 empty] | 3696 | 772324.2679 | 3696 | 626783.5813
[6 empty] | 3697 | 0 | 3697 | 0
[6 empty] | 3698 | 0 | 3698 | 0
[6 empty] | 3699 | 4212001.7205 | 3699 | 4212001.7205
[6 empty] | 3700 | 0 | 3700 | 0
[6 empty] | 3701 | 0 | 3701 | 0
[6 empty] | 3702 | 6261901.6156 | 3702 | 0
[6 empty] | 3703 | 402851.4701 | 3703 | 0
[6 empty] | 3704 | 3948563.579 | 3704 | 222141.1872
[6 empty] | 3705 | 0 | 3705 | 0
[6 empty] | 3706 | 0 | 3706 | 0
[6 empty] | 3707 | 0 | 3707 | 0
[6 empty] | 3708 | 3665462.1861 | 3708 | 3665462.1861
[6 empty] | 3709 | 184025.3721 | 3709 | 184025.3721
[6 empty] | 3710 | 358095.4792 | 3710 | 358095.4792
[6 empty] | 3711 | 0 | 3711 | 0
[6 empty] | 3712 | 0 | 3712 | 0
[6 empty] | 3713 | 0 | 3713 | 0
[6 empty] | 3714 | 199908.5601 | 3714 | 199908.5601
[6 empty] | 3715 | 3081574.5584 | 3715 | 0
[6 empty] | 3716 | 420837.9666 | 3716 | 420837.9666
[6 empty] | 3717 | 5025263.9545 | 3717 | 5025263.9545
[6 empty] | 3718 | 0 | 3718 | 0
[6 empty] | 3719 | 1050370.7234 | 3719 | 846420.2304
[6 empty] | 3720 | 0 | 3720 | 0
[6 empty] | 3721 | 840561.3931 | 3721 | 840561.3931
[6 empty] | 3722 | 0 | 3722 | 0
[6 empty] | 3723 | 0 | 3723 | 0
[6 empty] | 3724 | 12605517.3655 | 3724 | 0
[6 empty] | 3725 | 7970846.6631 | 3725 | 5039699.6236
[6 empty] | 3726 | 485086.696 | 3726 | 173562.2558
[6 empty] | 3727 | 0 | 3727 | 0
[6 empty] | 3728 | 2479244.8803 | 3728 | 0
[6 empty] | 3729 | 453853.6066 | 3729 | 453853.6066
[6 empty] | 3730 | 0 | 3730 | 0
[6 empty] | 3731 | 226875.7015 | 3731 | 0
[6 empty] | 3732 | 0 | 3732 | 0
[6 empty] | 3733 | 0 | 3733 | 0
[6 empty] | 3734 | 249492.5832 | 3734 | 249492.5832
[6 empty] | 3735 | 5909088.1264 | 3735 | 545475.3714
[6 empty] | 3736 | 2854901.607 | 3736 | 2674571.5108
[6 empty] | 3737 | 0 | 3737 | 0
[6 empty] | 3738 | 0 | 3738 | 0
[6 empty] | 3739 | 0 | 3739 | 0
[6 empty] | 3740 | 0 | 3740 | 0
[6 empty] | 3741 | 2809306.2749 | 3741 | 2809306.2749
[6 empty] | 3742 | 277915.5887 | 3742 | 277915.5887
[6 empty] | 3743 | 5273826.5019 | 3743 | 0
[6 empty] | 3744 | 0 | 3744 | 0
[6 empty] | 3745 | 7878927.3735 | 3745 | 3415676.1376
[6 empty] | 3746 | 0 | 3746 | 0
[6 empty] | 3747 | 3389046.1402 | 3747 | 0
[6 empty] | 3748 | 0 | 3748 | 0
[6 empty] | 3749 | 0 | 3749 | 0
[6 empty] | 3750 | 0 | 3750 | 0
[6 empty] | 3751 | 163712.3586 | 3751 | 163712.3586
[6 empty] | 3752 | 1679321.11 | 3752 | 0
[6 empty] | 3753 | 2854640.4 | 3753 | 0
[6 empty] | 3754 | 0 | 3754 | 0
[6 empty] | 3755 | 4500616.2048 | 3755 | 1820859.2825
[6 empty] | 3756 | 1659779.6326 | 3756 | 269199.8259
[6 empty] | 3757 | 5696632.1975 | 3757 | 5696632.1975
[6 empty] | 3758 | 8071394.1079 | 3758 | 6553887.8117
[6 empty] | 3759 | 4072118.0865 | 3759 | 746590.3787
[6 empty] | 3760 | 0 | 3760 | 0
[6 empty] | 3761 | 0 | 3761 | 0
[6 empty] | 3762 | 201787.7715 | 3762 | 0
[6 empty] | 3763 | 0 | 3763 | 0
[6 empty] | 3764 | 175813.234 | 3764 | 175813.234
[6 empty] | 3765 | 193526.2244 | 3765 | 0
[6 empty] | 3766 | 641588.9165 | 3766 | 0
[6 empty] | 3767 | 0 | 3767 | 0
[6 empty] | 3768 | 0 | 3768 | 0
[6 empty] | 3769 | 0 | 3769 | 0
[6 empty] | 3770 | 0 | 3770 | 0
[6 empty] | 3771 | 0 | 3771 | 0
[6 empty] | 3772 | 2221448.974 | 3772 | 0
[6 empty] | 3773 | 351745.7289 | 3773 | 351745.7289
[6 empty] | 3774 | 423306.1481 | 3774 | 423306.1481
[6 empty] | 3775 | 0 | 3775 | 0
[6 empty] | 3776 | 0 | 3776 | 0
[6 empty] | 3777 | 4441216.802 | 3777 | 0
[6 empty] | 3778 | 0 | 3778 | 0
[6 empty] | 3779 | 2587749.5574 | 3779 | 2587749.5574
[6 empty] | 3780 | 0 | 3780 | 0
[6 empty] | 3781 | 5162897.8531 | 3781 | 0
[6 empty] | 3782 | 4586154.2826 | 3782 | 0
[6 empty] | 3783 | 0 | 3783 | 0
[6 empty] | 3784 | 0 | 3784 | 0
[6 empty] | 3785 | 177970.2473 | 3785 | 0
[6 empty] | 3786 | 6508039.092 | 3786 | 6508039.092
[6 empty] | 3787 | 3269298.0486 | 3787 | 0
[6 empty] | 3788 | 1497433.392 | 3788 | 1497433.392
[6 empty] | 3789 | 193997.0347 | 3789 | 193997.0347
[6 empty] | 3790 | 0 | 3790 | 0
[6 empty] | 3791 | 0 | 3791 | 0
[6 empty] | 3792 | 0 | 3792 | 0
[6 empty] | 3793 | 0 | 3793 | 0
[6 empty] | 3794 | 0 | 3794 | 0
[6 empty] | 3795 | 523795.3791 | 3795 | 523795.3791
[6 empty] | 3796 | 0 | 3796 | 0
[6 empty] | 3797 | 0 | 3797 | 0
[6 empty] | 3798 | 236167.2802 | 3798 | 236167.2802
[6 empty] | 3799 | 0 | 3799 | 0
[6 empty] | 3800 | 0 | 3800 | 0
[6 empty] | 3801 | 0 | 3801 | 0
[6 empty] | 3802 | 119275.0343 | 3802 | 119275.0343
[6 empty] | 3803 | 353300.2592 | 3803 | 353300.2592
[6 empty] | 3804 | 1204025.0595 | 3804 | 1204025.0595
[6 empty] | 3805 | 12716175.57 | 3805 | 0
[6 empty] | 3806 | 0 | 3806 | 0
[6 empty] | 3807 | 0 | 3807 | 0
[6 empty] | 3808 | 3917729.5265 | 3808 | 0
[6 empty] | 3809 | 0 | 3809 | 0
[6 empty] | 3810 | 0 | 3810 | 0
[6 empty] | 3811 | 0 | 3811 | 0
[6 empty] | 3812 | 228686.5535 | 3812 | 228686.5535
[6 empty] | 3813 | 5433958.8714 | 3813 | 5433958.8714
[6 empty] | 3814 | 4063221.6933 | 3814 | 4063221.6933
[6 empty] | 3815 | 0 | 3815 | 0
[6 empty] | 3816 | 0 | 3816 | 0
[6 empty] | 3817 | 0 | 3817 | 0
[6 empty] | 3818 | 0 | 3818 | 0
[6 empty] | 3819 | 238255.0795 | 3819 | 238255.0795
[6 empty] | 3820 | 615189.0718 | 3820 | 0
[6 empty] | 3821 | 745319.4318 | 3821 | 745319.4318
[6 empty] | 3822 | 336574.2683 | 3822 | 336574.2683
[6 empty] | 3823 | 5352925.0506 | 3823 | 4797505.4999
[6 empty] | 3824 | 227306.0991 | 3824 | 227306.0991
[6 empty] | 3825 | 453054.5323 | 3825 | 453054.5323
[6 empty] | 3826 | 15032286.1857 | 3826 | 232781.318
[6 empty] | 3827 | 0 | 3827 | 0
[6 empty] | 3828 | 0 | 3828 | 0
[6 empty] | 3829 | 2171261.7856 | 3829 | 2171261.7856
[6 empty] | 3830 | 0 | 3830 | 0
[6 empty] | 3831 | 2039127.6945 | 3831 | 2039127.6945
[6 empty] | 3832 | 197582.907 | 3832 | 197582.907
[6 empty] | 3833 | 0 | 3833 | 0
[6 empty] | 3834 | 251689.0789 | 3834 | 251689.0789
[6 empty] | 3835 | 0 | 3835 | 0
[6 empty] | 3836 | 2429199.4669 | 3836 | 0
[6 empty] | 3837 | 1149710.0627 | 3837 | 0
[6 empty] | 3838 | 0 | 3838 | 0
[6 empty] | 3839 | 1346598.9912 | 3839 | 1346598.9912
[6 empty] | 3840 | 9662384.2023 | 3840 | 9662384.2023
[6 empty] | 3841 | 0 | 3841 | 0
[6 empty] | 3842 | 210198.2547 | 3842 | 210198.2547
[6 empty] | 3843 | 2232535.611 | 3843 | 2232535.611
[6 empty] | 3844 | 0 | 3844 | 0
[6 empty] | 3845 | 0 | 3845 | 0
[6 empty] | 3846 | 4229825.2024 | 3846 | 0
[6 empty] | 3847 | 0 | 3847 | 0
[6 empty] | 3848 | 2248137.7757 | 3848 | 2248137.7757
[6 empty] | 3849 | 951918.1211 | 3849 | 741919.9572
[6 empty] | 3850 | 0 | 3850 | 0
[6 empty] | 3851 | 0 | 3851 | 0
[6 empty] | 3852 | 638139.8813 | 3852 | 638139.8813
[6 empty] | 3853 | 0 | 3853 | 0
[6 empty] | 3854 | 3481434.2057 | 3854 | 0
[6 empty] | 3855 | 292039.11 | 3855 | 292039.11
[6 empty] | 3856 | 0 | 3856 | 0
[6 empty] | 3857 | 0 | 3857 | 0
[6 empty] | 3858 | 829993.5601 | 3858 | 829993.5601
[6 empty] | 3859 | 0 | 3859 | 0
[6 empty] | 3860 | 0 | 3860 | 0
[6 empty] | 3861 | 0 | 3861 | 0
[6 empty] | 3862 | 0 | 3862 | 0
[6 empty] | 3863 | 203499.6701 | 3863 | 203499.6701
[6 empty] | 3864 | 0 | 3864 | 0
[6 empty] | 3865 | 1993142.3242 | 3865 | 0
[6 empty] | 3866 | 0 | 3866 | 0
[6 empty] | 3867 | 0 | 3867 | 0
[6 empty] | 3868 | 1718245.7509 | 3868 | 1718245.7509
[6 empty] | 3869 | 0 | 3869 | 0
[6 empty] | 3870 | 0 | 3870 | 0
[6 empty] | 3871 | 2323655.0701 | 3871 | 2323655.0701
[6 empty] | 3872 | 0 | 3872 | 0
[6 empty] | 3873 | 168279.4895 | 3873 | 168279.4895
[6 empty] | 3874 | 3544509.8531 | 3874 | 255666.2982
[6 empty] | 3875 | 3160566.2972 | 3875 | 3160566.2972
[6 empty] | 3876 | 0 | 3876 | 0
[6 empty] | 3877 | 285181.3898 | 3877 | 285181.3898
[6 empty] | 3878 | 1237968.3927 | 3878 | 0
[6 empty] | 3879 | 211192.8081 | 3879 | 0
[6 empty] | 3880 | 2010456.5791 | 3880 | 2010456.5791
[6 empty] | 3881 | 448221.6395 | 3881 | 448221.6395
[6 empty] | 3882 | 0 | 3882 | 0
[6 empty] | 3883 | 0 | 3883 | 0
[6 empty] | 3884 | 4661160.0865 | 3884 | 0
[6 empty] | 3885 | 504038.6422 | 3885 | 504038.6422
[6 empty] | 3886 | 0 | 3886 | 0
[6 empty] | 3887 | 0 | 3887 | 0
[6 empty] | 3888 | 0 | 3888 | 0
[6 empty] | 3889 | 0 | 3889 | 0
[6 empty] | 3890 | 0 | 3890 | 0
[6 empty] | 3891 | 0 | 3891 | 0
[6 empty] | 3892 | 6913018.8112 | 3892 | 6913018.8112
[6 empty] | 3893 | 248083.8328 | 3893 | 248083.8328
[6 empty] | 3894 | 317088.1008 | 3894 | 317088.1008
[6 empty] | 3895 | 0 | 3895 | 0
[6 empty] | 3896 | 0 | 3896 | 0
[6 empty] | 3897 | 225260.646 | 3897 | 225260.646
[6 empty] | 3898 | 0 | 3898 | 0
[6 empty] | 3899 | 0 | 3899 | 0
[6 empty] | 3900 | 1188878.7061 | 3900 | 1188878.7061
[6 empty] | 3901 | 0 | 3901 | 0
[6 empty] | 3902 | 185383.8606 | 3902 | 185383.8606
[6 empty] | 3903 | 0 | 3903 | 0
[6 empty] | 3904 | 3233495.5144 | 3904 | 0
[6 empty] | 3905 | 23587999.2498 | 3905 | 0
[6 empty] | 3906 | 11379502.5545 | 3906 | 0
[6 empty] | 3907 | 0 | 3907 | 0
[6 empty] | 3908 | 0 | 3908 | 0
[6 empty] | 3909 | 4613824.9578 | 3909 | 4613824.9578
[6 empty] | 3910 | 2895770.5279 | 3910 | 0
[6 empty] | 3911 | 3717428.228 | 3911 | 3717428.228
[6 empty] | 3912 | 146148.1167 | 3912 | 146148.1167
[6 empty] | 3913 | 0 | 3913 | 0
[6 empty] | 3914 | 0 | 3914 | 0
[6 empty] | 3915 | 442093.7619 | 3915 | 442093.7619
[6 empty] | 3916 | 2153772.5367 | 3916 | 0
[6 empty] | 3917 | 151244.3165 | 3917 | 151244.3165
[6 empty] | 3918 | 0 | 3918 | 0
[6 empty] | 3919 | 1089312.8527 | 3919 | 1089312.8527
[6 empty] | 3920 | 3404454.1686 | 3920 | 0
[6 empty] | 3921 | 3754273.1466 | 3921 | 0
[6 empty] | 3922 | 0 | 3922 | 0
[6 empty] | 3923 | 1980661.5903 | 3923 | 357899.0198
[6 empty] | 3924 | 228033.4168 | 3924 | 228033.4168
[6 empty] | 3925 | 0 | 3925 | 0
[6 empty] | 3926 | 300155.5296 | 3926 | 300155.5296
[6 empty] | 3927 | 2758374.0241 | 3927 | 2758374.0241
[6 empty] | 3928 | 192935.0264 | 3928 | 192935.0264
[6 empty] | 3929 | 4183438.5931 | 3929 | 3951422.9995
[6 empty] | 3930 | 315843.5634 | 3930 | 0
[6 empty] | 3931 | 2838405.3185 | 3931 | 157750.1125
[6 empty] | 3932 | 0 | 3932 | 0
[6 empty] | 3933 | 0 | 3933 | 0
[6 empty] | 3934 | 0 | 3934 | 0
[6 empty] | 3935 | 2439125.6943 | 3935 | 143070.7313
[6 empty] | 3936 | 0 | 3936 | 0
[6 empty] | 3937 | 1198757.1956 | 3937 | 1198757.1956
[6 empty] | 3938 | 0 | 3938 | 0
[6 empty] | 3939 | 3706775.3893 | 3939 | 3706775.3893
[6 empty] | 3940 | 24046017.5166 | 3940 | 0
[6 empty] | 3941 | 6405419.5939 | 3941 | 3524956.8284
[6 empty] | 3942 | 1362205.9021 | 3942 | 0
[6 empty] | 3943 | 0 | 3943 | 0
[6 empty] | 3944 | 0 | 3944 | 0
[6 empty] | 3945 | 2045568.2375 | 3945 | 2045568.2375
[6 empty] | 3946 | 808978.6675 | 3946 | 808978.6675
[6 empty] | 3947 | 0 | 3947 | 0
[6 empty] | 3948 | 0 | 3948 | 0
[6 empty] | 3949 | 2862775.5518 | 3949 | 2862775.5518
[6 empty] | 3950 | 0 | 3950 | 0
[6 empty] | 3951 | 2118787.4788 | 3951 | 0
[6 empty] | 3952 | 481915.9333 | 3952 | 481915.9333
[6 empty] | 3953 | 0 | 3953 | 0
[6 empty] | 3954 | 0 | 3954 | 0
[6 empty] | 3955 | 0 | 3955 | 0
[6 empty] | 3956 | 0 | 3956 | 0
[6 empty] | 3957 | 0 | 3957 | 0
[6 empty] | 3958 | 0 | 3958 | 0
[6 empty] | 3959 | 219997.6105 | 3959 | 219997.6105
[6 empty] | 3960 | 0 | 3960 | 0
[6 empty] | 3961 | 240583.8018 | 3961 | 240583.8018
[6 empty] | 3962 | 0 | 3962 | 0
[6 empty] | 3963 | 778580.7104 | 3963 | 778580.7104
[6 empty] | 3964 | 280623.8577 | 3964 | 0
[6 empty] | 3965 | 3476961.3587 | 3965 | 3476961.3587
[6 empty] | 3966 | 2966004.2686 | 3966 | 0
[6 empty] | 3967 | 0 | 3967 | 0
[6 empty] | 3968 | 3848323.8184 | 3968 | 3026086.0207
[6 empty] | 3969 | 4013891.0975 | 3969 | 4013891.0975
[6 empty] | 3970 | 4912185.6073 | 3970 | 0
[6 empty] | 3971 | 1879875.0985 | 3971 | 431109.5347
[6 empty] | 3972 | 734994.325 | 3972 | 734994.325
[6 empty] | 3973 | 0 | 3973 | 0
[6 empty] | 3974 | 8577626.2988 | 3974 | 0
[6 empty] | 3975 | 0 | 3975 | 0
[6 empty] | 3976 | 1183205.4209 | 3976 | 1183205.4209
[6 empty] | 3977 | 0 | 3977 | 0
[6 empty] | 3978 | 0 | 3978 | 0
[6 empty] | 3979 | 0 | 3979 | 0
[6 empty] | 3980 | 0 | 3980 | 0
[6 empty] | 3981 | 0 | 3981 | 0
[6 empty] | 3982 | 0 | 3982 | 0
[6 empty] | 3983 | 0 | 3983 | 0
[6 empty] | 3984 | 0 | 3984 | 0
[6 empty] | 3985 | 0 | 3985 | 0
[6 empty] | 3986 | 4354728.0918 | 3986 | 4354728.0918
[6 empty] | 3987 | 200432.4086 | 3987 | 0
[6 empty] | 3988 | 0 | 3988 | 0
[6 empty] | 3989 | 0 | 3989 | 0
[6 empty] | 3990 | 0 | 3990 | 0
[6 empty] | 3991 | 0 | 3991 | 0
[6 empty] | 3992 | 29415302.742 | 3992 | 478048.3294
[6 empty] | 3993 | 0 | 3993 | 0
[6 empty] | 3994 | 2320554.5358 | 3994 | 2320554.5358
[6 empty] | 3995 | 0 | 3995 | 0
[6 empty] | 3996 | 156876.0409 | 3996 | 156876.0409
[6 empty] | 3997 | 0 | 3997 | 0
[6 empty] | 3998 | 0 | 3998 | 0
[6 empty] | 3999 | 1804843.7591 | 3999 | 0
[6 empty] | 4000 | 4652558.3408 | 4000 | 0
[6 empty] | 4001 | 0 | 4001 | 0
[6 empty] | 4002 | 0 | 4002 | 0
[6 empty] | 4003 | 243503.8286 | 4003 | 0
[6 empty] | 4004 | 0 | 4004 | 0
[6 empty] | 4005 | 2951650.6219 | 4005 | 343622.6103
[6 empty] | 4006 | 0 | 4006 | 0
[6 empty] | 4007 | 0 | 4007 | 0
[6 empty] | 4008 | 0 | 4008 | 0
[6 empty] | 4009 | 7574766.3378 | 4009 | 4781998.8935
[6 empty] | 4010 | 0 | 4010 | 0
[6 empty] | 4011 | 0 | 4011 | 0
[6 empty] | 4012 | 3751079.9773 | 4012 | 412101.5213
[6 empty] | 4013 | 3018863.5192 | 4013 | 3018863.5192
[6 empty] | 4014 | 3004373.0078 | 4014 | 0
[6 empty] | 4015 | 1859149.7545 | 4015 | 0
[6 empty] | 4016 | 0 | 4016 | 0
[6 empty] | 4017 | 4819344.7987 | 4017 | 4819344.7987
[6 empty] | 4018 | 1115600.0648 | 4018 | 460005.408
[6 empty] | 4019 | 0 | 4019 | 0
[6 empty] | 4020 | 937674.9341 | 4020 | 937674.9341
[6 empty] | 4021 | 282371.2131 | 4021 | 282371.2131
[6 empty] | 4022 | 0 | 4022 | 0
[6 empty] | 4023 | 0 | 4023 | 0
[6 empty] | 4024 | 0 | 4024 | 0
[6 empty] | 4025 | 191499.2812 | 4025 | 191499.2812
[6 empty] | 4026 | 1477963.1846 | 4026 | 1477963.1846
[6 empty] | 4027 | 0 | 4027 | 0
[6 empty] | 4028 | 0 | 4028 | 0
[6 empty] | 4029 | 0 | 4029 | 0
[6 empty] | 4030 | 0 | 4030 | 0
[6 empty] | 4031 | 2120338.222 | 4031 | 0
[6 empty] | 4032 | 491321.8879 | 4032 | 491321.8879
[6 empty] | 4033 | 331501.3308 | 4033 | 331501.3308
[6 empty] | 4034 | 0 | 4034 | 0
[6 empty] | 4035 | 235164.3215 | 4035 | 235164.3215
[6 empty] | 4036 | 1688826.8251 | 4036 | 1688826.8251
[6 empty] | 4037 | 0 | 4037 | 0
[6 empty] | 4038 | 243070.6663 | 4038 | 243070.6663
[6 empty] | 4039 | 414287.2081 | 4039 | 414287.2081
[6 empty] | 4040 | 0 | 4040 | 0
[6 empty] | 4041 | 275812.7063 | 4041 | 275812.7063
[6 empty] | 4042 | 0 | 4042 | 0
[6 empty] | 4043 | 2592069.2429 | 4043 | 2592069.2429
[6 empty] | 4044 | 3232480.8299 | 4044 | 3232480.8299
[6 empty] | 4045 | 0 | 4045 | 0
[6 empty] | 4046 | 243231.7004 | 4046 | 0
[6 empty] | 4047 | 0 | 4047 | 0
[6 empty] | 4048 | 880662.4927 | 4048 | 0
[6 empty] | 4049 | 3148740.4068 | 4049 | 636606.9281
[6 empty] | 4050 | 0 | 4050 | 0
[6 empty] | 4051 | 2345935.1803 | 4051 | 0
[6 empty] | 4052 | 312036.6192 | 4052 | 312036.6192
[6 empty] | 4053 | 0 | 4053 | 0
[6 empty] | 4054 | 25977719.8917 | 4054 | 25977719.8917
[6 empty] | 4055 | 181831.4034 | 4055 | 181831.4034
[6 empty] | 4056 | 4186133.1985 | 4056 | 450955.6618
[6 empty] | 4057 | 0 | 4057 | 0
[6 empty] | 4058 | 2885139.0283 | 4058 | 2616270.3708
[6 empty] | 4059 | 7424209.5997 | 4059 | 7424209.5997
[6 empty] | 4060 | 1089739.6222 | 4060 | 1089739.6222
[6 empty] | 4061 | 130643.0566 | 4061 | 130643.0566
[6 empty] | 4062 | 4645970.6709 | 4062 | 4645970.6709
[6 empty] | 4063 | 0 | 4063 | 0
[6 empty] | 4064 | 0 | 4064 | 0
[6 empty] | 4065 | 0 | 4065 | 0
[6 empty] | 4066 | 3781874.9962 | 4066 | 244145.363
[6 empty] | 4067 | 0 | 4067 | 0
[6 empty] | 4068 | 9420261.7668 | 4068 | 5032553.3492
[6 empty] | 4069 | 0 | 4069 | 0
[6 empty] | 4070 | 4640010.5756 | 4070 | 4640010.5756
[6 empty] | 4071 | 7931904.2926 | 4071 | 7931904.2926
[6 empty] | 4072 | 0 | 4072 | 0
[6 empty] | 4073 | 1083730.0284 | 4073 | 0
[6 empty] | 4074 | 0 | 4074 | 0
[6 empty] | 4075 | 0 | 4075 | 0
[6 empty] | 4076 | 721386.4362 | 4076 | 721386.4362
[6 empty] | 4077 | 0 | 4077 | 0
[6 empty] | 4078 | 2912926.4528 | 4078 | 2912926.4528
[6 empty] | 4079 | 3215456.4808 | 4079 | 3215456.4808
[6 empty] | 4080 | 0 | 4080 | 0
[6 empty] | 4081 | 0 | 4081 | 0
[6 empty] | 4082 | 399225.6376 | 4082 | 399225.6376
[6 empty] | 4083 | 0 | 4083 | 0
[6 empty] | 4084 | 0 | 4084 | 0
[6 empty] | 4085 | 0 | 4085 | 0
[6 empty] | 4086 | 509346.4401 | 4086 | 509346.4401
[6 empty] | 4087 | 0 | 4087 | 0
[6 empty] | 4088 | 150412.2415 | 4088 | 150412.2415
[6 empty] | 4089 | 1850038.2146 | 4089 | 1850038.2146
[6 empty] | 4090 | 7746434.487 | 4090 | 7746434.487
[6 empty] | 4091 | 2174964.0427 | 4091 | 2174964.0427
[6 empty] | 4092 | 10161467.3829 | 4092 | 0
[6 empty] | 4093 | 1094250.5036 | 4093 | 1094250.5036
[6 empty] | 4094 | 2321079.2263 | 4094 | 213165.7721
[6 empty] | 4095 | 0 | 4095 | 0
[6 empty] | 4096 | 3824367.5006 | 4096 | 3824367.5006
[6 empty] | 4097 | 0 | 4097 | 0
[6 empty] | 4098 | 717459.9482 | 4098 | 717459.9482
[6 empty] | 4099 | 270674.0409 | 4099 | 0
[6 empty] | 4100 | 413549.9831 | 4100 | 413549.9831
[6 empty] | 4101 | 3055056.7296 | 4101 | 3055056.7296
[6 empty] | 4102 | 1636370.0626 | 4102 | 1636370.0626
[6 empty] | 4103 | 0 | 4103 | 0
[6 empty] | 4104 | 18608308.5255 | 4104 | 4687913.9725
[6 empty] | 4105 | 0 | 4105 | 0
[6 empty] | 4106 | 0 | 4106 | 0
[6 empty] | 4107 | 0 | 4107 | 0
[6 empty] | 4108 | 0 | 4108 | 0
[6 empty] | 4109 | 0 | 4109 | 0
[6 empty] | 4110 | 0 | 4110 | 0
[6 empty] | 4111 | 0 | 4111 | 0
[6 empty] | 4112 | 0 | 4112 | 0
[6 empty] | 4113 | 562313.5401 | 4113 | 334738.025
[6 empty] | 4114 | 875243.4064 | 4114 | 875243.4064
[6 empty] | 4115 | 300175.7679 | 4115 | 300175.7679
[6 empty] | 4116 | 680219.2032 | 4116 | 680219.2032
[6 empty] | 4117 | 0 | 4117 | 0
[6 empty] | 4118 | 260469.7865 | 4118 | 260469.7865
[6 empty] | 4119 | 231718.7612 | 4119 | 0
[6 empty] | 4120 | 0 | 4120 | 0
[6 empty] | 4121 | 0 | 4121 | 0
[6 empty] | 4122 | 0 | 4122 | 0
[6 empty] | 4123 | 125935.2033 | 4123 | 125935.2033
[6 empty] | 4124 | 2778873.8498 | 4124 | 2778873.8498
[6 empty] | 4125 | 0 | 4125 | 0
[6 empty] | 4126 | 503152.0073 | 4126 | 246186.8064
[6 empty] | 4127 | 209147.0022 | 4127 | 209147.0022
[6 empty] | 4128 | 312760.1477 | 4128 | 0
[6 empty] | 4129 | 6421388.8365 | 4129 | 3215910.4539
[6 empty] | 4130 | 53244842.7689 | 4130 | 0
[6 empty] | 4131 | 306729.011 | 4131 | 306729.011
[6 empty] | 4132 | 0 | 4132 | 0
[6 empty] | 4133 | 0 | 4133 | 0
[6 empty] | 4134 | 0 | 4134 | 0
[6 empty] | 4135 | 5641892.2837 | 4135 | 5641892.2837
[6 empty] | 4136 | 0 | 4136 | 0
[6 empty] | 4137 | 0 | 4137 | 0
[6 empty] | 4138 | 0 | 4138 | 0
[6 empty] | 4139 | 3543241.0671 | 4139 | 3543241.0671
[6 empty] | 4140 | 0 | 4140 | 0
[6 empty] | 4141 | 0 | 4141 | 0
[6 empty] | 4142 | 502362.4207 | 4142 | 502362.4207
[6 empty] | 4143 | 6746882.1297 | 4143 | 1430538.3512
[6 empty] | 4144 | 0 | 4144 | 0
[6 empty] | 4145 | 0 | 4145 | 0
[6 empty] | 4146 | 0 | 4146 | 0
[6 empty] | 4147 | 4432014.0853 | 4147 | 4432014.0853
[6 empty] | 4148 | 748602.4619 | 4148 | 748602.4619
[6 empty] | 4149 | 1217293.2832 | 4149 | 1217293.2832
[6 empty] | 4150 | 2728537.1655 | 4150 | 2728537.1655
[6 empty] | 4151 | 3076091.3259 | 4151 | 3076091.3259
[6 empty] | 4152 | 285006.7186 | 4152 | 285006.7186
[6 empty] | 4153 | 3246360.7074 | 4153 | 3246360.7074
[6 empty] | 4154 | 2911761.1831 | 4154 | 2911761.1831
[6 empty] | 4155 | 0 | 4155 | 0
[6 empty] | 4156 | 0 | 4156 | 0
[6 empty] | 4157 | 352214.1241 | 4157 | 352214.1241
[6 empty] | 4158 | 0 | 4158 | 0
[6 empty] | 4159 | 0 | 4159 | 0
[6 empty] | 4160 | 146101.51 | 4160 | 146101.51
[6 empty] | 4161 | 0 | 4161 | 0
[6 empty] | 4162 | 0 | 4162 | 0
[6 empty] | 4163 | 0 | 4163 | 0
[6 empty] | 4164 | 198996.9249 | 4164 | 0
[6 empty] | 4165 | 561182.0664 | 4165 | 561182.0664
[6 empty] | 4166 | 0 | 4166 | 0
[6 empty] | 4167 | 0 | 4167 | 0
[6 empty] | 4168 | 4739094.4246 | 4168 | 0
[6 empty] | 4169 | 5419853.7467 | 4169 | 0
[6 empty] | 4170 | 1723273.2935 | 4170 | 1723273.2935
[6 empty] | 4171 | 3506371.2966 | 4171 | 0
[6 empty] | 4172 | 0 | 4172 | 0
[6 empty] | 4173 | 0 | 4173 | 0
[6 empty] | 4174 | 0 | 4174 | 0
[6 empty] | 4175 | 593494.2758 | 4175 | 0
[6 empty] | 4176 | 212857.2991 | 4176 | 0
[6 empty] | 4177 | 2471916.1319 | 4177 | 0
[6 empty] | 4178 | 176162.1643 | 4178 | 176162.1643
[6 empty] | 4179 | 0 | 4179 | 0
[6 empty] | 4180 | 5907112.1047 | 4180 | 3789099.0228
[6 empty] | 4181 | 0 | 4181 | 0
[6 empty] | 4182 | 3239272.9232 | 4182 | 0
[6 empty] | 4183 | 0 | 4183 | 0
[6 empty] | 4184 | 0 | 4184 | 0
[6 empty] | 4185 | 0 | 4185 | 0
[6 empty] | 4186 | 1005116.0908 | 4186 | 0
[6 empty] | 4187 | 782603.6161 | 4187 | 782603.6161
[6 empty] | 4188 | 7098373.2903 | 4188 | 6935565.3597
[6 empty] | 4189 | 2600902.671 | 4189 | 2600902.671
[6 empty] | 4190 | 0 | 4190 | 0
[6 empty] | 4191 | 1306642.5751 | 4191 | 0
[6 empty] | 4192 | 1612129.2257 | 4192 | 1612129.2257
[6 empty] | 4193 | 618774.3352 | 4193 | 402260.9086
[6 empty] | 4194 | 191183.5437 | 4194 | 191183.5437
[6 empty] | 4195 | 250622.5771 | 4195 | 0
[6 empty] | 4196 | 0 | 4196 | 0
[6 empty] | 4197 | 0 | 4197 | 0
[6 empty] | 4198 | 1874141.9016 | 4198 | 212831.0739
[6 empty] | 4199 | 0 | 4199 | 0
[6 empty] | 4200 | 435315.2924 | 4200 | 435315.2924
[6 empty] | 4201 | 7755081.3888 | 4201 | 772561.0711
[6 empty] | 4202 | 0 | 4202 | 0
[6 empty] | 4203 | 0 | 4203 | 0
[6 empty] | 4204 | 0 | 4204 | 0
[6 empty] | 4205 | 0 | 4205 | 0
[6 empty] | 4206 | 3072947.7605 | 4206 | 0
[6 empty] | 4207 | 1280893.0542 | 4207 | 1280893.0542
[6 empty] | 4208 | 198354.5258 | 4208 | 0
[6 empty] | 4209 | 1047447.5115 | 4209 | 851885.9537
[6 empty] | 4210 | 391246.2822 | 4210 | 391246.2822
[6 empty] | 4211 | 0 | 4211 | 0
[6 empty] | 4212 | 2983294.8736 | 4212 | 2983294.8736
[6 empty] | 4213 | 0 | 4213 | 0
[6 empty] | 4214 | 0 | 4214 | 0
[6 empty] | 4215 | 0 | 4215 | 0
[6 empty] | 4216 | 0 | 4216 | 0
[6 empty] | 4217 | 3174048.2571 | 4217 | 0
[6 empty] | 4218 | 0 | 4218 | 0
[6 empty] | 4219 | 0 | 4219 | 0
[6 empty] | 4220 | 310679.4964 | 4220 | 0
[6 empty] | 4221 | 259621.9277 | 4221 | 259621.9277
[6 empty] | 4222 | 876876.6686 | 4222 | 0
[6 empty] | 4223 | 2551917.2222 | 4223 | 0
[6 empty] | 4224 | 0 | 4224 | 0
[6 empty] | 4225 | 12876053.9756 | 4225 | 0
[6 empty] | 4226 | 0 | 4226 | 0
[6 empty] | 4227 | 231235.9933 | 4227 | 0
[6 empty] | 4228 | 0 | 4228 | 0
[6 empty] | 4229 | 0 | 4229 | 0
[6 empty] | 4230 | 252256.7909 | 4230 | 0
[6 empty] | 4231 | 2032189.0754 | 4231 | 283965.2374
[6 empty] | 4232 | 0 | 4232 | 0
[6 empty] | 4233 | 0 | 4233 | 0
[6 empty] | 4234 | 448151.0782 | 4234 | 448151.0782
[6 empty] | 4235 | 1292000.0619 | 4235 | 280972.4794
[6 empty] | 4236 | 1896828.0998 | 4236 | 1896828.0998
[6 empty] | 4237 | 0 | 4237 | 0
[6 empty] | 4238 | 1759409.7679 | 4238 | 1759409.7679
[6 empty] | 4239 | 0 | 4239 | 0
[6 empty] | 4240 | 0 | 4240 | 0
[6 empty] | 4241 | 0 | 4241 | 0
[6 empty] | 4242 | 698008.3138 | 4242 | 698008.3138
[6 empty] | 4243 | 2996543.7894 | 4243 | 2996543.7894
[6 empty] | 4244 | 0 | 4244 | 0
[6 empty] | 4245 | 936274.8494 | 4245 | 936274.8494
[6 empty] | 4246 | 202511.4609 | 4246 | 0
[6 empty] | 4247 | 3854162.742 | 4247 | 3854162.742
[6 empty] | 4248 | 265208.785 | 4248 | 265208.785
[6 empty] | 4249 | 0 | 4249 | 0
[6 empty] | 4250 | 0 | 4250 | 0
[6 empty] | 4251 | 466415.4789 | 4251 | 466415.4789
[6 empty] | 4252 | 0 | 4252 | 0
[6 empty] | 4253 | 4513447.9297 | 4253 | 4513447.9297
[6 empty] | 4254 | 260170.619 | 4254 | 260170.619
[6 empty] | 4255 | 0 | 4255 | 0
[6 empty] | 4256 | 0 | 4256 | 0
[6 empty] | 4257 | 0 | 4257 | 0
[6 empty] | 4258 | 110235.8455 | 4258 | 110235.8455
[6 empty] | 4259 | 3554831.7396 | 4259 | 0
[6 empty] | 4260 | 0 | 4260 | 0
[6 empty] | 4261 | 3061814.4148 | 4261 | 3061814.4148
[6 empty] | 4262 | 191995.7515 | 4262 | 0
[6 empty] | 4263 | 0 | 4263 | 0
[6 empty] | 4264 | 0 | 4264 | 0
[6 empty] | 4265 | 3973771.0458 | 4265 | 274729.1827
[6 empty] | 4266 | 4051620.3224 | 4266 | 0
[6 empty] | 4267 | 0 | 4267 | 0
[6 empty] | 4268 | 0 | 4268 | 0
[6 empty] | 4269 | 222549.9945 | 4269 | 222549.9945
[6 empty] | 4270 | 1180969.8105 | 4270 | 1180969.8105
[6 empty] | 4271 | 957334.0104 | 4271 | 0
[6 empty] | 4272 | 0 | 4272 | 0
[6 empty] | 4273 | 0 | 4273 | 0
[6 empty] | 4274 | 10886946.8145 | 4274 | 0
[6 empty] | 4275 | 0 | 4275 | 0
[6 empty] | 4276 | 0 | 4276 | 0
[6 empty] | 4277 | 2789761.1374 | 4277 | 0
[6 empty] | 4278 | 0 | 4278 | 0
[6 empty] | 4279 | 4112585.8909 | 4279 | 0
[6 empty] | 4280 | 1853109.7419 | 4280 | 0
[6 empty] | 4281 | 0 | 4281 | 0
[6 empty] | 4282 | 0 | 4282 | 0
[6 empty] | 4283 | 915034.3908 | 4283 | 915034.3908
[6 empty] | 4284 | 0 | 4284 | 0
[6 empty] | 4285 | 267557.0006 | 4285 | 267557.0006
[6 empty] | 4286 | 0 | 4286 | 0
[6 empty] | 4287 | 0 | 4287 | 0
[6 empty] | 4288 | 1855757.4085 | 4288 | 0
[6 empty] | 4289 | 0 | 4289 | 0
[6 empty] | 4290 | 0 | 4290 | 0
[6 empty] | 4291 | 0 | 4291 | 0
[6 empty] | 4292 | 5194881.9646 | 4292 | 0
[6 empty] | 4293 | 0 | 4293 | 0
[6 empty] | 4294 | 336647.3873 | 4294 | 0
[6 empty] | 4295 | 1969777.6072 | 4295 | 0
[6 empty] | 4296 | 2459370.2855 | 4296 | 0
[6 empty] | 4297 | 0 | 4297 | 0
[6 empty] | 4298 | 5057325.6162 | 4298 | 5057325.6162
[6 empty] | 4299 | 0 | 4299 | 0
[6 empty] | 4300 | 3429363.2065 | 4300 | 0
[6 empty] | 4301 | 0 | 4301 | 0
[6 empty] | 4302 | 0 | 4302 | 0
[6 empty] | 4303 | 182054.2875 | 4303 | 0
[6 empty] | 4304 | 0 | 4304 | 0
[6 empty] | 4305 | 0 | 4305 | 0
[6 empty] | 4306 | 7223968.542 | 4306 | 0
[6 empty] | 4307 | 4132354.5212 | 4307 | 4132354.5212
[6 empty] | 4308 | 480718.3194 | 4308 | 480718.3194
[6 empty] | 4309 | 0 | 4309 | 0
[6 empty] | 4310 | 0 | 4310 | 0
[6 empty] | 4311 | 18310711.7884 | 4311 | 0
[6 empty] | 4312 | 0 | 4312 | 0
[6 empty] | 4313 | 201198.9274 | 4313 | 201198.9274
[6 empty] | 4314 | 0 | 4314 | 0
[6 empty] | 4315 | 123489.5841 | 4315 | 123489.5841
[6 empty] | 4316 | 254827.0188 | 4316 | 254827.0188
[6 empty] | 4317 | 320132.8705 | 4317 | 320132.8705
[6 empty] | 4318 | 0 | 4318 | 0
[6 empty] | 4319 | 0 | 4319 | 0
[6 empty] | 4320 | 329225.4059 | 4320 | 329225.4059
[6 empty] | 4321 | 3535047.6249 | 4321 | 1938798.1088
[6 empty] | 4322 | 0 | 4322 | 0
[6 empty] | 4323 | 0 | 4323 | 0
[6 empty] | 4324 | 0 | 4324 | 0
[6 empty] | 4325 | 0 | 4325 | 0
[6 empty] | 4326 | 0 | 4326 | 0
[6 empty] | 4327 | 280968.5376 | 4327 | 280968.5376
[6 empty] | 4328 | 0 | 4328 | 0
[6 empty] | 4329 | 0 | 4329 | 0
[6 empty] | 4330 | 0 | 4330 | 0
[6 empty] | 4331 | 419541.1116 | 4331 | 419541.1116
[6 empty] | 4332 | 267569.4811 | 4332 | 267569.4811
[6 empty] | 4333 | 6452771.9797 | 4333 | 6452771.9797
[6 empty] | 4334 | 0 | 4334 | 0
[6 empty] | 4335 | 0 | 4335 | 0
[6 empty] | 4336 | 3307034.5857 | 4336 | 3307034.5857
[6 empty] | 4337 | 0 | 4337 | 0
[6 empty] | 4338 | 0 | 4338 | 0
[6 empty] | 4339 | 2667113.4482 | 4339 | 235610.5005
[6 empty] | 4340 | 2328083.6032 | 4340 | 0
[6 empty] | 4341 | 0 | 4341 | 0
[6 empty] | 4342 | 0 | 4342 | 0
[6 empty] | 4343 | 0 | 4343 | 0
[6 empty] | 4344 | 5591785.505 | 4344 | 5591785.505
[6 empty] | 4345 | 0 | 4345 | 0
[6 empty] | 4346 | 2339669.8551 | 4346 | 0
[6 empty] | 4347 | 0 | 4347 | 0
[6 empty] | 4348 | 0 | 4348 | 0
[6 empty] | 4349 | 0 | 4349 | 0
[6 empty] | 4350 | 0 | 4350 | 0
[6 empty] | 4351 | 208173.8605 | 4351 | 0
[6 empty] | 4352 | 2393475.2305 | 4352 | 0
[6 empty] | 4353 | 2690222.9463 | 4353 | 0
[6 empty] | 4354 | 0 | 4354 | 0
[6 empty] | 4355 | 0 | 4355 | 0
[6 empty] | 4356 | 4515319.1097 | 4356 | 4515319.1097
[6 empty] | 4357 | 227051.0806 | 4357 | 227051.0806
[6 empty] | 4358 | 2782719.2363 | 4358 | 393513.2943
[6 empty] | 4359 | 0 | 4359 | 0
[6 empty] | 4360 | 204135.9825 | 4360 | 0
[6 empty] | 4361 | 15238753.7338 | 4361 | 2554591.3889
[6 empty] | 4362 | 6375795.3674 | 4362 | 6375795.3674
[6 empty] | 4363 | 0 | 4363 | 0
[6 empty] | 4364 | 0 | 4364 | 0
[6 empty] | 4365 | 5752125.1456 | 4365 | 204224.5678
[6 empty] | 4366 | 0 | 4366 | 0
[6 empty] | 4367 | 0 | 4367 | 0
[6 empty] | 4368 | 0 | 4368 | 0
[6 empty] | 4369 | 2652151.9632 | 4369 | 2652151.9632
[6 empty] | 4370 | 0 | 4370 | 0
[6 empty] | 4371 | 0 | 4371 | 0
[6 empty] | 4372 | 0 | 4372 | 0
[6 empty] | 4373 | 0 | 4373 | 0
[6 empty] | 4374 | 0 | 4374 | 0
[6 empty] | 4375 | 0 | 4375 | 0
[6 empty] | 4376 | 3461241.3931 | 4376 | 0
[6 empty] | 4377 | 144408.1378 | 4377 | 144408.1378
[6 empty] | 4378 | 0 | 4378 | 0
[6 empty] | 4379 | 224189.4075 | 4379 | 0
[6 empty] | 4380 | 2231481.0892 | 4380 | 2231481.0892
[6 empty] | 4381 | 826915.1577 | 4381 | 826915.1577
[6 empty] | 4382 | 3336977.4663 | 4382 | 3336977.4663
[6 empty] | 4383 | 356614.3678 | 4383 | 356614.3678
[6 empty] | 4384 | 0 | 4384 | 0
[6 empty] | 4385 | 0 | 4385 | 0
[6 empty] | 4386 | 502159.8678 | 4386 | 502159.8678
[6 empty] | 4387 | 0 | 4387 | 0
[6 empty] | 4388 | 240269.3687 | 4388 | 0
[6 empty] | 4389 | 4591835.5686 | 4389 | 3360148.0442
[6 empty] | 4390 | 0 | 4390 | 0
[6 empty] | 4391 | 589335.3071 | 4391 | 589335.3071
[6 empty] | 4392 | 6874498.0695 | 4392 | 293458.0582
[6 empty] | 4393 | 0 | 4393 | 0
[6 empty] | 4394 | 2678191.4099 | 4394 | 0
[6 empty] | 4395 | 4164514.2757 | 4395 | 0
[6 empty] | 4396 | 0 | 4396 | 0
[6 empty] | 4397 | 0 | 4397 | 0
[6 empty] | 4398 | 161527.3772 | 4398 | 0
[6 empty] | 4399 | 0 | 4399 | 0
[6 empty] | 4400 | 202489.9408 | 4400 | 202489.9408
[6 empty] | 4401 | 3111414.4086 | 4401 | 0
[6 empty] | 4402 | 225973.122 | 4402 | 225973.122
[6 empty] | 4403 | 2901658.3243 | 4403 | 187816.7891
[6 empty] | 4404 | 0 | 4404 | 0
[6 empty] | 4405 | 207465.9854 | 4405 | 207465.9854
[6 empty] | 4406 | 175968.7282 | 4406 | 175968.7282
[6 empty] | 4407 | 153475.4426 | 4407 | 153475.4426
[6 empty] | 4408 | 1335524.3492 | 4408 | 0
[6 empty] | 4409 | 0 | 4409 | 0
[6 empty] | 4410 | 0 | 4410 | 0
[6 empty] | 4411 | 2574856.8396 | 4411 | 0
[6 empty] | 4412 | 951933.9631 | 4412 | 951933.9631
[6 empty] | 4413 | 186615.0874 | 4413 | 186615.0874
[6 empty] | 4414 | 4861735.7219 | 4414 | 0
[6 empty] | 4415 | 0 | 4415 | 0
[6 empty] | 4416 | 662336.6761 | 4416 | 662336.6761
[6 empty] | 4417 | 0 | 4417 | 0
[6 empty] | 4418 | 0 | 4418 | 0
[6 empty] | 4419 | 201783.8203 | 4419 | 201783.8203
[6 empty] | 4420 | 8008262.3156 | 4420 | 7062209.084
[6 empty] | 4421 | 0 | 4421 | 0
[6 empty] | 4422 | 2617652.421 | 4422 | 0
[6 empty] | 4423 | 0 | 4423 | 0
[6 empty] | 4424 | 0 | 4424 | 0
[6 empty] | 4425 | 4788138.2082 | 4425 | 0
[6 empty] | 4426 | 0 | 4426 | 0
[6 empty] | 4427 | 0 | 4427 | 0
[6 empty] | 4428 | 0 | 4428 | 0
[6 empty] | 4429 | 3819292.3197 | 4429 | 0
[6 empty] | 4430 | 17209296.4728 | 4430 | 0
[6 empty] | 4431 | 399326.959 | 4431 | 399326.959
[6 empty] | 4432 | 0 | 4432 | 0
[6 empty] | 4433 | 0 | 4433 | 0
[6 empty] | 4434 | 3971641.2025 | 4434 | 0
[6 empty] | 4435 | 3717337.7775 | 4435 | 0
[6 empty] | 4436 | 0 | 4436 | 0
[6 empty] | 4437 | 0 | 4437 | 0
[6 empty] | 4438 | 1124973.3159 | 4438 | 1124973.3159
[6 empty] | 4439 | 169386.15 | 4439 | 169386.15
[6 empty] | 4440 | 0 | 4440 | 0
[6 empty] | 4441 | 0 | 4441 | 0
[6 empty] | 4442 | 0 | 4442 | 0
[6 empty] | 4443 | 0 | 4443 | 0
[6 empty] | 4444 | 2594276.6994 | 4444 | 2594276.6994
[6 empty] | 4445 | 1565278.1936 | 4445 | 0
[6 empty] | 4446 | 0 | 4446 | 0
[6 empty] | 4447 | 100006.7898 | 4447 | 100006.7898
[6 empty] | 4448 | 0 | 4448 | 0
[6 empty] | 4449 | 0 | 4449 | 0
[6 empty] | 4450 | 0 | 4450 | 0
[6 empty] | 4451 | 851734.5417 | 4451 | 0
[6 empty] | 4452 | 3375846.61 | 4452 | 3375846.61
[6 empty] | 4453 | 218240.9035 | 4453 | 218240.9035
[6 empty] | 4454 | 0 | 4454 | 0
[6 empty] | 4455 | 0 | 4455 | 0
[6 empty] | 4456 | 0 | 4456 | 0
[6 empty] | 4457 | 158516.935 | 4457 | 0
[6 empty] | 4458 | 3700269.8124 | 4458 | 0
[6 empty] | 4459 | 0 | 4459 | 0
[6 empty] | 4460 | 0 | 4460 | 0
[6 empty] | 4461 | 2636528.6031 | 4461 | 2403767.1945
[6 empty] | 4462 | 5882484.5803 | 4462 | 0
[6 empty] | 4463 | 210580.2614 | 4463 | 210580.2614
[6 empty] | 4464 | 3720301.965 | 4464 | 3720301.965
[6 empty] | 4465 | 287167.4148 | 4465 | 0
[6 empty] | 4466 | 1222097.7992 | 4466 | 1222097.7992
[6 empty] | 4467 | 0 | 4467 | 0
[6 empty] | 4468 | 979056.6152 | 4468 | 979056.6152
[6 empty] | 4469 | 4607377.1011 | 4469 | 0
[6 empty] | 4470 | 0 | 4470 | 0
[6 empty] | 4471 | 0 | 4471 | 0
[6 empty] | 4472 | 0 | 4472 | 0
[6 empty] | 4473 | 0 | 4473 | 0
[6 empty] | 4474 | 13731781.9763 | 4474 | 13731781.9763
[6 empty] | 4475 | 2998931.5009 | 4475 | 2998931.5009
[6 empty] | 4476 | 1136882.7865 | 4476 | 0
[6 empty] | 4477 | 208297.6271 | 4477 | 208297.6271
[6 empty] | 4478 | 172509.6416 | 4478 | 172509.6416
[6 empty] | 4479 | 2085703.5079 | 4479 | 1835374.7129
[6 empty] | 4480 | 0 | 4480 | 0
[6 empty] | 4481 | 0 | 4481 | 0
[6 empty] | 4482 | 0 | 4482 | 0
[6 empty] | 4483 | 1948609.2411 | 4483 | 0
[6 empty] | 4484 | 0 | 4484 | 0
[6 empty] | 4485 | 353175.1856 | 4485 | 353175.1856
[6 empty] | 4486 | 237499.9466 | 4486 | 0
[6 empty] | 4487 | 0 | 4487 | 0
[6 empty] | 4488 | 252365.6186 | 4488 | 0
[6 empty] | 4489 | 170834.2783 | 4489 | 0
[6 empty] | 4490 | 0 | 4490 | 0
[6 empty] | 4491 | 0 | 4491 | 0
[6 empty] | 4492 | 244712.5945 | 4492 | 244712.5945
[6 empty] | 4493 | 0 | 4493 | 0
[6 empty] | 4494 | 0 | 4494 | 0
[6 empty] | 4495 | 0 | 4495 | 0
[6 empty] | 4496 | 0 | 4496 | 0
[6 empty] | 4497 | 0 | 4497 | 0
[6 empty] | 4498 | 0 | 4498 | 0
[6 empty] | 4499 | 0 | 4499 | 0
[6 empty] | 4500 | 0 | 4500 | 0
[6 empty] | 4501 | 593521.5206 | 4501 | 593521.5206
[6 empty] | 4502 | 0 | 4502 | 0
[6 empty] | 4503 | 4192956.1174 | 4503 | 4192956.1174
[6 empty] | 4504 | 5279448.5942 | 4504 | 0
[6 empty] | 4505 | 2225229.9516 | 4505 | 2225229.9516
[6 empty] | 4506 | 0 | 4506 | 0
[6 empty] | 4507 | 0 | 4507 | 0
[6 empty] | 4508 | 7392057.8413 | 4508 | 5424366.9165
[6 empty] | 4509 | 234820.1343 | 4509 | 234820.1343
[6 empty] | 4510 | 0 | 4510 | 0
[6 empty] | 4511 | 182979.5543 | 4511 | 182979.5543
[6 empty] | 4512 | 210944.7197 | 4512 | 0
[6 empty] | 4513 | 0 | 4513 | 0
[6 empty] | 4514 | 0 | 4514 | 0
[6 empty] | 4515 | 21104984.8262 | 4515 | 200946.7517
[6 empty] | 4516 | 3560943.3401 | 4516 | 3560943.3401
[6 empty] | 4517 | 0 | 4517 | 0
[6 empty] | 4518 | 195109.4705 | 4518 | 195109.4705
[6 empty] | 4519 | 1650364.2218 | 4519 | 0
[6 empty] | 4520 | 0 | 4520 | 0
[6 empty] | 4521 | 4047862.9398 | 4521 | 4047862.9398
[6 empty] | 4522 | 0 | 4522 | 0
[6 empty] | 4523 | 0 | 4523 | 0
[6 empty] | 4524 | 6816854.2774 | 4524 | 2966390.5021
[6 empty] | 4525 | 997981.0466 | 4525 | 997981.0466
[6 empty] | 4526 | 0 | 4526 | 0
[6 empty] | 4527 | 4019606.0899 | 4527 | 4019606.0899
[6 empty] | 4528 | 276124.0749 | 4528 | 0
[6 empty] | 4529 | 0 | 4529 | 0
[6 empty] | 4530 | 197106.9589 | 4530 | 197106.9589
[6 empty] | 4531 | 0 | 4531 | 0
[6 empty] | 4532 | 0 | 4532 | 0
[6 empty] | 4533 | 0 | 4533 | 0
[6 empty] | 4534 | 0 | 4534 | 0
[6 empty] | 4535 | 211335.8679 | 4535 | 0
[6 empty] | 4536 | 4607222.5432 | 4536 | 4607222.5432
[6 empty] | 4537 | 0 | 4537 | 0
[6 empty] | 4538 | 21591130.1713 | 4538 | 0
[6 empty] | 4539 | 169090.9393 | 4539 | 169090.9393
[6 empty] | 4540 | 212206.3108 | 4540 | 212206.3108
[6 empty] | 4541 | 0 | 4541 | 0
[6 empty] | 4542 | 0 | 4542 | 0
[6 empty] | 4543 | 280204.3811 | 4543 | 280204.3811
[6 empty] | 4544 | 329495.9929 | 4544 | 329495.9929
[6 empty] | 4545 | 0 | 4545 | 0
[6 empty] | 4546 | 1873392.7978 | 4546 | 923132.8464
[6 empty] | 4547 | 4399705.9167 | 4547 | 0
[6 empty] | 4548 | 0 | 4548 | 0
[6 empty] | 4549 | 879829.9335 | 4549 | 879829.9335
[6 empty] | 4550 | 0 | 4550 | 0
[6 empty] | 4551 | 2973890.0761 | 4551 | 1886903.5221
[6 empty] | 4552 | 127639.3993 | 4552 | 127639.3993
[6 empty] | 4553 | 250403.232 | 4553 | 250403.232
[6 empty] | 4554 | 0 | 4554 | 0
[6 empty] | 4555 | 179969.5855 | 4555 | 179969.5855
[6 empty] | 4556 | 0 | 4556 | 0
[6 empty] | 4557 | 0 | 4557 | 0
[6 empty] | 4558 | 4501894.591 | 4558 | 0
[6 empty] | 4559 | 0 | 4559 | 0
[6 empty] | 4560 | 340978.2685 | 4560 | 340978.2685
[6 empty] | 4561 | 35477499.0815 | 4561 | 421713.7156
[6 empty] | 4562 | 390551.0431 | 4562 | 390551.0431
[6 empty] | 4563 | 522902.7916 | 4563 | 522902.7916
[6 empty] | 4564 | 7678851.5422 | 4564 | 85495.7243
[6 empty] | 4565 | 310586.8771 | 4565 | 310586.8771
[6 empty] | 4566 | 879884.7909 | 4566 | 879884.7909
[6 empty] | 4567 | 0 | 4567 | 0
[6 empty] | 4568 | 0 | 4568 | 0
[6 empty] | 4569 | 2633369.6573 | 4569 | 0
[6 empty] | 4570 | 352709.6757 | 4570 | 352709.6757
[6 empty] | 4571 | 1944029.5818 | 4571 | 1944029.5818
[6 empty] | 4572 | 686955.8205 | 4572 | 467845.8191
[6 empty] | 4573 | 1178636.9253 | 4573 | 0
[6 empty] | 4574 | 2605941.3974 | 4574 | 2605941.3974
[6 empty] | 4575 | 0 | 4575 | 0
[6 empty] | 4576 | 125166.2412 | 4576 | 125166.2412
[6 empty] | 4577 | 333719.1772 | 4577 | 333719.1772
[6 empty] | 4578 | 1413469.7738 | 4578 | 1413469.7738
[6 empty] | 4579 | 0 | 4579 | 0
[6 empty] | 4580 | 1577495.696 | 4580 | 48854.5639
[6 empty] | 4581 | 2657502.5143 | 4581 | 0
[6 empty] | 4582 | 278214.4539 | 4582 | 278214.4539
[6 empty] | 4583 | 0 | 4583 | 0
[6 empty] | 4584 | 0 | 4584 | 0
[6 empty] | 4585 | 0 | 4585 | 0
[6 empty] | 4586 | 0 | 4586 | 0
[6 empty] | 4587 | 507217.6188 | 4587 | 507217.6188
[6 empty] | 4588 | 715702.9226 | 4588 | 715702.9226
[6 empty] | 4589 | 38451923.5566 | 4589 | 38451923.5566
[6 empty] | 4590 | 1014097.0403 | 4590 | 0
[6 empty] | 4591 | 286177.7782 | 4591 | 0
[6 empty] | 4592 | 180144.8338 | 4592 | 180144.8338
[6 empty] | 4593 | 0 | 4593 | 0
[6 empty] | 4594 | 4993184.5471 | 4594 | 4993184.5471
[6 empty] | 4595 | 849603.1325 | 4595 | 203327.2979
[6 empty] | 4596 | 4846853.7068 | 4596 | 940968.3757
[6 empty] | 4597 | 0 | 4597 | 0
[6 empty] | 4598 | 0 | 4598 | 0
[6 empty] | 4599 | 0 | 4599 | 0
[6 empty] | 4600 | 0 | 4600 | 0
[6 empty] | 4601 | 0 | 4601 | 0
[6 empty] | 4602 | 0 | 4602 | 0
[6 empty] | 4603 | 2425178.172 | 4603 | 2425178.172
[6 empty] | 4604 | 5817676.7946 | 4604 | 5228141.7115
[6 empty] | 4605 | 184937.6899 | 4605 | 0
[6 empty] | 4606 | 0 | 4606 | 0
[6 empty] | 4607 | 0 | 4607 | 0
[6 empty] | 4608 | 4467761.5004 | 4608 | 4281577.358
[6 empty] | 4609 | 626091.061 | 4609 | 0
[6 empty] | 4610 | 0 | 4610 | 0
[6 empty] | 4611 | 0 | 4611 | 0
[6 empty] | 4612 | 1070335.2444 | 4612 | 0
[6 empty] | 4613 | 0 | 4613 | 0
[6 empty] | 4614 | 247987.9778 | 4614 | 247987.9778
[6 empty] | 4615 | 0 | 4615 | 0
[6 empty] | 4616 | 0 | 4616 | 0
[6 empty] | 4617 | 0 | 4617 | 0
[6 empty] | 4618 | 3148887.5976 | 4618 | 3148887.5976
[6 empty] | 4619 | 0 | 4619 | 0
[6 empty] | 4620 | 215864.9613 | 4620 | 215864.9613
[6 empty] | 4621 | 0 | 4621 | 0
[6 empty] | 4622 | 0 | 4622 | 0
[6 empty] | 4623 | 224516.3123 | 4623 | 224516.3123
[6 empty] | 4624 | 4489408.3404 | 4624 | 720666.7887
[6 empty] | 4625 | 1558376.4768 | 4625 | 0
[6 empty] | 4626 | 176993.9695 | 4626 | 0
[6 empty] | 4627 | 0 | 4627 | 0
[6 empty] | 4628 | 0 | 4628 | 0
[6 empty] | 4629 | 0 | 4629 | 0
[6 empty] | 4630 | 134708.0802 | 4630 | 134708.0802
[6 empty] | 4631 | 168138.5328 | 4631 | 168138.5328
[6 empty] | 4632 | 0 | 4632 | 0
[6 empty] | 4633 | 2372223.2934 | 4633 | 2372223.2934
[6 empty] | 4634 | 0 | 4634 | 0
[6 empty] | 4635 | 471022.9299 | 4635 | 0
[6 empty] | 4636 | 3010942.7369 | 4636 | 3010942.7369
[6 empty] | 4637 | 4618098.7901 | 4637 | 4618098.7901
[6 empty] | 4638 | 3247450.6142 | 4638 | 0
[6 empty] | 4639 | 0 | 4639 | 0
[6 empty] | 4640 | 2563940.691 | 4640 | 0
[6 empty] | 4641 | 434155.4429 | 4641 | 434155.4429
[6 empty] | 4642 | 0 | 4642 | 0
[6 empty] | 4643 | 1493816.8728 | 4643 | 0
[6 empty] | 4644 | 1244106.5101 | 4644 | 360126.0487
[6 empty] | 4645 | 4328028.3888 | 4645 | 4328028.3888
[6 empty] | 4646 | 0 | 4646 | 0
[6 empty] | 4647 | 0 | 4647 | 0
[6 empty] | 4648 | 214236.4848 | 4648 | 214236.4848
[6 empty] | 4649 | 3580729.5734 | 4649 | 113811.5769
[6 empty] | 4650 | 0 | 4650 | 0
[6 empty] | 4651 | 0 | 4651 | 0
[6 empty] | 4652 | 0 | 4652 | 0
[6 empty] | 4653 | 0 | 4653 | 0
[6 empty] | 4654 | 702192.1759 | 4654 | 0
[6 empty] | 4655 | 842562.7278 | 4655 | 0
[6 empty] | 4656 | 980655.6605 | 4656 | 0
[6 empty] | 4657 | 11891935.9023 | 4657 | 0
[6 empty] | 4658 | 0 | 4658 | 0
[6 empty] | 4659 | 0 | 4659 | 0
[6 empty] | 4660 | 0 | 4660 | 0
[6 empty] | 4661 | 0 | 4661 | 0
[6 empty] | 4662 | 0 | 4662 | 0
[6 empty] | 4663 | 3359365.0954 | 4663 | 751756.772
[6 empty] | 4664 | 0 | 4664 | 0
[6 empty] | 4665 | 0 | 4665 | 0
[6 empty] | 4666 | 0 | 4666 | 0
[6 empty] | 4667 | 234055.5575 | 4667 | 234055.5575
[6 empty] | 4668 | 0 | 4668 | 0
[6 empty] | 4669 | 297304.901 | 4669 | 0
[6 empty] | 4670 | 582768.2071 | 4670 | 582768.2071
[6 empty] | 4671 | 0 | 4671 | 0
[6 empty] | 4672 | 2644292.6155 | 4672 | 2644292.6155
[6 empty] | 4673 | 200392.5772 | 4673 | 0
[6 empty] | 4674 | 7016587.445 | 4674 | 7016587.445
[6 empty] | 4675 | 3229394.8153 | 4675 | 3229394.8153
[6 empty] | 4676 | 4120962.2333 | 4676 | 231976.8644
[6 empty] | 4677 | 203092.1376 | 4677 | 203092.1376
[6 empty] | 4678 | 557897.1793 | 4678 | 0
[6 empty] | 4679 | 0 | 4679 | 0
[6 empty] | 4680 | 0 | 4680 | 0
[6 empty] | 4681 | 2846067.9873 | 4681 | 0
[6 empty] | 4682 | 0 | 4682 | 0
[6 empty] | 4683 | 7877144.221 | 4683 | 7877144.221
[6 empty] | 4684 | 0 | 4684 | 0
[6 empty] | 4685 | 0 | 4685 | 0
[6 empty] | 4686 | 0 | 4686 | 0
[6 empty] | 4687 | 220189.6356 | 4687 | 220189.6356
[6 empty] | 4688 | 0 | 4688 | 0
[6 empty] | 4689 | 0 | 4689 | 0
[6 empty] | 4690 | 205532.0255 | 4690 | 205532.0255
[6 empty] | 4691 | 0 | 4691 | 0
[6 empty] | 4692 | 3491353.4657 | 4692 | 3286354.0699
[6 empty] | 4693 | 271822.2276 | 4693 | 271822.2276
[6 empty] | 4694 | 0 | 4694 | 0
[6 empty] | 4695 | 194066.417 | 4695 | 194066.417
[6 empty] | 4696 | 224691.2568 | 4696 | 224691.2568
[6 empty] | 4697 | 0 | 4697 | 0
[6 empty] | 4698 | 0 | 4698 | 0
[6 empty] | 4699 | 200987.4301 | 4699 | 200987.4301
[6 empty] | 4700 | 1107069.2504 | 4700 | 0
[6 empty] | 4701 | 0 | 4701 | 0
[6 empty] | 4702 | 3168701.4876 | 4702 | 0
[6 empty] | 4703 | 0 | 4703 | 0
[6 empty] | 4704 | 0 | 4704 | 0
[6 empty] | 4705 | 0 | 4705 | 0
[6 empty] | 4706 | 229503.2411 | 4706 | 229503.2411
[6 empty] | 4707 | 0 | 4707 | 0
[6 empty] | 4708 | 0 | 4708 | 0
[6 empty] | 4709 | 8173596.4842 | 4709 | 373402.4489
[6 empty] | 4710 | 4261849.7761 | 4710 | 1212618.0252
[6 empty] | 4711 | 0 | 4711 | 0
[6 empty] | 4712 | 5741088.2685 | 4712 | 665924.7374
[6 empty] | 4713 | 0 | 4713 | 0
[6 empty] | 4714 | 204165.3914 | 4714 | 0
[6 empty] | 4715 | 0 | 4715 | 0
[6 empty] | 4716 | 0 | 4716 | 0
[6 empty] | 4717 | 345786.9726 | 4717 | 345786.9726
[6 empty] | 4718 | 0 | 4718 | 0
[6 empty] | 4719 | 0 | 4719 | 0
[6 empty] | 4720 | 2428174.5655 | 4720 | 0
[6 empty] | 4721 | 0 | 4721 | 0
[6 empty] | 4722 | 0 | 4722 | 0
[6 empty] | 4723 | 2164123.2535 | 4723 | 2164123.2535
[6 empty] | 4724 | 0 | 4724 | 0
[6 empty] | 4725 | 0 | 4725 | 0
[6 empty] | 4726 | 2824717.8871 | 4726 | 2824717.8871
[6 empty] | 4727 | 0 | 4727 | 0
[6 empty] | 4728 | 0 | 4728 | 0
[6 empty] | 4729 | 1689551.2161 | 4729 | 109437.0273
[6 empty] | 4730 | 1831076.3226 | 4730 | 1831076.3226
[6 empty] | 4731 | 1024018.9545 | 4731 | 1024018.9545
[6 empty] | 4732 | 0 | 4732 | 0
[6 empty] | 4733 | 0 | 4733 | 0
[6 empty] | 4734 | 388582.5518 | 4734 | 388582.5518
[6 empty] | 4735 | 6899091.3505 | 4735 | 6899091.3505
[6 empty] | 4736 | 358684.3289 | 4736 | 358684.3289
[6 empty] | 4737 | 0 | 4737 | 0
[6 empty] | 4738 | 0 | 4738 | 0
[6 empty] | 4739 | 0 | 4739 | 0
[6 empty] | 4740 | 413853.3144 | 4740 | 413853.3144
[6 empty] | 4741 | 3478248.5486 | 4741 | 3478248.5486
[6 empty] | 4742 | 0 | 4742 | 0
[6 empty] | 4743 | 179197.8665 | 4743 | 179197.8665
[6 empty] | 4744 | 0 | 4744 | 0
[6 empty] | 4745 | 349012.7489 | 4745 | 349012.7489
[6 empty] | 4746 | 6720123.0846 | 4746 | 6720123.0846
[6 empty] | 4747 | 1881213.1364 | 4747 | 1881213.1364
[6 empty] | 4748 | 599720.1817 | 4748 | 365349.1039
[6 empty] | 4749 | 0 | 4749 | 0
[6 empty] | 4750 | 471930.8196 | 4750 | 0
[6 empty] | 4751 | 226748.8873 | 4751 | 0
[6 empty] | 4752 | 0 | 4752 | 0
[6 empty] | 4753 | 0 | 4753 | 0
[6 empty] | 4754 | 920100.0045 | 4754 | 0
[6 empty] | 4755 | 2488068.5915 | 4755 | 2488068.5915
[6 empty] | 4756 | 0 | 4756 | 0
[6 empty] | 4757 | 0 | 4757 | 0
[6 empty] | 4758 | 271191.4567 | 4758 | 271191.4567
[6 empty] | 4759 | 0 | 4759 | 0
[6 empty] | 4760 | 0 | 4760 | 0
[6 empty] | 4761 | 0 | 4761 | 0
[6 empty] | 4762 | 2377702.3319 | 4762 | 0
[6 empty] | 4763 | 2471781.5641 | 4763 | 0
[6 empty] | 4764 | 0 | 4764 | 0
[6 empty] | 4765 | 0 | 4765 | 0
[6 empty] | 4766 | 0 | 4766 | 0
[6 empty] | 4767 | 0 | 4767 | 0
[6 empty] | 4768 | 0 | 4768 | 0
[6 empty] | 4769 | 3473885.0245 | 4769 | 1296996.7074
[6 empty] | 4770 | 0 | 4770 | 0
[6 empty] | 4771 | 0 | 4771 | 0
[6 empty] | 4772 | 325401.4164 | 4772 | 325401.4164
[6 empty] | 4773 | 0 | 4773 | 0
[6 empty] | 4774 | 3766311.8838 | 4774 | 3766311.8838
[6 empty] | 4775 | 361227.3624 | 4775 | 361227.3624
[6 empty] | 4776 | 0 | 4776 | 0
[6 empty] | 4777 | 204718.6515 | 4777 | 204718.6515
[6 empty] | 4778 | 0 | 4778 | 0
[6 empty] | 4779 | 2454424.5733 | 4779 | 0
[6 empty] | 4780 | 3565634.3874 | 4780 | 3565634.3874
[6 empty] | 4781 | 456063.4853 | 4781 | 456063.4853
[6 empty] | 4782 | 193982.231 | 4782 | 193982.231
[6 empty] | 4783 | 0 | 4783 | 0
[6 empty] | 4784 | 753261.9714 | 4784 | 0
[6 empty] | 4785 | 469488.3934 | 4785 | 276533.2469
[6 empty] | 4786 | 3010525.2829 | 4786 | 3010525.2829
[6 empty] | 4787 | 3185387.2665 | 4787 | 0
[6 empty] | 4788 | 319597.8828 | 4788 | 319597.8828
[6 empty] | 4789 | 3208335.6773 | 4789 | 3208335.6773
[6 empty] | 4790 | 0 | 4790 | 0
[6 empty] | 4791 | 0 | 4791 | 0
[6 empty] | 4792 | 0 | 4792 | 0
[6 empty] | 4793 | 0 | 4793 | 0
[6 empty] | 4794 | 1508833.1932 | 4794 | 0
[6 empty] | 4795 | 1448373.048 | 4795 | 0
[6 empty] | 4796 | 0 | 4796 | 0
[6 empty] | 4797 | 0 | 4797 | 0
[6 empty] | 4798 | 160117.4135 | 4798 | 160117.4135
[6 empty] | 4799 | 0 | 4799 | 0
[6 empty] | 4800 | 3748667.796 | 4800 | 406543.6942
[6 empty] | 4801 | 0 | 4801 | 0
[6 empty] | 4802 | 2376499.7091 | 4802 | 2376499.7091
[6 empty] | 4803 | 431019.5823 | 4803 | 431019.5823
[6 empty] | 4804 | 3944338.9684 | 4804 | 0
[6 empty] | 4805 | 3924462.9281 | 4805 | 0
[6 empty] | 4806 | 3779449.865 | 4806 | 0
[6 empty] | 4807 | 9103532.3593 | 4807 | 9103532.3593
[6 empty] | 4808 | 3165659.4342 | 4808 | 0
[6 empty] | 4809 | 727851.5522 | 4809 | 493981.4369
[6 empty] | 4810 | 859912.7033 | 4810 | 0
[6 empty] | 4811 | 116044.0041 | 4811 | 116044.0041
[6 empty] | 4812 | 0 | 4812 | 0
[6 empty] | 4813 | 0 | 4813 | 0
[6 empty] | 4814 | 3699089.9022 | 4814 | 0
[6 empty] | 4815 | 318661.6733 | 4815 | 318661.6733
[6 empty] | 4816 | 0 | 4816 | 0
[6 empty] | 4817 | 0 | 4817 | 0
[6 empty] | 4818 | 517699.2922 | 4818 | 517699.2922
[6 empty] | 4819 | 0 | 4819 | 0
[6 empty] | 4820 | 3881423.3649 | 4820 | 131457.4368
[6 empty] | 4821 | 0 | 4821 | 0
[6 empty] | 4822 | 258471.7076 | 4822 | 258471.7076
[6 empty] | 4823 | 220381.7525 | 4823 | 0
[6 empty] | 4824 | 190222.8229 | 4824 | 0
[6 empty] | 4825 | 479705.2548 | 4825 | 249180.4604
[6 empty] | 4826 | 0 | 4826 | 0
[6 empty] | 4827 | 143145.5248 | 4827 | 143145.5248
[6 empty] | 4828 | 0 | 4828 | 0
[6 empty] | 4829 | 0 | 4829 | 0
[6 empty] | 4830 | 982514.3547 | 4830 | 982514.3547
[6 empty] | 4831 | 0 | 4831 | 0
[6 empty] | 4832 | 498841.1349 | 4832 | 318573.7472
[6 empty] | 4833 | 0 | 4833 | 0
[6 empty] | 4834 | 2187398.9259 | 4834 | 0
[6 empty] | 4835 | 1555753.3721 | 4835 | 1555753.3721
[6 empty] | 4836 | 1537918.8168 | 4836 | 0
[6 empty] | 4837 | 0 | 4837 | 0
[6 empty] | 4838 | 0 | 4838 | 0
[6 empty] | 4839 | 0 | 4839 | 0
[6 empty] | 4840 | 0 | 4840 | 0
[6 empty] | 4841 | 0 | 4841 | 0
[6 empty] | 4842 | 0 | 4842 | 0
[6 empty] | 4843 | 0 | 4843 | 0
[6 empty] | 4844 | 4297977.8632 | 4844 | 184796.8781
[6 empty] | 4845 | 212462.4631 | 4845 | 212462.4631
[6 empty] | 4846 | 2866015.3278 | 4846 | 186397.4042
[6 empty] | 4847 | 960945.833 | 4847 | 960945.833
[6 empty] | 4848 | 0 | 4848 | 0
[6 empty] | 4849 | 3292596.898 | 4849 | 3292596.898
[6 empty] | 4850 | 0 | 4850 | 0
[6 empty] | 4851 | 0 | 4851 | 0
[6 empty] | 4852 | 1671237.2141 | 4852 | 1671237.2141
[6 empty] | 4853 | 2033592.7867 | 4853 | 2033592.7867
[6 empty] | 4854 | 0 | 4854 | 0
[6 empty] | 4855 | 0 | 4855 | 0
[6 empty] | 4856 | 0 | 4856 | 0
[6 empty] | 4857 | 0 | 4857 | 0
[6 empty] | 4858 | 0 | 4858 | 0
[6 empty] | 4859 | 0 | 4859 | 0
[6 empty] | 4860 | 0 | 4860 | 0
[6 empty] | 4861 | 0 | 4861 | 0
[6 empty] | 4862 | 0 | 4862 | 0
[6 empty] | 4863 | 14444342.1716 | 4863 | 14444342.1716
[6 empty] | 4864 | 156454.0716 | 4864 | 156454.0716
[6 empty] | 4865 | 939848.5939 | 4865 | 939848.5939
[6 empty] | 4866 | 0 | 4866 | 0
[6 empty] | 4867 | 0 | 4867 | 0
[6 empty] | 4868 | 196920.1013 | 4868 | 196920.1013
[6 empty] | 4869 | 0 | 4869 | 0
[6 empty] | 4870 | 575377.9344 | 4870 | 575377.9344
[6 empty] | 4871 | 0 | 4871 | 0
[6 empty] | 4872 | 3030900.0649 | 4872 | 3030900.0649
[6 empty] | 4873 | 291085.6349 | 4873 | 291085.6349
[6 empty] | 4874 | 140103.3935 | 4874 | 140103.3935
[6 empty] | 4875 | 325910.2054 | 4875 | 325910.2054
[6 empty] | 4876 | 4696740.2529 | 4876 | 0
[6 empty] | 4877 | 190232.2877 | 4877 | 0
[6 empty] | 4878 | 0 | 4878 | 0
[6 empty] | 4879 | 0 | 4879 | 0
[6 empty] | 4880 | 0 | 4880 | 0
[6 empty] | 4881 | 0 | 4881 | 0
[6 empty] | 4882 | 3967433.589 | 4882 | 3967433.589
[6 empty] | 4883 | 4017114.1491 | 4883 | 4017114.1491
[6 empty] | 4884 | 3095350.8233 | 4884 | 0
[6 empty] | 4885 | 13105013.6475 | 4885 | 0
[6 empty] | 4886 | 0 | 4886 | 0
[6 empty] | 4887 | 0 | 4887 | 0
[6 empty] | 4888 | 10308984.5196 | 4888 | 0
[6 empty] | 4889 | 0 | 4889 | 0
[6 empty] | 4890 | 7795665.1457 | 4890 | 0
[6 empty] | 4891 | 283958.6813 | 4891 | 0
[6 empty] | 4892 | 484505.2703 | 4892 | 484505.2703
[6 empty] | 4893 | 0 | 4893 | 0
[6 empty] | 4894 | 776250.3579 | 4894 | 776250.3579
[6 empty] | 4895 | 0 | 4895 | 0
[6 empty] | 4896 | 6142778.5782 | 4896 | 6142778.5782
[6 empty] | 4897 | 99343.6683 | 4897 | 99343.6683
[6 empty] | 4898 | 230640.5719 | 4898 | 0
[6 empty] | 4899 | 5723071.0119 | 4899 | 0
[6 empty] | 4900 | 0 | 4900 | 0
[6 empty] | 4901 | 0 | 4901 | 0
[6 empty] | 4902 | 0 | 4902 | 0
[6 empty] | 4903 | 238363.9982 | 4903 | 0
[6 empty] | 4904 | 0 | 4904 | 0
[6 empty] | 4905 | 624509.7741 | 4905 | 624509.7741
[6 empty] | 4906 | 3337359.4882 | 4906 | 3337359.4882
[6 empty] | 4907 | 0 | 4907 | 0
[6 empty] | 4908 | 3302027.9097 | 4908 | 0
[6 empty] | 4909 | 0 | 4909 | 0
[6 empty] | 4910 | 0 | 4910 | 0
[6 empty] | 4911 | 3946558.5086 | 4911 | 3946558.5086
[6 empty] | 4912 | 243236.5313 | 4912 | 0
[6 empty] | 4913 | 0 | 4913 | 0
[6 empty] | 4914 | 0 | 4914 | 0
[6 empty] | 4915 | 2660718.8019 | 4915 | 2660718.8019
[6 empty] | 4916 | 3328141.4024 | 4916 | 3328141.4024
[6 empty] | 4917 | 2200499.8418 | 4917 | 2014575.7265
[6 empty] | 4918 | 537435.445 | 4918 | 537435.445
[6 empty] | 4919 | 0 | 4919 | 0
[6 empty] | 4920 | 0 | 4920 | 0
[6 empty] | 4921 | 0 | 4921 | 0
[6 empty] | 4922 | 504416.6706 | 4922 | 298424.1073
[6 empty] | 4923 | 0 | 4923 | 0
[6 empty] | 4924 | 236731.7331 | 4924 | 0
[6 empty] | 4925 | 0 | 4925 | 0
[6 empty] | 4926 | 0 | 4926 | 0
[6 empty] | 4927 | 0 | 4927 | 0
[6 empty] | 4928 | 0 | 4928 | 0
[6 empty] | 4929 | 0 | 4929 | 0
[6 empty] | 4930 | 321795.025 | 4930 | 321795.025
[6 empty] | 4931 | 551167.9123 | 4931 | 551167.9123
[6 empty] | 4932 | 3732493.181 | 4932 | 1713633.1637
[6 empty] | 4933 | 770778.0378 | 4933 | 770778.0378
[6 empty] | 4934 | 1221266.2839 | 4934 | 0
[6 empty] | 4935 | 0 | 4935 | 0
[6 empty] | 4936 | 0 | 4936 | 0
[6 empty] | 4937 | 180928.8791 | 4937 | 180928.8791
[6 empty] | 4938 | 426357.8257 | 4938 | 426357.8257
[6 empty] | 4939 | 0 | 4939 | 0
[6 empty] | 4940 | 0 | 4940 | 0
[6 empty] | 4941 | 236132.2771 | 4941 | 236132.2771
[6 empty] | 4942 | 3102971.2349 | 4942 | 199442.7082
[6 empty] | 4943 | 237735.2507 | 4943 | 237735.2507
[6 empty] | 4944 | 0 | 4944 | 0
[6 empty] | 4945 | 0 | 4945 | 0
[6 empty] | 4946 | 253833.0179 | 4946 | 253833.0179
[6 empty] | 4947 | 0 | 4947 | 0
[6 empty] | 4948 | 773685.0149 | 4948 | 0
[6 empty] | 4949 | 0 | 4949 | 0
[6 empty] | 4950 | 0 | 4950 | 0
[6 empty] | 4951 | 338126.7 | 4951 | 338126.7
[6 empty] | 4952 | 0 | 4952 | 0
[6 empty] | 4953 | 3636975.7722 | 4953 | 3636975.7722
[6 empty] | 4954 | 0 | 4954 | 0
[6 empty] | 4955 | 0 | 4955 | 0
[6 empty] | 4956 | 3704352.9392 | 4956 | 0
[6 empty] | 4957 | 0 | 4957 | 0
[6 empty] | 4958 | 0 | 4958 | 0
[6 empty] | 4959 | 181978.8582 | 4959 | 181978.8582
[6 empty] | 4960 | 0 | 4960 | 0
[6 empty] | 4961 | 0 | 4961 | 0
[6 empty] | 4962 | 277883.4205 | 4962 | 277883.4205
[6 empty] | 4963 | 0 | 4963 | 0
[6 empty] | 4964 | 2020898.3638 | 4964 | 2020898.3638
[6 empty] | 4965 | 1598974.2263 | 4965 | 1598974.2263
[6 empty] | 4966 | 0 | 4966 | 0
[6 empty] | 4967 | 0 | 4967 | 0
[6 empty] | 4968 | 1489070.7382 | 4968 | 0
[6 empty] | 4969 | 141699.4261 | 4969 | 0
[6 empty] | 4970 | 0 | 4970 | 0
[6 empty] | 4971 | 993175.4412 | 4971 | 107042.812
[6 empty] | 4972 | 234008.9477 | 4972 | 0
[6 empty] | 4973 | 78098.4052 | 4973 | 78098.4052
[6 empty] | 4974 | 59814.6303 | 4974 | 59814.6303
[6 empty] | 4975 | 677868.9626 | 4975 | 677868.9626
[6 empty] | 4976 | 0 | 4976 | 0
[6 empty] | 4977 | 0 | 4977 | 0
[6 empty] | 4978 | 0 | 4978 | 0
[6 empty] | 4979 | 233172.4353 | 4979 | 233172.4353
[6 empty] | 4980 | 3283396.5309 | 4980 | 3061545.9123
[6 empty] | 4981 | 0 | 4981 | 0
[6 empty] | 4982 | 3007344.3171 | 4982 | 3007344.3171
[6 empty] | 4983 | 678243.7479 | 4983 | 678243.7479
[6 empty] | 4984 | 0 | 4984 | 0
[6 empty] | 4985 | 355924.1605 | 4985 | 355924.1605
[6 empty] | 4986 | 0 | 4986 | 0
[6 empty] | 4987 | 0 | 4987 | 0
[6 empty] | 4988 | 0 | 4988 | 0
[6 empty] | 4989 | 0 | 4989 | 0
[6 empty] | 4990 | 319668.7084 | 4990 | 319668.7084
[6 empty] | 4991 | 2810345.4099 | 4991 | 2810345.4099
[6 empty] | 4992 | 165732.3157 | 4992 | 0
[6 empty] | 4993 | 0 | 4993 | 0
[6 empty] | 4994 | 0 | 4994 | 0
[6 empty] | 4995 | 0 | 4995 | 0
[6 empty] | 4996 | 294410.651 | 4996 | 104929.2872
[6 empty] | 4997 | 431112.8861 | 4997 | 431112.8861
[6 empty] | 4998 | 0 | 4998 | 0
[6 empty] | 4999 | 2124100.026 | 4999 | 288842.5817
[6 empty] | 5000 | 2400010.7783 | 5000 | 0
[6 empty] | 5001 | 9901824.8029 | 5001 | 1524106.3883
[6 empty] | 5002 | 181392.0308 | 5002 | 181392.0308
[6 empty] | 5003 | 0 | 5003 | 0
[6 empty] | 5004 | 5074608.4832 | 5004 | 0
[6 empty] | 5005 | 6093107.8243 | 5005 | 0
[6 empty] | 5006 | 292926.0163 | 5006 | 292926.0163
[6 empty] | 5007 | 243785.7874 | 5007 | 243785.7874
[6 empty] | 5008 | 400924.6138 | 5008 | 257697.6214
[6 empty] | 5009 | 0 | 5009 | 0
[6 empty] | 5010 | 998980.9299 | 5010 | 843987.6793
[6 empty] | 5011 | 920924.0738 | 5011 | 920924.0738
[6 empty] | 5012 | 178760.0006 | 5012 | 178760.0006
[6 empty] | 5013 | 320558.8916 | 5013 | 320558.8916
[6 empty] | 5014 | 0 | 5014 | 0
[6 empty] | 5015 | 278015.5714 | 5015 | 278015.5714
[6 empty] | 5016 | 3053429.018 | 5016 | 280543.3968
[6 empty] | 5017 | 328386.8895 | 5017 | 0
[6 empty] | 5018 | 0 | 5018 | 0
[6 empty] | 5019 | 159655.1211 | 5019 | 159655.1211
[6 empty] | 5020 | 0 | 5020 | 0
[6 empty] | 5021 | 0 | 5021 | 0
[6 empty] | 5022 | 0 | 5022 | 0
[6 empty] | 5023 | 6903121.6348 | 5023 | 1033884.6035
[6 empty] | 5024 | 0 | 5024 | 0
[6 empty] | 5025 | 0 | 5025 | 0
[6 empty] | 5026 | 2899726.584 | 5026 | 153643.6049
[6 empty] | 5027 | 0 | 5027 | 0
[6 empty] | 5028 | 3891327.3181 | 5028 | 3891327.3181
[6 empty] | 5029 | 0 | 5029 | 0
[6 empty] | 5030 | 1780299.582 | 5030 | 125344.3262
[6 empty] | 5031 | 163568.3981 | 5031 | 0
[6 empty] | 5032 | 0 | 5032 | 0
[6 empty] | 5033 | 3996317.8888 | 5033 | 0
[6 empty] | 5034 | 0 | 5034 | 0
[6 empty] | 5035 | 6387571.9767 | 5035 | 1103714.2552
[6 empty] | 5036 | 0 | 5036 | 0
[6 empty] | 5037 | 0 | 5037 | 0
[6 empty] | 5038 | 0 | 5038 | 0
[6 empty] | 5039 | 0 | 5039 | 0
[6 empty] | 5040 | 5148342.2005 | 5040 | 4962531.4126
[6 empty] | 5041 | 2972530.2668 | 5041 | 0
[6 empty] | 5042 | 1553145.8407 | 5042 | 0
[6 empty] | 5043 | 50359124.9457 | 5043 | 78706.4368
[6 empty] | 5044 | 3530707.3963 | 5044 | 3530707.3963
[6 empty] | 5045 | 12282331.9163 | 5045 | 12282331.9163
[6 empty] | 5046 | 6554355.66 | 5046 | 291162.9934
[6 empty] | 5047 | 0 | 5047 | 0
[6 empty] | 5048 | 414041.5874 | 5048 | 242452.9121
[6 empty] | 5049 | 356655.3463 | 5049 | 356655.3463
[6 empty] | 5050 | 3803627.6297 | 5050 | 3803627.6297
[6 empty] | 5051 | 0 | 5051 | 0
[6 empty] | 5052 | 316340.4873 | 5052 | 316340.4873
[6 empty] | 5053 | 806601.5522 | 5053 | 237967.6011
[6 empty] | 5054 | 171640.4284 | 5054 | 171640.4284
[6 empty] | 5055 | 215130.1215 | 5055 | 215130.1215
[6 empty] | 5056 | 0 | 5056 | 0
[6 empty] | 5057 | 241535.2293 | 5057 | 0
[6 empty] | 5058 | 0 | 5058 | 0
[6 empty] | 5059 | 0 | 5059 | 0
[6 empty] | 5060 | 0 | 5060 | 0
[6 empty] | 5061 | 0 | 5061 | 0
[6 empty] | 5062 | 0 | 5062 | 0
[6 empty] | 5063 | 658182.9746 | 5063 | 658182.9746
[6 empty] | 5064 | 2736925.8011 | 5064 | 2736925.8011
[6 empty] | 5065 | 0 | 5065 | 0
[6 empty] | 5066 | 408021.6058 | 5066 | 133227.782
[6 empty] | 5067 | 243339.3005 | 5067 | 243339.3005
[6 empty] | 5068 | 460711.9405 | 5068 | 460711.9405
[6 empty] | 5069 | 3403945.2597 | 5069 | 333743.801
[6 empty] | 5070 | 0 | 5070 | 0
[6 empty] | 5071 | 0 | 5071 | 0
[6 empty] | 5072 | 245201.7801 | 5072 | 245201.7801
[6 empty] | 5073 | 5736849.5233 | 5073 | 5736849.5233
[6 empty] | 5074 | 0 | 5074 | 0
[6 empty] | 5075 | 0 | 5075 | 0
[6 empty] | 5076 | 226816.4559 | 5076 | 226816.4559
[6 empty] | 5077 | 2221319.1098 | 5077 | 0
[6 empty] | 5078 | 638006.0233 | 5078 | 638006.0233
[6 empty] | 5079 | 0 | 5079 | 0
[6 empty] | 5080 | 0 | 5080 | 0
[6 empty] | 5081 | 1597519.5195 | 5081 | 763300.4697
[6 empty] | 5082 | 92957.7661 | 5082 | 92957.7661
[6 empty] | 5083 | 0 | 5083 | 0
[6 empty] | 5084 | 0 | 5084 | 0
[6 empty] | 5085 | 0 | 5085 | 0
[6 empty] | 5086 | 1100681.9004 | 5086 | 1100681.9004
[6 empty] | 5087 | 0 | 5087 | 0
[6 empty] | 5088 | 6418156.7531 | 5088 | 0
[6 empty] | 5089 | 0 | 5089 | 0
[6 empty] | 5090 | 4105879.7425 | 5090 | 4105879.7425
[6 empty] | 5091 | 5921503.9975 | 5091 | 0
[6 empty] | 5092 | 7933694.3587 | 5092 | 0
[6 empty] | 5093 | 0 | 5093 | 0
[6 empty] | 5094 | 0 | 5094 | 0
[6 empty] | 5095 | 0 | 5095 | 0
[6 empty] | 5096 | 0 | 5096 | 0
[6 empty] | 5097 | 0 | 5097 | 0
[6 empty] | 5098 | 0 | 5098 | 0
[6 empty] | 5099 | 0 | 5099 | 0
[6 empty] | 5100 | 3113282.999 | 5100 | 0
[6 empty] | 5101 | 217800.2899 | 5101 | 0
[6 empty] | 5102 | 4372811.8827 | 5102 | 0
[6 empty] | 5103 | 2467177.2782 | 5103 | 657702.2166
[6 empty] | 5104 | 0 | 5104 | 0
[6 empty] | 5105 | 0 | 5105 | 0
[6 empty] | 5106 | 0 | 5106 | 0
[6 empty] | 5107 | 290493.9256 | 5107 | 290493.9256
[6 empty] | 5108 | 76184157.0918 | 5108 | 517772.0999
[6 empty] | 5109 | 3725545.1489 | 5109 | 0
[6 empty] | 5110 | 364067.8734 | 5110 | 364067.8734
[6 empty] | 5111 | 330612.1362 | 5111 | 330612.1362
[6 empty] | 5112 | 214878.4623 | 5112 | 0
[6 empty] | 5113 | 0 | 5113 | 0
[6 empty] | 5114 | 1959746.81 | 5114 | 0
[6 empty] | 5115 | 0 | 5115 | 0
[6 empty] | 5116 | 9883232.7426 | 5116 | 8814882.6344
[6 empty] | 5117 | 795326.9784 | 5117 | 622617.5802
[6 empty] | 5118 | 0 | 5118 | 0
[6 empty] | 5119 | 3370921.4827 | 5119 | 3147640.5662
[6 empty] | 5120 | 0 | 5120 | 0
[6 empty] | 5121 | 0 | 5121 | 0
[6 empty] | 5122 | 1395515.4073 | 5122 | 0
[6 empty] | 5123 | 0 | 5123 | 0
[6 empty] | 5124 | 0 | 5124 | 0
[6 empty] | 5125 | 0 | 5125 | 0
[6 empty] | 5126 | 0 | 5126 | 0
[6 empty] | 5127 | 0 | 5127 | 0
[6 empty] | 5128 | 0 | 5128 | 0
[6 empty] | 5129 | 0 | 5129 | 0
[6 empty] | 5130 | 0 | 5130 | 0
[6 empty] | 5131 | 2147077.6095 | 5131 | 0
[6 empty] | 5132 | 0 | 5132 | 0
[6 empty] | 5133 | 462540.0423 | 5133 | 462540.0423
[6 empty] | 5134 | 416354.6973 | 5134 | 416354.6973
[6 empty] | 5135 | 0 | 5135 | 0
[6 empty] | 5136 | 272292.2208 | 5136 | 0
[6 empty] | 5137 | 0 | 5137 | 0
[6 empty] | 5138 | 220027.5852 | 5138 | 0
[6 empty] | 5139 | 4467209.6371 | 5139 | 4467209.6371
[6 empty] | 5140 | 200332.6301 | 5140 | 0
[6 empty] | 5141 | 0 | 5141 | 0
[6 empty] | 5142 | 0 | 5142 | 0
[6 empty] | 5143 | 1568971.45 | 5143 | 0
[6 empty] | 5144 | 166435.2963 | 5144 | 166435.2963
[6 empty] | 5145 | 0 | 5145 | 0
[6 empty] | 5146 | 0 | 5146 | 0
[6 empty] | 5147 | 0 | 5147 | 0
[6 empty] | 5148 | 0 | 5148 | 0
[6 empty] | 5149 | 569967.3465 | 5149 | 348068.7719
[6 empty] | 5150 | 2645943.8815 | 5150 | 2645943.8815
[6 empty] | 5151 | 0 | 5151 | 0
[6 empty] | 5152 | 0 | 5152 | 0
[6 empty] | 5153 | 201256.8881 | 5153 | 0
[6 empty] | 5154 | 0 | 5154 | 0
[6 empty] | 5155 | 0 | 5155 | 0
[6 empty] | 5156 | 0 | 5156 | 0
[6 empty] | 5157 | 0 | 5157 | 0
[6 empty] | 5158 | 3862774.7987 | 5158 | 0
[6 empty] | 5159 | 3895862.3702 | 5159 | 3895862.3702
[6 empty] | 5160 | 0 | 5160 | 0
[6 empty] | 5161 | 133568.129 | 5161 | 0
[6 empty] | 5162 | 2030004.1794 | 5162 | 0
[6 empty] | 5163 | 899546.3988 | 5163 | 899546.3988
[6 empty] | 5164 | 2341330.9049 | 5164 | 2341330.9049
[6 empty] | 5165 | 0 | 5165 | 0
[6 empty] | 5166 | 0 | 5166 | 0
[6 empty] | 5167 | 252480.8612 | 5167 | 252480.8612
[6 empty] | 5168 | 218532.9713 | 5168 | 0
[6 empty] | 5169 | 0 | 5169 | 0
[6 empty] | 5170 | 376192.2792 | 5170 | 0
[6 empty] | 5171 | 0 | 5171 | 0
[6 empty] | 5172 | 2871963.811 | 5172 | 2871963.811
[6 empty] | 5173 | 0 | 5173 | 0
[6 empty] | 5174 | 0 | 5174 | 0
[6 empty] | 5175 | 0 | 5175 | 0
[6 empty] | 5176 | 0 | 5176 | 0
[6 empty] | 5177 | 0 | 5177 | 0
[6 empty] | 5178 | 0 | 5178 | 0
[6 empty] | 5179 | 4642632.7124 | 5179 | 4642632.7124
[6 empty] | 5180 | 816741.0593 | 5180 | 646426.6553
[6 empty] | 5181 | 0 | 5181 | 0
[6 empty] | 5182 | 0 | 5182 | 0
[6 empty] | 5183 | 0 | 5183 | 0
[6 empty] | 5184 | 4481534.864 | 5184 | 0
[6 empty] | 5185 | 8711781.4791 | 5185 | 2716697.816
[6 empty] | 5186 | 0 | 5186 | 0
[6 empty] | 5187 | 0 | 5187 | 0
[6 empty] | 5188 | 5428047.749 | 5188 | 2463538.3377
[6 empty] | 5189 | 2048201.2918 | 5189 | 271287.0236
[6 empty] | 5190 | 104123.2826 | 5190 | 104123.2826
[6 empty] | 5191 | 0 | 5191 | 0
[6 empty] | 5192 | 5120574.83 | 5192 | 5120574.83
[6 empty] | 5193 | 196775.0973 | 5193 | 196775.0973
[6 empty] | 5194 | 0 | 5194 | 0
[6 empty] | 5195 | 718666.1359 | 5195 | 718666.1359
[6 empty] | 5196 | 219721.1802 | 5196 | 0
[6 empty] | 5197 | 0 | 5197 | 0
[6 empty] | 5198 | 0 | 5198 | 0
[6 empty] | 5199 | 229491.3987 | 5199 | 0
[6 empty] | 5200 | 554285.5471 | 5200 | 314585.5378
[6 empty] | 5201 | 0 | 5201 | 0
[6 empty] | 5202 | 3495698.134 | 5202 | 3495698.134
[6 empty] | 5203 | 2691587.8535 | 5203 | 2691587.8535
[6 empty] | 5204 | 7175337.4952 | 5204 | 2246600.6624
[6 empty] | 5205 | 3522733.7883 | 5205 | 444703.5571
[6 empty] | 5206 | 0 | 5206 | 0
[6 empty] | 5207 | 1787239.971 | 5207 | 1787239.971
[6 empty] | 5208 | 196106.7346 | 5208 | 196106.7346
[6 empty] | 5209 | 0 | 5209 | 0
[6 empty] | 5210 | 0 | 5210 | 0
[6 empty] | 5211 | 3141027.7385 | 5211 | 0
[6 empty] | 5212 | 0 | 5212 | 0
[6 empty] | 5213 | 0 | 5213 | 0
[6 empty] | 5214 | 0 | 5214 | 0
[6 empty] | 5215 | 1040674.2005 | 5215 | 1040674.2005
[6 empty] | 5216 | 0 | 5216 | 0
[6 empty] | 5217 | 0 | 5217 | 0
[6 empty] | 5218 | 0 | 5218 | 0
[6 empty] | 5219 | 454865.8182 | 5219 | 253459.5477
[6 empty] | 5220 | 0 | 5220 | 0
[6 empty] | 5221 | 0 | 5221 | 0
[6 empty] | 5222 | 3017263.4183 | 5222 | 3017263.4183
[6 empty] | 5223 | 1316875.9704 | 5223 | 1118294.0788
[6 empty] | 5224 | 0 | 5224 | 0
[6 empty] | 5225 | 398892.2719 | 5225 | 398892.2719
[6 empty] | 5226 | 6289761.2736 | 5226 | 6289761.2736
[6 empty] | 5227 | 0 | 5227 | 0
[6 empty] | 5228 | 0 | 5228 | 0
[6 empty] | 5229 | 1458213.3843 | 5229 | 0
[6 empty] | 5230 | 2766978.3801 | 5230 | 0
[6 empty] | 5231 | 0 | 5231 | 0
[6 empty] | 5232 | 299955.9236 | 5232 | 299955.9236
[6 empty] | 5233 | 3344194.3819 | 5233 | 3344194.3819
[6 empty] | 5234 | 0 | 5234 | 0
[6 empty] | 5235 | 0 | 5235 | 0
[6 empty] | 5236 | 0 | 5236 | 0
[6 empty] | 5237 | 0 | 5237 | 0
[6 empty] | 5238 | 257283.2823 | 5238 | 257283.2823
[6 empty] | 5239 | 2652422.6322 | 5239 | 0
[6 empty] | 5240 | 0 | 5240 | 0
[6 empty] | 5241 | 245809.4012 | 5241 | 245809.4012
[6 empty] | 5242 | 0 | 5242 | 0
[6 empty] | 5243 | 341297.5592 | 5243 | 341297.5592
[6 empty] | 5244 | 0 | 5244 | 0
[6 empty] | 5245 | 2624088.6099 | 5245 | 0
[6 empty] | 5246 | 0 | 5246 | 0
[6 empty] | 5247 | 0 | 5247 | 0
[6 empty] | 5248 | 5089600.5461 | 5248 | 5089600.5461
[6 empty] | 5249 | 3089115.3872 | 5249 | 0
[6 empty] | 5250 | 4430305.2809 | 5250 | 0
[6 empty] | 5251 | 0 | 5251 | 0
[6 empty] | 5252 | 0 | 5252 | 0
[6 empty] | 5253 | 261674.6024 | 5253 | 261674.6024
[6 empty] | 5254 | 0 | 5254 | 0
[6 empty] | 5255 | 0 | 5255 | 0
[6 empty] | 5256 | 0 | 5256 | 0
[6 empty] | 5257 | 1966660.6122 | 5257 | 1775208.8538
[6 empty] | 5258 | 8287935.0711 | 5258 | 8287935.0711
[6 empty] | 5259 | 1609205.7426 | 5259 | 0
[6 empty] | 5260 | 281499.5487 | 5260 | 281499.5487
[6 empty] | 5261 | 0 | 5261 | 0
[6 empty] | 5262 | 5949808.3405 | 5262 | 0
[6 empty] | 5263 | 0 | 5263 | 0
[6 empty] | 5264 | 0 | 5264 | 0
[6 empty] | 5265 | 424758.8569 | 5265 | 424758.8569
[6 empty] | 5266 | 0 | 5266 | 0
[6 empty] | 5267 | 0 | 5267 | 0
[6 empty] | 5268 | 0 | 5268 | 0
[6 empty] | 5269 | 95523.1298 | 5269 | 95523.1298
[6 empty] | 5270 | 3548732.8303 | 5270 | 0
[6 empty] | 5271 | 318327.1589 | 5271 | 318327.1589
[6 empty] | 5272 | 0 | 5272 | 0
[6 empty] | 5273 | 6028230.7792 | 5273 | 0
[6 empty] | 5274 | 0 | 5274 | 0
[6 empty] | 5275 | 276568.2938 | 5275 | 276568.2938
[6 empty] | 5276 | 0 | 5276 | 0
[6 empty] | 5277 | 0 | 5277 | 0
[6 empty] | 5278 | 552964.1088 | 5278 | 552964.1088
[6 empty] | 5279 | 427423.6337 | 5279 | 427423.6337
[6 empty] | 5280 | 1226109.8776 | 5280 | 1226109.8776
[6 empty] | 5281 | 2033275.2412 | 5281 | 0
[6 empty] | 5282 | 0 | 5282 | 0
[6 empty] | 5283 | 3839625.1887 | 5283 | 3839625.1887
[6 empty] | 5284 | 0 | 5284 | 0
[6 empty] | 5285 | 1210493.58 | 5285 | 1210493.58
[6 empty] | 5286 | 1539338.336 | 5286 | 0
[6 empty] | 5287 | 2815642.9249 | 5287 | 0
[6 empty] | 5288 | 476361.3406 | 5288 | 476361.3406
[6 empty] | 5289 | 562454.6128 | 5289 | 562454.6128
[6 empty] | 5290 | 3578917.4724 | 5290 | 3270854.7183
[6 empty] | 5291 | 0 | 5291 | 0
[6 empty] | 5292 | 3344542.6912 | 5292 | 3344542.6912
[6 empty] | 5293 | 0 | 5293 | 0
[6 empty] | 5294 | 226901.9334 | 5294 | 226901.9334
[6 empty] | 5295 | 5153996.4302 | 5295 | 0
[6 empty] | 5296 | 299919.7329 | 5296 | 299919.7329
[6 empty] | 5297 | 8817067.7083 | 5297 | 8817067.7083
[6 empty] | 5298 | 383509.2922 | 5298 | 383509.2922
[6 empty] | 5299 | 868918.4179 | 5299 | 868918.4179
[6 empty] | 5300 | 266453.8629 | 5300 | 266453.8629
[6 empty] | 5301 | 3878350.533 | 5301 | 0
[6 empty] | 5302 | 2970416.5182 | 5302 | 2970416.5182
[6 empty] | 5303 | 0 | 5303 | 0
[6 empty] | 5304 | 0 | 5304 | 0
[6 empty] | 5305 | 0 | 5305 | 0
[6 empty] | 5306 | 9053142.1869 | 5306 | 0
[6 empty] | 5307 | 3221963.0349 | 5307 | 3221963.0349
[6 empty] | 5308 | 110260.6739 | 5308 | 110260.6739
[6 empty] | 5309 | 0 | 5309 | 0
[6 empty] | 5310 | 2147409.0176 | 5310 | 186097.4016
[6 empty] | 5311 | 2128231.8668 | 5311 | 0
[6 empty] | 5312 | 1673241.0729 | 5312 | 254476.2789
[6 empty] | 5313 | 0 | 5313 | 0
[6 empty] | 5314 | 0 | 5314 | 0
[6 empty] | 5315 | 0 | 5315 | 0
[6 empty] | 5316 | 226265.4883 | 5316 | 226265.4883
[6 empty] | 5317 | 0 | 5317 | 0
[6 empty] | 5318 | 285602.3686 | 5318 | 285602.3686
[6 empty] | 5319 | 0 | 5319 | 0
[6 empty] | 5320 | 778311.7651 | 5320 | 535487.705
[6 empty] | 5321 | 2259879.8633 | 5321 | 442790.2918
[6 empty] | 5322 | 0 | 5322 | 0
[6 empty] | 5323 | 9870066.966 | 5323 | 0
[6 empty] | 5324 | 0 | 5324 | 0
[6 empty] | 5325 | 1627991.2397 | 5325 | 1627991.2397
[6 empty] | 5326 | 475379.7637 | 5326 | 475379.7637
[6 empty] | 5327 | 0 | 5327 | 0
[6 empty] | 5328 | 0 | 5328 | 0
[6 empty] | 5329 | 0 | 5329 | 0
[6 empty] | 5330 | 217972.4588 | 5330 | 217972.4588
[6 empty] | 5331 | 2063403.3608 | 5331 | 0
[6 empty] | 5332 | 0 | 5332 | 0
[6 empty] | 5333 | 0 | 5333 | 0
[6 empty] | 5334 | 1716190.5944 | 5334 | 0
[6 empty] | 5335 | 0 | 5335 | 0
[6 empty] | 5336 | 0 | 5336 | 0
[6 empty] | 5337 | 0 | 5337 | 0
[6 empty] | 5338 | 0 | 5338 | 0
[6 empty] | 5339 | 0 | 5339 | 0
[6 empty] | 5340 | 3109561.5646 | 5340 | 0
[6 empty] | 5341 | 0 | 5341 | 0
[6 empty] | 5342 | 353208.5177 | 5342 | 353208.5177
[6 empty] | 5343 | 0 | 5343 | 0
[6 empty] | 5344 | 1188893.7795 | 5344 | 1188893.7795
[6 empty] | 5345 | 0 | 5345 | 0
[6 empty] | 5346 | 968757.0798 | 5346 | 968757.0798
[6 empty] | 5347 | 0 | 5347 | 0
[6 empty] | 5348 | 0 | 5348 | 0
[6 empty] | 5349 | 0 | 5349 | 0
[6 empty] | 5350 | 0 | 5350 | 0
[6 empty] | 5351 | 0 | 5351 | 0
[6 empty] | 5352 | 0 | 5352 | 0
[6 empty] | 5353 | 612900.668 | 5353 | 612900.668
[6 empty] | 5354 | 0 | 5354 | 0
[6 empty] | 5355 | 2680408.2171 | 5355 | 2680408.2171
[6 empty] | 5356 | 3805540.2914 | 5356 | 3805540.2914
[6 empty] | 5357 | 2066449.7001 | 5357 | 2066449.7001
[6 empty] | 5358 | 0 | 5358 | 0
[6 empty] | 5359 | 185725.7246 | 5359 | 185725.7246
[6 empty] | 5360 | 0 | 5360 | 0
[6 empty] | 5361 | 0 | 5361 | 0
[6 empty] | 5362 | 0 | 5362 | 0
[6 empty] | 5363 | 0 | 5363 | 0
[6 empty] | 5364 | 0 | 5364 | 0
[6 empty] | 5365 | 0 | 5365 | 0
[6 empty] | 5366 | 0 | 5366 | 0
[6 empty] | 5367 | 0 | 5367 | 0
[6 empty] | 5368 | 0 | 5368 | 0
[6 empty] | 5369 | 3478818.2355 | 5369 | 3478818.2355
[6 empty] | 5370 | 0 | 5370 | 0
[6 empty] | 5371 | 2745695.7828 | 5371 | 0
[6 empty] | 5372 | 0 | 5372 | 0
[6 empty] | 5373 | 0 | 5373 | 0
[6 empty] | 5374 | 4663187.7428 | 5374 | 1848354.7036
[6 empty] | 5375 | 0 | 5375 | 0
[6 empty] | 5376 | 2450283.2485 | 5376 | 0
[6 empty] | 5377 | 0 | 5377 | 0
[6 empty] | 5378 | 0 | 5378 | 0
[6 empty] | 5379 | 771312.7095 | 5379 | 771312.7095
[6 empty] | 5380 | 0 | 5380 | 0
[6 empty] | 5381 | 232572.7337 | 5381 | 232572.7337
[6 empty] | 5382 | 0 | 5382 | 0
[6 empty] | 5383 | 619630.669 | 5383 | 619630.669
[6 empty] | 5384 | 0 | 5384 | 0
[6 empty] | 5385 | 227443.2876 | 5385 | 227443.2876
[6 empty] | 5386 | 5851790.248 | 5386 | 0
[6 empty] | 5387 | 6714370.8512 | 5387 | 1932750.3181
[6 empty] | 5388 | 0 | 5388 | 0
[6 empty] | 5389 | 0 | 5389 | 0
[6 empty] | 5390 | 0 | 5390 | 0
[6 empty] | 5391 | 0 | 5391 | 0
[6 empty] | 5392 | 369657.2275 | 5392 | 369657.2275
[6 empty] | 5393 | 5321756.5581 | 5393 | 996323.5207
[6 empty] | 5394 | 0 | 5394 | 0
[6 empty] | 5395 | 206562.8375 | 5395 | 0
[6 empty] | 5396 | 0 | 5396 | 0
[6 empty] | 5397 | 1014348.0759 | 5397 | 0
[6 empty] | 5398 | 0 | 5398 | 0
[6 empty] | 5399 | 5945076.1027 | 5399 | 5715040.3075
[6 empty] | 5400 | 2836163.5576 | 5400 | 2836163.5576
[6 empty] | 5401 | 288674.7062 | 5401 | 288674.7062
[6 empty] | 5402 | 0 | 5402 | 0
[6 empty] | 5403 | 0 | 5403 | 0
[6 empty] | 5404 | 0 | 5404 | 0
[6 empty] | 5405 | 171468.5846 | 5405 | 0
[6 empty] | 5406 | 0 | 5406 | 0
[6 empty] | 5407 | 3911998.4948 | 5407 | 1588028.1027
[6 empty] | 5408 | 0 | 5408 | 0
[6 empty] | 5409 | 0 | 5409 | 0
[6 empty] | 5410 | 0 | 5410 | 0
[6 empty] | 5411 | 350575.8627 | 5411 | 350575.8627
[6 empty] | 5412 | 17665523.0239 | 5412 | 0
[6 empty] | 5413 | 3993138.7628 | 5413 | 3993138.7628
[6 empty] | 5414 | 793070.9054 | 5414 | 793070.9054
[6 empty] | 5415 | 0 | 5415 | 0
[6 empty] | 5416 | 0 | 5416 | 0
[6 empty] | 5417 | 0 | 5417 | 0
[6 empty] | 5418 | 2679295.1748 | 5418 | 0
[6 empty] | 5419 | 251024.2796 | 5419 | 251024.2796
[6 empty] | 5420 | 7853733.1575 | 5420 | 0
[6 empty] | 5421 | 187150.8734 | 5421 | 187150.8734
[6 empty] | 5422 | 4975594.2438 | 5422 | 4975594.2438
[6 empty] | 5423 | 0 | 5423 | 0
[6 empty] | 5424 | 0 | 5424 | 0
[6 empty] | 5425 | 0 | 5425 | 0
[6 empty] | 5426 | 3907342.6565 | 5426 | 227514.9682
[6 empty] | 5427 | 1802533.7014 | 5427 | 1802533.7014
[6 empty] | 5428 | 257056.0978 | 5428 | 0
[6 empty] | 5429 | 0 | 5429 | 0
[6 empty] | 5430 | 0 | 5430 | 0
[6 empty] | 5431 | 16209384.3363 | 5431 | 427181.0961
[6 empty] | 5432 | 0 | 5432 | 0
[6 empty] | 5433 | 2905591.2436 | 5433 | 2905591.2436
[6 empty] | 5434 | 0 | 5434 | 0
[6 empty] | 5435 | 2510002.8915 | 5435 | 0
[6 empty] | 5436 | 0 | 5436 | 0
[6 empty] | 5437 | 178004.3453 | 5437 | 0
[6 empty] | 5438 | 0 | 5438 | 0
[6 empty] | 5439 | 0 | 5439 | 0
[6 empty] | 5440 | 0 | 5440 | 0
[6 empty] | 5441 | 639687.6457 | 5441 | 639687.6457
[6 empty] | 5442 | 0 | 5442 | 0
[6 empty] | 5443 | 4643530.64 | 5443 | 0
[6 empty] | 5444 | 193048.4642 | 5444 | 193048.4642
[6 empty] | 5445 | 2962044.1408 | 5445 | 0
[6 empty] | 5446 | 0 | 5446 | 0
[6 empty] | 5447 | 1589220.395 | 5447 | 1589220.395
[6 empty] | 5448 | 0 | 5448 | 0
[6 empty] | 5449 | 2490341.4539 | 5449 | 0
[6 empty] | 5450 | 208686.6628 | 5450 | 208686.6628
[6 empty] | 5451 | 12450774.9014 | 5451 | 0
[6 empty] | 5452 | 273647.2172 | 5452 | 273647.2172
[6 empty] | 5453 | 3525953.5568 | 5453 | 3525953.5568
[6 empty] | 5454 | 0 | 5454 | 0
[6 empty] | 5455 | 0 | 5455 | 0
[6 empty] | 5456 | 18591657.6622 | 5456 | 3466452.1134
[6 empty] | 5457 | 265827.7588 | 5457 | 265827.7588
[6 empty] | 5458 | 0 | 5458 | 0
[6 empty] | 5459 | 204391.7892 | 5459 | 0
[6 empty] | 5460 | 0 | 5460 | 0
[6 empty] | 5461 | 0 | 5461 | 0
[6 empty] | 5462 | 0 | 5462 | 0
[6 empty] | 5463 | 0 | 5463 | 0
[6 empty] | 5464 | 222370.4538 | 5464 | 0
[6 empty] | 5465 | 0 | 5465 | 0
[6 empty] | 5466 | 0 | 5466 | 0
[6 empty] | 5467 | 0 | 5467 | 0
[6 empty] | 5468 | 0 | 5468 | 0
[6 empty] | 5469 | 313134.705 | 5469 | 313134.705
[6 empty] | 5470 | 0 | 5470 | 0
[6 empty] | 5471 | 2485615.427 | 5471 | 0
[6 empty] | 5472 | 0 | 5472 | 0
[6 empty] | 5473 | 4723041.7532 | 5473 | 4723041.7532
[6 empty] | 5474 | 2922217.8978 | 5474 | 2922217.8978
[6 empty] | 5475 | 771339.7537 | 5475 | 451188.1583
[6 empty] | 5476 | 2256781.1501 | 5476 | 0
[6 empty] | 5477 | 1534084.8194 | 5477 | 0
[6 empty] | 5478 | 6030162.4954 | 5478 | 183216.5895
[6 empty] | 5479 | 3039834.0156 | 5479 | 3039834.0156
[6 empty] | 5480 | 0 | 5480 | 0
[6 empty] | 5481 | 0 | 5481 | 0
[6 empty] | 5482 | 0 | 5482 | 0
[6 empty] | 5483 | 0 | 5483 | 0
[6 empty] | 5484 | 0 | 5484 | 0
[6 empty] | 5485 | 10715957.9067 | 5485 | 0
[6 empty] | 5486 | 488072.5078 | 5486 | 488072.5078
[6 empty] | 5487 | 0 | 5487 | 0
[6 empty] | 5488 | 4532323.5191 | 5488 | 0
[6 empty] | 5489 | 1340043.6642 | 5489 | 1340043.6642
[6 empty] | 5490 | 0 | 5490 | 0
[6 empty] | 5491 | 0 | 5491 | 0
[6 empty] | 5492 | 302647.8836 | 5492 | 302647.8836
[6 empty] | 5493 | 4554040.8236 | 5493 | 0
[6 empty] | 5494 | 0 | 5494 | 0
[6 empty] | 5495 | 627915.3265 | 5495 | 627915.3265
[6 empty] | 5496 | 0 | 5496 | 0
[6 empty] | 5497 | 0 | 5497 | 0
[6 empty] | 5498 | 1614112.1563 | 5498 | 205193.6391
[6 empty] | 5499 | 0 | 5499 | 0
[6 empty] | 5500 | 0 | 5500 | 0
[6 empty] | 5501 | 2543179.0156 | 5501 | 2543179.0156
[6 empty] | 5502 | 0 | 5502 | 0
[6 empty] | 5503 | 167737.3151 | 5503 | 0
[6 empty] | 5504 | 724205.7219 | 5504 | 724205.7219
[6 empty] | 5505 | 5007983.1061 | 5505 | 0
[6 empty] | 5506 | 0 | 5506 | 0
[6 empty] | 5507 | 0 | 5507 | 0
[6 empty] | 5508 | 227999.722 | 5508 | 227999.722
[6 empty] | 5509 | 0 | 5509 | 0
[6 empty] | 5510 | 1230635.841 | 5510 | 1230635.841
[6 empty] | 5511 | 2674475.7641 | 5511 | 2674475.7641
[6 empty] | 5512 | 0 | 5512 | 0
[6 empty] | 5513 | 0 | 5513 | 0
[6 empty] | 5514 | 0 | 5514 | 0
[6 empty] | 5515 | 1416711.748 | 5515 | 141021.5112
[6 empty] | 5516 | 0 | 5516 | 0
[6 empty] | 5517 | 4053083.9464 | 5517 | 0
[6 empty] | 5518 | 1209392.4933 | 5518 | 1209392.4933
[6 empty] | 5519 | 2754598.2562 | 5519 | 2591810.3952
[6 empty] | 5520 | 253103.2975 | 5520 | 253103.2975
[6 empty] | 5521 | 0 | 5521 | 0
[6 empty] | 5522 | 0 | 5522 | 0
[6 empty] | 5523 | 5139585.3918 | 5523 | 0
[6 empty] | 5524 | 216931.6435 | 5524 | 216931.6435
[6 empty] | 5525 | 0 | 5525 | 0
[6 empty] | 5526 | 0 | 5526 | 0
[6 empty] | 5527 | 1939523.8481 | 5527 | 1939523.8481
[6 empty] | 5528 | 0 | 5528 | 0
[6 empty] | 5529 | 0 | 5529 | 0
[6 empty] | 5530 | 5677713.1211 | 5530 | 2340936.3291
[6 empty] | 5531 | 0 | 5531 | 0
[6 empty] | 5532 | 0 | 5532 | 0
[6 empty] | 5533 | 0 | 5533 | 0
[6 empty] | 5534 | 283047.543 | 5534 | 0
[6 empty] | 5535 | 0 | 5535 | 0
[6 empty] | 5536 | 0 | 5536 | 0
[6 empty] | 5537 | 157250.3232 | 5537 | 157250.3232
[6 empty] | 5538 | 0 | 5538 | 0
[6 empty] | 5539 | 0 | 5539 | 0
[6 empty] | 5540 | 847789.0778 | 5540 | 847789.0778
[6 empty] | 5541 | 236826.9153 | 5541 | 236826.9153
[6 empty] | 5542 | 4492495.0041 | 5542 | 264687.0413
[6 empty] | 5543 | 209477.8259 | 5543 | 209477.8259
[6 empty] | 5544 | 0 | 5544 | 0
[6 empty] | 5545 | 0 | 5545 | 0
[6 empty] | 5546 | 0 | 5546 | 0
[6 empty] | 5547 | 436794.9822 | 5547 | 436794.9822
[6 empty] | 5548 | 0 | 5548 | 0
[6 empty] | 5549 | 1295806.3657 | 5549 | 1295806.3657
[6 empty] | 5550 | 0 | 5550 | 0
[6 empty] | 5551 | 257803.9326 | 5551 | 0
[6 empty] | 5552 | 0 | 5552 | 0
[6 empty] | 5553 | 10434336.477 | 5553 | 0
[6 empty] | 5554 | 0 | 5554 | 0
[6 empty] | 5555 | 223829.8619 | 5555 | 0
[6 empty] | 5556 | 2988993.6657 | 5556 | 215740.3581
[6 empty] | 5557 | 698624.7283 | 5557 | 108429.9633
[6 empty] | 5558 | 5179807.6994 | 5558 | 764878.0984
[6 empty] | 5559 | 0 | 5559 | 0
[6 empty] | 5560 | 0 | 5560 | 0
[6 empty] | 5561 | 0 | 5561 | 0
[6 empty] | 5562 | 0 | 5562 | 0
[6 empty] | 5563 | 1726749.0556 | 5563 | 1726749.0556
[6 empty] | 5564 | 0 | 5564 | 0
[6 empty] | 5565 | 0 | 5565 | 0
[6 empty] | 5566 | 212458.9116 | 5566 | 212458.9116
[6 empty] | 5567 | 0 | 5567 | 0
[6 empty] | 5568 | 0 | 5568 | 0
[6 empty] | 5569 | 0 | 5569 | 0
[6 empty] | 5570 | 0 | 5570 | 0
[6 empty] | 5571 | 0 | 5571 | 0
[6 empty] | 5572 | 8501948.2334 | 5572 | 8501948.2334
[6 empty] | 5573 | 226690.5799 | 5573 | 226690.5799
[6 empty] | 5574 | 7808466.8878 | 5574 | 298875.7395
[6 empty] | 5575 | 0 | 5575 | 0
[6 empty] | 5576 | 0 | 5576 | 0
[6 empty] | 5577 | 339765.391 | 5577 | 339765.391
[6 empty] | 5578 | 0 | 5578 | 0
[6 empty] | 5579 | 0 | 5579 | 0
[6 empty] | 5580 | 5154433.6794 | 5580 | 5154433.6794
[6 empty] | 5581 | 926472.9674 | 5581 | 926472.9674
[6 empty] | 5582 | 0 | 5582 | 0
[6 empty] | 5583 | 266528.611 | 5583 | 266528.611
[6 empty] | 5584 | 197110.8829 | 5584 | 197110.8829
[6 empty] | 5585 | 0 | 5585 | 0
[6 empty] | 5586 | 0 | 5586 | 0
[6 empty] | 5587 | 0 | 5587 | 0
[6 empty] | 5588 | 224169.0227 | 5588 | 0
[6 empty] | 5589 | 3403074.7779 | 5589 | 0
[6 empty] | 5590 | 246165.6592 | 5590 | 93242.7713
[6 empty] | 5591 | 0 | 5591 | 0
[6 empty] | 5592 | 235327.0813 | 5592 | 235327.0813
[6 empty] | 5593 | 3317661.7053 | 5593 | 0
[6 empty] | 5594 | 0 | 5594 | 0
[6 empty] | 5595 | 1458778.3956 | 5595 | 0
[6 empty] | 5596 | 0 | 5596 | 0
[6 empty] | 5597 | 3356646.4052 | 5597 | 3356646.4052
[6 empty] | 5598 | 0 | 5598 | 0
[6 empty] | 5599 | 11806961.4817 | 5599 | 11806961.4817
[6 empty] | 5600 | 0 | 5600 | 0
[6 empty] | 5601 | 0 | 5601 | 0
[6 empty] | 5602 | 0 | 5602 | 0
[6 empty] | 5603 | 0 | 5603 | 0
[6 empty] | 5604 | 0 | 5604 | 0
[6 empty] | 5605 | 0 | 5605 | 0
[6 empty] | 5606 | 907930.7242 | 5606 | 907930.7242
[6 empty] | 5607 | 3816624.9487 | 5607 | 0
[6 empty] | 5608 | 337779.4353 | 5608 | 337779.4353
[6 empty] | 5609 | 747257.4118 | 5609 | 521979.6018
[6 empty] | 5610 | 7359590.0933 | 5610 | 7359590.0933
[6 empty] | 5611 | 534392.9137 | 5611 | 534392.9137
[6 empty] | 5612 | 0 | 5612 | 0
[6 empty] | 5613 | 0 | 5613 | 0
[6 empty] | 5614 | 0 | 5614 | 0
[6 empty] | 5615 | 4485719.1584 | 5615 | 116793.6199
[6 empty] | 5616 | 0 | 5616 | 0
[6 empty] | 5617 | 0 | 5617 | 0
[6 empty] | 5618 | 0 | 5618 | 0
[6 empty] | 5619 | 147432.1141 | 5619 | 147432.1141
[6 empty] | 5620 | 1026020.6605 | 5620 | 0
[6 empty] | 5621 | 3410225.6187 | 5621 | 3410225.6187
[6 empty] | 5622 | 0 | 5622 | 0
[6 empty] | 5623 | 389003.6658 | 5623 | 253312.9745
[6 empty] | 5624 | 266976.9661 | 5624 | 0
[6 empty] | 5625 | 5053790.8229 | 5625 | 5053790.8229
[6 empty] | 5626 | 4285884.3438 | 5626 | 4285884.3438
[6 empty] | 5627 | 642317.7171 | 5627 | 335535.3866
[6 empty] | 5628 | 5053478.952 | 5628 | 0
[6 empty] | 5629 | 2653311.4374 | 5629 | 0
[6 empty] | 5630 | 4521805.1579 | 5630 | 0
[6 empty] | 5631 | 512080.934 | 5631 | 512080.934
[6 empty] | 5632 | 319282.171 | 5632 | 319282.171
[6 empty] | 5633 | 3230669.4663 | 5633 | 3012031.4858
[6 empty] | 5634 | 261730.9331 | 5634 | 0
[6 empty] | 5635 | 2089536.9626 | 5635 | 2089536.9626
[6 empty] | 5636 | 4512297.4623 | 5636 | 4512297.4623
[6 empty] | 5637 | 0 | 5637 | 0
[6 empty] | 5638 | 84895.7076 | 5638 | 84895.7076
[6 empty] | 5639 | 0 | 5639 | 0
[6 empty] | 5640 | 3176584.3429 | 5640 | 3176584.3429
[6 empty] | 5641 | 0 | 5641 | 0
[6 empty] | 5642 | 153401.9449 | 5642 | 0
[6 empty] | 5643 | 249102.3048 | 5643 | 249102.3048
[6 empty] | 5644 | 0 | 5644 | 0
[6 empty] | 5645 | 0 | 5645 | 0
[6 empty] | 5646 | 402070.599 | 5646 | 402070.599
[6 empty] | 5647 | 0 | 5647 | 0
[6 empty] | 5648 | 0 | 5648 | 0
[6 empty] | 5649 | 0 | 5649 | 0
[6 empty] | 5650 | 6002498.503 | 5650 | 0
[6 empty] | 5651 | 4721034.2167 | 5651 | 0
[6 empty] | 5652 | 0 | 5652 | 0
[6 empty] | 5653 | 0 | 5653 | 0
[6 empty] | 5654 | 216428.8762 | 5654 | 216428.8762
[6 empty] | 5655 | 0 | 5655 | 0
[6 empty] | 5656 | 280944.0253 | 5656 | 280944.0253
[6 empty] | 5657 | 223377.9034 | 5657 | 223377.9034
[6 empty] | 5658 | 944751.8045 | 5658 | 944751.8045
[6 empty] | 5659 | 3514188.177 | 5659 | 0
[6 empty] | 5660 | 215933.7756 | 5660 | 215933.7756
[6 empty] | 5661 | 7664014.4541 | 5661 | 0
[6 empty] | 5662 | 0 | 5662 | 0
[6 empty] | 5663 | 8787896.774 | 5663 | 0
[6 empty] | 5664 | 164644.5658 | 5664 | 164644.5658
[6 empty] | 5665 | 187407.2885 | 5665 | 187407.2885
[6 empty] | 5666 | 0 | 5666 | 0
[6 empty] | 5667 | 0 | 5667 | 0
[6 empty] | 5668 | 0 | 5668 | 0
[6 empty] | 5669 | 230705.7699 | 5669 | 230705.7699
[6 empty] | 5670 | 3312209.0391 | 5670 | 0
[6 empty] | 5671 | 145003.0527 | 5671 | 145003.0527
[6 empty] | 5672 | 1809146.8476 | 5672 | 1809146.8476
[6 empty] | 5673 | 3842489.7513 | 5673 | 3842489.7513
[6 empty] | 5674 | 0 | 5674 | 0
[6 empty] | 5675 | 0 | 5675 | 0
[6 empty] | 5676 | 215772.9544 | 5676 | 215772.9544
[6 empty] | 5677 | 3851538.1105 | 5677 | 2491793.9467
[6 empty] | 5678 | 0 | 5678 | 0
[6 empty] | 5679 | 175519.8705 | 5679 | 0
[6 empty] | 5680 | 0 | 5680 | 0
[6 empty] | 5681 | 228468.7955 | 5681 | 228468.7955
[6 empty] | 5682 | 0 | 5682 | 0
[6 empty] | 5683 | 249529.0919 | 5683 | 0
[6 empty] | 5684 | 3542812.166 | 5684 | 0
[6 empty] | 5685 | 1345421.5452 | 5685 | 646559.4
[6 empty] | 5686 | 0 | 5686 | 0
[6 empty] | 5687 | 0 | 5687 | 0
[6 empty] | 5688 | 0 | 5688 | 0
[6 empty] | 5689 | 273111.2945 | 5689 | 273111.2945
[6 empty] | 5690 | 0 | 5690 | 0
[6 empty] | 5691 | 703059.2618 | 5691 | 0
[6 empty] | 5692 | 911478.2241 | 5692 | 0
[6 empty] | 5693 | 0 | 5693 | 0
[6 empty] | 5694 | 223819.7457 | 5694 | 0
[6 empty] | 5695 | 0 | 5695 | 0
[6 empty] | 5696 | 147178.9242 | 5696 | 147178.9242
[6 empty] | 5697 | 0 | 5697 | 0
[6 empty] | 5698 | 0 | 5698 | 0
[6 empty] | 5699 | 225351.2603 | 5699 | 225351.2603
[6 empty] | 5700 | 206303.362 | 5700 | 206303.362
[6 empty] | 5701 | 0 | 5701 | 0
[6 empty] | 5702 | 1201757.6626 | 5702 | 0
[6 empty] | 5703 | 8499667.8469 | 5703 | 8499667.8469
[6 empty] | 5704 | 0 | 5704 | 0
[6 empty] | 5705 | 11018054.6681 | 5705 | 1186843.5542
[6 empty] | 5706 | 0 | 5706 | 0
[6 empty] | 5707 | 0 | 5707 | 0
[6 empty] | 5708 | 2314523.9525 | 5708 | 0
[6 empty] | 5709 | 371323.7515 | 5709 | 371323.7515
[6 empty] | 5710 | 0 | 5710 | 0
[6 empty] | 5711 | 281969.1627 | 5711 | 281969.1627
[6 empty] | 5712 | 0 | 5712 | 0
[6 empty] | 5713 | 731264.9158 | 5713 | 731264.9158
[6 empty] | 5714 | 881878.2545 | 5714 | 0
[6 empty] | 5715 | 2743940.8867 | 5715 | 0
[6 empty] | 5716 | 0 | 5716 | 0
[6 empty] | 5717 | 156388.6775 | 5717 | 156388.6775
[6 empty] | 5718 | 7174701.4812 | 5718 | 0
[6 empty] | 5719 | 0 | 5719 | 0
[6 empty] | 5720 | 891165.8487 | 5720 | 189731.787
[6 empty] | 5721 | 0 | 5721 | 0
[6 empty] | 5722 | 1241296.1858 | 5722 | 1241296.1858
[6 empty] | 5723 | 137207.5455 | 5723 | 137207.5455
[6 empty] | 5724 | 0 | 5724 | 0
[6 empty] | 5725 | 3855485.3196 | 5725 | 0
[6 empty] | 5726 | 0 | 5726 | 0
[6 empty] | 5727 | 158625.4921 | 5727 | 158625.4921
[6 empty] | 5728 | 0 | 5728 | 0
[6 empty] | 5729 | 0 | 5729 | 0
[6 empty] | 5730 | 0 | 5730 | 0
[6 empty] | 5731 | 10629629.3661 | 5731 | 0
[6 empty] | 5732 | 0 | 5732 | 0
[6 empty] | 5733 | 17658711.8668 | 5733 | 390006.282
[6 empty] | 5734 | 95508.1976 | 5734 | 95508.1976
[6 empty] | 5735 | 515342.155 | 5735 | 260045.0758
[6 empty] | 5736 | 2911155.1402 | 5736 | 2911155.1402
[6 empty] | 5737 | 0 | 5737 | 0
[6 empty] | 5738 | 5573044.6053 | 5738 | 0
[6 empty] | 5739 | 22037753.685 | 5739 | 0
[6 empty] | 5740 | 0 | 5740 | 0
[6 empty] | 5741 | 0 | 5741 | 0
[6 empty] | 5742 | 2170836.1175 | 5742 | 0
[6 empty] | 5743 | 0 | 5743 | 0
[6 empty] | 5744 | 0 | 5744 | 0
[6 empty] | 5745 | 0 | 5745 | 0
[6 empty] | 5746 | 4289033.1447 | 5746 | 4045392.7824
[6 empty] | 5747 | 0 | 5747 | 0
[6 empty] | 5748 | 0 | 5748 | 0
[6 empty] | 5749 | 0 | 5749 | 0
[6 empty] | 5750 | 0 | 5750 | 0
[6 empty] | 5751 | 158855.522 | 5751 | 158855.522
[6 empty] | 5752 | 159208.8344 | 5752 | 0
[6 empty] | 5753 | 6280298.0336 | 5753 | 2381384.418
[6 empty] | 5754 | 249910.6128 | 5754 | 0
[6 empty] | 5755 | 2299645.777 | 5755 | 2299645.777
[6 empty] | 5756 | 452787.7877 | 5756 | 452787.7877
[6 empty] | 5757 | 0 | 5757 | 0
[6 empty] | 5758 | 0 | 5758 | 0
[6 empty] | 5759 | 1372761.0929 | 5759 | 1372761.0929
[6 empty] | 5760 | 5091757.7917 | 5760 | 5091757.7917
[6 empty] | 5761 | 0 | 5761 | 0
[6 empty] | 5762 | 184416.3849 | 5762 | 184416.3849
[6 empty] | 5763 | 0 | 5763 | 0
[6 empty] | 5764 | 0 | 5764 | 0
[6 empty] | 5765 | 0 | 5765 | 0
[6 empty] | 5766 | 260565.3071 | 5766 | 0
[6 empty] | 5767 | 3064647.8772 | 5767 | 0
[6 empty] | 5768 | 310810.2747 | 5768 | 310810.2747
[6 empty] | 5769 | 2531048.5448 | 5769 | 2531048.5448
[6 empty] | 5770 | 864937.0868 | 5770 | 677164.7145
[6 empty] | 5771 | 4158005.023 | 5771 | 0
[6 empty] | 5772 | 3171682.8268 | 5772 | 3171682.8268
[6 empty] | 5773 | 6937408.9121 | 5773 | 0
[6 empty] | 5774 | 2742943.6905 | 5774 | 2742943.6905
[6 empty] | 5775 | 0 | 5775 | 0
[6 empty] | 5776 | 0 | 5776 | 0
[6 empty] | 5777 | 3858511.4416 | 5777 | 3858511.4416
[6 empty] | 5778 | 0 | 5778 | 0
[6 empty] | 5779 | 0 | 5779 | 0
[6 empty] | 5780 | 3194756.2891 | 5780 | 3194756.2891
[6 empty] | 5781 | 2337423.1148 | 5781 | 0
[6 empty] | 5782 | 0 | 5782 | 0
[6 empty] | 5783 | 0 | 5783 | 0
[6 empty] | 5784 | 4908965.2346 | 5784 | 182739.8957
[6 empty] | 5785 | 0 | 5785 | 0
[6 empty] | 5786 | 0 | 5786 | 0
[6 empty] | 5787 | 0 | 5787 | 0
[6 empty] | 5788 | 0 | 5788 | 0
[6 empty] | 5789 | 9222910.2932 | 5789 | 0
[6 empty] | 5790 | 0 | 5790 | 0
[6 empty] | 5791 | 0 | 5791 | 0
[6 empty] | 5792 | 0 | 5792 | 0
[6 empty] | 5793 | 1181296.174 | 5793 | 209950.8427
[6 empty] | 5794 | 5800749.0062 | 5794 | 252796.4039
[6 empty] | 5795 | 6881954.5148 | 5795 | 0
[6 empty] | 5796 | 0 | 5796 | 0
[6 empty] | 5797 | 2577211.8568 | 5797 | 0
[6 empty] | 5798 | 0 | 5798 | 0
[6 empty] | 5799 | 0 | 5799 | 0
[6 empty] | 5800 | 0 | 5800 | 0
[6 empty] | 5801 | 2856177.8065 | 5801 | 2856177.8065
[6 empty] | 5802 | 4255151.9587 | 5802 | 3095946.4807
[6 empty] | 5803 | 258883.9445 | 5803 | 258883.9445
[6 empty] | 5804 | 0 | 5804 | 0
[6 empty] | 5805 | 2331094.4134 | 5805 | 246893.407
[6 empty] | 5806 | 0 | 5806 | 0
[6 empty] | 5807 | 181892.1821 | 5807 | 181892.1821
[6 empty] | 5808 | 0 | 5808 | 0
[6 empty] | 5809 | 2579722.1958 | 5809 | 449088.075
[6 empty] | 5810 | 0 | 5810 | 0
[6 empty] | 5811 | 429238.8082 | 5811 | 429238.8082
[6 empty] | 5812 | 498903.5628 | 5812 | 498903.5628
[6 empty] | 5813 | 0 | 5813 | 0
[6 empty] | 5814 | 591067.6351 | 5814 | 591067.6351
[6 empty] | 5815 | 1674212.9819 | 5815 | 0
[6 empty] | 5816 | 2515982.5393 | 5816 | 276828.9272
[6 empty] | 5817 | 0 | 5817 | 0
[6 empty] | 5818 | 240662.9179 | 5818 | 240662.9179
[6 empty] | 5819 | 0 | 5819 | 0
[6 empty] | 5820 | 220952.7352 | 5820 | 0
[6 empty] | 5821 | 204979.6909 | 5821 | 0
[6 empty] | 5822 | 0 | 5822 | 0
[6 empty] | 5823 | 2835000.3893 | 5823 | 0
[6 empty] | 5824 | 0 | 5824 | 0
[6 empty] | 5825 | 0 | 5825 | 0
[6 empty] | 5826 | 0 | 5826 | 0
[6 empty] | 5827 | 0 | 5827 | 0
[6 empty] | 5828 | 2564429.3544 | 5828 | 0
[6 empty] | 5829 | 0 | 5829 | 0
[6 empty] | 5830 | 0 | 5830 | 0
[6 empty] | 5831 | 0 | 5831 | 0
[6 empty] | 5832 | 3111816.5136 | 5832 | 0
[6 empty] | 5833 | 5914300.2386 | 5833 | 2034169.7426
[6 empty] | 5834 | 2832242.9674 | 5834 | 0
[6 empty] | 5835 | 0 | 5835 | 0
[6 empty] | 5836 | 573885.4222 | 5836 | 0
[6 empty] | 5837 | 0 | 5837 | 0
[6 empty] | 5838 | 0 | 5838 | 0
[6 empty] | 5839 | 506858.0277 | 5839 | 506858.0277
[6 empty] | 5840 | 0 | 5840 | 0
[6 empty] | 5841 | 185626.4115 | 5841 | 185626.4115
[6 empty] | 5842 | 1063184.3442 | 5842 | 1063184.3442
[6 empty] | 5843 | 246744.3758 | 5843 | 0
[6 empty] | 5844 | 3394430.5423 | 5844 | 0
[6 empty] | 5845 | 225548.5602 | 5845 | 225548.5602
[6 empty] | 5846 | 0 | 5846 | 0
[6 empty] | 5847 | 0 | 5847 | 0
[6 empty] | 5848 | 0 | 5848 | 0
[6 empty] | 5849 | 3104569.096 | 5849 | 3104569.096
[6 empty] | 5850 | 0 | 5850 | 0
[6 empty] | 5851 | 0 | 5851 | 0
[6 empty] | 5852 | 0 | 5852 | 0
[6 empty] | 5853 | 0 | 5853 | 0
[6 empty] | 5854 | 0 | 5854 | 0
[6 empty] | 5855 | 205525.8515 | 5855 | 205525.8515
[6 empty] | 5856 | 215952.0598 | 5856 | 215952.0598
[6 empty] | 5857 | 0 | 5857 | 0
[6 empty] | 5858 | 165930.5799 | 5858 | 0
[6 empty] | 5859 | 0 | 5859 | 0
[6 empty] | 5860 | 0 | 5860 | 0
[6 empty] | 5861 | 0 | 5861 | 0
[6 empty] | 5862 | 2459676.0094 | 5862 | 2459676.0094
[6 empty] | 5863 | 0 | 5863 | 0
[6 empty] | 5864 | 194656.3554 | 5864 | 194656.3554
[6 empty] | 5865 | 2252089.3481 | 5865 | 0
[6 empty] | 5866 | 0 | 5866 | 0
[6 empty] | 5867 | 2567200.8805 | 5867 | 2567200.8805
[6 empty] | 5868 | 0 | 5868 | 0
[6 empty] | 5869 | 0 | 5869 | 0
[6 empty] | 5870 | 271452.2396 | 5870 | 0
[6 empty] | 5871 | 1527049.8368 | 5871 | 0
[6 empty] | 5872 | 2547779.1135 | 5872 | 0
[6 empty] | 5873 | 3047074.6522 | 5873 | 2751080.7669
[6 empty] | 5874 | 0 | 5874 | 0
[6 empty] | 5875 | 0 | 5875 | 0
[6 empty] | 5876 | 271616.3909 | 5876 | 271616.3909
[6 empty] | 5877 | 0 | 5877 | 0
[6 empty] | 5878 | 0 | 5878 | 0
[6 empty] | 5879 | 2834729.208 | 5879 | 2834729.208
[6 empty] | 5880 | 290503.7434 | 5880 | 0
[6 empty] | 5881 | 0 | 5881 | 0
[6 empty] | 5882 | 0 | 5882 | 0
[6 empty] | 5883 | 0 | 5883 | 0
[6 empty] | 5884 | 558698.2705 | 5884 | 558698.2705
[6 empty] | 5885 | 0 | 5885 | 0
[6 empty] | 5886 | 0 | 5886 | 0
[6 empty] | 5887 | 4434655.2843 | 5887 | 0
[6 empty] | 5888 | 0 | 5888 | 0
[6 empty] | 5889 | 0 | 5889 | 0
[6 empty] | 5890 | 190671.2707 | 5890 | 0
[6 empty] | 5891 | 0 | 5891 | 0
[6 empty] | 5892 | 0 | 5892 | 0
[6 empty] | 5893 | 0 | 5893 | 0
[6 empty] | 5894 | 0 | 5894 | 0
[6 empty] | 5895 | 0 | 5895 | 0
[6 empty] | 5896 | 0 | 5896 | 0
[6 empty] | 5897 | 107795.4833 | 5897 | 107795.4833
[6 empty] | 5898 | 3708044.4927 | 5898 | 0
[6 empty] | 5899 | 0 | 5899 | 0
[6 empty] | 5900 | 555684.2109 | 5900 | 555684.2109
[6 empty] | 5901 | 1783319.5698 | 5901 | 1783319.5698
[6 empty] | 5902 | 472237.5673 | 5902 | 472237.5673
[6 empty] | 5903 | 3587134.6476 | 5903 | 0
[6 empty] | 5904 | 2184300.0056 | 5904 | 2184300.0056
[6 empty] | 5905 | 490205.7238 | 5905 | 244513.4969
[6 empty] | 5906 | 420951.3221 | 5906 | 420951.3221
[6 empty] | 5907 | 4532004.3839 | 5907 | 4532004.3839
[6 empty] | 5908 | 0 | 5908 | 0
[6 empty] | 5909 | 0 | 5909 | 0
[6 empty] | 5910 | 646628.7944 | 5910 | 646628.7944
[6 empty] | 5911 | 269188.2615 | 5911 | 0
[6 empty] | 5912 | 312875.7829 | 5912 | 312875.7829
[6 empty] | 5913 | 277622.5386 | 5913 | 0
[6 empty] | 5914 | 950896.077 | 5914 | 950896.077
[6 empty] | 5915 | 0 | 5915 | 0
[6 empty] | 5916 | 0 | 5916 | 0
[6 empty] | 5917 | 3331153.9587 | 5917 | 3331153.9587
[6 empty] | 5918 | 291723.1956 | 5918 | 291723.1956
[6 empty] | 5919 | 7151993.0266 | 5919 | 0
[6 empty] | 5920 | 0 | 5920 | 0
[6 empty] | 5921 | 283841.5345 | 5921 | 283841.5345
[6 empty] | 5922 | 4391274.8819 | 5922 | 4391274.8819
[6 empty] | 5923 | 944810.6905 | 5923 | 660399.7205
[6 empty] | 5924 | 0 | 5924 | 0
[6 empty] | 5925 | 0 | 5925 | 0
[6 empty] | 5926 | 0 | 5926 | 0
[6 empty] | 5927 | 4134449.2827 | 5927 | 0
[6 empty] | 5928 | 216127.303 | 5928 | 0
[6 empty] | 5929 | 0 | 5929 | 0
[6 empty] | 5930 | 0 | 5930 | 0
[6 empty] | 5931 | 4072992.5574 | 5931 | 4072992.5574
[6 empty] | 5932 | 0 | 5932 | 0
[6 empty] | 5933 | 0 | 5933 | 0
[6 empty] | 5934 | 11659145.3196 | 5934 | 3203539.4869
[6 empty] | 5935 | 202589.8097 | 5935 | 0
[6 empty] | 5936 | 0 | 5936 | 0
[6 empty] | 5937 | 179310.8677 | 5937 | 0
[6 empty] | 5938 | 2569730.218 | 5938 | 173708.817
[6 empty] | 5939 | 0 | 5939 | 0
[6 empty] | 5940 | 0 | 5940 | 0
[6 empty] | 5941 | 140781.7782 | 5941 | 140781.7782
[6 empty] | 5942 | 18718027.5724 | 5942 | 0
[6 empty] | 5943 | 0 | 5943 | 0
[6 empty] | 5944 | 0 | 5944 | 0
[6 empty] | 5945 | 0 | 5945 | 0
[6 empty] | 5946 | 0 | 5946 | 0
[6 empty] | 5947 | 8205414.5119 | 5947 | 0
[6 empty] | 5948 | 210016.6178 | 5948 | 0
[6 empty] | 5949 | 0 | 5949 | 0
[6 empty] | 5950 | 1847249.3354 | 5950 | 500245.2701
[6 empty] | 5951 | 0 | 5951 | 0
[6 empty] | 5952 | 3682804.106 | 5952 | 621086.8589
[6 empty] | 5953 | 0 | 5953 | 0
[6 empty] | 5954 | 0 | 5954 | 0
[6 empty] | 5955 | 993861.0303 | 5955 | 241004.8493
[6 empty] | 5956 | 7280129.527 | 5956 | 213287.6347
[6 empty] | 5957 | 252904.4586 | 5957 | 252904.4586
[6 empty] | 5958 | 0 | 5958 | 0
[6 empty] | 5959 | 0 | 5959 | 0
[6 empty] | 5960 | 0 | 5960 | 0
[6 empty] | 5961 | 3126371.9481 | 5961 | 3126371.9481
[6 empty] | 5962 | 0 | 5962 | 0
[6 empty] | 5963 | 0 | 5963 | 0
[6 empty] | 5964 | 0 | 5964 | 0
[6 empty] | 5965 | 0 | 5965 | 0
[6 empty] | 5966 | 0 | 5966 | 0
[6 empty] | 5967 | 0 | 5967 | 0
[6 empty] | 5968 | 2265231.5499 | 5968 | 418031.1819
[6 empty] | 5969 | 0 | 5969 | 0
[6 empty] | 5970 | 2766455.5715 | 5970 | 0
[6 empty] | 5971 | 0 | 5971 | 0
[6 empty] | 5972 | 0 | 5972 | 0
[6 empty] | 5973 | 0 | 5973 | 0
[6 empty] | 5974 | 195131.1909 | 5974 | 195131.1909
[6 empty] | 5975 | 0 | 5975 | 0
[6 empty] | 5976 | 1861509.3193 | 5976 | 0
[6 empty] | 5977 | 0 | 5977 | 0
[6 empty] | 5978 | 0 | 5978 | 0
[6 empty] | 5979 | 0 | 5979 | 0
[6 empty] | 5980 | 2932795.0305 | 5980 | 2932795.0305
[6 empty] | 5981 | 0 | 5981 | 0
[6 empty] | 5982 | 51093416.2176 | 5982 | 0
[6 empty] | 5983 | 2999728.9427 | 5983 | 0
[6 empty] | 5984 | 143406.1109 | 5984 | 0
[6 empty] | 5985 | 908722.6274 | 5985 | 908722.6274
[6 empty] | 5986 | 6775732.5438 | 5986 | 3993235.6473
[6 empty] | 5987 | 2647223.4532 | 5987 | 0
[6 empty] | 5988 | 2898677.9163 | 5988 | 2898677.9163
[6 empty] | 5989 | 0 | 5989 | 0
[6 empty] | 5990 | 0 | 5990 | 0
[6 empty] | 5991 | 0 | 5991 | 0
[6 empty] | 5992 | 0 | 5992 | 0
[6 empty] | 5993 | 0 | 5993 | 0
[6 empty] | 5994 | 0 | 5994 | 0
[6 empty] | 5995 | 0 | 5995 | 0
[6 empty] | 5996 | 179627.3872 | 5996 | 179627.3872
[6 empty] | 5997 | 0 | 5997 | 0
[6 empty] | 5998 | 0 | 5998 | 0
[6 empty] | 5999 | 0 | 5999 | 0
[6 empty] | 6000 | 0 | 6000 | 0
[6 empty] | 6001 | 0 | 6001 | 0
[6 empty] | 6002 | 0 | 6002 | 0
[6 empty] | 6003 | 0 | 6003 | 0
[6 empty] | 6004 | 0 | 6004 | 0
[6 empty] | 6005 | 330022.0946 | 6005 | 330022.0946
[6 empty] | 6006 | 0 | 6006 | 0
[6 empty] | 6007 | 40735241.4589 | 6007 | 1368477.6941
[6 empty] | 6008 | 0 | 6008 | 0
[6 empty] | 6009 | 390980.8068 | 6009 | 390980.8068
[6 empty] | 6010 | 1740516.4751 | 6010 | 1512146.5224
[6 empty] | 6011 | 676655.7087 | 6011 | 676655.7087
[6 empty] | 6012 | 1067885.1602 | 6012 | 772843.0581
[6 empty] | 6013 | 633137.2899 | 6013 | 633137.2899
[6 empty] | 6014 | 0 | 6014 | 0
[6 empty] | 6015 | 5775564.3635 | 6015 | 5775564.3635
[6 empty] | 6016 | 384903.4298 | 6016 | 384903.4298
[6 empty] | 6017 | 1390302.4936 | 6017 | 0
[6 empty] | 6018 | 0 | 6018 | 0
[6 empty] | 6019 | 4342085.3612 | 6019 | 258251.7363
[6 empty] | 6020 | 1548640.2649 | 6020 | 168126.6453
[6 empty] | 6021 | 0 | 6021 | 0
[6 empty] | 6022 | 702480.3411 | 6022 | 702480.3411
[6 empty] | 6023 | 0 | 6023 | 0
[6 empty] | 6024 | 204571.3295 | 6024 | 204571.3295
[6 empty] | 6025 | 1113476.0585 | 6025 | 1113476.0585
[6 empty] | 6026 | 240678.5042 | 6026 | 240678.5042
[6 empty] | 6027 | 16225062.1104 | 6027 | 0
[6 empty] | 6028 | 16470538.8031 | 6028 | 16470538.8031
[6 empty] | 6029 | 0 | 6029 | 0
[6 empty] | 6030 | 0 | 6030 | 0
[6 empty] | 6031 | 392688.765 | 6031 | 392688.765
[6 empty] | 6032 | 0 | 6032 | 0
[6 empty] | 6033 | 0 | 6033 | 0
[6 empty] | 6034 | 0 | 6034 | 0
[6 empty] | 6035 | 0 | 6035 | 0
[6 empty] | 6036 | 4929215.1135 | 6036 | 0
[6 empty] | 6037 | 844847.0746 | 6037 | 844847.0746
[6 empty] | 6038 | 182443.6963 | 6038 | 0
[6 empty] | 6039 | 0 | 6039 | 0
[6 empty] | 6040 | 0 | 6040 | 0
[6 empty] | 6041 | 0 | 6041 | 0
[6 empty] | 6042 | 0 | 6042 | 0
[6 empty] | 6043 | 3207742.6091 | 6043 | 219101.9157
[6 empty] | 6044 | 285822.1525 | 6044 | 285822.1525
[6 empty] | 6045 | 0 | 6045 | 0
[6 empty] | 6046 | 362843.4164 | 6046 | 362843.4164
[6 empty] | 6047 | 1353845.3005 | 6047 | 1353845.3005
[6 empty] | 6048 | 797016.1127 | 6048 | 0
[6 empty] | 6049 | 0 | 6049 | 0
[6 empty] | 6050 | 0 | 6050 | 0
[6 empty] | 6051 | 0 | 6051 | 0
[6 empty] | 6052 | 0 | 6052 | 0
[6 empty] | 6053 | 0 | 6053 | 0
[6 empty] | 6054 | 0 | 6054 | 0
[6 empty] | 6055 | 0 | 6055 | 0
[6 empty] | 6056 | 0 | 6056 | 0
[6 empty] | 6057 | 4205092.6251 | 6057 | 3237707.943
[6 empty] | 6058 | 239580.1758 | 6058 | 0
[6 empty] | 6059 | 1188672.0021 | 6059 | 1188672.0021
[6 empty] | 6060 | 4486603.2835 | 6060 | 4486603.2835
[6 empty] | 6061 | 3127566.13 | 6061 | 0
[6 empty] | 6062 | 1659988.4428 | 6062 | 1659988.4428
[6 empty] | 6063 | 6871956.2996 | 6063 | 282306.4599
[6 empty] | 6064 | 98804.3277 | 6064 | 98804.3277
[6 empty] | 6065 | 211998.0018 | 6065 | 211998.0018
[6 empty] | 6066 | 356528.0661 | 6066 | 356528.0661
[6 empty] | 6067 | 0 | 6067 | 0
[6 empty] | 6068 | 1577062.1145 | 6068 | 1295130.6629
[6 empty] | 6069 | 0 | 6069 | 0
[6 empty] | 6070 | 0 | 6070 | 0
[6 empty] | 6071 | 0 | 6071 | 0
[6 empty] | 6072 | 600500.0039 | 6072 | 600500.0039
[6 empty] | 6073 | 336065.7826 | 6073 | 336065.7826
[6 empty] | 6074 | 1018656.6953 | 6074 | 1018656.6953
[6 empty] | 6075 | 0 | 6075 | 0
[6 empty] | 6076 | 0 | 6076 | 0
[6 empty] | 6077 | 0 | 6077 | 0
[6 empty] | 6078 | 0 | 6078 | 0
[6 empty] | 6079 | 173216.0852 | 6079 | 173216.0852
[6 empty] | 6080 | 0 | 6080 | 0
[6 empty] | 6081 | 0 | 6081 | 0
[6 empty] | 6082 | 0 | 6082 | 0
[6 empty] | 6083 | 572342.0319 | 6083 | 572342.0319
[6 empty] | 6084 | 5090976.4301 | 6084 | 5090976.4301
[6 empty] | 6085 | 4513977.0302 | 6085 | 187873.0023
[6 empty] | 6086 | 506060.3754 | 6086 | 506060.3754
[6 empty] | 6087 | 262483.8948 | 6087 | 262483.8948
[6 empty] | 6088 | 0 | 6088 | 0
[6 empty] | 6089 | 156386.3933 | 6089 | 156386.3933
[6 empty] | 6090 | 2361170.0314 | 6090 | 0
[6 empty] | 6091 | 466913.827 | 6091 | 466913.827
[6 empty] | 6092 | 2960116.787 | 6092 | 2960116.787
[6 empty] | 6093 | 0 | 6093 | 0
[6 empty] | 6094 | 191567.0364 | 6094 | 0
[6 empty] | 6095 | 0 | 6095 | 0
[6 empty] | 6096 | 0 | 6096 | 0
[6 empty] | 6097 | 0 | 6097 | 0
[6 empty] | 6098 | 0 | 6098 | 0
[6 empty] | 6099 | 0 | 6099 | 0
[6 empty] | 6100 | 3028994.3654 | 6100 | 3028994.3654
[6 empty] | 6101 | 4521390.3717 | 6101 | 0
[6 empty] | 6102 | 11950872.9795 | 6102 | 11950872.9795
[6 empty] | 6103 | 1538110.4756 | 6103 | 1250928.3249
[6 empty] | 6104 | 0 | 6104 | 0
[6 empty] | 6105 | 177779.0796 | 6105 | 177779.0796
[6 empty] | 6106 | 255070.6457 | 6106 | 255070.6457
[6 empty] | 6107 | 193621.6958 | 6107 | 0
[6 empty] | 6108 | 0 | 6108 | 0
[6 empty] | 6109 | 160910.2244 | 6109 | 160910.2244
[6 empty] | 6110 | 0 | 6110 | 0
[6 empty] | 6111 | 264959.2836 | 6111 | 264959.2836
[6 empty] | 6112 | 0 | 6112 | 0
[6 empty] | 6113 | 0 | 6113 | 0
[6 empty] | 6114 | 0 | 6114 | 0
[6 empty] | 6115 | 3208785.8739 | 6115 | 0
[6 empty] | 6116 | 1602066.8217 | 6116 | 0
[6 empty] | 6117 | 0 | 6117 | 0
[6 empty] | 6118 | 278622.6581 | 6118 | 0
[6 empty] | 6119 | 0 | 6119 | 0
[6 empty] | 6120 | 0 | 6120 | 0
[6 empty] | 6121 | 798304.3296 | 6121 | 0
[6 empty] | 6122 | 0 | 6122 | 0
[6 empty] | 6123 | 0 | 6123 | 0
[6 empty] | 6124 | 0 | 6124 | 0
[6 empty] | 6125 | 0 | 6125 | 0
[6 empty] | 6126 | 0 | 6126 | 0
[6 empty] | 6127 | 0 | 6127 | 0
[6 empty] | 6128 | 3581111.0392 | 6128 | 0
[6 empty] | 6129 | 0 | 6129 | 0
[6 empty] | 6130 | 345367.8086 | 6130 | 345367.8086
[6 empty] | 6131 | 0 | 6131 | 0
[6 empty] | 6132 | 0 | 6132 | 0
[6 empty] | 6133 | 0 | 6133 | 0
[6 empty] | 6134 | 0 | 6134 | 0
[6 empty] | 6135 | 0 | 6135 | 0
[6 empty] | 6136 | 0 | 6136 | 0
[6 empty] | 6137 | 2885122.8345 | 6137 | 2885122.8345
[6 empty] | 6138 | 0 | 6138 | 0
[6 empty] | 6139 | 0 | 6139 | 0
[6 empty] | 6140 | 0 | 6140 | 0
[6 empty] | 6141 | 0 | 6141 | 0
[6 empty] | 6142 | 295969.8403 | 6142 | 0
[6 empty] | 6143 | 229224.3235 | 6143 | 0
[6 empty] | 6144 | 0 | 6144 | 0
[6 empty] | 6145 | 188081.1588 | 6145 | 188081.1588
[6 empty] | 6146 | 4698295.3163 | 6146 | 0
[6 empty] | 6147 | 2432139.7232 | 6147 | 247508.025
[6 empty] | 6148 | 3801957.2606 | 6148 | 0
[6 empty] | 6149 | 0 | 6149 | 0
[6 empty] | 6150 | 0 | 6150 | 0
[6 empty] | 6151 | 0 | 6151 | 0
[6 empty] | 6152 | 0 | 6152 | 0
[6 empty] | 6153 | 2315611.1578 | 6153 | 0
[6 empty] | 6154 | 1301720.7215 | 6154 | 1301720.7215
[6 empty] | 6155 | 191477.8487 | 6155 | 0
[6 empty] | 6156 | 0 | 6156 | 0
[6 empty] | 6157 | 0 | 6157 | 0
[6 empty] | 6158 | 0 | 6158 | 0
[6 empty] | 6159 | 362761.1861 | 6159 | 362761.1861
[6 empty] | 6160 | 2124321.4055 | 6160 | 0
[6 empty] | 6161 | 0 | 6161 | 0
[6 empty] | 6162 | 0 | 6162 | 0
[6 empty] | 6163 | 0 | 6163 | 0
[6 empty] | 6164 | 2376115.0415 | 6164 | 2376115.0415
[6 empty] | 6165 | 8398118.0277 | 6165 | 8398118.0277
[6 empty] | 6166 | 0 | 6166 | 0
[6 empty] | 6167 | 0 | 6167 | 0
[6 empty] | 6168 | 0 | 6168 | 0
[6 empty] | 6169 | 241542.7418 | 6169 | 241542.7418
[6 empty] | 6170 | 230017.7095 | 6170 | 230017.7095
[6 empty] | 6171 | 0 | 6171 | 0
[6 empty] | 6172 | 0 | 6172 | 0
[6 empty] | 6173 | 18004058.5763 | 6173 | 5100673.2014
[6 empty] | 6174 | 0 | 6174 | 0
[6 empty] | 6175 | 3396180.6639 | 6175 | 3396180.6639
[6 empty] | 6176 | 406054.4686 | 6176 | 406054.4686
[6 empty] | 6177 | 0 | 6177 | 0
[6 empty] | 6178 | 0 | 6178 | 0
[6 empty] | 6179 | 0 | 6179 | 0
[6 empty] | 6180 | 0 | 6180 | 0
[6 empty] | 6181 | 239465.676 | 6181 | 239465.676
[6 empty] | 6182 | 0 | 6182 | 0
[6 empty] | 6183 | 0 | 6183 | 0
[6 empty] | 6184 | 0 | 6184 | 0
[6 empty] | 6185 | 0 | 6185 | 0
[6 empty] | 6186 | 221626.8179 | 6186 | 221626.8179
[6 empty] | 6187 | 0 | 6187 | 0
[6 empty] | 6188 | 0 | 6188 | 0
[6 empty] | 6189 | 246576.3382 | 6189 | 246576.3382
[6 empty] | 6190 | 0 | 6190 | 0
[6 empty] | 6191 | 0 | 6191 | 0
[6 empty] | 6192 | 0 | 6192 | 0
[6 empty] | 6193 | 162920.1885 | 6193 | 162920.1885
[6 empty] | 6194 | 0 | 6194 | 0
[6 empty] | 6195 | 0 | 6195 | 0
[6 empty] | 6196 | 0 | 6196 | 0
[6 empty] | 6197 | 272214.2467 | 6197 | 272214.2467
[6 empty] | 6198 | 3063866.2326 | 6198 | 0
[6 empty] | 6199 | 0 | 6199 | 0
[6 empty] | 6200 | 0 | 6200 | 0
[6 empty] | 6201 | 10242707.8466 | 6201 | 0
[6 empty] | 6202 | 184561.8772 | 6202 | 184561.8772
[6 empty] | 6203 | 4856480.2628 | 6203 | 4685466.0356
[6 empty] | 6204 | 898751.755 | 6204 | 898751.755
[6 empty] | 6205 | 0 | 6205 | 0
[6 empty] | 6206 | 5495275.3887 | 6206 | 331205.2242
[6 empty] | 6207 | 0 | 6207 | 0
[6 empty] | 6208 | 0 | 6208 | 0
[6 empty] | 6209 | 0 | 6209 | 0
[6 empty] | 6210 | 3059893.7097 | 6210 | 472413.928
[6 empty] | 6211 | 1223210.4612 | 6211 | 1223210.4612
[6 empty] | 6212 | 1881449.5755 | 6212 | 184014.617
[6 empty] | 6213 | 0 | 6213 | 0
[6 empty] | 6214 | 1562680.5649 | 6214 | 1562680.5649
[6 empty] | 6215 | 0 | 6215 | 0
[6 empty] | 6216 | 4545067.9802 | 6216 | 904586.1533
[6 empty] | 6217 | 5530089.4138 | 6217 | 0
[6 empty] | 6218 | 205597.5992 | 6218 | 0
[6 empty] | 6219 | 3323620.4514 | 6219 | 0
[6 empty] | 6220 | 182764.4154 | 6220 | 0
[6 empty] | 6221 | 315706.7994 | 6221 | 315706.7994
[6 empty] | 6222 | 0 | 6222 | 0
[6 empty] | 6223 | 345292.4537 | 6223 | 345292.4537
[6 empty] | 6224 | 0 | 6224 | 0
[6 empty] | 6225 | 632106.1746 | 6225 | 632106.1746
[6 empty] | 6226 | 0 | 6226 | 0
[6 empty] | 6227 | 0 | 6227 | 0
[6 empty] | 6228 | 17872089.9891 | 6228 | 0
[6 empty] | 6229 | 213153.3921 | 6229 | 0
[6 empty] | 6230 | 174423.6255 | 6230 | 174423.6255
[6 empty] | 6231 | 225861.1895 | 6231 | 225861.1895
[6 empty] | 6232 | 354174.9014 | 6232 | 0
[6 empty] | 6233 | 0 | 6233 | 0
[6 empty] | 6234 | 7390326.0501 | 6234 | 0
[6 empty] | 6235 | 3290051.7039 | 6235 | 0
[6 empty] | 6236 | 0 | 6236 | 0
[6 empty] | 6237 | 929797.7143 | 6237 | 671682.7082
[6 empty] | 6238 | 271431.6531 | 6238 | 0
[6 empty] | 6239 | 0 | 6239 | 0
[6 empty] | 6240 | 0 | 6240 | 0
[6 empty] | 6241 | 0 | 6241 | 0
[6 empty] | 6242 | 0 | 6242 | 0
[6 empty] | 6243 | 628644.6087 | 6243 | 628644.6087
[6 empty] | 6244 | 0 | 6244 | 0
[6 empty] | 6245 | 0 | 6245 | 0
[6 empty] | 6246 | 0 | 6246 | 0
[6 empty] | 6247 | 0 | 6247 | 0
[6 empty] | 6248 | 3909714.0952 | 6248 | 0
[6 empty] | 6249 | 0 | 6249 | 0
[6 empty] | 6250 | 0 | 6250 | 0
[6 empty] | 6251 | 0 | 6251 | 0
[6 empty] | 6252 | 0 | 6252 | 0
[6 empty] | 6253 | 0 | 6253 | 0
[6 empty] | 6254 | 0 | 6254 | 0
[6 empty] | 6255 | 0 | 6255 | 0
[6 empty] | 6256 | 368888.1132 | 6256 | 368888.1132
[6 empty] | 6257 | 0 | 6257 | 0
[6 empty] | 6258 | 172373.5257 | 6258 | 0
[6 empty] | 6259 | 4484995.4499 | 6259 | 0
[6 empty] | 6260 | 0 | 6260 | 0
[6 empty] | 6261 | 0 | 6261 | 0
[6 empty] | 6262 | 12837066.486 | 6262 | 0
[6 empty] | 6263 | 290613.6529 | 6263 | 290613.6529
[6 empty] | 6264 | 0 | 6264 | 0
[6 empty] | 6265 | 1028280.9844 | 6265 | 1028280.9844
[6 empty] | 6266 | 5152263.0072 | 6266 | 5152263.0072
[6 empty] | 6267 | 122676.5329 | 6267 | 122676.5329
[6 empty] | 6268 | 0 | 6268 | 0
[6 empty] | 6269 | 0 | 6269 | 0
[6 empty] | 6270 | 0 | 6270 | 0
[6 empty] | 6271 | 117712.656 | 6271 | 117712.656
[6 empty] | 6272 | 0 | 6272 | 0
[6 empty] | 6273 | 0 | 6273 | 0
[6 empty] | 6274 | 0 | 6274 | 0
[6 empty] | 6275 | 0 | 6275 | 0
[6 empty] | 6276 | 0 | 6276 | 0
[6 empty] | 6277 | 0 | 6277 | 0
[6 empty] | 6278 | 0 | 6278 | 0
[6 empty] | 6279 | 1916049.1668 | 6279 | 0
[6 empty] | 6280 | 1196312.3801 | 6280 | 1196312.3801
[6 empty] | 6281 | 2743898.8404 | 6281 | 253966.4631
[6 empty] | 6282 | 1429060.6322 | 6282 | 0
[6 empty] | 6283 | 3620992.1296 | 6283 | 3411716.152
[6 empty] | 6284 | 3611148.3312 | 6284 | 0
[6 empty] | 6285 | 4860410.0846 | 6285 | 0
[6 empty] | 6286 | 7726941.4776 | 6286 | 0
[6 empty] | 6287 | 0 | 6287 | 0
[6 empty] | 6288 | 6983494.7255 | 6288 | 932998.7479
[6 empty] | 6289 | 5161122.5914 | 6289 | 1105206.3753
[6 empty] | 6290 | 0 | 6290 | 0
[6 empty] | 6291 | 0 | 6291 | 0
[6 empty] | 6292 | 0 | 6292 | 0
[6 empty] | 6293 | 3977031.0771 | 6293 | 0
[6 empty] | 6294 | 0 | 6294 | 0
[6 empty] | 6295 | 0 | 6295 | 0
[6 empty] | 6296 | 0 | 6296 | 0
[6 empty] | 6297 | 1358145.0782 | 6297 | 0
[6 empty] | 6298 | 0 | 6298 | 0
[6 empty] | 6299 | 310932.8041 | 6299 | 310932.8041
[6 empty] | 6300 | 0 | 6300 | 0
[6 empty] | 6301 | 0 | 6301 | 0
[6 empty] | 6302 | 0 | 6302 | 0
[6 empty] | 6303 | 0 | 6303 | 0
[6 empty] | 6304 | 0 | 6304 | 0
[6 empty] | 6305 | 0 | 6305 | 0
[6 empty] | 6306 | 0 | 6306 | 0
[6 empty] | 6307 | 0 | 6307 | 0
[6 empty] | 6308 | 4132972.6836 | 6308 | 4132972.6836
[6 empty] | 6309 | 2232178.8094 | 6309 | 0
[6 empty] | 6310 | 344360.3101 | 6310 | 344360.3101
[6 empty] | 6311 | 4527228.2902 | 6311 | 4527228.2902
[6 empty] | 6312 | 3153155.3035 | 6312 | 3153155.3035
[6 empty] | 6313 | 983829.7072 | 6313 | 0
[6 empty] | 6314 | 0 | 6314 | 0
[6 empty] | 6315 | 1327481.102 | 6315 | 1327481.102
[6 empty] | 6316 | 0 | 6316 | 0
[6 empty] | 6317 | 812176.1957 | 6317 | 0
[6 empty] | 6318 | 458361.3374 | 6318 | 458361.3374
[6 empty] | 6319 | 585997.454 | 6319 | 585997.454
[6 empty] | 6320 | 176181.6387 | 6320 | 176181.6387
[6 empty] | 6321 | 656528.9393 | 6321 | 656528.9393
[6 empty] | 6322 | 1436562.3371 | 6322 | 1436562.3371
[6 empty] | 6323 | 329738.154 | 6323 | 329738.154
[6 empty] | 6324 | 190001.3175 | 6324 | 190001.3175
[6 empty] | 6325 | 0 | 6325 | 0
[6 empty] | 6326 | 184016.278 | 6326 | 184016.278
[6 empty] | 6327 | 310382.652 | 6327 | 310382.652
[6 empty] | 6328 | 0 | 6328 | 0
[6 empty] | 6329 | 11768222.6661 | 6329 | 0
[6 empty] | 6330 | 0 | 6330 | 0
[6 empty] | 6331 | 0 | 6331 | 0
[6 empty] | 6332 | 195918.7023 | 6332 | 195918.7023
[6 empty] | 6333 | 0 | 6333 | 0
[6 empty] | 6334 | 4002156.5557 | 6334 | 0
[6 empty] | 6335 | 2833737.8699 | 6335 | 0
[6 empty] | 6336 | 0 | 6336 | 0
[6 empty] | 6337 | 0 | 6337 | 0
[6 empty] | 6338 | 0 | 6338 | 0
[6 empty] | 6339 | 0 | 6339 | 0
[6 empty] | 6340 | 227119.8801 | 6340 | 0
[6 empty] | 6341 | 0 | 6341 | 0
[6 empty] | 6342 | 0 | 6342 | 0
[6 empty] | 6343 | 0 | 6343 | 0
[6 empty] | 6344 | 264489.6084 | 6344 | 264489.6084
[6 empty] | 6345 | 0 | 6345 | 0
[6 empty] | 6346 | 17663898.493 | 6346 | 0
[6 empty] | 6347 | 0 | 6347 | 0
[6 empty] | 6348 | 0 | 6348 | 0
[6 empty] | 6349 | 0 | 6349 | 0
[6 empty] | 6350 | 11714846.1743 | 6350 | 7066391.5666
[6 empty] | 6351 | 2700410.2316 | 6351 | 194967.4435
[6 empty] | 6352 | 0 | 6352 | 0
[6 empty] | 6353 | 281032.0655 | 6353 | 281032.0655
[6 empty] | 6354 | 0 | 6354 | 0
[6 empty] | 6355 | 2981196.5769 | 6355 | 2981196.5769
[6 empty] | 6356 | 0 | 6356 | 0
[6 empty] | 6357 | 599404.3639 | 6357 | 599404.3639
[6 empty] | 6358 | 0 | 6358 | 0
[6 empty] | 6359 | 392125.6472 | 6359 | 392125.6472
[6 empty] | 6360 | 0 | 6360 | 0
[6 empty] | 6361 | 0 | 6361 | 0
[6 empty] | 6362 | 0 | 6362 | 0
[6 empty] | 6363 | 794902.4528 | 6363 | 794902.4528
[6 empty] | 6364 | 0 | 6364 | 0
[6 empty] | 6365 | 560474.5332 | 6365 | 560474.5332
[6 empty] | 6366 | 0 | 6366 | 0
[6 empty] | 6367 | 645911.262 | 6367 | 645911.262
[6 empty] | 6368 | 0 | 6368 | 0
[6 empty] | 6369 | 0 | 6369 | 0
[6 empty] | 6370 | 0 | 6370 | 0
[6 empty] | 6371 | 316254.5234 | 6371 | 316254.5234
[6 empty] | 6372 | 2686485.6455 | 6372 | 0
[6 empty] | 6373 | 0 | 6373 | 0
[6 empty] | 6374 | 1514024.9123 | 6374 | 1514024.9123
[6 empty] | 6375 | 0 | 6375 | 0
[6 empty] | 6376 | 150244.956 | 6376 | 150244.956
[6 empty] | 6377 | 468671.1759 | 6377 | 468671.1759
[6 empty] | 6378 | 3599481.6548 | 6378 | 3599481.6548
[6 empty] | 6379 | 2907040.873 | 6379 | 178787.3208
[6 empty] | 6380 | 0 | 6380 | 0
[6 empty] | 6381 | 162708.3667 | 6381 | 162708.3667
[6 empty] | 6382 | 0 | 6382 | 0
[6 empty] | 6383 | 0 | 6383 | 0
[6 empty] | 6384 | 480726.3011 | 6384 | 480726.3011
[6 empty] | 6385 | 0 | 6385 | 0
[6 empty] | 6386 | 0 | 6386 | 0
[6 empty] | 6387 | 0 | 6387 | 0
[6 empty] | 6388 | 375729.868 | 6388 | 375729.868
[6 empty] | 6389 | 7224800.6865 | 6389 | 7224800.6865
[6 empty] | 6390 | 2541804.0359 | 6390 | 0
[6 empty] | 6391 | 0 | 6391 | 0
[6 empty] | 6392 | 0 | 6392 | 0
[6 empty] | 6393 | 194735.6319 | 6393 | 194735.6319
[6 empty] | 6394 | 3885931.321 | 6394 | 3885931.321
[6 empty] | 6395 | 0 | 6395 | 0
[6 empty] | 6396 | 216077.1179 | 6396 | 216077.1179
[6 empty] | 6397 | 0 | 6397 | 0
[6 empty] | 6398 | 517397.3194 | 6398 | 517397.3194
[6 empty] | 6399 | 0 | 6399 | 0
[6 empty] | 6400 | 378236.2409 | 6400 | 378236.2409
[6 empty] | 6401 | 296333.6511 | 6401 | 296333.6511
[6 empty] | 6402 | 0 | 6402 | 0
[6 empty] | 6403 | 208674.9707 | 6403 | 0
[6 empty] | 6404 | 0 | 6404 | 0
[6 empty] | 6405 | 0 | 6405 | 0
[6 empty] | 6406 | 518619.0604 | 6406 | 0
[6 empty] | 6407 | 0 | 6407 | 0
[6 empty] | 6408 | 187111.5264 | 6408 | 0
[6 empty] | 6409 | 0 | 6409 | 0
[6 empty] | 6410 | 127261.6591 | 6410 | 127261.6591
[6 empty] | 6411 | 1365642.5915 | 6411 | 1365642.5915
[6 empty] | 6412 | 0 | 6412 | 0
[6 empty] | 6413 | 746870.0253 | 6413 | 232548.7074
[6 empty] | 6414 | 0 | 6414 | 0
[6 empty] | 6415 | 0 | 6415 | 0
[6 empty] | 6416 | 218332.8885 | 6416 | 218332.8885
[6 empty] | 6417 | 0 | 6417 | 0
[6 empty] | 6418 | 5008293.7957 | 6418 | 347712.2022
[6 empty] | 6419 | 0 | 6419 | 0
[6 empty] | 6420 | 235093.6902 | 6420 | 0
[6 empty] | 6421 | 2921530.5007 | 6421 | 2921530.5007
[6 empty] | 6422 | 0 | 6422 | 0
[6 empty] | 6423 | 163070.2653 | 6423 | 0
[6 empty] | 6424 | 0 | 6424 | 0
[6 empty] | 6425 | 0 | 6425 | 0
[6 empty] | 6426 | 0 | 6426 | 0
[6 empty] | 6427 | 0 | 6427 | 0
[6 empty] | 6428 | 220682.0799 | 6428 | 220682.0799
[6 empty] | 6429 | 0 | 6429 | 0
[6 empty] | 6430 | 0 | 6430 | 0
[6 empty] | 6431 | 0 | 6431 | 0
[6 empty] | 6432 | 0 | 6432 | 0
[6 empty] | 6433 | 0 | 6433 | 0
[6 empty] | 6434 | 13036603.4317 | 6434 | 0
[6 empty] | 6435 | 0 | 6435 | 0
[6 empty] | 6436 | 2212139.5659 | 6436 | 2021242.3511
[6 empty] | 6437 | 0 | 6437 | 0
[6 empty] | 6438 | 1121894.1671 | 6438 | 0
[6 empty] | 6439 | 266255.6709 | 6439 | 266255.6709
[6 empty] | 6440 | 2738247.0276 | 6440 | 2738247.0276
[6 empty] | 6441 | 0 | 6441 | 0
[6 empty] | 6442 | 167760.8249 | 6442 | 167760.8249
[6 empty] | 6443 | 13886299.9488 | 6443 | 13735216.4056
[6 empty] | 6444 | 0 | 6444 | 0
[6 empty] | 6445 | 561036.6108 | 6445 | 561036.6108
[6 empty] | 6446 | 58207.847 | 6446 | 58207.847
[6 empty] | 6447 | 0 | 6447 | 0
[6 empty] | 6448 | 0 | 6448 | 0
[6 empty] | 6449 | 0 | 6449 | 0
[6 empty] | 6450 | 262532.6958 | 6450 | 262532.6958
[6 empty] | 6451 | 1763337.5489 | 6451 | 1763337.5489
[6 empty] | 6452 | 0 | 6452 | 0
[6 empty] | 6453 | 252504.5363 | 6453 | 252504.5363
[6 empty] | 6454 | 3642912.6207 | 6454 | 3642912.6207
[6 empty] | 6455 | 0 | 6455 | 0
[6 empty] | 6456 | 0 | 6456 | 0
[6 empty] | 6457 | 0 | 6457 | 0
[6 empty] | 6458 | 2521545.6503 | 6458 | 2521545.6503
[6 empty] | 6459 | 0 | 6459 | 0
[6 empty] | 6460 | 0 | 6460 | 0
[6 empty] | 6461 | 74345.7185 | 6461 | 74345.7185
[6 empty] | 6462 | 0 | 6462 | 0
[6 empty] | 6463 | 0 | 6463 | 0
[6 empty] | 6464 | 1394221.2537 | 6464 | 0
[6 empty] | 6465 | 0 | 6465 | 0
[6 empty] | 6466 | 0 | 6466 | 0
[6 empty] | 6467 | 2681863.4263 | 6467 | 2681863.4263
[6 empty] | 6468 | 304587.7464 | 6468 | 304587.7464
[6 empty] | 6469 | 0 | 6469 | 0
[6 empty] | 6470 | 0 | 6470 | 0
[6 empty] | 6471 | 0 | 6471 | 0
[6 empty] | 6472 | 1530226.4496 | 6472 | 1309317.4359
[6 empty] | 6473 | 0 | 6473 | 0
[6 empty] | 6474 | 0 | 6474 | 0
[6 empty] | 6475 | 11083774.5781 | 6475 | 0
[6 empty] | 6476 | 0 | 6476 | 0
[6 empty] | 6477 | 0 | 6477 | 0
[6 empty] | 6478 | 0 | 6478 | 0
[6 empty] | 6479 | 7254423.0925 | 6479 | 7254423.0925
[6 empty] | 6480 | 686160.8177 | 6480 | 497712.7359
[6 empty] | 6481 | 780959.3862 | 6481 | 538408.8086
[6 empty] | 6482 | 0 | 6482 | 0
[6 empty] | 6483 | 0 | 6483 | 0
[6 empty] | 6484 | 213405.3232 | 6484 | 213405.3232
[6 empty] | 6485 | 0 | 6485 | 0
[6 empty] | 6486 | 0 | 6486 | 0
[6 empty] | 6487 | 0 | 6487 | 0
[6 empty] | 6488 | 3398662.7172 | 6488 | 3398662.7172
[6 empty] | 6489 | 0 | 6489 | 0
[6 empty] | 6490 | 289132.7375 | 6490 | 289132.7375
[6 empty] | 6491 | 264816.5305 | 6491 | 264816.5305
[6 empty] | 6492 | 443075.4885 | 6492 | 443075.4885
[6 empty] | 6493 | 0 | 6493 | 0
[6 empty] | 6494 | 242090.4292 | 6494 | 242090.4292
[6 empty] | 6495 | 5659387.0511 | 6495 | 44018.0372
[6 empty] | 6496 | 0 | 6496 | 0
[6 empty] | 6497 | 5917037.6754 | 6497 | 0
[6 empty] | 6498 | 368909.9011 | 6498 | 0
[6 empty] | 6499 | 0 | 6499 | 0
[6 empty] | 6500 | 202420.5103 | 6500 | 0
[6 empty] | 6501 | 0 | 6501 | 0
[6 empty] | 6502 | 0 | 6502 | 0
[6 empty] | 6503 | 10823662.2607 | 6503 | 0
[6 empty] | 6504 | 0 | 6504 | 0
[6 empty] | 6505 | 0 | 6505 | 0
[6 empty] | 6506 | 569148.6265 | 6506 | 569148.6265
[6 empty] | 6507 | 0 | 6507 | 0
[6 empty] | 6508 | 0 | 6508 | 0
[6 empty] | 6509 | 0 | 6509 | 0
[6 empty] | 6510 | 0 | 6510 | 0
[6 empty] | 6511 | 0 | 6511 | 0
[6 empty] | 6512 | 0 | 6512 | 0
[6 empty] | 6513 | 172162.6368 | 6513 | 172162.6368
[6 empty] | 6514 | 0 | 6514 | 0
[6 empty] | 6515 | 0 | 6515 | 0
[6 empty] | 6516 | 0 | 6516 | 0
[6 empty] | 6517 | 0 | 6517 | 0
[6 empty] | 6518 | 0 | 6518 | 0
[6 empty] | 6519 | 296410.9125 | 6519 | 296410.9125
[6 empty] | 6520 | 194084.6034 | 6520 | 194084.6034
[6 empty] | 6521 | 0 | 6521 | 0
[6 empty] | 6522 | 317798.1657 | 6522 | 317798.1657
[6 empty] | 6523 | 0 | 6523 | 0
[6 empty] | 6524 | 0 | 6524 | 0
[6 empty] | 6525 | 626902.8189 | 6525 | 626902.8189
[6 empty] | 6526 | 3999355.1514 | 6526 | 0
[6 empty] | 6527 | 0 | 6527 | 0
[6 empty] | 6528 | 2750377.2297 | 6528 | 2750377.2297
[6 empty] | 6529 | 4907497.3473 | 6529 | 444903.0592
[6 empty] | 6530 | 3576760.6076 | 6530 | 3576760.6076
[6 empty] | 6531 | 4515584.1119 | 6531 | 3768820.7743
[6 empty] | 6532 | 3191911.0394 | 6532 | 3191911.0394
[6 empty] | 6533 | 0 | 6533 | 0
[6 empty] | 6534 | 102613.7258 | 6534 | 102613.7258
[6 empty] | 6535 | 0 | 6535 | 0
[6 empty] | 6536 | 0 | 6536 | 0
[6 empty] | 6537 | 0 | 6537 | 0
[6 empty] | 6538 | 0 | 6538 | 0
[6 empty] | 6539 | 0 | 6539 | 0
[6 empty] | 6540 | 9322743.2573 | 6540 | 0
[6 empty] | 6541 | 0 | 6541 | 0
[6 empty] | 6542 | 3525672.829 | 6542 | 3525672.829
[6 empty] | 6543 | 0 | 6543 | 0
[6 empty] | 6544 | 766531.7368 | 6544 | 766531.7368
[6 empty] | 6545 | 0 | 6545 | 0
[6 empty] | 6546 | 3605361.4836 | 6546 | 3605361.4836
[6 empty] | 6547 | 0 | 6547 | 0
[6 empty] | 6548 | 0 | 6548 | 0
[6 empty] | 6549 | 0 | 6549 | 0
[6 empty] | 6550 | 0 | 6550 | 0
[6 empty] | 6551 | 136813.9496 | 6551 | 136813.9496
[6 empty] | 6552 | 1077949.6695 | 6552 | 0
[6 empty] | 6553 | 1618028.8914 | 6553 | 1618028.8914
[6 empty] | 6554 | 0 | 6554 | 0
[6 empty] | 6555 | 0 | 6555 | 0
[6 empty] | 6556 | 0 | 6556 | 0
[6 empty] | 6557 | 2729559.841 | 6557 | 0
[6 empty] | 6558 | 0 | 6558 | 0
[6 empty] | 6559 | 211631.8293 | 6559 | 0
[6 empty] | 6560 | 0 | 6560 | 0
[6 empty] | 6561 | 0 | 6561 | 0
[6 empty] | 6562 | 248233.5083 | 6562 | 248233.5083
[6 empty] | 6563 | 0 | 6563 | 0
[6 empty] | 6564 | 0 | 6564 | 0
[6 empty] | 6565 | 0 | 6565 | 0
[6 empty] | 6566 | 0 | 6566 | 0
[6 empty] | 6567 | 0 | 6567 | 0
[6 empty] | 6568 | 0 | 6568 | 0
[6 empty] | 6569 | 0 | 6569 | 0
[6 empty] | 6570 | 459371.1907 | 6570 | 459371.1907
[6 empty] | 6571 | 0 | 6571 | 0
[6 empty] | 6572 | 0 | 6572 | 0
[6 empty] | 6573 | 3779440.6124 | 6573 | 0
[6 empty] | 6574 | 270960.028 | 6574 | 270960.028
[6 empty] | 6575 | 3328429.8338 | 6575 | 3328429.8338
[6 empty] | 6576 | 0 | 6576 | 0
[6 empty] | 6577 | 256316.4369 | 6577 | 256316.4369
[6 empty] | 6578 | 0 | 6578 | 0
[6 empty] | 6579 | 2407182.4893 | 6579 | 0
[6 empty] | 6580 | 2515746.5653 | 6580 | 2515746.5653
[6 empty] | 6581 | 0 | 6581 | 0
[6 empty] | 6582 | 2500712.4017 | 6582 | 0
[6 empty] | 6583 | 197160.1599 | 6583 | 0
[6 empty] | 6584 | 0 | 6584 | 0
[6 empty] | 6585 | 0 | 6585 | 0
[6 empty] | 6586 | 0 | 6586 | 0
[6 empty] | 6587 | 42071.7903 | 6587 | 42071.7903
[6 empty] | 6588 | 0 | 6588 | 0
[6 empty] | 6589 | 296905.8755 | 6589 | 0
[6 empty] | 6590 | 0 | 6590 | 0
[6 empty] | 6591 | 0 | 6591 | 0
[6 empty] | 6592 | 2731331.8424 | 6592 | 0
[6 empty] | 6593 | 0 | 6593 | 0
[6 empty] | 6594 | 0 | 6594 | 0
[6 empty] | 6595 | 252049.9421 | 6595 | 0
[6 empty] | 6596 | 0 | 6596 | 0
[6 empty] | 6597 | 321246.5108 | 6597 | 0
[6 empty] | 6598 | 0 | 6598 | 0
[6 empty] | 6599 | 4193378.8241 | 6599 | 4193378.8241
[6 empty] | 6600 | 0 | 6600 | 0
[6 empty] | 6601 | 0 | 6601 | 0
[6 empty] | 6602 | 0 | 6602 | 0
[6 empty] | 6603 | 0 | 6603 | 0
[6 empty] | 6604 | 0 | 6604 | 0
[6 empty] | 6605 | 799599.5765 | 6605 | 799599.5765
[6 empty] | 6606 | 2336145.0084 | 6606 | 2336145.0084
[6 empty] | 6607 | 0 | 6607 | 0
[6 empty] | 6608 | 4236076.2317 | 6608 | 0
[6 empty] | 6609 | 3794541.821 | 6609 | 3794541.821
[6 empty] | 6610 | 1200287.3921 | 6610 | 1200287.3921
[6 empty] | 6611 | 202632.7918 | 6611 | 202632.7918
[6 empty] | 6612 | 831317.0591 | 6612 | 831317.0591
[6 empty] | 6613 | 3949690.2008 | 6613 | 197635.8131
[6 empty] | 6614 | 1499550.9019 | 6614 | 0
[6 empty] | 6615 | 0 | 6615 | 0
[6 empty] | 6616 | 253666.6835 | 6616 | 0
[6 empty] | 6617 | 320825.099 | 6617 | 320825.099
[6 empty] | 6618 | 0 | 6618 | 0
[6 empty] | 6619 | 1659233.3228 | 6619 | 1659233.3228
[6 empty] | 6620 | 198321.3974 | 6620 | 198321.3974
[6 empty] | 6621 | 0 | 6621 | 0
[6 empty] | 6622 | 0 | 6622 | 0
[6 empty] | 6623 | 184392.4918 | 6623 | 184392.4918
[6 empty] | 6624 | 0 | 6624 | 0
[6 empty] | 6625 | 1060161.8412 | 6625 | 1060161.8412
[6 empty] | 6626 | 1826273.2781 | 6626 | 0
[6 empty] | 6627 | 259049.0901 | 6627 | 0
[6 empty] | 6628 | 3446939.1029 | 6628 | 0
[6 empty] | 6629 | 0 | 6629 | 0
[6 empty] | 6630 | 0 | 6630 | 0
[6 empty] | 6631 | 0 | 6631 | 0
[6 empty] | 6632 | 8937218.5044 | 6632 | 194659.8938
[6 empty] | 6633 | 580073.1411 | 6633 | 0
[6 empty] | 6634 | 0 | 6634 | 0
[6 empty] | 6635 | 200145.4161 | 6635 | 200145.4161
[6 empty] | 6636 | 228143.4202 | 6636 | 0
[6 empty] | 6637 | 194985.286 | 6637 | 194985.286
[6 empty] | 6638 | 2981215.5542 | 6638 | 2981215.5542
[6 empty] | 6639 | 580515.0728 | 6639 | 580515.0728
[6 empty] | 6640 | 0 | 6640 | 0
[6 empty] | 6641 | 0 | 6641 | 0
[6 empty] | 6642 | 0 | 6642 | 0
[6 empty] | 6643 | 0 | 6643 | 0
[6 empty] | 6644 | 306937.4311 | 6644 | 306937.4311
[6 empty] | 6645 | 0 | 6645 | 0
[6 empty] | 6646 | 4351401.8376 | 6646 | 0
[6 empty] | 6647 | 0 | 6647 | 0
[6 empty] | 6648 | 5070230.4843 | 6648 | 978881.5483
[6 empty] | 6649 | 1384921.1449 | 6649 | 0
[6 empty] | 6650 | 0 | 6650 | 0
[6 empty] | 6651 | 0 | 6651 | 0
[6 empty] | 6652 | 0 | 6652 | 0
[6 empty] | 6653 | 0 | 6653 | 0
[6 empty] | 6654 | 0 | 6654 | 0
[6 empty] | 6655 | 0 | 6655 | 0
[6 empty] | 6656 | 4832930.4114 | 6656 | 4832930.4114
[6 empty] | 6657 | 53795.5111 | 6657 | 53795.5111
[6 empty] | 6658 | 3638238.3099 | 6658 | 168759.9518
[6 empty] | 6659 | 269536.8765 | 6659 | 269536.8765
[6 empty] | 6660 | 0 | 6660 | 0
[6 empty] | 6661 | 0 | 6661 | 0
[6 empty] | 6662 | 0 | 6662 | 0
[6 empty] | 6663 | 0 | 6663 | 0
[6 empty] | 6664 | 4391736.5483 | 6664 | 3332834.2007
[6 empty] | 6665 | 0 | 6665 | 0
[6 empty] | 6666 | 0 | 6666 | 0
[6 empty] | 6667 | 0 | 6667 | 0
[6 empty] | 6668 | 2953814.4882 | 6668 | 2953814.4882
[6 empty] | 6669 | 0 | 6669 | 0
[6 empty] | 6670 | 2880155.1531 | 6670 | 2880155.1531
[6 empty] | 6671 | 0 | 6671 | 0
[6 empty] | 6672 | 0 | 6672 | 0
[6 empty] | 6673 | 0 | 6673 | 0
[6 empty] | 6674 | 0 | 6674 | 0
[6 empty] | 6675 | 1220735.419 | 6675 | 994201.3126
[6 empty] | 6676 | 0 | 6676 | 0
[6 empty] | 6677 | 345030.3406 | 6677 | 345030.3406
[6 empty] | 6678 | 1742158.2082 | 6678 | 0
[6 empty] | 6679 | 152165.0402 | 6679 | 152165.0402
[6 empty] | 6680 | 4198766.4267 | 6680 | 4198766.4267
[6 empty] | 6681 | 0 | 6681 | 0
[6 empty] | 6682 | 0 | 6682 | 0
[6 empty] | 6683 | 0 | 6683 | 0
[6 empty] | 6684 | 0 | 6684 | 0
[6 empty] | 6685 | 6521172.9319 | 6685 | 3064660.8991
[6 empty] | 6686 | 7106990.5933 | 6686 | 0
[6 empty] | 6687 | 0 | 6687 | 0
[6 empty] | 6688 | 0 | 6688 | 0
[6 empty] | 6689 | 0 | 6689 | 0
[6 empty] | 6690 | 0 | 6690 | 0
[6 empty] | 6691 | 0 | 6691 | 0
[6 empty] | 6692 | 2557588.5266 | 6692 | 2557588.5266
[6 empty] | 6693 | 356965.1975 | 6693 | 356965.1975
[6 empty] | 6694 | 178520.1011 | 6694 | 178520.1011
[6 empty] | 6695 | 0 | 6695 | 0
[6 empty] | 6696 | 1031820.9365 | 6696 | 1031820.9365
[6 empty] | 6697 | 0 | 6697 | 0
[6 empty] | 6698 | 0 | 6698 | 0
[6 empty] | 6699 | 0 | 6699 | 0
[6 empty] | 6700 | 0 | 6700 | 0
[6 empty] | 6701 | 1579170.1737 | 6701 | 0
[6 empty] | 6702 | 0 | 6702 | 0
[6 empty] | 6703 | 0 | 6703 | 0
[6 empty] | 6704 | 247778.5043 | 6704 | 247778.5043
[6 empty] | 6705 | 4978801.9713 | 6705 | 4978801.9713
[6 empty] | 6706 | 4066143.8612 | 6706 | 0
[6 empty] | 6707 | 0 | 6707 | 0
[6 empty] | 6708 | 0 | 6708 | 0
[6 empty] | 6709 | 0 | 6709 | 0
[6 empty] | 6710 | 3032579.2681 | 6710 | 3032579.2681
[6 empty] | 6711 | 0 | 6711 | 0
[6 empty] | 6712 | 566006.6693 | 6712 | 566006.6693
[6 empty] | 6713 | 97027.6098 | 6713 | 97027.6098
[6 empty] | 6714 | 266634.379 | 6714 | 266634.379
[6 empty] | 6715 | 121235.013 | 6715 | 121235.013
[6 empty] | 6716 | 3477280.8653 | 6716 | 3111973.3472
[6 empty] | 6717 | 0 | 6717 | 0
[6 empty] | 6718 | 0 | 6718 | 0
[6 empty] | 6719 | 3856371.7489 | 6719 | 0
[6 empty] | 6720 | 1259190.7871 | 6720 | 105462.1381
[6 empty] | 6721 | 2424164.3523 | 6721 | 2424164.3523
[6 empty] | 6722 | 0 | 6722 | 0
[6 empty] | 6723 | 0 | 6723 | 0
[6 empty] | 6724 | 169275.3563 | 6724 | 0
[6 empty] | 6725 | 0 | 6725 | 0
[6 empty] | 6726 | 0 | 6726 | 0
[6 empty] | 6727 | 0 | 6727 | 0
[6 empty] | 6728 | 3733061.3584 | 6728 | 3496464.6427
[6 empty] | 6729 | 798869.9329 | 6729 | 0
[6 empty] | 6730 | 2171512.7243 | 6730 | 463236.6849
[6 empty] | 6731 | 192398.2279 | 6731 | 192398.2279
[6 empty] | 6732 | 3304250.3703 | 6732 | 0
[6 empty] | 6733 | 388694.727 | 6733 | 388694.727
[6 empty] | 6734 | 200750.6845 | 6734 | 200750.6845
[6 empty] | 6735 | 0 | 6735 | 0
[6 empty] | 6736 | 473965.6014 | 6736 | 473965.6014
[6 empty] | 6737 | 0 | 6737 | 0
[6 empty] | 6738 | 4155276.0313 | 6738 | 0
[6 empty] | 6739 | 0 | 6739 | 0
[6 empty] | 6740 | 246090.4032 | 6740 | 0
[6 empty] | 6741 | 0 | 6741 | 0
[6 empty] | 6742 | 520368.1363 | 6742 | 520368.1363
[6 empty] | 6743 | 190151.4371 | 6743 | 190151.4371
[6 empty] | 6744 | 0 | 6744 | 0
[6 empty] | 6745 | 1186429.5275 | 6745 | 1186429.5275
[6 empty] | 6746 | 0 | 6746 | 0
[6 empty] | 6747 | 13058918.5963 | 6747 | 0
[6 empty] | 6748 | 0 | 6748 | 0
[6 empty] | 6749 | 275616.1528 | 6749 | 0
[6 empty] | 6750 | 183647.0873 | 6750 | 0
[6 empty] | 6751 | 0 | 6751 | 0
[6 empty] | 6752 | 0 | 6752 | 0
[6 empty] | 6753 | 0 | 6753 | 0
[6 empty] | 6754 | 0 | 6754 | 0
[6 empty] | 6755 | 198360.9869 | 6755 | 198360.9869
[6 empty] | 6756 | 90459.8685 | 6756 | 90459.8685
[6 empty] | 6757 | 307281.1373 | 6757 | 307281.1373
[6 empty] | 6758 | 0 | 6758 | 0
[6 empty] | 6759 | 291309.3884 | 6759 | 0
[6 empty] | 6760 | 0 | 6760 | 0
[6 empty] | 6761 | 0 | 6761 | 0
[6 empty] | 6762 | 0 | 6762 | 0
[6 empty] | 6763 | 255298.2793 | 6763 | 255298.2793
[6 empty] | 6764 | 496814.1849 | 6764 | 496814.1849
[6 empty] | 6765 | 150349.1379 | 6765 | 150349.1379
[6 empty] | 6766 | 0 | 6766 | 0
[6 empty] | 6767 | 0 | 6767 | 0
[6 empty] | 6768 | 0 | 6768 | 0
[6 empty] | 6769 | 2559081.6222 | 6769 | 0
[6 empty] | 6770 | 298534.9861 | 6770 | 0
[6 empty] | 6771 | 1588960.596 | 6771 | 1588960.596
[6 empty] | 6772 | 0 | 6772 | 0
[6 empty] | 6773 | 0 | 6773 | 0
[6 empty] | 6774 | 1325873.8299 | 6774 | 1325873.8299
[6 empty] | 6775 | 0 | 6775 | 0
[6 empty] | 6776 | 18410389.9505 | 6776 | 18410389.9505
[6 empty] | 6777 | 0 | 6777 | 0
[6 empty] | 6778 | 558633.7782 | 6778 | 558633.7782
[6 empty] | 6779 | 0 | 6779 | 0
[6 empty] | 6780 | 1307671.622 | 6780 | 1307671.622
[6 empty] | 6781 | 292776.7536 | 6781 | 292776.7536
[6 empty] | 6782 | 0 | 6782 | 0
[6 empty] | 6783 | 0 | 6783 | 0
[6 empty] | 6784 | 3251878.0447 | 6784 | 3251878.0447
[6 empty] | 6785 | 0 | 6785 | 0
[6 empty] | 6786 | 5246013.7177 | 6786 | 782538.5901
[6 empty] | 6787 | 2018362.9903 | 6787 | 1834288.0437
[6 empty] | 6788 | 0 | 6788 | 0
[6 empty] | 6789 | 0 | 6789 | 0
[6 empty] | 6790 | 3502634.9726 | 6790 | 138906.6871
[6 empty] | 6791 | 0 | 6791 | 0
[6 empty] | 6792 | 4564694.2148 | 6792 | 0
[6 empty] | 6793 | 232590.5908 | 6793 | 0
[6 empty] | 6794 | 6921660.4767 | 6794 | 262291.2709
[6 empty] | 6795 | 231275.8972 | 6795 | 231275.8972
[6 empty] | 6796 | 0 | 6796 | 0
[6 empty] | 6797 | 0 | 6797 | 0
[6 empty] | 6798 | 0 | 6798 | 0
[6 empty] | 6799 | 0 | 6799 | 0
[6 empty] | 6800 | 251411.4903 | 6800 | 251411.4903
[6 empty] | 6801 | 0 | 6801 | 0
[6 empty] | 6802 | 376727.658 | 6802 | 376727.658
[6 empty] | 6803 | 0 | 6803 | 0
[6 empty] | 6804 | 204530.2238 | 6804 | 204530.2238
[6 empty] | 6805 | 0 | 6805 | 0
[6 empty] | 6806 | 0 | 6806 | 0
[6 empty] | 6807 | 981569.3924 | 6807 | 981569.3924
[6 empty] | 6808 | 710063.5307 | 6808 | 0
[6 empty] | 6809 | 157756.7041 | 6809 | 157756.7041
[6 empty] | 6810 | 0 | 6810 | 0
[6 empty] | 6811 | 363494.2853 | 6811 | 363494.2853
[6 empty] | 6812 | 0 | 6812 | 0
[6 empty] | 6813 | 3189050.0099 | 6813 | 2923769.0537
[6 empty] | 6814 | 0 | 6814 | 0
[6 empty] | 6815 | 509484.4513 | 6815 | 509484.4513
[6 empty] | 6816 | 4721010.4146 | 6816 | 3264445.7036
[6 empty] | 6817 | 0 | 6817 | 0
[6 empty] | 6818 | 0 | 6818 | 0
[6 empty] | 6819 | 4367229.4027 | 6819 | 2711846.1273
[6 empty] | 6820 | 1935154.7357 | 6820 | 1935154.7357
[6 empty] | 6821 | 155246.2637 | 6821 | 0
[6 empty] | 6822 | 4209002.3805 | 6822 | 4209002.3805
[6 empty] | 6823 | 0 | 6823 | 0
[6 empty] | 6824 | 0 | 6824 | 0
[6 empty] | 6825 | 0 | 6825 | 0
[6 empty] | 6826 | 189230.3276 | 6826 | 189230.3276
[6 empty] | 6827 | 0 | 6827 | 0
[6 empty] | 6828 | 166160.9729 | 6828 | 166160.9729
[6 empty] | 6829 | 228728.9261 | 6829 | 228728.9261
[6 empty] | 6830 | 0 | 6830 | 0
[6 empty] | 6831 | 0 | 6831 | 0
[6 empty] | 6832 | 0 | 6832 | 0
[6 empty] | 6833 | 0 | 6833 | 0
[6 empty] | 6834 | 1304747.8729 | 6834 | 0
[6 empty] | 6835 | 0 | 6835 | 0
[6 empty] | 6836 | 0 | 6836 | 0
[6 empty] | 6837 | 343450.2328 | 6837 | 0
[6 empty] | 6838 | 766981.3627 | 6838 | 766981.3627
[6 empty] | 6839 | 297185.4339 | 6839 | 297185.4339
[6 empty] | 6840 | 243748.0555 | 6840 | 243748.0555
[6 empty] | 6841 | 0 | 6841 | 0
[6 empty] | 6842 | 0 | 6842 | 0
[6 empty] | 6843 | 0 | 6843 | 0
[6 empty] | 6844 | 468521.3743 | 6844 | 468521.3743
[6 empty] | 6845 | 155114.1089 | 6845 | 155114.1089
[6 empty] | 6846 | 0 | 6846 | 0
[6 empty] | 6847 | 0 | 6847 | 0
[6 empty] | 6848 | 0 | 6848 | 0
[6 empty] | 6849 | 0 | 6849 | 0
[6 empty] | 6850 | 0 | 6850 | 0
[6 empty] | 6851 | 3422578.3648 | 6851 | 3422578.3648
[6 empty] | 6852 | 0 | 6852 | 0
[6 empty] | 6853 | 270338.1376 | 6853 | 0
[6 empty] | 6854 | 0 | 6854 | 0
[6 empty] | 6855 | 0 | 6855 | 0
[6 empty] | 6856 | 0 | 6856 | 0
[6 empty] | 6857 | 0 | 6857 | 0
[6 empty] | 6858 | 3876995.6838 | 6858 | 298003.0895
[6 empty] | 6859 | 0 | 6859 | 0
[6 empty] | 6860 | 410666.6361 | 6860 | 410666.6361
[6 empty] | 6861 | 7043101.0104 | 6861 | 0
[6 empty] | 6862 | 0 | 6862 | 0
[6 empty] | 6863 | 2477788.0118 | 6863 | 0
[6 empty] | 6864 | 245444.3064 | 6864 | 245444.3064
[6 empty] | 6865 | 4647026.2463 | 6865 | 193409.0042
[6 empty] | 6866 | 217751.4869 | 6866 | 217751.4869
[6 empty] | 6867 | 0 | 6867 | 0
[6 empty] | 6868 | 480899.6983 | 6868 | 480899.6983
[6 empty] | 6869 | 0 | 6869 | 0
[6 empty] | 6870 | 481344.4618 | 6870 | 481344.4618
[6 empty] | 6871 | 322817.1447 | 6871 | 322817.1447
[6 empty] | 6872 | 0 | 6872 | 0
[6 empty] | 6873 | 604426.4437 | 6873 | 604426.4437
[6 empty] | 6874 | 28554858.2669 | 6874 | 0
[6 empty] | 6875 | 0 | 6875 | 0
[6 empty] | 6876 | 0 | 6876 | 0
[6 empty] | 6877 | 0 | 6877 | 0
[6 empty] | 6878 | 0 | 6878 | 0
[6 empty] | 6879 | 0 | 6879 | 0
[6 empty] | 6880 | 2197252.2356 | 6880 | 0
[6 empty] | 6881 | 2401051.192 | 6881 | 0
[6 empty] | 6882 | 0 | 6882 | 0
[6 empty] | 6883 | 171656.2485 | 6883 | 171656.2485
[6 empty] | 6884 | 0 | 6884 | 0
[6 empty] | 6885 | 213469.9605 | 6885 | 0
[6 empty] | 6886 | 0 | 6886 | 0
[6 empty] | 6887 | 1455725.3923 | 6887 | 815019.0464
[6 empty] | 6888 | 581618.8769 | 6888 | 581618.8769
[6 empty] | 6889 | 157754.8157 | 6889 | 0
[6 empty] | 6890 | 0 | 6890 | 0
[6 empty] | 6891 | 0 | 6891 | 0
[6 empty] | 6892 | 0 | 6892 | 0
[6 empty] | 6893 | 310981.5409 | 6893 | 310981.5409
[6 empty] | 6894 | 0 | 6894 | 0
[6 empty] | 6895 | 0 | 6895 | 0
[6 empty] | 6896 | 0 | 6896 | 0
[6 empty] | 6897 | 4485368.4004 | 6897 | 4485368.4004
[6 empty] | 6898 | 0 | 6898 | 0
[6 empty] | 6899 | 0 | 6899 | 0
[6 empty] | 6900 | 3319567.4961 | 6900 | 128203.0969
[6 empty] | 6901 | 0 | 6901 | 0
[6 empty] | 6902 | 0 | 6902 | 0
[6 empty] | 6903 | 0 | 6903 | 0
[6 empty] | 6904 | 0 | 6904 | 0
[6 empty] | 6905 | 2536241.1995 | 6905 | 0
[6 empty] | 6906 | 2962643.3892 | 6906 | 0
[6 empty] | 6907 | 0 | 6907 | 0
[6 empty] | 6908 | 0 | 6908 | 0
[6 empty] | 6909 | 0 | 6909 | 0
[6 empty] | 6910 | 4124257.2253 | 6910 | 0
[6 empty] | 6911 | 3870556.5221 | 6911 | 3870556.5221
[6 empty] | 6912 | 0 | 6912 | 0
[6 empty] | 6913 | 0 | 6913 | 0
[6 empty] | 6914 | 360262.7531 | 6914 | 171000.1687
[6 empty] | 6915 | 0 | 6915 | 0
[6 empty] | 6916 | 240996.3971 | 6916 | 0
[6 empty] | 6917 | 7748077.3518 | 6917 | 0
[6 empty] | 6918 | 1621238.3618 | 6918 | 0
[6 empty] | 6919 | 0 | 6919 | 0
[6 empty] | 6920 | 416665.3801 | 6920 | 416665.3801
[6 empty] | 6921 | 0 | 6921 | 0
[6 empty] | 6922 | 258834.5963 | 6922 | 0
[6 empty] | 6923 | 0 | 6923 | 0
[6 empty] | 6924 | 3641894.2699 | 6924 | 3641894.2699
[6 empty] | 6925 | 4017361.2383 | 6925 | 0
[6 empty] | 6926 | 4445149.0093 | 6926 | 4445149.0093
[6 empty] | 6927 | 573493.5332 | 6927 | 573493.5332
[6 empty] | 6928 | 396019.1493 | 6928 | 396019.1493
[6 empty] | 6929 | 0 | 6929 | 0
[6 empty] | 6930 | 978189.7912 | 6930 | 978189.7912
[6 empty] | 6931 | 4327574.6213 | 6931 | 1546915.1279
[6 empty] | 6932 | 3877756.9781 | 6932 | 3703863.0268
[6 empty] | 6933 | 1807363.681 | 6933 | 221828.7386
[6 empty] | 6934 | 206544.4446 | 6934 | 206544.4446
[6 empty] | 6935 | 0 | 6935 | 0
[6 empty] | 6936 | 3528219.3077 | 6936 | 0
[6 empty] | 6937 | 0 | 6937 | 0
[6 empty] | 6938 | 0 | 6938 | 0
[6 empty] | 6939 | 4155573.8706 | 6939 | 0
[6 empty] | 6940 | 4541356.442 | 6940 | 4206150.8359
[6 empty] | 6941 | 0 | 6941 | 0
[6 empty] | 6942 | 1192240.6983 | 6942 | 1192240.6983
[6 empty] | 6943 | 0 | 6943 | 0
[6 empty] | 6944 | 0 | 6944 | 0
[6 empty] | 6945 | 0 | 6945 | 0
[6 empty] | 6946 | 0 | 6946 | 0
[6 empty] | 6947 | 291998.2872 | 6947 | 291998.2872
[6 empty] | 6948 | 0 | 6948 | 0
[6 empty] | 6949 | 0 | 6949 | 0
[6 empty] | 6950 | 1351745.6732 | 6950 | 1351745.6732
[6 empty] | 6951 | 0 | 6951 | 0
[6 empty] | 6952 | 372667.2297 | 6952 | 169105.1084
[6 empty] | 6953 | 0 | 6953 | 0
[6 empty] | 6954 | 175874.0072 | 6954 | 175874.0072
[6 empty] | 6955 | 0 | 6955 | 0
[6 empty] | 6956 | 293382.9146 | 6956 | 293382.9146
[6 empty] | 6957 | 0 | 6957 | 0
[6 empty] | 6958 | 0 | 6958 | 0
[6 empty] | 6959 | 4087329.1968 | 6959 | 0
[6 empty] | 6960 | 0 | 6960 | 0
[6 empty] | 6961 | 4469713.5016 | 6961 | 4469713.5016
[6 empty] | 6962 | 1785597.7054 | 6962 | 0
[6 empty] | 6963 | 0 | 6963 | 0
[6 empty] | 6964 | 0 | 6964 | 0
[6 empty] | 6965 | 2340570.045 | 6965 | 716320.266
[6 empty] | 6966 | 0 | 6966 | 0
[6 empty] | 6967 | 0 | 6967 | 0
[6 empty] | 6968 | 0 | 6968 | 0
[6 empty] | 6969 | 0 | 6969 | 0
[6 empty] | 6970 | 0 | 6970 | 0
[6 empty] | 6971 | 0 | 6971 | 0
[6 empty] | 6972 | 0 | 6972 | 0
[6 empty] | 6973 | 23406368.5024 | 6973 | 0
[6 empty] | 6974 | 0 | 6974 | 0
[6 empty] | 6975 | 0 | 6975 | 0
[6 empty] | 6976 | 196650.656 | 6976 | 196650.656
[6 empty] | 6977 | 0 | 6977 | 0
[6 empty] | 6978 | 3870993.0031 | 6978 | 0
[6 empty] | 6979 | 0 | 6979 | 0
[6 empty] | 6980 | 0 | 6980 | 0
[6 empty] | 6981 | 2259221.217 | 6981 | 263639.5556
[6 empty] | 6982 | 3020716.8807 | 6982 | 0
[6 empty] | 6983 | 317048.7697 | 6983 | 317048.7697
[6 empty] | 6984 | 0 | 6984 | 0
[6 empty] | 6985 | 164779.7167 | 6985 | 0
[6 empty] | 6986 | 0 | 6986 | 0
[6 empty] | 6987 | 0 | 6987 | 0
[6 empty] | 6988 | 0 | 6988 | 0
[6 empty] | 6989 | 0 | 6989 | 0
[6 empty] | 6990 | 0 | 6990 | 0
[6 empty] | 6991 | 0 | 6991 | 0
[6 empty] | 6992 | 0 | 6992 | 0
[6 empty] | 6993 | 216220.6441 | 6993 | 216220.6441
[6 empty] | 6994 | 0 | 6994 | 0
[6 empty] | 6995 | 0 | 6995 | 0
[6 empty] | 6996 | 0 | 6996 | 0
[6 empty] | 6997 | 1677330.0989 | 6997 | 0
[6 empty] | 6998 | 0 | 6998 | 0
[6 empty] | 6999 | 0 | 6999 | 0
[6 empty] | 7000 | 125985.4454 | 7000 | 125985.4454
[6 empty] | 7001 | 0 | 7001 | 0
[6 empty] | 7002 | 2704429.0579 | 7002 | 2704429.0579
[6 empty] | 7003 | 634719.6838 | 7003 | 634719.6838
[6 empty] | 7004 | 176099.1423 | 7004 | 0
[6 empty] | 7005 | 352002.707 | 7005 | 352002.707
[6 empty] | 7006 | 2916592.6873 | 7006 | 0
[6 empty] | 7007 | 201498.3922 | 7007 | 201498.3922
[6 empty] | 7008 | 3331436.2029 | 7008 | 3331436.2029
[6 empty] | 7009 | 0 | 7009 | 0
[6 empty] | 7010 | 3218325.0099 | 7010 | 0
[6 empty] | 7011 | 2529920.9529 | 7011 | 2529920.9529
[6 empty] | 7012 | 3075684.545 | 7012 | 0
[6 empty] | 7013 | 150792.8011 | 7013 | 150792.8011
[6 empty] | 7014 | 175007.3116 | 7014 | 0
[6 empty] | 7015 | 183989.437 | 7015 | 183989.437
[6 empty] | 7016 | 0 | 7016 | 0
[6 empty] | 7017 | 5277923.4675 | 7017 | 5277923.4675
[6 empty] | 7018 | 1872023.7052 | 7018 | 186595.3299
[6 empty] | 7019 | 0 | 7019 | 0
[6 empty] | 7020 | 1314157.0291 | 7020 | 1314157.0291
[6 empty] | 7021 | 766293.7894 | 7021 | 766293.7894
[6 empty] | 7022 | 0 | 7022 | 0
[6 empty] | 7023 | 0 | 7023 | 0
[6 empty] | 7024 | 0 | 7024 | 0
[6 empty] | 7025 | 3245404.7728 | 7025 | 0
[6 empty] | 7026 | 3153158.5288 | 7026 | 0
[6 empty] | 7027 | 154867.2803 | 7027 | 154867.2803
[6 empty] | 7028 | 0 | 7028 | 0
[6 empty] | 7029 | 296209.5702 | 7029 | 296209.5702
[6 empty] | 7030 | 190928.9923 | 7030 | 0
[6 empty] | 7031 | 0 | 7031 | 0
[6 empty] | 7032 | 3258636.7977 | 7032 | 0
[6 empty] | 7033 | 0 | 7033 | 0
[6 empty] | 7034 | 0 | 7034 | 0
[6 empty] | 7035 | 0 | 7035 | 0
[6 empty] | 7036 | 1773841.1135 | 7036 | 1773841.1135
[6 empty] | 7037 | 0 | 7037 | 0
[6 empty] | 7038 | 0 | 7038 | 0
[6 empty] | 7039 | 0 | 7039 | 0
[6 empty] | 7040 | 0 | 7040 | 0
[6 empty] | 7041 | 1167299.571 | 7041 | 1167299.571
[6 empty] | 7042 | 0 | 7042 | 0
[6 empty] | 7043 | 341355.0652 | 7043 | 341355.0652
[6 empty] | 7044 | 1264227.5132 | 7044 | 0
[6 empty] | 7045 | 751359.0121 | 7045 | 751359.0121
[6 empty] | 7046 | 0 | 7046 | 0
[6 empty] | 7047 | 0 | 7047 | 0
[6 empty] | 7048 | 0 | 7048 | 0
[6 empty] | 7049 | 280537.8221 | 7049 | 0
[6 empty] | 7050 | 552736.1511 | 7050 | 552736.1511
[6 empty] | 7051 | 1555710.304 | 7051 | 1555710.304
[6 empty] | 7052 | 0 | 7052 | 0
[6 empty] | 7053 | 1424894.9825 | 7053 | 1424894.9825
[6 empty] | 7054 | 0 | 7054 | 0
[6 empty] | 7055 | 284978.9108 | 7055 | 284978.9108
[6 empty] | 7056 | 668544.2083 | 7056 | 668544.2083
[6 empty] | 7057 | 0 | 7057 | 0
[6 empty] | 7058 | 0 | 7058 | 0
[6 empty] | 7059 | 0 | 7059 | 0
[6 empty] | 7060 | 0 | 7060 | 0
[6 empty] | 7061 | 4238483.9145 | 7061 | 0
[6 empty] | 7062 | 0 | 7062 | 0
[6 empty] | 7063 | 86695.3377 | 7063 | 86695.3377
[6 empty] | 7064 | 0 | 7064 | 0
[6 empty] | 7065 | 0 | 7065 | 0
[6 empty] | 7066 | 595111.7441 | 7066 | 595111.7441
[6 empty] | 7067 | 0 | 7067 | 0
[6 empty] | 7068 | 259866.6944 | 7068 | 259866.6944
[6 empty] | 7069 | 4765532.6269 | 7069 | 4765532.6269
[6 empty] | 7070 | 2012923.9369 | 7070 | 2012923.9369
[6 empty] | 7071 | 1982379.1565 | 7071 | 1982379.1565
[6 empty] | 7072 | 0 | 7072 | 0
[6 empty] | 7073 | 0 | 7073 | 0
[6 empty] | 7074 | 0 | 7074 | 0
[6 empty] | 7075 | 182709.328 | 7075 | 0
[6 empty] | 7076 | 4333896.6419 | 7076 | 4333896.6419
[6 empty] | 7077 | 2811885.2408 | 7077 | 2811885.2408
[6 empty] | 7078 | 1566869.1136 | 7078 | 1566869.1136
[6 empty] | 7079 | 17324990.0319 | 7079 | 0
[6 empty] | 7080 | 0 | 7080 | 0
[6 empty] | 7081 | 142669.1254 | 7081 | 142669.1254
[6 empty] | 7082 | 566714.7478 | 7082 | 566714.7478
[6 empty] | 7083 | 0 | 7083 | 0
[6 empty] | 7084 | 0 | 7084 | 0
[6 empty] | 7085 | 0 | 7085 | 0
[6 empty] | 7086 | 0 | 7086 | 0
[6 empty] | 7087 | 0 | 7087 | 0
[6 empty] | 7088 | 0 | 7088 | 0
[6 empty] | 7089 | 0 | 7089 | 0
[6 empty] | 7090 | 5572974.6718 | 7090 | 5372077.6239
[6 empty] | 7091 | 0 | 7091 | 0
[6 empty] | 7092 | 2824911.9116 | 7092 | 616163.2049
[6 empty] | 7093 | 0 | 7093 | 0
[6 empty] | 7094 | 4415019.5468 | 7094 | 751897.0716
[6 empty] | 7095 | 0 | 7095 | 0
[6 empty] | 7096 | 289705.1821 | 7096 | 289705.1821
[6 empty] | 7097 | 0 | 7097 | 0
[6 empty] | 7098 | 0 | 7098 | 0
[6 empty] | 7099 | 257095.7315 | 7099 | 0
[6 empty] | 7100 | 2473217.767 | 7100 | 2473217.767
[6 empty] | 7101 | 561804.6375 | 7101 | 561804.6375
[6 empty] | 7102 | 1030084.4378 | 7102 | 1030084.4378
[6 empty] | 7103 | 0 | 7103 | 0
[6 empty] | 7104 | 1775043.278 | 7104 | 0
[6 empty] | 7105 | 4775794.2009 | 7105 | 0
[6 empty] | 7106 | 4392155.3715 | 7106 | 4392155.3715
[6 empty] | 7107 | 241225.0311 | 7107 | 241225.0311
[6 empty] | 7108 | 10740469.9679 | 7108 | 0
[6 empty] | 7109 | 189979.205 | 7109 | 189979.205
[6 empty] | 7110 | 2912316.1433 | 7110 | 0
[6 empty] | 7111 | 225475.0789 | 7111 | 225475.0789
[6 empty] | 7112 | 3069614.9643 | 7112 | 0
[6 empty] | 7113 | 0 | 7113 | 0
[6 empty] | 7114 | 237235.824 | 7114 | 0
[6 empty] | 7115 | 913512.7133 | 7115 | 0
[6 empty] | 7116 | 0 | 7116 | 0
[6 empty] | 7117 | 0 | 7117 | 0
[6 empty] | 7118 | 161882.6458 | 7118 | 161882.6458
[6 empty] | 7119 | 4847351.2018 | 7119 | 4603516.6501
[6 empty] | 7120 | 3091459.5285 | 7120 | 2103140.4991
[6 empty] | 7121 | 0 | 7121 | 0
[6 empty] | 7122 | 320546.8638 | 7122 | 320546.8638
[6 empty] | 7123 | 246578.101 | 7123 | 0
[6 empty] | 7124 | 150559.9484 | 7124 | 150559.9484
[6 empty] | 7125 | 0 | 7125 | 0
[6 empty] | 7126 | 0 | 7126 | 0
[6 empty] | 7127 | 770982.954 | 7127 | 0
[6 empty] | 7128 | 0 | 7128 | 0
[6 empty] | 7129 | 3465660.788 | 7129 | 331386.7895
[6 empty] | 7130 | 0 | 7130 | 0
[6 empty] | 7131 | 3056276.0655 | 7131 | 0
[6 empty] | 7132 | 0 | 7132 | 0
[6 empty] | 7133 | 146088.6359 | 7133 | 146088.6359
[6 empty] | 7134 | 312297.215 | 7134 | 312297.215
[6 empty] | 7135 | 0 | 7135 | 0
[6 empty] | 7136 | 0 | 7136 | 0
[6 empty] | 7137 | 1560816.6193 | 7137 | 0
[6 empty] | 7138 | 0 | 7138 | 0
[6 empty] | 7139 | 0 | 7139 | 0
[6 empty] | 7140 | 990855.4589 | 7140 | 990855.4589
[6 empty] | 7141 | 591183.8721 | 7141 | 591183.8721
[6 empty] | 7142 | 0 | 7142 | 0
[6 empty] | 7143 | 260059.6798 | 7143 | 260059.6798
[6 empty] | 7144 | 618465.8471 | 7144 | 618465.8471
[6 empty] | 7145 | 169936.4672 | 7145 | 169936.4672
[6 empty] | 7146 | 2916778.215 | 7146 | 2916778.215
[6 empty] | 7147 | 0 | 7147 | 0
[6 empty] | 7148 | 0 | 7148 | 0
[6 empty] | 7149 | 5725902.5772 | 7149 | 0
[6 empty] | 7150 | 5022902.7808 | 7150 | 5022902.7808
[6 empty] | 7151 | 484659.163 | 7151 | 484659.163
[6 empty] | 7152 | 0 | 7152 | 0
[6 empty] | 7153 | 107375.223 | 7153 | 107375.223
[6 empty] | 7154 | 409626.7267 | 7154 | 409626.7267
[6 empty] | 7155 | 205630.9767 | 7155 | 0
[6 empty] | 7156 | 4938933.803 | 7156 | 4938933.803
[6 empty] | 7157 | 0 | 7157 | 0
[6 empty] | 7158 | 0 | 7158 | 0
[6 empty] | 7159 | 3999317.7323 | 7159 | 3999317.7323
[6 empty] | 7160 | 0 | 7160 | 0
[6 empty] | 7161 | 376197.4841 | 7161 | 376197.4841
[6 empty] | 7162 | 140376.086 | 7162 | 140376.086
[6 empty] | 7163 | 0 | 7163 | 0
[6 empty] | 7164 | 1025707.0297 | 7164 | 253017.5681
[6 empty] | 7165 | 0 | 7165 | 0
[6 empty] | 7166 | 0 | 7166 | 0
[6 empty] | 7167 | 3115496.9311 | 7167 | 242468.6118
[6 empty] | 7168 | 0 | 7168 | 0
[6 empty] | 7169 | 0 | 7169 | 0
[6 empty] | 7170 | 0 | 7170 | 0
[6 empty] | 7171 | 149563.7358 | 7171 | 149563.7358
[6 empty] | 7172 | 0 | 7172 | 0
[6 empty] | 7173 | 0 | 7173 | 0
[6 empty] | 7174 | 0 | 7174 | 0
[6 empty] | 7175 | 165468.8622 | 7175 | 165468.8622
[6 empty] | 7176 | 0 | 7176 | 0
[6 empty] | 7177 | 4531719.4207 | 7177 | 1071141.354
[6 empty] | 7178 | 0 | 7178 | 0
[6 empty] | 7179 | 6382068.7525 | 7179 | 6382068.7525
[6 empty] | 7180 | 0 | 7180 | 0
[6 empty] | 7181 | 0 | 7181 | 0
[6 empty] | 7182 | 0 | 7182 | 0
[6 empty] | 7183 | 214648.2992 | 7183 | 0
[6 empty] | 7184 | 0 | 7184 | 0
[6 empty] | 7185 | 0 | 7185 | 0
[6 empty] | 7186 | 0 | 7186 | 0
[6 empty] | 7187 | 0 | 7187 | 0
[6 empty] | 7188 | 0 | 7188 | 0
[6 empty] | 7189 | 0 | 7189 | 0
[6 empty] | 7190 | 0 | 7190 | 0
[6 empty] | 7191 | 2395515.8981 | 7191 | 0
[6 empty] | 7192 | 0 | 7192 | 0
[6 empty] | 7193 | 210148.56 | 7193 | 210148.56
[6 empty] | 7194 | 0 | 7194 | 0
[6 empty] | 7195 | 0 | 7195 | 0
[6 empty] | 7196 | 0 | 7196 | 0
[6 empty] | 7197 | 138577.6193 | 7197 | 0
[6 empty] | 7198 | 0 | 7198 | 0
[6 empty] | 7199 | 661312.1195 | 7199 | 661312.1195
[6 empty] | 7200 | 0 | 7200 | 0
[6 empty] | 7201 | 0 | 7201 | 0
[6 empty] | 7202 | 0 | 7202 | 0
[6 empty] | 7203 | 0 | 7203 | 0
[6 empty] | 7204 | 0 | 7204 | 0
[6 empty] | 7205 | 7998879.1084 | 7205 | 0
[6 empty] | 7206 | 2594334.4022 | 7206 | 0
[6 empty] | 7207 | 0 | 7207 | 0
[6 empty] | 7208 | 2686440.6722 | 7208 | 2686440.6722
[6 empty] | 7209 | 0 | 7209 | 0
[6 empty] | 7210 | 0 | 7210 | 0
[6 empty] | 7211 | 100474.8804 | 7211 | 100474.8804
[6 empty] | 7212 | 0 | 7212 | 0
[6 empty] | 7213 | 315735.8923 | 7213 | 315735.8923
[6 empty] | 7214 | 2845864.9241 | 7214 | 2845864.9241
[6 empty] | 7215 | 3073827.7158 | 7215 | 3073827.7158
[6 empty] | 7216 | 0 | 7216 | 0
[6 empty] | 7217 | 0 | 7217 | 0
[6 empty] | 7218 | 3408180.6615 | 7218 | 390942.1989
[6 empty] | 7219 | 0 | 7219 | 0
[6 empty] | 7220 | 4958232.6074 | 7220 | 0
[6 empty] | 7221 | 234255.4959 | 7221 | 234255.4959
[6 empty] | 7222 | 3844203.2292 | 7222 | 0
[6 empty] | 7223 | 5205998.6005 | 7223 | 3696021.9412
[6 empty] | 7224 | 153597.0631 | 7224 | 0
[6 empty] | 7225 | 0 | 7225 | 0
[6 empty] | 7226 | 222731.0387 | 7226 | 0
[6 empty] | 7227 | 345495.7794 | 7227 | 345495.7794
[6 empty] | 7228 | 0 | 7228 | 0
[6 empty] | 7229 | 0 | 7229 | 0
[6 empty] | 7230 | 879295.6225 | 7230 | 879295.6225
[6 empty] | 7231 | 191081.5958 | 7231 | 191081.5958
[6 empty] | 7232 | 121471.5352 | 7232 | 121471.5352
[6 empty] | 7233 | 2377960.2806 | 7233 | 0
[6 empty] | 7234 | 0 | 7234 | 0
[6 empty] | 7235 | 148792.5719 | 7235 | 148792.5719
[6 empty] | 7236 | 1855177.6809 | 7236 | 0
[6 empty] | 7237 | 0 | 7237 | 0
[6 empty] | 7238 | 946221.872 | 7238 | 0
[6 empty] | 7239 | 0 | 7239 | 0
[6 empty] | 7240 | 4329772.5127 | 7240 | 4329772.5127
[6 empty] | 7241 | 0 | 7241 | 0
[6 empty] | 7242 | 2086274.3133 | 7242 | 0
[6 empty] | 7243 | 0 | 7243 | 0
[6 empty] | 7244 | 0 | 7244 | 0
[6 empty] | 7245 | 0 | 7245 | 0
[6 empty] | 7246 | 0 | 7246 | 0
[6 empty] | 7247 | 8405878.6228 | 7247 | 88620.8913
[6 empty] | 7248 | 10367350.1011 | 7248 | 0
[6 empty] | 7249 | 0 | 7249 | 0
[6 empty] | 7250 | 298786.2073 | 7250 | 298786.2073
[6 empty] | 7251 | 230118.5003 | 7251 | 230118.5003
[6 empty] | 7252 | 282579.9787 | 7252 | 0
[6 empty] | 7253 | 3074908.3499 | 7253 | 0
[6 empty] | 7254 | 603213.4565 | 7254 | 603213.4565
[6 empty] | 7255 | 346034.0799 | 7255 | 346034.0799
[6 empty] | 7256 | 112556.2543 | 7256 | 112556.2543
[6 empty] | 7257 | 238001.2881 | 7257 | 238001.2881
[6 empty] | 7258 | 811758.9757 | 7258 | 811758.9757
[6 empty] | 7259 | 0 | 7259 | 0
[6 empty] | 7260 | 285206.1043 | 7260 | 0
[6 empty] | 7261 | 194392.0319 | 7261 | 0
[6 empty] | 7262 | 0 | 7262 | 0
[6 empty] | 7263 | 3698877.1086 | 7263 | 3698877.1086
[6 empty] | 7264 | 0 | 7264 | 0
[6 empty] | 7265 | 0 | 7265 | 0
[6 empty] | 7266 | 2792760.2407 | 7266 | 2792760.2407
[6 empty] | 7267 | 784311.9547 | 7267 | 784311.9547
[6 empty] | 7268 | 0 | 7268 | 0
[6 empty] | 7269 | 0 | 7269 | 0
[6 empty] | 7270 | 0 | 7270 | 0
[6 empty] | 7271 | 0 | 7271 | 0
[6 empty] | 7272 | 0 | 7272 | 0
[6 empty] | 7273 | 0 | 7273 | 0
[6 empty] | 7274 | 602851.1425 | 7274 | 0
[6 empty] | 7275 | 2443168.2408 | 7275 | 2443168.2408
[6 empty] | 7276 | 3921432.48 | 7276 | 3921432.48
[6 empty] | 7277 | 4344107.0435 | 7277 | 4344107.0435
[6 empty] | 7278 | 3844392 | 7278 | 373402.247
[6 empty] | 7279 | 0 | 7279 | 0
[6 empty] | 7280 | 4625952.085 | 7280 | 686218.3101
[6 empty] | 7281 | 0 | 7281 | 0
[6 empty] | 7282 | 64509.3009 | 7282 | 64509.3009
[6 empty] | 7283 | 246613.897 | 7283 | 0
[6 empty] | 7284 | 163754.0162 | 7284 | 163754.0162
[6 empty] | 7285 | 402710.9135 | 7285 | 200323.4963
[6 empty] | 7286 | 0 | 7286 | 0
[6 empty] | 7287 | 0 | 7287 | 0
[6 empty] | 7288 | 0 | 7288 | 0
[6 empty] | 7289 | 0 | 7289 | 0
[6 empty] | 7290 | 1664022.2213 | 7290 | 1455960.9044
[6 empty] | 7291 | 2283334.2531 | 7291 | 180494.2286
[6 empty] | 7292 | 414525.9534 | 7292 | 414525.9534
[6 empty] | 7293 | 266939.699 | 7293 | 266939.699
[6 empty] | 7294 | 0 | 7294 | 0
[6 empty] | 7295 | 0 | 7295 | 0
[6 empty] | 7296 | 0 | 7296 | 0
[6 empty] | 7297 | 0 | 7297 | 0
[6 empty] | 7298 | 0 | 7298 | 0
[6 empty] | 7299 | 6472906.2878 | 7299 | 6472906.2878
[6 empty] | 7300 | 5946793.6599 | 7300 | 1273983.5053
[6 empty] | 7301 | 0 | 7301 | 0
[6 empty] | 7302 | 0 | 7302 | 0
[6 empty] | 7303 | 0 | 7303 | 0
[6 empty] | 7304 | 0 | 7304 | 0
[6 empty] | 7305 | 2674607.0133 | 7305 | 0
[6 empty] | 7306 | 0 | 7306 | 0
[6 empty] | 7307 | 0 | 7307 | 0
[6 empty] | 7308 | 218355.9772 | 7308 | 218355.9772
[6 empty] | 7309 | 0 | 7309 | 0
[6 empty] | 7310 | 2573132.2643 | 7310 | 2573132.2643
[6 empty] | 7311 | 1631464.8187 | 7311 | 0
[6 empty] | 7312 | 2840847.9486 | 7312 | 0
[6 empty] | 7313 | 0 | 7313 | 0
[6 empty] | 7314 | 1201849.3265 | 7314 | 1201849.3265
[6 empty] | 7315 | 0 | 7315 | 0
[6 empty] | 7316 | 0 | 7316 | 0
[6 empty] | 7317 | 821023.2052 | 7317 | 821023.2052
[6 empty] | 7318 | 0 | 7318 | 0
[6 empty] | 7319 | 0 | 7319 | 0
[6 empty] | 7320 | 0 | 7320 | 0
[6 empty] | 7321 | 0 | 7321 | 0
[6 empty] | 7322 | 0 | 7322 | 0
[6 empty] | 7323 | 0 | 7323 | 0
[6 empty] | 7324 | 231927.9574 | 7324 | 0
[6 empty] | 7325 | 2225919.7594 | 7325 | 214838.1792
[6 empty] | 7326 | 0 | 7326 | 0
[6 empty] | 7327 | 4138098.8827 | 7327 | 0
[6 empty] | 7328 | 4466747.6679 | 7328 | 901494.9718
[6 empty] | 7329 | 3039767.6553 | 7329 | 3039767.6553
[6 empty] | 7330 | 276726.523 | 7330 | 276726.523
[6 empty] | 7331 | 0 | 7331 | 0
[6 empty] | 7332 | 127770.2115 | 7332 | 127770.2115
[6 empty] | 7333 | 342022.0284 | 7333 | 342022.0284
[6 empty] | 7334 | 0 | 7334 | 0
[6 empty] | 7335 | 2032721.0173 | 7335 | 1665016.5822
[6 empty] | 7336 | 0 | 7336 | 0
[6 empty] | 7337 | 2433468.8577 | 7337 | 0
[6 empty] | 7338 | 779768.5631 | 7338 | 446901.5326
[6 empty] | 7339 | 0 | 7339 | 0
[6 empty] | 7340 | 0 | 7340 | 0
[6 empty] | 7341 | 1359192.5439 | 7341 | 0
[6 empty] | 7342 | 0 | 7342 | 0
[6 empty] | 7343 | 4084622.0838 | 7343 | 4084622.0838
[6 empty] | 7344 | 0 | 7344 | 0
[6 empty] | 7345 | 262542.3716 | 7345 | 0
[6 empty] | 7346 | 0 | 7346 | 0
[6 empty] | 7347 | 295613.1371 | 7347 | 295613.1371
[6 empty] | 7348 | 1514186.9139 | 7348 | 1514186.9139
[6 empty] | 7349 | 0 | 7349 | 0
[6 empty] | 7350 | 305815.2224 | 7350 | 0
[6 empty] | 7351 | 267359.5219 | 7351 | 81146.7885
[6 empty] | 7352 | 0 | 7352 | 0
[6 empty] | 7353 | 446737.55 | 7353 | 446737.55
[6 empty] | 7354 | 755212.3815 | 7354 | 755212.3815
[6 empty] | 7355 | 0 | 7355 | 0
[6 empty] | 7356 | 0 | 7356 | 0
[6 empty] | 7357 | 183719.9837 | 7357 | 183719.9837
[6 empty] | 7358 | 287558.4174 | 7358 | 287558.4174
[6 empty] | 7359 | 371559.5689 | 7359 | 152567.7721
[6 empty] | 7360 | 817491.2267 | 7360 | 817491.2267
[6 empty] | 7361 | 0 | 7361 | 0
[6 empty] | 7362 | 0 | 7362 | 0
[6 empty] | 7363 | 0 | 7363 | 0
[6 empty] | 7364 | 0 | 7364 | 0
[6 empty] | 7365 | 3531679.137 | 7365 | 482728.5458
[6 empty] | 7366 | 162655.9969 | 7366 | 0
[6 empty] | 7367 | 5256028.4683 | 7367 | 688065.9046
[6 empty] | 7368 | 0 | 7368 | 0
[6 empty] | 7369 | 2839201.2297 | 7369 | 0
[6 empty] | 7370 | 0 | 7370 | 0
[6 empty] | 7371 | 0 | 7371 | 0
[6 empty] | 7372 | 159968.2085 | 7372 | 159968.2085
[6 empty] | 7373 | 0 | 7373 | 0
[6 empty] | 7374 | 0 | 7374 | 0
[6 empty] | 7375 | 0 | 7375 | 0
[6 empty] | 7376 | 0 | 7376 | 0
[6 empty] | 7377 | 191927.0475 | 7377 | 191927.0475
[6 empty] | 7378 | 16124281.1988 | 7378 | 350516.2779
[6 empty] | 7379 | 0 | 7379 | 0
[6 empty] | 7380 | 0 | 7380 | 0
[6 empty] | 7381 | 1491366.1481 | 7381 | 0
[6 empty] | 7382 | 1726537.5853 | 7382 | 1515578.8274
[6 empty] | 7383 | 2777549.4486 | 7383 | 0
[6 empty] | 7384 | 3364581.3605 | 7384 | 3364581.3605
[6 empty] | 7385 | 2527198.589 | 7385 | 2312250.1899
[6 empty] | 7386 | 0 | 7386 | 0
[6 empty] | 7387 | 1469768.8731 | 7387 | 0
[6 empty] | 7388 | 0 | 7388 | 0
[6 empty] | 7389 | 0 | 7389 | 0
[6 empty] | 7390 | 0 | 7390 | 0
[6 empty] | 7391 | 0 | 7391 | 0
[6 empty] | 7392 | 0 | 7392 | 0
[6 empty] | 7393 | 402537.9483 | 7393 | 179021.8519
[6 empty] | 7394 | 0 | 7394 | 0
[6 empty] | 7395 | 0 | 7395 | 0
[6 empty] | 7396 | 0 | 7396 | 0
[6 empty] | 7397 | 0 | 7397 | 0
[6 empty] | 7398 | 3036865.5136 | 7398 | 0
[6 empty] | 7399 | 4728210.1234 | 7399 | 0
[6 empty] | 7400 | 330053.8979 | 7400 | 0
[6 empty] | 7401 | 2580076.6214 | 7401 | 2580076.6214
[6 empty] | 7402 | 6001072.4932 | 7402 | 3981464.3249
[6 empty] | 7403 | 159589.0263 | 7403 | 159589.0263
[6 empty] | 7404 | 5270476.8186 | 7404 | 3468791.8192
[6 empty] | 7405 | 288720.7881 | 7405 | 288720.7881
[6 empty] | 7406 | 2122965.0852 | 7406 | 0
[6 empty] | 7407 | 0 | 7407 | 0
[6 empty] | 7408 | 2351411.6826 | 7408 | 315509.333
[6 empty] | 7409 | 4945143.5304 | 7409 | 4945143.5304
[6 empty] | 7410 | 4326741.0499 | 7410 | 4326741.0499
[6 empty] | 7411 | 3209605.1175 | 7411 | 3209605.1175
[6 empty] | 7412 | 0 | 7412 | 0
[6 empty] | 7413 | 561686.523 | 7413 | 561686.523
[6 empty] | 7414 | 0 | 7414 | 0
[6 empty] | 7415 | 0 | 7415 | 0
[6 empty] | 7416 | 4252647.6297 | 7416 | 0
[6 empty] | 7417 | 241803.3219 | 7417 | 241803.3219
[6 empty] | 7418 | 111524.2459 | 7418 | 111524.2459
[6 empty] | 7419 | 3781868.3409 | 7419 | 0
[6 empty] | 7420 | 3239292.277 | 7420 | 0
[6 empty] | 7421 | 2640333.5644 | 7421 | 2640333.5644
[6 empty] | 7422 | 6485709.0145 | 7422 | 0
[6 empty] | 7423 | 0 | 7423 | 0
[6 empty] | 7424 | 237734.6069 | 7424 | 237734.6069
[6 empty] | 7425 | 0 | 7425 | 0
[6 empty] | 7426 | 0 | 7426 | 0
[6 empty] | 7427 | 2490613.4668 | 7427 | 2490613.4668
[6 empty] | 7428 | 0 | 7428 | 0
[6 empty] | 7429 | 0 | 7429 | 0
[6 empty] | 7430 | 1284979.7879 | 7430 | 0
[6 empty] | 7431 | 191071.8428 | 7431 | 191071.8428
[6 empty] | 7432 | 0 | 7432 | 0
[6 empty] | 7433 | 190698.1898 | 7433 | 190698.1898
[6 empty] | 7434 | 2347540.2823 | 7434 | 2075451.6979
[6 empty] | 7435 | 0 | 7435 | 0
[6 empty] | 7436 | 0 | 7436 | 0
[6 empty] | 7437 | 127100.8242 | 7437 | 0
[6 empty] | 7438 | 0 | 7438 | 0
[6 empty] | 7439 | 3450967.0237 | 7439 | 3169320.0503
[6 empty] | 7440 | 3283206.7266 | 7440 | 3283206.7266
[6 empty] | 7441 | 0 | 7441 | 0
[6 empty] | 7442 | 2432717.5637 | 7442 | 2432717.5637
[6 empty] | 7443 | 656436.7049 | 7443 | 656436.7049
[6 empty] | 7444 | 0 | 7444 | 0
[6 empty] | 7445 | 174709.877 | 7445 | 174709.877
[6 empty] | 7446 | 0 | 7446 | 0
[6 empty] | 7447 | 308665.6372 | 7447 | 308665.6372
[6 empty] | 7448 | 0 | 7448 | 0
[6 empty] | 7449 | 1267539.6166 | 7449 | 1267539.6166
[6 empty] | 7450 | 273560.7332 | 7450 | 273560.7332
[6 empty] | 7451 | 0 | 7451 | 0
[6 empty] | 7452 | 135963.8072 | 7452 | 135963.8072
[6 empty] | 7453 | 0 | 7453 | 0
[6 empty] | 7454 | 0 | 7454 | 0
[6 empty] | 7455 | 866947.1718 | 7455 | 0
[6 empty] | 7456 | 0 | 7456 | 0
[6 empty] | 7457 | 1016877.1903 | 7457 | 214420.5874
[6 empty] | 7458 | 0 | 7458 | 0
[6 empty] | 7459 | 0 | 7459 | 0
[6 empty] | 7460 | 4693606.4388 | 7460 | 4693606.4388
[6 empty] | 7461 | 4170191.7669 | 7461 | 0
[6 empty] | 7462 | 384828.5684 | 7462 | 384828.5684
[6 empty] | 7463 | 5236906.3214 | 7463 | 0
[6 empty] | 7464 | 0 | 7464 | 0
[6 empty] | 7465 | 1345333.1435 | 7465 | 1345333.1435
[6 empty] | 7466 | 0 | 7466 | 0
[6 empty] | 7467 | 178889.0914 | 7467 | 178889.0914
[6 empty] | 7468 | 0 | 7468 | 0
[6 empty] | 7469 | 7441571.2579 | 7469 | 7441571.2579
[6 empty] | 7470 | 0 | 7470 | 0
[6 empty] | 7471 | 2807877.7262 | 7471 | 0
[6 empty] | 7472 | 4094811.0512 | 7472 | 354284.6765
[6 empty] | 7473 | 0 | 7473 | 0
[6 empty] | 7474 | 0 | 7474 | 0
[6 empty] | 7475 | 1270893.3833 | 7475 | 378106.668
[6 empty] | 7476 | 255506.4317 | 7476 | 255506.4317
[6 empty] | 7477 | 6332630.7674 | 7477 | 6088495.7023
[6 empty] | 7478 | 2951407.2604 | 7478 | 0
[6 empty] | 7479 | 7241315.7415 | 7479 | 0
[6 empty] | 7480 | 0 | 7480 | 0
[6 empty] | 7481 | 2877179.3926 | 7481 | 0
[6 empty] | 7482 | 556396.005 | 7482 | 556396.005
[6 empty] | 7483 | 0 | 7483 | 0
[6 empty] | 7484 | 0 | 7484 | 0
[6 empty] | 7485 | 5998297.1511 | 7485 | 5998297.1511
[6 empty] | 7486 | 0 | 7486 | 0
[6 empty] | 7487 | 0 | 7487 | 0
[6 empty] | 7488 | 0 | 7488 | 0
[6 empty] | 7489 | 0 | 7489 | 0
[6 empty] | 7490 | 177017.6783 | 7490 | 177017.6783
[6 empty] | 7491 | 527980.2739 | 7491 | 527980.2739
[6 empty] | 7492 | 3557759.5526 | 7492 | 0
[6 empty] | 7493 | 11501464.7508 | 7493 | 0
[6 empty] | 7494 | 0 | 7494 | 0
[6 empty] | 7495 | 0 | 7495 | 0
[6 empty] | 7496 | 2967934.6444 | 7496 | 2967934.6444
[6 empty] | 7497 | 0 | 7497 | 0
[6 empty] | 7498 | 0 | 7498 | 0
[6 empty] | 7499 | 0 | 7499 | 0
[6 empty] | 7500 | 415681.9313 | 7500 | 415681.9313
[6 empty] | 7501 | 0 | 7501 | 0
[6 empty] | 7502 | 2968894.838 | 7502 | 320359.262
[6 empty] | 7503 | 3457798.4856 | 7503 | 0
[6 empty] | 7504 | 0 | 7504 | 0
[6 empty] | 7505 | 235681.4155 | 7505 | 0
[6 empty] | 7506 | 0 | 7506 | 0
[6 empty] | 7507 | 0 | 7507 | 0
[6 empty] | 7508 | 324395.5774 | 7508 | 324395.5774
[6 empty] | 7509 | 3824289.8758 | 7509 | 3824289.8758
[6 empty] | 7510 | 0 | 7510 | 0
[6 empty] | 7511 | 0 | 7511 | 0
[6 empty] | 7512 | 692615.1878 | 7512 | 692615.1878
[6 empty] | 7513 | 0 | 7513 | 0
[6 empty] | 7514 | 0 | 7514 | 0
[6 empty] | 7515 | 0 | 7515 | 0
[6 empty] | 7516 | 191261.5478 | 7516 | 0
[6 empty] | 7517 | 0 | 7517 | 0
[6 empty] | 7518 | 230970.4102 | 7518 | 230970.4102
[6 empty] | 7519 | 0 | 7519 | 0
[6 empty] | 7520 | 0 | 7520 | 0
[6 empty] | 7521 | 229081.2454 | 7521 | 229081.2454
[6 empty] | 7522 | 433008.6978 | 7522 | 433008.6978
[6 empty] | 7523 | 0 | 7523 | 0
[6 empty] | 7524 | 4518449.4588 | 7524 | 551595.0304
[6 empty] | 7525 | 0 | 7525 | 0
[6 empty] | 7526 | 0 | 7526 | 0
[6 empty] | 7527 | 0 | 7527 | 0
[6 empty] | 7528 | 0 | 7528 | 0
[6 empty] | 7529 | 0 | 7529 | 0
[6 empty] | 7530 | 0 | 7530 | 0
[6 empty] | 7531 | 4103870.9865 | 7531 | 0
[6 empty] | 7532 | 0 | 7532 | 0
[6 empty] | 7533 | 0 | 7533 | 0
[6 empty] | 7534 | 0 | 7534 | 0
[6 empty] | 7535 | 5955108.5153 | 7535 | 0
[6 empty] | 7536 | 0 | 7536 | 0
[6 empty] | 7537 | 207968.8634 | 7537 | 207968.8634
[6 empty] | 7538 | 1048453.5993 | 7538 | 899005.899
[6 empty] | 7539 | 0 | 7539 | 0
[6 empty] | 7540 | 0 | 7540 | 0
[6 empty] | 7541 | 130962.7396 | 7541 | 0
[6 empty] | 7542 | 248529.1997 | 7542 | 248529.1997
[6 empty] | 7543 | 4546346.5058 | 7543 | 0
[6 empty] | 7544 | 2847110.4428 | 7544 | 392103.8306
[6 empty] | 7545 | 0 | 7545 | 0
[6 empty] | 7546 | 0 | 7546 | 0
[6 empty] | 7547 | 0 | 7547 | 0
[6 empty] | 7548 | 0 | 7548 | 0
[6 empty] | 7549 | 0 | 7549 | 0
[6 empty] | 7550 | 0 | 7550 | 0
[6 empty] | 7551 | 381306.2841 | 7551 | 381306.2841
[6 empty] | 7552 | 5313056.4108 | 7552 | 5313056.4108
[6 empty] | 7553 | 0 | 7553 | 0
[6 empty] | 7554 | 0 | 7554 | 0
[6 empty] | 7555 | 0 | 7555 | 0
[6 empty] | 7556 | 0 | 7556 | 0
[6 empty] | 7557 | 0 | 7557 | 0
[6 empty] | 7558 | 0 | 7558 | 0
[6 empty] | 7559 | 256865.07 | 7559 | 256865.07
[6 empty] | 7560 | 0 | 7560 | 0
[6 empty] | 7561 | 0 | 7561 | 0
[6 empty] | 7562 | 0 | 7562 | 0
[6 empty] | 7563 | 1937538.1339 | 7563 | 0
[6 empty] | 7564 | 247277.6682 | 7564 | 247277.6682
[6 empty] | 7565 | 0 | 7565 | 0
[6 empty] | 7566 | 0 | 7566 | 0
[6 empty] | 7567 | 1271025.0363 | 7567 | 0
[6 empty] | 7568 | 0 | 7568 | 0
[6 empty] | 7569 | 1890036.5074 | 7569 | 1890036.5074
[6 empty] | 7570 | 11282931.7517 | 7570 | 11282931.7517
[6 empty] | 7571 | 0 | 7571 | 0
[6 empty] | 7572 | 9440012.0528 | 7572 | 9440012.0528
[6 empty] | 7573 | 372636.8101 | 7573 | 372636.8101
[6 empty] | 7574 | 0 | 7574 | 0
[6 empty] | 7575 | 0 | 7575 | 0
[6 empty] | 7576 | 0 | 7576 | 0
[6 empty] | 7577 | 4481132.3491 | 7577 | 1423656.7159
[6 empty] | 7578 | 15284798.0454 | 7578 | 15284798.0454
[6 empty] | 7579 | 1874211.4925 | 7579 | 0
[6 empty] | 7580 | 0 | 7580 | 0
[6 empty] | 7581 | 0 | 7581 | 0
[6 empty] | 7582 | 0 | 7582 | 0
[6 empty] | 7583 | 0 | 7583 | 0
[6 empty] | 7584 | 3100727.6947 | 7584 | 0
[6 empty] | 7585 | 278487.5699 | 7585 | 278487.5699
[6 empty] | 7586 | 2778171.47 | 7586 | 2778171.47
[6 empty] | 7587 | 0 | 7587 | 0
[6 empty] | 7588 | 0 | 7588 | 0
[6 empty] | 7589 | 0 | 7589 | 0
[6 empty] | 7590 | 0 | 7590 | 0
[6 empty] | 7591 | 0 | 7591 | 0
[6 empty] | 7592 | 0 | 7592 | 0
[6 empty] | 7593 | 0 | 7593 | 0
[6 empty] | 7594 | 175984.9569 | 7594 | 0
[6 empty] | 7595 | 0 | 7595 | 0
[6 empty] | 7596 | 5998461.3671 | 7596 | 2689508.4686
[6 empty] | 7597 | 0 | 7597 | 0
[6 empty] | 7598 | 0 | 7598 | 0
[6 empty] | 7599 | 4078542.729 | 7599 | 0
[6 empty] | 7600 | 3661086.0273 | 7600 | 250406.9326
[6 empty] | 7601 | 0 | 7601 | 0
[6 empty] | 7602 | 4927138.9549 | 7602 | 488303.6049
[6 empty] | 7603 | 246488.1168 | 7603 | 0
[6 empty] | 7604 | 2226629.9798 | 7604 | 2226629.9798
[6 empty] | 7605 | 3770445.9384 | 7605 | 206877.1031
[6 empty] | 7606 | 0 | 7606 | 0
[6 empty] | 7607 | 0 | 7607 | 0
[6 empty] | 7608 | 0 | 7608 | 0
[6 empty] | 7609 | 2936920.6395 | 7609 | 2936920.6395
[6 empty] | 7610 | 1268629.409 | 7610 | 1268629.409
[6 empty] | 7611 | 188826.0239 | 7611 | 188826.0239
[6 empty] | 7612 | 249736.7334 | 7612 | 0
[6 empty] | 7613 | 0 | 7613 | 0
[6 empty] | 7614 | 6534611.0045 | 7614 | 0
[6 empty] | 7615 | 199387.9731 | 7615 | 0
[6 empty] | 7616 | 560953.2296 | 7616 | 351903.7331
[6 empty] | 7617 | 0 | 7617 | 0
[6 empty] | 7618 | 0 | 7618 | 0
[6 empty] | 7619 | 17040909.2534 | 7619 | 0
[6 empty] | 7620 | 0 | 7620 | 0
[6 empty] | 7621 | 0 | 7621 | 0
[6 empty] | 7622 | 0 | 7622 | 0
[6 empty] | 7623 | 0 | 7623 | 0
[6 empty] | 7624 | 0 | 7624 | 0
[6 empty] | 7625 | 0 | 7625 | 0
[6 empty] | 7626 | 49155.4782 | 7626 | 49155.4782
[6 empty] | 7627 | 0 | 7627 | 0
[6 empty] | 7628 | 233493.3877 | 7628 | 0
[6 empty] | 7629 | 0 | 7629 | 0
[6 empty] | 7630 | 211518.2147 | 7630 | 211518.2147
[6 empty] | 7631 | 0 | 7631 | 0
[6 empty] | 7632 | 0 | 7632 | 0
[6 empty] | 7633 | 0 | 7633 | 0
[6 empty] | 7634 | 0 | 7634 | 0
[6 empty] | 7635 | 0 | 7635 | 0
[6 empty] | 7636 | 0 | 7636 | 0
[6 empty] | 7637 | 2451313.1258 | 7637 | 2451313.1258
[6 empty] | 7638 | 0 | 7638 | 0
[6 empty] | 7639 | 0 | 7639 | 0
[6 empty] | 7640 | 0 | 7640 | 0
[6 empty] | 7641 | 0 | 7641 | 0
[6 empty] | 7642 | 212002.6372 | 7642 | 0
[6 empty] | 7643 | 0 | 7643 | 0
[6 empty] | 7644 | 302036.182 | 7644 | 302036.182
[6 empty] | 7645 | 2999035.7654 | 7645 | 0
[6 empty] | 7646 | 0 | 7646 | 0
[6 empty] | 7647 | 0 | 7647 | 0
[6 empty] | 7648 | 9680986.2321 | 7648 | 0
[6 empty] | 7649 | 0 | 7649 | 0
[6 empty] | 7650 | 6669517.8663 | 7650 | 6669517.8663
[6 empty] | 7651 | 0 | 7651 | 0
[6 empty] | 7652 | 7638682.6291 | 7652 | 412732.9941
[6 empty] | 7653 | 0 | 7653 | 0
[6 empty] | 7654 | 137610.2107 | 7654 | 137610.2107
[6 empty] | 7655 | 0 | 7655 | 0
[6 empty] | 7656 | 0 | 7656 | 0
[6 empty] | 7657 | 0 | 7657 | 0
[6 empty] | 7658 | 194241.1042 | 7658 | 194241.1042
[6 empty] | 7659 | 0 | 7659 | 0
[6 empty] | 7660 | 2747019.6563 | 7660 | 2747019.6563
[6 empty] | 7661 | 0 | 7661 | 0
[6 empty] | 7662 | 9136811.8784 | 7662 | 9136811.8784
[6 empty] | 7663 | 269708.9199 | 7663 | 269708.9199
[6 empty] | 7664 | 0 | 7664 | 0
[6 empty] | 7665 | 0 | 7665 | 0
[6 empty] | 7666 | 0 | 7666 | 0
[6 empty] | 7667 | 3506495.5379 | 7667 | 458860.6944
[6 empty] | 7668 | 3025718.2569 | 7668 | 0
[6 empty] | 7669 | 480239.585 | 7669 | 480239.585
[6 empty] | 7670 | 0 | 7670 | 0
[6 empty] | 7671 | 0 | 7671 | 0
[6 empty] | 7672 | 213336.4364 | 7672 | 0
[6 empty] | 7673 | 2628242.7527 | 7673 | 0
[6 empty] | 7674 | 0 | 7674 | 0
[6 empty] | 7675 | 0 | 7675 | 0
[6 empty] | 7676 | 221321.8275 | 7676 | 221321.8275
[6 empty] | 7677 | 0 | 7677 | 0
[6 empty] | 7678 | 7205220.1507 | 7678 | 0
[6 empty] | 7679 | 2520652.4187 | 7679 | 0
[6 empty] | 7680 | 0 | 7680 | 0
[6 empty] | 7681 | 3963567.5593 | 7681 | 3963567.5593
[6 empty] | 7682 | 0 | 7682 | 0
[6 empty] | 7683 | 561849.6429 | 7683 | 296172.5386
[6 empty] | 7684 | 0 | 7684 | 0
[6 empty] | 7685 | 0 | 7685 | 0
[6 empty] | 7686 | 0 | 7686 | 0
[6 empty] | 7687 | 0 | 7687 | 0
[6 empty] | 7688 | 0 | 7688 | 0
[6 empty] | 7689 | 0 | 7689 | 0
[6 empty] | 7690 | 0 | 7690 | 0
[6 empty] | 7691 | 158242.8169 | 7691 | 158242.8169
[6 empty] | 7692 | 0 | 7692 | 0
[6 empty] | 7693 | 2275511.3528 | 7693 | 2275511.3528
[6 empty] | 7694 | 0 | 7694 | 0
[6 empty] | 7695 | 450105.7486 | 7695 | 450105.7486
[6 empty] | 7696 | 0 | 7696 | 0
[6 empty] | 7697 | 575074.6307 | 7697 | 575074.6307
[6 empty] | 7698 | 0 | 7698 | 0
[6 empty] | 7699 | 0 | 7699 | 0
[6 empty] | 7700 | 0 | 7700 | 0
[6 empty] | 7701 | 25552464.0911 | 7701 | 0
[6 empty] | 7702 | 5471805.8227 | 7702 | 0
[6 empty] | 7703 | 0 | 7703 | 0
[6 empty] | 7704 | 208287.375 | 7704 | 208287.375
[6 empty] | 7705 | 0 | 7705 | 0
[6 empty] | 7706 | 290784.3529 | 7706 | 290784.3529
[6 empty] | 7707 | 0 | 7707 | 0
[6 empty] | 7708 | 0 | 7708 | 0
[6 empty] | 7709 | 0 | 7709 | 0
[6 empty] | 7710 | 439224.8418 | 7710 | 439224.8418
[6 empty] | 7711 | 6108464.9898 | 7711 | 797871.7552
[6 empty] | 7712 | 183601.9943 | 7712 | 183601.9943
[6 empty] | 7713 | 0 | 7713 | 0
[6 empty] | 7714 | 0 | 7714 | 0
[6 empty] | 7715 | 3463897.7099 | 7715 | 3463897.7099
[6 empty] | 7716 | 293903.5302 | 7716 | 293903.5302
[6 empty] | 7717 | 0 | 7717 | 0
[6 empty] | 7718 | 2217336.415 | 7718 | 2217336.415
[6 empty] | 7719 | 0 | 7719 | 0
[6 empty] | 7720 | 860291.3571 | 7720 | 860291.3571
[6 empty] | 7721 | 1876077.6445 | 7721 | 1876077.6445
[6 empty] | 7722 | 0 | 7722 | 0
[6 empty] | 7723 | 0 | 7723 | 0
[6 empty] | 7724 | 353152.0603 | 7724 | 353152.0603
[6 empty] | 7725 | 0 | 7725 | 0
[6 empty] | 7726 | 4662181.1948 | 7726 | 4662181.1948
[6 empty] | 7727 | 0 | 7727 | 0
[6 empty] | 7728 | 2012375.5425 | 7728 | 2012375.5425
[6 empty] | 7729 | 0 | 7729 | 0
[6 empty] | 7730 | 0 | 7730 | 0
[6 empty] | 7731 | 0 | 7731 | 0
[6 empty] | 7732 | 177764.4635 | 7732 | 177764.4635
[6 empty] | 7733 | 0 | 7733 | 0
[6 empty] | 7734 | 0 | 7734 | 0
[6 empty] | 7735 | 236286.6087 | 7735 | 236286.6087
[6 empty] | 7736 | 0 | 7736 | 0
[6 empty] | 7737 | 0 | 7737 | 0
[6 empty] | 7738 | 93994.6686 | 7738 | 93994.6686
[6 empty] | 7739 | 180419.6377 | 7739 | 180419.6377
[6 empty] | 7740 | 2782766.538 | 7740 | 0
[6 empty] | 7741 | 0 | 7741 | 0
[6 empty] | 7742 | 0 | 7742 | 0
[6 empty] | 7743 | 0 | 7743 | 0
[6 empty] | 7744 | 0 | 7744 | 0
[6 empty] | 7745 | 3402556.0869 | 7745 | 3402556.0869
[6 empty] | 7746 | 0 | 7746 | 0
[6 empty] | 7747 | 0 | 7747 | 0
[6 empty] | 7748 | 0 | 7748 | 0
[6 empty] | 7749 | 2128084.8832 | 7749 | 0
[6 empty] | 7750 | 183397.3957 | 7750 | 183397.3957
[6 empty] | 7751 | 0 | 7751 | 0
[6 empty] | 7752 | 145205.8216 | 7752 | 145205.8216
[6 empty] | 7753 | 0 | 7753 | 0
[6 empty] | 7754 | 0 | 7754 | 0
[6 empty] | 7755 | 237464.4459 | 7755 | 0
[6 empty] | 7756 | 319770.711 | 7756 | 0
[6 empty] | 7757 | 0 | 7757 | 0
[6 empty] | 7758 | 0 | 7758 | 0
[6 empty] | 7759 | 249210.2159 | 7759 | 249210.2159
[6 empty] | 7760 | 0 | 7760 | 0
[6 empty] | 7761 | 0 | 7761 | 0
[6 empty] | 7762 | 0 | 7762 | 0
[6 empty] | 7763 | 0 | 7763 | 0
[6 empty] | 7764 | 595609.6148 | 7764 | 595609.6148
[6 empty] | 7765 | 0 | 7765 | 0
[6 empty] | 7766 | 0 | 7766 | 0
[6 empty] | 7767 | 0 | 7767 | 0
[6 empty] | 7768 | 0 | 7768 | 0
[6 empty] | 7769 | 1996387.9554 | 7769 | 1996387.9554
[6 empty] | 7770 | 0 | 7770 | 0
[6 empty] | 7771 | 5339813.3978 | 7771 | 1860247.1244
[6 empty] | 7772 | 244013.5147 | 7772 | 244013.5147
[6 empty] | 7773 | 3595478.8569 | 7773 | 3595478.8569
[6 empty] | 7774 | 1844909.7781 | 7774 | 0
[6 empty] | 7775 | 0 | 7775 | 0
[6 empty] | 7776 | 0 | 7776 | 0
[6 empty] | 7777 | 1422981.8873 | 7777 | 0
[6 empty] | 7778 | 0 | 7778 | 0
[6 empty] | 7779 | 5637541.9444 | 7779 | 4089764.7481
[6 empty] | 7780 | 0 | 7780 | 0
[6 empty] | 7781 | 0 | 7781 | 0
[6 empty] | 7782 | 549745.2058 | 7782 | 549745.2058
[6 empty] | 7783 | 0 | 7783 | 0
[6 empty] | 7784 | 0 | 7784 | 0
[6 empty] | 7785 | 0 | 7785 | 0
[6 empty] | 7786 | 0 | 7786 | 0
[6 empty] | 7787 | 3078417.3274 | 7787 | 238018.1997
[6 empty] | 7788 | 0 | 7788 | 0
[6 empty] | 7789 | 0 | 7789 | 0
[6 empty] | 7790 | 0 | 7790 | 0
[6 empty] | 7791 | 0 | 7791 | 0
[6 empty] | 7792 | 14214656.8822 | 7792 | 359865.1369
[6 empty] | 7793 | 0 | 7793 | 0
[6 empty] | 7794 | 0 | 7794 | 0
[6 empty] | 7795 | 6414117.2021 | 7795 | 6414117.2021
[6 empty] | 7796 | 177345.7132 | 7796 | 177345.7132
[6 empty] | 7797 | 1085446.2152 | 7797 | 1085446.2152
[6 empty] | 7798 | 176846.6533 | 7798 | 176846.6533
[6 empty] | 7799 | 0 | 7799 | 0
[6 empty] | 7800 | 0 | 7800 | 0
[6 empty] | 7801 | 0 | 7801 | 0
[6 empty] | 7802 | 0 | 7802 | 0
[6 empty] | 7803 | 722746.2116 | 7803 | 722746.2116
[6 empty] | 7804 | 0 | 7804 | 0
[6 empty] | 7805 | 3039885.443 | 7805 | 3039885.443
[6 empty] | 7806 | 0 | 7806 | 0
[6 empty] | 7807 | 163810.4686 | 7807 | 163810.4686
[6 empty] | 7808 | 2419989.8757 | 7808 | 2419989.8757
[6 empty] | 7809 | 910755.7333 | 7809 | 546219.1029
[6 empty] | 7810 | 259533.7024 | 7810 | 259533.7024
[6 empty] | 7811 | 0 | 7811 | 0
[6 empty] | 7812 | 245966.3963 | 7812 | 0
[6 empty] | 7813 | 2330976.2172 | 7813 | 0
[6 empty] | 7814 | 264570.3131 | 7814 | 264570.3131
[6 empty] | 7815 | 246531.5921 | 7815 | 0
[6 empty] | 7816 | 0 | 7816 | 0
[6 empty] | 7817 | 200771.2285 | 7817 | 200771.2285
[6 empty] | 7818 | 816615.1051 | 7818 | 816615.1051
[6 empty] | 7819 | 5875008.9782 | 7819 | 4113747.7315
[6 empty] | 7820 | 3476399.7213 | 7820 | 0
[6 empty] | 7821 | 3951458.443 | 7821 | 0
[6 empty] | 7822 | 406733.5996 | 7822 | 406733.5996
[6 empty] | 7823 | 217512.1854 | 7823 | 0
[6 empty] | 7824 | 3110409.5722 | 7824 | 3110409.5722
[6 empty] | 7825 | 0 | 7825 | 0
[6 empty] | 7826 | 794926.3153 | 7826 | 794926.3153
[6 empty] | 7827 | 0 | 7827 | 0
[6 empty] | 7828 | 3286520.7175 | 7828 | 0
[6 empty] | 7829 | 0 | 7829 | 0
[6 empty] | 7830 | 0 | 7830 | 0
[6 empty] | 7831 | 0 | 7831 | 0
[6 empty] | 7832 | 497342.5576 | 7832 | 497342.5576
[6 empty] | 7833 | 0 | 7833 | 0
[6 empty] | 7834 | 2008828.8356 | 7834 | 0
[6 empty] | 7835 | 0 | 7835 | 0
[6 empty] | 7836 | 4885107.9854 | 7836 | 336240.0535
[6 empty] | 7837 | 5130552.9885 | 7837 | 1917859.0924
[6 empty] | 7838 | 0 | 7838 | 0
[6 empty] | 7839 | 305098.1877 | 7839 | 305098.1877
[6 empty] | 7840 | 0 | 7840 | 0
[6 empty] | 7841 | 191067.4906 | 7841 | 0
[6 empty] | 7842 | 0 | 7842 | 0
[6 empty] | 7843 | 0 | 7843 | 0
[6 empty] | 7844 | 0 | 7844 | 0
[6 empty] | 7845 | 1618982.4957 | 7845 | 0
[6 empty] | 7846 | 0 | 7846 | 0
[6 empty] | 7847 | 0 | 7847 | 0
[6 empty] | 7848 | 469638.0332 | 7848 | 469638.0332
[6 empty] | 7849 | 4162403.3673 | 7849 | 4162403.3673
[6 empty] | 7850 | 0 | 7850 | 0
[6 empty] | 7851 | 0 | 7851 | 0
[6 empty] | 7852 | 0 | 7852 | 0
[6 empty] | 7853 | 0 | 7853 | 0
[6 empty] | 7854 | 0 | 7854 | 0
[6 empty] | 7855 | 0 | 7855 | 0
[6 empty] | 7856 | 0 | 7856 | 0
[6 empty] | 7857 | 229668.2442 | 7857 | 0
[6 empty] | 7858 | 5063756.6175 | 7858 | 0
[6 empty] | 7859 | 0 | 7859 | 0
[6 empty] | 7860 | 0 | 7860 | 0
[6 empty] | 7861 | 0 | 7861 | 0
[6 empty] | 7862 | 548843.9305 | 7862 | 0
[6 empty] | 7863 | 282511.7037 | 7863 | 282511.7037
[6 empty] | 7864 | 204862.5394 | 7864 | 0
[6 empty] | 7865 | 0 | 7865 | 0
[6 empty] | 7866 | 10682418.5672 | 7866 | 10682418.5672
[6 empty] | 7867 | 0 | 7867 | 0
[6 empty] | 7868 | 0 | 7868 | 0
[6 empty] | 7869 | 0 | 7869 | 0
[6 empty] | 7870 | 554346.2232 | 7870 | 554346.2232
[6 empty] | 7871 | 0 | 7871 | 0
[6 empty] | 7872 | 279578.5928 | 7872 | 0
[6 empty] | 7873 | 4642148.0856 | 7873 | 0
[6 empty] | 7874 | 0 | 7874 | 0
[6 empty] | 7875 | 0 | 7875 | 0
[6 empty] | 7876 | 2858382.4849 | 7876 | 2858382.4849
[6 empty] | 7877 | 0 | 7877 | 0
[6 empty] | 7878 | 1364177.8366 | 7878 | 1364177.8366
[6 empty] | 7879 | 2242115.2829 | 7879 | 0
[6 empty] | 7880 | 0 | 7880 | 0
[6 empty] | 7881 | 0 | 7881 | 0
[6 empty] | 7882 | 0 | 7882 | 0
[6 empty] | 7883 | 2853886.9045 | 7883 | 499504.8678
[6 empty] | 7884 | 0 | 7884 | 0
[6 empty] | 7885 | 851630.7783 | 7885 | 851630.7783
[6 empty] | 7886 | 3311949.8826 | 7886 | 3311949.8826
[6 empty] | 7887 | 0 | 7887 | 0
[6 empty] | 7888 | 0 | 7888 | 0
[6 empty] | 7889 | 233503.4478 | 7889 | 0
[6 empty] | 7890 | 0 | 7890 | 0
[6 empty] | 7891 | 5229940.1369 | 7891 | 5229940.1369
[6 empty] | 7892 | 0 | 7892 | 0
[6 empty] | 7893 | 0 | 7893 | 0
[6 empty] | 7894 | 3940505.0866 | 7894 | 693947.3321
[6 empty] | 7895 | 4201682.7635 | 7895 | 565756.626
[6 empty] | 7896 | 2269474.7241 | 7896 | 2269474.7241
[6 empty] | 7897 | 0 | 7897 | 0
[6 empty] | 7898 | 0 | 7898 | 0
[6 empty] | 7899 | 0 | 7899 | 0
[6 empty] | 7900 | 7814095.8386 | 7900 | 0
[6 empty] | 7901 | 3040216.7241 | 7901 | 0
[6 empty] | 7902 | 391053.9015 | 7902 | 391053.9015
[6 empty] | 7903 | 0 | 7903 | 0
[6 empty] | 7904 | 0 | 7904 | 0
[6 empty] | 7905 | 0 | 7905 | 0
[6 empty] | 7906 | 0 | 7906 | 0
[6 empty] | 7907 | 0 | 7907 | 0
[6 empty] | 7908 | 0 | 7908 | 0
[6 empty] | 7909 | 4657541.1056 | 7909 | 4657541.1056
[6 empty] | 7910 | 0 | 7910 | 0
[6 empty] | 7911 | 0 | 7911 | 0
[6 empty] | 7912 | 0 | 7912 | 0
[6 empty] | 7913 | 0 | 7913 | 0
[6 empty] | 7914 | 690113.0217 | 7914 | 690113.0217
[6 empty] | 7915 | 0 | 7915 | 0
[6 empty] | 7916 | 0 | 7916 | 0
[6 empty] | 7917 | 182170.9793 | 7917 | 0
[6 empty] | 7918 | 3935702.5817 | 7918 | 274883.9333
[6 empty] | 7919 | 0 | 7919 | 0
[6 empty] | 7920 | 131234.6789 | 7920 | 131234.6789
[6 empty] | 7921 | 0 | 7921 | 0
[6 empty] | 7922 | 1074561.8486 | 7922 | 0
[6 empty] | 7923 | 0 | 7923 | 0
[6 empty] | 7924 | 9468628.7438 | 7924 | 0
[6 empty] | 7925 | 4865472.5369 | 7925 | 4865472.5369
[6 empty] | 7926 | 853659.0252 | 7926 | 853659.0252
[6 empty] | 7927 | 0 | 7927 | 0
[6 empty] | 7928 | 2610738.4354 | 7928 | 0
[6 empty] | 7929 | 0 | 7929 | 0
[6 empty] | 7930 | 5189250.3314 | 7930 | 2877256.0041
[6 empty] | 7931 | 0 | 7931 | 0
[6 empty] | 7932 | 1576882.3328 | 7932 | 695700.5395
[6 empty] | 7933 | 98403.5484 | 7933 | 98403.5484
[6 empty] | 7934 | 0 | 7934 | 0
[6 empty] | 7935 | 0 | 7935 | 0
[6 empty] | 7936 | 0 | 7936 | 0
[6 empty] | 7937 | 2111291.5159 | 7937 | 0
[6 empty] | 7938 | 238488.6527 | 7938 | 238488.6527
[6 empty] | 7939 | 0 | 7939 | 0
[6 empty] | 7940 | 0 | 7940 | 0
[6 empty] | 7941 | 904063.1591 | 7941 | 0
[6 empty] | 7942 | 2972415.1564 | 7942 | 0
[6 empty] | 7943 | 0 | 7943 | 0
[6 empty] | 7944 | 0 | 7944 | 0
[6 empty] | 7945 | 1065351.9851 | 7945 | 0
[6 empty] | 7946 | 369447.432 | 7946 | 369447.432
[6 empty] | 7947 | 0 | 7947 | 0
[6 empty] | 7948 | 0 | 7948 | 0
[6 empty] | 7949 | 4548267.9309 | 7949 | 0
[6 empty] | 7950 | 362489.0802 | 7950 | 362489.0802
[6 empty] | 7951 | 303510.5221 | 7951 | 303510.5221
[6 empty] | 7952 | 0 | 7952 | 0
[6 empty] | 7953 | 0 | 7953 | 0
[6 empty] | 7954 | 1023872.2373 | 7954 | 1023872.2373
[6 empty] | 7955 | 3168286.0218 | 7955 | 2981954.5774
[6 empty] | 7956 | 0 | 7956 | 0
[6 empty] | 7957 | 0 | 7957 | 0
[6 empty] | 7958 | 0 | 7958 | 0
[6 empty] | 7959 | 0 | 7959 | 0
[6 empty] | 7960 | 0 | 7960 | 0
[6 empty] | 7961 | 0 | 7961 | 0
[6 empty] | 7962 | 255988.3396 | 7962 | 255988.3396
[6 empty] | 7963 | 0 | 7963 | 0
[6 empty] | 7964 | 0 | 7964 | 0
[6 empty] | 7965 | 0 | 7965 | 0
[6 empty] | 7966 | 0 | 7966 | 0
[6 empty] | 7967 | 1156872.7901 | 7967 | 1156872.7901
[6 empty] | 7968 | 0 | 7968 | 0
[6 empty] | 7969 | 0 | 7969 | 0
[6 empty] | 7970 | 0 | 7970 | 0
[6 empty] | 7971 | 0 | 7971 | 0
[6 empty] | 7972 | 0 | 7972 | 0
[6 empty] | 7973 | 0 | 7973 | 0
[6 empty] | 7974 | 129100.5268 | 7974 | 0
[6 empty] | 7975 | 12470049.945 | 7975 | 0
[6 empty] | 7976 | 918235.0726 | 7976 | 0
[6 empty] | 7977 | 0 | 7977 | 0
[6 empty] | 7978 | 2977934.2341 | 7978 | 0
[6 empty] | 7979 | 3548153.1029 | 7979 | 0
[6 empty] | 7980 | 0 | 7980 | 0
[6 empty] | 7981 | 0 | 7981 | 0
[6 empty] | 7982 | 3866468.0974 | 7982 | 3866468.0974
[6 empty] | 7983 | 0 | 7983 | 0
[6 empty] | 7984 | 0 | 7984 | 0
[6 empty] | 7985 | 561698.334 | 7985 | 561698.334
[6 empty] | 7986 | 0 | 7986 | 0
[6 empty] | 7987 | 0 | 7987 | 0
[6 empty] | 7988 | 1854452.9575 | 7988 | 1854452.9575
[6 empty] | 7989 | 635275.2822 | 7989 | 635275.2822
[6 empty] | 7990 | 200953.728 | 7990 | 200953.728
[6 empty] | 7991 | 7425108.0308 | 7991 | 552391.1267
[6 empty] | 7992 | 403904.2478 | 7992 | 403904.2478
[6 empty] | 7993 | 0 | 7993 | 0
[6 empty] | 7994 | 2395604.8289 | 7994 | 0
[6 empty] | 7995 | 458340.4455 | 7995 | 458340.4455
[6 empty] | 7996 | 0 | 7996 | 0
[6 empty] | 7997 | 227003.6901 | 7997 | 227003.6901
[6 empty] | 7998 | 0 | 7998 | 0
[6 empty] | 7999 | 390513.1069 | 7999 | 390513.1069
[6 empty] | 8000 | 0 | 8000 | 0
[6 empty] | 8001 | 212100.6894 | 8001 | 212100.6894
[6 empty] | 8002 | 0 | 8002 | 0
[6 empty] | 8003 | 161507.6586 | 8003 | 161507.6586
[6 empty] | 8004 | 0 | 8004 | 0
[6 empty] | 8005 | 27545936.6446 | 8005 | 0
[6 empty] | 8006 | 2435774.2668 | 8006 | 247522.3628
[6 empty] | 8007 | 5542313.1858 | 8007 | 219515.8365
[6 empty] | 8008 | 4433140.2204 | 8008 | 429765.8854
[6 empty] | 8009 | 0 | 8009 | 0
[6 empty] | 8010 | 0 | 8010 | 0
[6 empty] | 8011 | 186388.532 | 8011 | 186388.532
[6 empty] | 8012 | 0 | 8012 | 0
[6 empty] | 8013 | 2925506.0622 | 8013 | 162518.181
[6 empty] | 8014 | 0 | 8014 | 0
[6 empty] | 8015 | 604221.5517 | 8015 | 604221.5517
[6 empty] | 8016 | 269898.9331 | 8016 | 269898.9331
[6 empty] | 8017 | 0 | 8017 | 0
[6 empty] | 8018 | 0 | 8018 | 0
[6 empty] | 8019 | 843002.3995 | 8019 | 843002.3995
[6 empty] | 8020 | 0 | 8020 | 0
[6 empty] | 8021 | 3820998.2045 | 8021 | 174433.264
[6 empty] | 8022 | 3634129.1712 | 8022 | 3634129.1712
[6 empty] | 8023 | 0 | 8023 | 0
[6 empty] | 8024 | 0 | 8024 | 0
[6 empty] | 8025 | 0 | 8025 | 0
[6 empty] | 8026 | 305236.0848 | 8026 | 305236.0848
[6 empty] | 8027 | 0 | 8027 | 0
[6 empty] | 8028 | 0 | 8028 | 0
[6 empty] | 8029 | 0 | 8029 | 0
[6 empty] | 8030 | 0 | 8030 | 0
[6 empty] | 8031 | 2052677.7579 | 8031 | 0
[6 empty] | 8032 | 240062.8936 | 8032 | 0
[6 empty] | 8033 | 403824.6334 | 8033 | 403824.6334
[6 empty] | 8034 | 180651.2248 | 8034 | 0
[6 empty] | 8035 | 0 | 8035 | 0
[6 empty] | 8036 | 0 | 8036 | 0
[6 empty] | 8037 | 3457431.1061 | 8037 | 3457431.1061
[6 empty] | 8038 | 0 | 8038 | 0
[6 empty] | 8039 | 0 | 8039 | 0
[6 empty] | 8040 | 1709180.6514 | 8040 | 1709180.6514
[6 empty] | 8041 | 6190134.5702 | 8041 | 0
[6 empty] | 8042 | 0 | 8042 | 0
[6 empty] | 8043 | 0 | 8043 | 0
[6 empty] | 8044 | 0 | 8044 | 0
[6 empty] | 8045 | 0 | 8045 | 0
[6 empty] | 8046 | 0 | 8046 | 0
[6 empty] | 8047 | 3972534.169 | 8047 | 185493.49
[6 empty] | 8048 | 0 | 8048 | 0
[6 empty] | 8049 | 307593.6103 | 8049 | 307593.6103
[6 empty] | 8050 | 0 | 8050 | 0
[6 empty] | 8051 | 183524.6047 | 8051 | 183524.6047
[6 empty] | 8052 | 3631252.8474 | 8052 | 3457933.7316
[6 empty] | 8053 | 255974.7982 | 8053 | 255974.7982
[6 empty] | 8054 | 3276510.8582 | 8054 | 3276510.8582
[6 empty] | 8055 | 3786283.7378 | 8055 | 3786283.7378
[6 empty] | 8056 | 198175.4942 | 8056 | 198175.4942
[6 empty] | 8057 | 713249.8965 | 8057 | 713249.8965
[6 empty] | 8058 | 0 | 8058 | 0
[6 empty] | 8059 | 0 | 8059 | 0
[6 empty] | 8060 | 205608.6862 | 8060 | 205608.6862
[6 empty] | 8061 | 0 | 8061 | 0
[6 empty] | 8062 | 812928.8203 | 8062 | 812928.8203
[6 empty] | 8063 | 568185.1835 | 8063 | 568185.1835
[6 empty] | 8064 | 229263.9345 | 8064 | 0
[6 empty] | 8065 | 0 | 8065 | 0
[6 empty] | 8066 | 0 | 8066 | 0
[6 empty] | 8067 | 0 | 8067 | 0
[6 empty] | 8068 | 32958459.4778 | 8068 | 32721026.4565
[6 empty] | 8069 | 0 | 8069 | 0
[6 empty] | 8070 | 162431.1085 | 8070 | 0
[6 empty] | 8071 | 136653.7586 | 8071 | 0
[6 empty] | 8072 | 0 | 8072 | 0
[6 empty] | 8073 | 194638.8775 | 8073 | 194638.8775
[6 empty] | 8074 | 2262681.5797 | 8074 | 0
[6 empty] | 8075 | 187249.6569 | 8075 | 0
[6 empty] | 8076 | 0 | 8076 | 0
[6 empty] | 8077 | 0 | 8077 | 0
[6 empty] | 8078 | 3989316.6435 | 8078 | 3989316.6435
[6 empty] | 8079 | 167226.009 | 8079 | 167226.009
[6 empty] | 8080 | 2123531.5081 | 8080 | 2123531.5081
[6 empty] | 8081 | 0 | 8081 | 0
[6 empty] | 8082 | 0 | 8082 | 0
[6 empty] | 8083 | 10216424.0322 | 8083 | 0
[6 empty] | 8084 | 0 | 8084 | 0
[6 empty] | 8085 | 0 | 8085 | 0
[6 empty] | 8086 | 0 | 8086 | 0
[6 empty] | 8087 | 0 | 8087 | 0
[6 empty] | 8088 | 2583897.8195 | 8088 | 2583897.8195
[6 empty] | 8089 | 308635.0203 | 8089 | 308635.0203
[6 empty] | 8090 | 245884.2488 | 8090 | 245884.2488
[6 empty] | 8091 | 0 | 8091 | 0
[6 empty] | 8092 | 0 | 8092 | 0
[6 empty] | 8093 | 162472.9243 | 8093 | 162472.9243
[6 empty] | 8094 | 192217.7052 | 8094 | 192217.7052
[6 empty] | 8095 | 0 | 8095 | 0
[6 empty] | 8096 | 1911368.6838 | 8096 | 1911368.6838
[6 empty] | 8097 | 7519545.9589 | 8097 | 7519545.9589
[6 empty] | 8098 | 3260616.7592 | 8098 | 0
[6 empty] | 8099 | 0 | 8099 | 0
[6 empty] | 8100 | 0 | 8100 | 0
[6 empty] | 8101 | 0 | 8101 | 0
[6 empty] | 8102 | 0 | 8102 | 0
[6 empty] | 8103 | 303583.9521 | 8103 | 303583.9521
[6 empty] | 8104 | 2767280.5367 | 8104 | 0
[6 empty] | 8105 | 0 | 8105 | 0
[6 empty] | 8106 | 0 | 8106 | 0
[6 empty] | 8107 | 474088.1586 | 8107 | 291947.4341
[6 empty] | 8108 | 0 | 8108 | 0
[6 empty] | 8109 | 0 | 8109 | 0
[6 empty] | 8110 | 451893.4629 | 8110 | 451893.4629
[6 empty] | 8111 | 0 | 8111 | 0
[6 empty] | 8112 | 239918.5565 | 8112 | 0
[6 empty] | 8113 | 0 | 8113 | 0
[6 empty] | 8114 | 2451918.8028 | 8114 | 0
[6 empty] | 8115 | 0 | 8115 | 0
[6 empty] | 8116 | 353260.1979 | 8116 | 0
[6 empty] | 8117 | 328823.3618 | 8117 | 328823.3618
[6 empty] | 8118 | 1162451.2757 | 8118 | 0
[6 empty] | 8119 | 0 | 8119 | 0
[6 empty] | 8120 | 0 | 8120 | 0
[6 empty] | 8121 | 0 | 8121 | 0
[6 empty] | 8122 | 1194913.9748 | 8122 | 1194913.9748
[6 empty] | 8123 | 2845133.6998 | 8123 | 528647.5917
[6 empty] | 8124 | 1458496.2053 | 8124 | 1458496.2053
[6 empty] | 8125 | 0 | 8125 | 0
[6 empty] | 8126 | 243939.1186 | 8126 | 0
[6 empty] | 8127 | 186420.683 | 8127 | 186420.683
[6 empty] | 8128 | 0 | 8128 | 0
[6 empty] | 8129 | 0 | 8129 | 0
[6 empty] | 8130 | 0 | 8130 | 0
[6 empty] | 8131 | 0 | 8131 | 0
[6 empty] | 8132 | 917167.5527 | 8132 | 917167.5527
[6 empty] | 8133 | 0 | 8133 | 0
[6 empty] | 8134 | 0 | 8134 | 0
[6 empty] | 8135 | 0 | 8135 | 0
[6 empty] | 8136 | 0 | 8136 | 0
[6 empty] | 8137 | 0 | 8137 | 0
[6 empty] | 8138 | 1849931.6238 | 8138 | 1849931.6238
[6 empty] | 8139 | 4367886.2013 | 8139 | 0
[6 empty] | 8140 | 238928.6047 | 8140 | 0
[6 empty] | 8141 | 0 | 8141 | 0
[6 empty] | 8142 | 396931.2213 | 8142 | 396931.2213
[6 empty] | 8143 | 0 | 8143 | 0
[6 empty] | 8144 | 348829.628 | 8144 | 348829.628
[6 empty] | 8145 | 878011.983 | 8145 | 878011.983
[6 empty] | 8146 | 0 | 8146 | 0
[6 empty] | 8147 | 0 | 8147 | 0
[6 empty] | 8148 | 0 | 8148 | 0
[6 empty] | 8149 | 2054505.4177 | 8149 | 2054505.4177
[6 empty] | 8150 | 0 | 8150 | 0
[6 empty] | 8151 | 0 | 8151 | 0
[6 empty] | 8152 | 0 | 8152 | 0
[6 empty] | 8153 | 0 | 8153 | 0
[6 empty] | 8154 | 0 | 8154 | 0
[6 empty] | 8155 | 0 | 8155 | 0
[6 empty] | 8156 | 347427.8658 | 8156 | 347427.8658
[6 empty] | 8157 | 0 | 8157 | 0
[6 empty] | 8158 | 0 | 8158 | 0
[6 empty] | 8159 | 205735.9829 | 8159 | 205735.9829
[6 empty] | 8160 | 0 | 8160 | 0
[6 empty] | 8161 | 4592833.152 | 8161 | 0
[6 empty] | 8162 | 465895.1028 | 8162 | 465895.1028
[6 empty] | 8163 | 3560925.0586 | 8163 | 3560925.0586
[6 empty] | 8164 | 0 | 8164 | 0
[6 empty] | 8165 | 678330.2358 | 8165 | 678330.2358
[6 empty] | 8166 | 3333775.0893 | 8166 | 1310207.4859
[6 empty] | 8167 | 0 | 8167 | 0
[6 empty] | 8168 | 233536.4734 | 8168 | 0
[6 empty] | 8169 | 0 | 8169 | 0
[6 empty] | 8170 | 8487635.3197 | 8170 | 0
[6 empty] | 8171 | 0 | 8171 | 0
[6 empty] | 8172 | 477993.6617 | 8172 | 0
[6 empty] | 8173 | 0 | 8173 | 0
[6 empty] | 8174 | 0 | 8174 | 0
[6 empty] | 8175 | 0 | 8175 | 0
[6 empty] | 8176 | 0 | 8176 | 0
[6 empty] | 8177 | 257641.5891 | 8177 | 257641.5891
[6 empty] | 8178 | 0 | 8178 | 0
[6 empty] | 8179 | 286916.4277 | 8179 | 286916.4277
[6 empty] | 8180 | 0 | 8180 | 0
[6 empty] | 8181 | 3536012.9677 | 8181 | 0
[6 empty] | 8182 | 0 | 8182 | 0
[6 empty] | 8183 | 4970291.3564 | 8183 | 0
[6 empty] | 8184 | 0 | 8184 | 0
[6 empty] | 8185 | 0 | 8185 | 0
[6 empty] | 8186 | 494668.2294 | 8186 | 494668.2294
[6 empty] | 8187 | 196797.2938 | 8187 | 196797.2938
[6 empty] | 8188 | 17080964.9181 | 8188 | 1262099.4352
[6 empty] | 8189 | 537117.8906 | 8189 | 537117.8906
[6 empty] | 8190 | 237062.4767 | 8190 | 237062.4767
[6 empty] | 8191 | 27798563.11 | 8191 | 23473912.5181
[6 empty] | 8192 | 122008.9357 | 8192 | 122008.9357
[6 empty] | 8193 | 106145.7323 | 8193 | 106145.7323
[6 empty] | 8194 | 0 | 8194 | 0
[6 empty] | 8195 | 3769162.1832 | 8195 | 2737615.7915
[6 empty] | 8196 | 261875.051 | 8196 | 0
[6 empty] | 8197 | 0 | 8197 | 0
[6 empty] | 8198 | 2013739.2554 | 8198 | 189849.2812
[6 empty] | 8199 | 0 | 8199 | 0
[6 empty] | 8200 | 0 | 8200 | 0
[6 empty] | 8201 | 0 | 8201 | 0
[6 empty] | 8202 | 2057313.6229 | 8202 | 0
[6 empty] | 8203 | 189987.8813 | 8203 | 189987.8813
[6 empty] | 8204 | 3504103.9649 | 8204 | 0
[6 empty] | 8205 | 0 | 8205 | 0
[6 empty] | 8206 | 927688.5122 | 8206 | 927688.5122
[6 empty] | 8207 | 0 | 8207 | 0
[6 empty] | 8208 | 6811277.0658 | 8208 | 0
[6 empty] | 8209 | 4365256.4046 | 8209 | 1294313.2415
[6 empty] | 8210 | 0 | 8210 | 0
[6 empty] | 8211 | 266313.0331 | 8211 | 0
[6 empty] | 8212 | 191933.3611 | 8212 | 191933.3611
[6 empty] | 8213 | 0 | 8213 | 0
[6 empty] | 8214 | 210969.7493 | 8214 | 0
[6 empty] | 8215 | 3477137.1038 | 8215 | 155083.3857
[6 empty] | 8216 | 60868.6587 | 8216 | 60868.6587
[6 empty] | 8217 | 0 | 8217 | 0
[6 empty] | 8218 | 204596.712 | 8218 | 0
[6 empty] | 8219 | 15787977.0031 | 8219 | 0
[6 empty] | 8220 | 339283.3032 | 8220 | 339283.3032
[6 empty] | 8221 | 0 | 8221 | 0
[6 empty] | 8222 | 804197.7623 | 8222 | 804197.7623
[6 empty] | 8223 | 2928127.7016 | 8223 | 2928127.7016
[6 empty] | 8224 | 178426.4786 | 8224 | 0
[6 empty] | 8225 | 0 | 8225 | 0
[6 empty] | 8226 | 3313562.0505 | 8226 | 0
[6 empty] | 8227 | 205291.5644 | 8227 | 0
[6 empty] | 8228 | 166867.1995 | 8228 | 166867.1995
[6 empty] | 8229 | 646209.5528 | 8229 | 646209.5528
[6 empty] | 8230 | 0 | 8230 | 0
[6 empty] | 8231 | 3637125.3051 | 8231 | 3637125.3051
[6 empty] | 8232 | 0 | 8232 | 0
[6 empty] | 8233 | 214322.893 | 8233 | 0
[6 empty] | 8234 | 0 | 8234 | 0
[6 empty] | 8235 | 0 | 8235 | 0
[6 empty] | 8236 | 472145.8153 | 8236 | 216953.2286
[6 empty] | 8237 | 0 | 8237 | 0
[6 empty] | 8238 | 0 | 8238 | 0
[6 empty] | 8239 | 3746757.9817 | 8239 | 0
[6 empty] | 8240 | 2311372.0216 | 8240 | 0
[6 empty] | 8241 | 911274.6045 | 8241 | 0
[6 empty] | 8242 | 2852084.7325 | 8242 | 0
[6 empty] | 8243 | 0 | 8243 | 0
[6 empty] | 8244 | 12660760.6643 | 8244 | 12492583.5792
[6 empty] | 8245 | 0 | 8245 | 0
[6 empty] | 8246 | 0 | 8246 | 0
[6 empty] | 8247 | 0 | 8247 | 0
[6 empty] | 8248 | 202438.5708 | 8248 | 202438.5708
[6 empty] | 8249 | 1537981.3309 | 8249 | 1537981.3309
[6 empty] | 8250 | 542967.424 | 8250 | 300317.8909
[6 empty] | 8251 | 352728.9638 | 8251 | 352728.9638
[6 empty] | 8252 | 1722901.5631 | 8252 | 0
[6 empty] | 8253 | 0 | 8253 | 0
[6 empty] | 8254 | 0 | 8254 | 0
[6 empty] | 8255 | 245005.5948 | 8255 | 245005.5948
[6 empty] | 8256 | 307283.2794 | 8256 | 307283.2794
[6 empty] | 8257 | 689440.4279 | 8257 | 689440.4279
[6 empty] | 8258 | 2530300.0506 | 8258 | 650197.4244
[6 empty] | 8259 | 0 | 8259 | 0
[6 empty] | 8260 | 0 | 8260 | 0
[6 empty] | 8261 | 224279.7975 | 8261 | 0
[6 empty] | 8262 | 259592.4522 | 8262 | 259592.4522
[6 empty] | 8263 | 2661297.9754 | 8263 | 1031068.3123
[6 empty] | 8264 | 0 | 8264 | 0
[6 empty] | 8265 | 0 | 8265 | 0
[6 empty] | 8266 | 0 | 8266 | 0
[6 empty] | 8267 | 0 | 8267 | 0
[6 empty] | 8268 | 218220.3445 | 8268 | 0
[6 empty] | 8269 | 672581.4817 | 8269 | 429713.6188
[6 empty] | 8270 | 1340594.5614 | 8270 | 1340594.5614
[6 empty] | 8271 | 5353688.0704 | 8271 | 0
[6 empty] | 8272 | 234233.8196 | 8272 | 0
[6 empty] | 8273 | 0 | 8273 | 0
[6 empty] | 8274 | 486243.9142 | 8274 | 486243.9142
[6 empty] | 8275 | 0 | 8275 | 0
[6 empty] | 8276 | 2311134.5871 | 8276 | 2311134.5871
[6 empty] | 8277 | 479491.0993 | 8277 | 479491.0993
[6 empty] | 8278 | 0 | 8278 | 0
[6 empty] | 8279 | 0 | 8279 | 0
[6 empty] | 8280 | 0 | 8280 | 0
[6 empty] | 8281 | 3132605.6616 | 8281 | 0
[6 empty] | 8282 | 10645101.9975 | 8282 | 0
[6 empty] | 8283 | 3307164.5779 | 8283 | 0
[6 empty] | 8284 | 0 | 8284 | 0
[6 empty] | 8285 | 0 | 8285 | 0
[6 empty] | 8286 | 0 | 8286 | 0
[6 empty] | 8287 | 0 | 8287 | 0
[6 empty] | 8288 | 0 | 8288 | 0
[6 empty] | 8289 | 0 | 8289 | 0
[6 empty] | 8290 | 0 | 8290 | 0
[6 empty] | 8291 | 0 | 8291 | 0
[6 empty] | 8292 | 0 | 8292 | 0
[6 empty] | 8293 | 0 | 8293 | 0
[6 empty] | 8294 | 0 | 8294 | 0
[6 empty] | 8295 | 0 | 8295 | 0
[6 empty] | 8296 | 0 | 8296 | 0
[6 empty] | 8297 | 204862.2389 | 8297 | 204862.2389
[6 empty] | 8298 | 2014833.6428 | 8298 | 2014833.6428
[6 empty] | 8299 | 2541378.7306 | 8299 | 2541378.7306
[6 empty] | 8300 | 0 | 8300 | 0
[6 empty] | 8301 | 186292.4008 | 8301 | 186292.4008
[6 empty] | 8302 | 0 | 8302 | 0
[6 empty] | 8303 | 0 | 8303 | 0
[6 empty] | 8304 | 0 | 8304 | 0
[6 empty] | 8305 | 0 | 8305 | 0
[6 empty] | 8306 | 1221488.6507 | 8306 | 337622.5468
[6 empty] | 8307 | 2795545.9139 | 8307 | 0
[6 empty] | 8308 | 584076.8147 | 8308 | 584076.8147
[6 empty] | 8309 | 0 | 8309 | 0
[6 empty] | 8310 | 6629803.1067 | 8310 | 358909.2574
[6 empty] | 8311 | 762545.3153 | 8311 | 762545.3153
[6 empty] | 8312 | 0 | 8312 | 0
[6 empty] | 8313 | 19456257.9762 | 8313 | 0
[6 empty] | 8314 | 1891104.798 | 8314 | 1891104.798
[6 empty] | 8315 | 0 | 8315 | 0
[6 empty] | 8316 | 0 | 8316 | 0
[6 empty] | 8317 | 0 | 8317 | 0
[6 empty] | 8318 | 0 | 8318 | 0
[6 empty] | 8319 | 0 | 8319 | 0
[6 empty] | 8320 | 0 | 8320 | 0
[6 empty] | 8321 | 4502332.9099 | 8321 | 0
[6 empty] | 8322 | 0 | 8322 | 0
[6 empty] | 8323 | 453243.8087 | 8323 | 453243.8087
[6 empty] | 8324 | 0 | 8324 | 0
[6 empty] | 8325 | 61764.301 | 8325 | 61764.301
[6 empty] | 8326 | 203290.5068 | 8326 | 203290.5068
[6 empty] | 8327 | 3748337.2617 | 8327 | 543009.4783
[6 empty] | 8328 | 4811175.2362 | 8328 | 973431.3112
[6 empty] | 8329 | 419353.2074 | 8329 | 217869.5584
[6 empty] | 8330 | 241945.0546 | 8330 | 241945.0546
[6 empty] | 8331 | 9385700.6791 | 8331 | 9385700.6791
[6 empty] | 8332 | 433602.537 | 8332 | 433602.537
[6 empty] | 8333 | 0 | 8333 | 0
[6 empty] | 8334 | 2536056.2794 | 8334 | 2536056.2794
[6 empty] | 8335 | 0 | 8335 | 0
[6 empty] | 8336 | 218799.0044 | 8336 | 218799.0044
[6 empty] | 8337 | 0 | 8337 | 0
[6 empty] | 8338 | 240757.666 | 8338 | 0
[6 empty] | 8339 | 1373222.1385 | 8339 | 1373222.1385
[6 empty] | 8340 | 4950075.5075 | 8340 | 0
[6 empty] | 8341 | 227456.5027 | 8341 | 0
[6 empty] | 8342 | 929237.1816 | 8342 | 0
[6 empty] | 8343 | 2932932.8089 | 8343 | 2932932.8089
[6 empty] | 8344 | 3125129.0925 | 8344 | 3125129.0925
[6 empty] | 8345 | 0 | 8345 | 0
[6 empty] | 8346 | 0 | 8346 | 0
[6 empty] | 8347 | 0 | 8347 | 0
[6 empty] | 8348 | 2665232.7236 | 8348 | 2665232.7236
[6 empty] | 8349 | 0 | 8349 | 0
[6 empty] | 8350 | 13896720.5978 | 8350 | 3153710.7285
[6 empty] | 8351 | 0 | 8351 | 0
[6 empty] | 8352 | 3260716.1024 | 8352 | 3260716.1024
[6 empty] | 8353 | 0 | 8353 | 0
[6 empty] | 8354 | 0 | 8354 | 0
[6 empty] | 8355 | 0 | 8355 | 0
[6 empty] | 8356 | 0 | 8356 | 0
[6 empty] | 8357 | 0 | 8357 | 0
[6 empty] | 8358 | 1423989.0445 | 8358 | 1423989.0445
[6 empty] | 8359 | 2545828.7665 | 8359 | 2545828.7665
[6 empty] | 8360 | 1078973.8223 | 8360 | 0
[6 empty] | 8361 | 0 | 8361 | 0
[6 empty] | 8362 | 220513.1571 | 8362 | 0
[6 empty] | 8363 | 0 | 8363 | 0
[6 empty] | 8364 | 5703360.1019 | 8364 | 5703360.1019
[6 empty] | 8365 | 207930.6364 | 8365 | 0
[6 empty] | 8366 | 4577931.1112 | 8366 | 1753470.7989
[6 empty] | 8367 | 302514.229 | 8367 | 302514.229
[6 empty] | 8368 | 0 | 8368 | 0
[6 empty] | 8369 | 0 | 8369 | 0
[6 empty] | 8370 | 12183441.1471 | 8370 | 12183441.1471
[6 empty] | 8371 | 250927.0438 | 8371 | 250927.0438
[6 empty] | 8372 | 6546501.7274 | 8372 | 6546501.7274
[6 empty] | 8373 | 0 | 8373 | 0
[6 empty] | 8374 | 0 | 8374 | 0
[6 empty] | 8375 | 303313.834 | 8375 | 303313.834
[6 empty] | 8376 | 247091.5064 | 8376 | 247091.5064
[6 empty] | 8377 | 0 | 8377 | 0
[6 empty] | 8378 | 205366.7888 | 8378 | 205366.7888
[6 empty] | 8379 | 5231311.5256 | 8379 | 1251073.106
[6 empty] | 8380 | 3740658.5743 | 8380 | 0
[6 empty] | 8381 | 846999.1948 | 8381 | 846999.1948
[6 empty] | 8382 | 345805.6981 | 8382 | 345805.6981
[6 empty] | 8383 | 9523301.8038 | 8383 | 178590.1702
[6 empty] | 8384 | 183545.6277 | 8384 | 183545.6277
[6 empty] | 8385 | 3813405.4439 | 8385 | 0
[6 empty] | 8386 | 0 | 8386 | 0
[6 empty] | 8387 | 234398.5957 | 8387 | 234398.5957
[6 empty] | 8388 | 0 | 8388 | 0
[6 empty] | 8389 | 189143.1952 | 8389 | 189143.1952
[6 empty] | 8390 | 1056186.7093 | 8390 | 0
[6 empty] | 8391 | 0 | 8391 | 0
[6 empty] | 8392 | 0 | 8392 | 0
[6 empty] | 8393 | 2112589.0001 | 8393 | 0
[6 empty] | 8394 | 0 | 8394 | 0
[6 empty] | 8395 | 632387.0289 | 8395 | 632387.0289
[6 empty] | 8396 | 0 | 8396 | 0
[6 empty] | 8397 | 187855.1773 | 8397 | 0
[6 empty] | 8398 | 6250016.5408 | 8398 | 0
[6 empty] | 8399 | 3261935.609 | 8399 | 0
[6 empty] | 8400 | 0 | 8400 | 0
[6 empty] | 8401 | 268597.95 | 8401 | 0
[6 empty] | 8402 | 190432.2496 | 8402 | 190432.2496
[6 empty] | 8403 | 0 | 8403 | 0
[6 empty] | 8404 | 454336.2278 | 8404 | 251478.3463
[6 empty] | 8405 | 0 | 8405 | 0
[6 empty] | 8406 | 0 | 8406 | 0
[6 empty] | 8407 | 0 | 8407 | 0
[6 empty] | 8408 | 0 | 8408 | 0
[6 empty] | 8409 | 4197060.2987 | 8409 | 4197060.2987
[6 empty] | 8410 | 809076.9424 | 8410 | 542053.5552
[6 empty] | 8411 | 4246219.1831 | 8411 | 0
[6 empty] | 8412 | 4065301.7111 | 8412 | 4065301.7111
[6 empty] | 8413 | 1284609.982 | 8413 | 0
[6 empty] | 8414 | 179265.3601 | 8414 | 179265.3601
[6 empty] | 8415 | 0 | 8415 | 0
[6 empty] | 8416 | 2115549.3167 | 8416 | 0
[6 empty] | 8417 | 2382954.4673 | 8417 | 2382954.4673
[6 empty] | 8418 | 234443.3704 | 8418 | 0
[6 empty] | 8419 | 212417.8227 | 8419 | 212417.8227
[6 empty] | 8420 | 0 | 8420 | 0
[6 empty] | 8421 | 518326.4603 | 8421 | 518326.4603
[6 empty] | 8422 | 6757988.9772 | 8422 | 6757988.9772
[6 empty] | 8423 | 0 | 8423 | 0
[6 empty] | 8424 | 4195878.9783 | 8424 | 0
[6 empty] | 8425 | 613090.0622 | 8425 | 346970.8415
[6 empty] | 8426 | 0 | 8426 | 0
[6 empty] | 8427 | 561809.4485 | 8427 | 561809.4485
[6 empty] | 8428 | 0 | 8428 | 0
[6 empty] | 8429 | 270287.6806 | 8429 | 0
[6 empty] | 8430 | 4072720.6612 | 8430 | 4072720.6612
[6 empty] | 8431 | 0 | 8431 | 0
[6 empty] | 8432 | 802687.0153 | 8432 | 802687.0153
[6 empty] | 8433 | 0 | 8433 | 0
[6 empty] | 8434 | 654373.6838 | 8434 | 654373.6838
[6 empty] | 8435 | 2720098.6326 | 8435 | 2720098.6326
[6 empty] | 8436 | 0 | 8436 | 0
[6 empty] | 8437 | 150637.2972 | 8437 | 0
[6 empty] | 8438 | 362127.5256 | 8438 | 362127.5256
[6 empty] | 8439 | 0 | 8439 | 0
[6 empty] | 8440 | 0 | 8440 | 0
[6 empty] | 8441 | 989566.4615 | 8441 | 989566.4615
[6 empty] | 8442 | 2696359.2189 | 8442 | 0
[6 empty] | 8443 | 2693038.7176 | 8443 | 619904.6455
[6 empty] | 8444 | 0 | 8444 | 0
[6 empty] | 8445 | 0 | 8445 | 0
[6 empty] | 8446 | 260578.9528 | 8446 | 260578.9528
[6 empty] | 8447 | 5230393.2488 | 8447 | 159847.6135
[6 empty] | 8448 | 0 | 8448 | 0
[6 empty] | 8449 | 0 | 8449 | 0
[6 empty] | 8450 | 0 | 8450 | 0
[6 empty] | 8451 | 0 | 8451 | 0
[6 empty] | 8452 | 4056282.8587 | 8452 | 0
[6 empty] | 8453 | 7277922.385 | 8453 | 7277922.385
[6 empty] | 8454 | 0 | 8454 | 0
[6 empty] | 8455 | 0 | 8455 | 0
[6 empty] | 8456 | 0 | 8456 | 0
[6 empty] | 8457 | 0 | 8457 | 0
[6 empty] | 8458 | 0 | 8458 | 0
[6 empty] | 8459 | 0 | 8459 | 0
[6 empty] | 8460 | 173794.6012 | 8460 | 173794.6012
[6 empty] | 8461 | 0 | 8461 | 0
[6 empty] | 8462 | 333456.6797 | 8462 | 333456.6797
[6 empty] | 8463 | 0 | 8463 | 0
[6 empty] | 8464 | 0 | 8464 | 0
[6 empty] | 8465 | 0 | 8465 | 0
[6 empty] | 8466 | 751487.7911 | 8466 | 0
[6 empty] | 8467 | 6988971.514 | 8467 | 0
[6 empty] | 8468 | 0 | 8468 | 0
[6 empty] | 8469 | 0 | 8469 | 0
[6 empty] | 8470 | 3176809.3787 | 8470 | 3176809.3787
[6 empty] | 8471 | 0 | 8471 | 0
[6 empty] | 8472 | 0 | 8472 | 0
[6 empty] | 8473 | 0 | 8473 | 0
[6 empty] | 8474 | 116427.5723 | 8474 | 116427.5723
[6 empty] | 8475 | 0 | 8475 | 0
[6 empty] | 8476 | 0 | 8476 | 0
[6 empty] | 8477 | 0 | 8477 | 0
[6 empty] | 8478 | 265761.7215 | 8478 | 265761.7215
[6 empty] | 8479 | 0 | 8479 | 0
[6 empty] | 8480 | 1600383.8807 | 8480 | 0
[6 empty] | 8481 | 3361871.8465 | 8481 | 0
[6 empty] | 8482 | 156508.6351 | 8482 | 156508.6351
[6 empty] | 8483 | 0 | 8483 | 0
[6 empty] | 8484 | 0 | 8484 | 0
[6 empty] | 8485 | 0 | 8485 | 0
[6 empty] | 8486 | 0 | 8486 | 0
[6 empty] | 8487 | 187136.0381 | 8487 | 187136.0381
[6 empty] | 8488 | 809865.044 | 8488 | 809865.044
[6 empty] | 8489 | 0 | 8489 | 0
[6 empty] | 8490 | 178857.196 | 8490 | 178857.196
[6 empty] | 8491 | 793021.2477 | 8491 | 793021.2477
[6 empty] | 8492 | 0 | 8492 | 0
[6 empty] | 8493 | 0 | 8493 | 0
[6 empty] | 8494 | 0 | 8494 | 0
[6 empty] | 8495 | 0 | 8495 | 0
[6 empty] | 8496 | 0 | 8496 | 0
[6 empty] | 8497 | 304735.6077 | 8497 | 304735.6077
[6 empty] | 8498 | 0 | 8498 | 0
[6 empty] | 8499 | 0 | 8499 | 0
[6 empty] | 8500 | 776037.6655 | 8500 | 0
[6 empty] | 8501 | 0 | 8501 | 0
[6 empty] | 8502 | 0 | 8502 | 0
[6 empty] | 8503 | 0 | 8503 | 0
[6 empty] | 8504 | 0 | 8504 | 0
[6 empty] | 8505 | 0 | 8505 | 0
[6 empty] | 8506 | 0 | 8506 | 0
[6 empty] | 8507 | 0 | 8507 | 0
[6 empty] | 8508 | 0 | 8508 | 0
[6 empty] | 8509 | 0 | 8509 | 0
[6 empty] | 8510 | 2373790.8273 | 8510 | 0
[6 empty] | 8511 | 24275078.805 | 8511 | 24275078.805
[6 empty] | 8512 | 954055.0789 | 8512 | 954055.0789
[6 empty] | 8513 | 0 | 8513 | 0
[6 empty] | 8514 | 0 | 8514 | 0
[6 empty] | 8515 | 0 | 8515 | 0
[6 empty] | 8516 | 0 | 8516 | 0
[6 empty] | 8517 | 0 | 8517 | 0
[6 empty] | 8518 | 2065453.0893 | 8518 | 0
[6 empty] | 8519 | 2900930.6831 | 8519 | 0
[6 empty] | 8520 | 1166459.5379 | 8520 | 153891.8537
[6 empty] | 8521 | 2006212.2217 | 8521 | 0
[6 empty] | 8522 | 0 | 8522 | 0
[6 empty] | 8523 | 0 | 8523 | 0
[6 empty] | 8524 | 204908.8093 | 8524 | 0
[6 empty] | 8525 | 10228104.5717 | 8525 | 0
[6 empty] | 8526 | 4790741.9552 | 8526 | 4790741.9552
[6 empty] | 8527 | 0 | 8527 | 0
[6 empty] | 8528 | 0 | 8528 | 0
[6 empty] | 8529 | 0 | 8529 | 0
[6 empty] | 8530 | 1883847.141 | 8530 | 1883847.141
[6 empty] | 8531 | 0 | 8531 | 0
[6 empty] | 8532 | 3451766.7882 | 8532 | 0
[6 empty] | 8533 | 4764445.6222 | 8533 | 532650.7688
[6 empty] | 8534 | 186444.295 | 8534 | 0
[6 empty] | 8535 | 3873366.7973 | 8535 | 0
[6 empty] | 8536 | 2117563.6224 | 8536 | 0
[6 empty] | 8537 | 778041.3019 | 8537 | 613304.1453
[6 empty] | 8538 | 3478184.7161 | 8538 | 673743.2923
[6 empty] | 8539 | 0 | 8539 | 0
[6 empty] | 8540 | 198935.1029 | 8540 | 0
[6 empty] | 8541 | 214614.7262 | 8541 | 214614.7262
[6 empty] | 8542 | 292934.2801 | 8542 | 292934.2801
[6 empty] | 8543 | 0 | 8543 | 0
[6 empty] | 8544 | 0 | 8544 | 0
[6 empty] | 8545 | 0 | 8545 | 0
[6 empty] | 8546 | 0 | 8546 | 0
[6 empty] | 8547 | 20488190.6236 | 8547 | 0
[6 empty] | 8548 | 190897.5846 | 8548 | 190897.5846
[6 empty] | 8549 | 242081.6968 | 8549 | 242081.6968
[6 empty] | 8550 | 691123.8737 | 8550 | 691123.8737
[6 empty] | 8551 | 0 | 8551 | 0
[6 empty] | 8552 | 0 | 8552 | 0
[6 empty] | 8553 | 3431509.9891 | 8553 | 3431509.9891
[6 empty] | 8554 | 1273394.181 | 8554 | 0
[6 empty] | 8555 | 2871244.8059 | 8555 | 0
[6 empty] | 8556 | 0 | 8556 | 0
[6 empty] | 8557 | 244170.3077 | 8557 | 244170.3077
[6 empty] | 8558 | 0 | 8558 | 0
[6 empty] | 8559 | 0 | 8559 | 0
[6 empty] | 8560 | 2637455.1793 | 8560 | 2637455.1793
[6 empty] | 8561 | 3494933.3957 | 8561 | 0
[6 empty] | 8562 | 605427.7263 | 8562 | 605427.7263
[6 empty] | 8563 | 0 | 8563 | 0
[6 empty] | 8564 | 0 | 8564 | 0
[6 empty] | 8565 | 3378483.2177 | 8565 | 3378483.2177
[6 empty] | 8566 | 0 | 8566 | 0
[6 empty] | 8567 | 180550.8355 | 8567 | 180550.8355
[6 empty] | 8568 | 0 | 8568 | 0
[6 empty] | 8569 | 0 | 8569 | 0
[6 empty] | 8570 | 0 | 8570 | 0
[6 empty] | 8571 | 347616.729 | 8571 | 347616.729
[6 empty] | 8572 | 2813247.1361 | 8572 | 0
[6 empty] | 8573 | 8037068.0263 | 8573 | 0
[6 empty] | 8574 | 0 | 8574 | 0
[6 empty] | 8575 | 1674046.8989 | 8575 | 0
[6 empty] | 8576 | 3663962.4578 | 8576 | 1599791.0152
[6 empty] | 8577 | 656144.129 | 8577 | 656144.129
[6 empty] | 8578 | 0 | 8578 | 0
[6 empty] | 8579 | 2315173.3935 | 8579 | 2315173.3935
[6 empty] | 8580 | 857436.8405 | 8580 | 857436.8405
[6 empty] | 8581 | 6228145.8361 | 8581 | 0
[6 empty] | 8582 | 0 | 8582 | 0
[6 empty] | 8583 | 847218.5018 | 8583 | 847218.5018
[6 empty] | 8584 | 0 | 8584 | 0
[6 empty] | 8585 | 0 | 8585 | 0
[6 empty] | 8586 | 0 | 8586 | 0
[6 empty] | 8587 | 1065166.7079 | 8587 | 0
[6 empty] | 8588 | 0 | 8588 | 0
[6 empty] | 8589 | 3645055.7261 | 8589 | 3645055.7261
[6 empty] | 8590 | 2619102.4428 | 8590 | 2619102.4428
[6 empty] | 8591 | 0 | 8591 | 0
[6 empty] | 8592 | 0 | 8592 | 0
[6 empty] | 8593 | 2864042.8457 | 8593 | 2864042.8457
[6 empty] | 8594 | 4579370.5975 | 8594 | 4270424.1629
[6 empty] | 8595 | 183451.3824 | 8595 | 183451.3824
[6 empty] | 8596 | 0 | 8596 | 0
[6 empty] | 8597 | 0 | 8597 | 0
[6 empty] | 8598 | 2587257.2237 | 8598 | 2428106.4511
[6 empty] | 8599 | 0 | 8599 | 0
[6 empty] | 8600 | 0 | 8600 | 0
[6 empty] | 8601 | 0 | 8601 | 0
[6 empty] | 8602 | 417004.4822 | 8602 | 417004.4822
[6 empty] | 8603 | 0 | 8603 | 0
[6 empty] | 8604 | 2637246.9833 | 8604 | 0
[6 empty] | 8605 | 2395951.379 | 8605 | 0
[6 empty] | 8606 | 215553.4744 | 8606 | 215553.4744
[6 empty] | 8607 | 157986.0675 | 8607 | 157986.0675
[6 empty] | 8608 | 6077829.7413 | 8608 | 0
[6 empty] | 8609 | 0 | 8609 | 0
[6 empty] | 8610 | 0 | 8610 | 0
[6 empty] | 8611 | 1824360.0816 | 8611 | 1636349.5288
[6 empty] | 8612 | 0 | 8612 | 0
[6 empty] | 8613 | 0 | 8613 | 0
[6 empty] | 8614 | 0 | 8614 | 0
[6 empty] | 8615 | 488885.2015 | 8615 | 488885.2015
[6 empty] | 8616 | 1814806.1465 | 8616 | 0
[6 empty] | 8617 | 0 | 8617 | 0
[6 empty] | 8618 | 0 | 8618 | 0
[6 empty] | 8619 | 0 | 8619 | 0
[6 empty] | 8620 | 125267.0456 | 8620 | 0
[6 empty] | 8621 | 4867476.8688 | 8621 | 4156353.3104
[6 empty] | 8622 | 231627.6325 | 8622 | 231627.6325
[6 empty] | 8623 | 0 | 8623 | 0
[6 empty] | 8624 | 0 | 8624 | 0
[6 empty] | 8625 | 4161986.3904 | 8625 | 1679462.2545
[6 empty] | 8626 | 3507381.4317 | 8626 | 3507381.4317
[6 empty] | 8627 | 1093835.3996 | 8627 | 0
[6 empty] | 8628 | 0 | 8628 | 0
[6 empty] | 8629 | 288081.2325 | 8629 | 288081.2325
[6 empty] | 8630 | 0 | 8630 | 0
[6 empty] | 8631 | 253467.0867 | 8631 | 253467.0867
[6 empty] | 8632 | 2465259.6867 | 8632 | 0
[6 empty] | 8633 | 481974.8936 | 8633 | 481974.8936
[6 empty] | 8634 | 0 | 8634 | 0
[6 empty] | 8635 | 244895.9111 | 8635 | 244895.9111
[6 empty] | 8636 | 0 | 8636 | 0
[6 empty] | 8637 | 11701654.0918 | 8637 | 11701654.0918
[6 empty] | 8638 | 225529.7771 | 8638 | 225529.7771
[6 empty] | 8639 | 0 | 8639 | 0
[6 empty] | 8640 | 0 | 8640 | 0
[6 empty] | 8641 | 213527.892 | 8641 | 213527.892
[6 empty] | 8642 | 312355.8914 | 8642 | 312355.8914
[6 empty] | 8643 | 8252289.2001 | 8643 | 0
[6 empty] | 8644 | 379920.8211 | 8644 | 189223.4536
[6 empty] | 8645 | 3094641.3918 | 8645 | 0
[6 empty] | 8646 | 0 | 8646 | 0
[6 empty] | 8647 | 237062.1816 | 8647 | 0
[6 empty] | 8648 | 729555.2621 | 8648 | 0
[6 empty] | 8649 | 0 | 8649 | 0
[6 empty] | 8650 | 0 | 8650 | 0
[6 empty] | 8651 | 0 | 8651 | 0
[6 empty] | 8652 | 0 | 8652 | 0
[6 empty] | 8653 | 111224.3664 | 8653 | 111224.3664
[6 empty] | 8654 | 404744.1544 | 8654 | 404744.1544
[6 empty] | 8655 | 0 | 8655 | 0
[6 empty] | 8656 | 192740.2944 | 8656 | 192740.2944
[6 empty] | 8657 | 219592.3767 | 8657 | 219592.3767
[6 empty] | 8658 | 539194.6337 | 8658 | 539194.6337
[6 empty] | 8659 | 0 | 8659 | 0
[6 empty] | 8660 | 0 | 8660 | 0
[6 empty] | 8661 | 182703.5666 | 8661 | 0
[6 empty] | 8662 | 0 | 8662 | 0
[6 empty] | 8663 | 6519957.0675 | 8663 | 0
[6 empty] | 8664 | 0 | 8664 | 0
[6 empty] | 8665 | 0 | 8665 | 0
[6 empty] | 8666 | 0 | 8666 | 0
[6 empty] | 8667 | 3443330.5958 | 8667 | 0
[6 empty] | 8668 | 405787.8542 | 8668 | 405787.8542
[6 empty] | 8669 | 0 | 8669 | 0
[6 empty] | 8670 | 4893240.6766 | 8670 | 4893240.6766
[6 empty] | 8671 | 0 | 8671 | 0
[6 empty] | 8672 | 528480.8163 | 8672 | 528480.8163
[6 empty] | 8673 | 0 | 8673 | 0
[6 empty] | 8674 | 0 | 8674 | 0
[6 empty] | 8675 | 0 | 8675 | 0
[6 empty] | 8676 | 10266696.4556 | 8676 | 1239511.0667
[6 empty] | 8677 | 0 | 8677 | 0
[6 empty] | 8678 | 0 | 8678 | 0
[6 empty] | 8679 | 0 | 8679 | 0
[6 empty] | 8680 | 0 | 8680 | 0
[6 empty] | 8681 | 432305.308 | 8681 | 432305.308
[6 empty] | 8682 | 0 | 8682 | 0
[6 empty] | 8683 | 0 | 8683 | 0
[6 empty] | 8684 | 0 | 8684 | 0
[6 empty] | 8685 | 1288354.5929 | 8685 | 1288354.5929
[6 empty] | 8686 | 0 | 8686 | 0
[6 empty] | 8687 | 6123417.5219 | 8687 | 4736479.2223
[6 empty] | 8688 | 183256.6892 | 8688 | 183256.6892
[6 empty] | 8689 | 0 | 8689 | 0
[6 empty] | 8690 | 0 | 8690 | 0
[6 empty] | 8691 | 0 | 8691 | 0
[6 empty] | 8692 | 3493006.2335 | 8692 | 3493006.2335
[6 empty] | 8693 | 19094430.844 | 8693 | 0
[6 empty] | 8694 | 0 | 8694 | 0
[6 empty] | 8695 | 4177711.0909 | 8695 | 760515.8388
[6 empty] | 8696 | 10547726.4491 | 8696 | 257234.815
[6 empty] | 8697 | 0 | 8697 | 0
[6 empty] | 8698 | 0 | 8698 | 0
[6 empty] | 8699 | 11337724.919 | 8699 | 1468873.1706
[6 empty] | 8700 | 0 | 8700 | 0
[6 empty] | 8701 | 0 | 8701 | 0
[6 empty] | 8702 | 0 | 8702 | 0
[6 empty] | 8703 | 251756.2645 | 8703 | 0
[6 empty] | 8704 | 0 | 8704 | 0
[6 empty] | 8705 | 0 | 8705 | 0
[6 empty] | 8706 | 0 | 8706 | 0
[6 empty] | 8707 | 4455085.9685 | 8707 | 0
[6 empty] | 8708 | 7525689.5589 | 8708 | 4481260.1882
[6 empty] | 8709 | 0 | 8709 | 0
[6 empty] | 8710 | 1035301.8323 | 8710 | 0
[6 empty] | 8711 | 4811880.4721 | 8711 | 540689.8583
[6 empty] | 8712 | 0 | 8712 | 0
[6 empty] | 8713 | 0 | 8713 | 0
[6 empty] | 8714 | 283164.7587 | 8714 | 0
[6 empty] | 8715 | 273772.1509 | 8715 | 0
[6 empty] | 8716 | 2987954.1292 | 8716 | 227750.8752
[6 empty] | 8717 | 405013.9482 | 8717 | 214046.6927
[6 empty] | 8718 | 0 | 8718 | 0
[6 empty] | 8719 | 0 | 8719 | 0
[6 empty] | 8720 | 0 | 8720 | 0
[6 empty] | 8721 | 0 | 8721 | 0
[6 empty] | 8722 | 431581.0849 | 8722 | 202943.5323
[6 empty] | 8723 | 0 | 8723 | 0
[6 empty] | 8724 | 0 | 8724 | 0
[6 empty] | 8725 | 4048707.2227 | 8725 | 365400.9484
[6 empty] | 8726 | 0 | 8726 | 0
[6 empty] | 8727 | 3040158.1272 | 8727 | 572157.7821
[6 empty] | 8728 | 0 | 8728 | 0
[6 empty] | 8729 | 4966847.3597 | 8729 | 0
[6 empty] | 8730 | 0 | 8730 | 0
[6 empty] | 8731 | 2841177.7756 | 8731 | 0
[6 empty] | 8732 | 0 | 8732 | 0
[6 empty] | 8733 | 30162970.209 | 8733 | 2099945.355
[6 empty] | 8734 | 410447.8132 | 8734 | 410447.8132
[6 empty] | 8735 | 1190970.1219 | 8735 | 1190970.1219
[6 empty] | 8736 | 3192340.0408 | 8736 | 0
[6 empty] | 8737 | 0 | 8737 | 0
[6 empty] | 8738 | 0 | 8738 | 0
[6 empty] | 8739 | 786090.5292 | 8739 | 786090.5292
[6 empty] | 8740 | 3044892.8065 | 8740 | 3044892.8065
[6 empty] | 8741 | 0 | 8741 | 0
[6 empty] | 8742 | 0 | 8742 | 0
[6 empty] | 8743 | 0 | 8743 | 0
[6 empty] | 8744 | 3261570.9136 | 8744 | 3261570.9136
[6 empty] | 8745 | 0 | 8745 | 0
[6 empty] | 8746 | 0 | 8746 | 0
[6 empty] | 8747 | 0 | 8747 | 0
[6 empty] | 8748 | 0 | 8748 | 0
[6 empty] | 8749 | 0 | 8749 | 0
[6 empty] | 8750 | 0 | 8750 | 0
[6 empty] | 8751 | 0 | 8751 | 0
[6 empty] | 8752 | 3535955.6357 | 8752 | 3535955.6357
[6 empty] | 8753 | 7407388.5197 | 8753 | 0
[6 empty] | 8754 | 0 | 8754 | 0
[6 empty] | 8755 | 0 | 8755 | 0
[6 empty] | 8756 | 0 | 8756 | 0
[6 empty] | 8757 | 268311.2425 | 8757 | 0
[6 empty] | 8758 | 0 | 8758 | 0
[6 empty] | 8759 | 283025.736 | 8759 | 283025.736
[6 empty] | 8760 | 0 | 8760 | 0
[6 empty] | 8761 | 8657027.0879 | 8761 | 0
[6 empty] | 8762 | 0 | 8762 | 0
[6 empty] | 8763 | 0 | 8763 | 0
[6 empty] | 8764 | 144906.0699 | 8764 | 144906.0699
[6 empty] | 8765 | 1315659.4577 | 8765 | 0
[6 empty] | 8766 | 0 | 8766 | 0
[6 empty] | 8767 | 253487.0105 | 8767 | 253487.0105
[6 empty] | 8768 | 3615191.5302 | 8768 | 3615191.5302
[6 empty] | 8769 | 0 | 8769 | 0
[6 empty] | 8770 | 2825806.5456 | 8770 | 0
[6 empty] | 8771 | 3877875.3758 | 8771 | 3877875.3758
[6 empty] | 8772 | 1687308.2282 | 8772 | 0
[6 empty] | 8773 | 0 | 8773 | 0
[6 empty] | 8774 | 0 | 8774 | 0
[6 empty] | 8775 | 0 | 8775 | 0
[6 empty] | 8776 | 782037.1897 | 8776 | 0
[6 empty] | 8777 | 0 | 8777 | 0
[6 empty] | 8778 | 6264307.217 | 8778 | 0
[6 empty] | 8779 | 207185.1276 | 8779 | 207185.1276
[6 empty] | 8780 | 0 | 8780 | 0
[6 empty] | 8781 | 0 | 8781 | 0
[6 empty] | 8782 | 773514.6328 | 8782 | 773514.6328
[6 empty] | 8783 | 1312905.4037 | 8783 | 98326.8143
[6 empty] | 8784 | 377645.2993 | 8784 | 176811.1096
[6 empty] | 8785 | 0 | 8785 | 0
[6 empty] | 8786 | 412575.7979 | 8786 | 412575.7979
[6 empty] | 8787 | 0 | 8787 | 0
[6 empty] | 8788 | 1022913.4592 | 8788 | 838549.1466
[6 empty] | 8789 | 3704028.2186 | 8789 | 3704028.2186
[6 empty] | 8790 | 0 | 8790 | 0
[6 empty] | 8791 | 0 | 8791 | 0
[6 empty] | 8792 | 1306418.1523 | 8792 | 1306418.1523
[6 empty] | 8793 | 0 | 8793 | 0
[6 empty] | 8794 | 14376648.7643 | 8794 | 14376648.7643
[6 empty] | 8795 | 9972083.4455 | 8795 | 7886229.8791
[6 empty] | 8796 | 3558322.4614 | 8796 | 0
[6 empty] | 8797 | 0 | 8797 | 0
[6 empty] | 8798 | 0 | 8798 | 0
[6 empty] | 8799 | 0 | 8799 | 0
[6 empty] | 8800 | 159699.6819 | 8800 | 159699.6819
[6 empty] | 8801 | 4696017.425 | 8801 | 4696017.425
[6 empty] | 8802 | 0 | 8802 | 0
[6 empty] | 8803 | 97551.6112 | 8803 | 97551.6112
[6 empty] | 8804 | 4481710.3862 | 8804 | 4481710.3862
[6 empty] | 8805 | 0 | 8805 | 0
[6 empty] | 8806 | 0 | 8806 | 0
[6 empty] | 8807 | 0 | 8807 | 0
[6 empty] | 8808 | 20853440.0058 | 8808 | 20853440.0058
[6 empty] | 8809 | 556874.6735 | 8809 | 556874.6735
[6 empty] | 8810 | 0 | 8810 | 0
[6 empty] | 8811 | 2236280.9199 | 8811 | 2236280.9199
[6 empty] | 8812 | 888646.0924 | 8812 | 0
[6 empty] | 8813 | 46315.3864 | 8813 | 46315.3864
[6 empty] | 8814 | 0 | 8814 | 0
[6 empty] | 8815 | 0 | 8815 | 0
[6 empty] | 8816 | 0 | 8816 | 0
[6 empty] | 8817 | 452289.5663 | 8817 | 452289.5663
[6 empty] | 8818 | 4419588.2003 | 8818 | 0
[6 empty] | 8819 | 0 | 8819 | 0
[6 empty] | 8820 | 0 | 8820 | 0
[6 empty] | 8821 | 0 | 8821 | 0
[6 empty] | 8822 | 0 | 8822 | 0
[6 empty] | 8823 | 663783.1194 | 8823 | 663783.1194
[6 empty] | 8824 | 235047.9005 | 8824 | 0
[6 empty] | 8825 | 3031686.9354 | 8825 | 136826.701
[6 empty] | 8826 | 194926.9468 | 8826 | 194926.9468
[6 empty] | 8827 | 0 | 8827 | 0
[6 empty] | 8828 | 0 | 8828 | 0
[6 empty] | 8829 | 7115869.7551 | 8829 | 7115869.7551
[6 empty] | 8830 | 3139130.4239 | 8830 | 0
[6 empty] | 8831 | 0 | 8831 | 0
[6 empty] | 8832 | 0 | 8832 | 0
[6 empty] | 8833 | 0 | 8833 | 0
[6 empty] | 8834 | 0 | 8834 | 0
[6 empty] | 8835 | 0 | 8835 | 0
[6 empty] | 8836 | 0 | 8836 | 0
[6 empty] | 8837 | 2510774.1285 | 8837 | 0
[6 empty] | 8838 | 0 | 8838 | 0
[6 empty] | 8839 | 0 | 8839 | 0
[6 empty] | 8840 | 8858952.627 | 8840 | 0
[6 empty] | 8841 | 69295.5136 | 8841 | 69295.5136
[6 empty] | 8842 | 479172.7757 | 8842 | 479172.7757
[6 empty] | 8843 | 0 | 8843 | 0
[6 empty] | 8844 | 231823.6689 | 8844 | 0
[6 empty] | 8845 | 2946608.8534 | 8845 | 163446.3911
[6 empty] | 8846 | 1915466.2876 | 8846 | 1915466.2876
[6 empty] | 8847 | 3776388.2121 | 8847 | 0
[6 empty] | 8848 | 0 | 8848 | 0
[6 empty] | 8849 | 3884238.4836 | 8849 | 3884238.4836
[6 empty] | 8850 | 578381.8682 | 8850 | 578381.8682
[6 empty] | 8851 | 2565405.1321 | 8851 | 0
[6 empty] | 8852 | 282428.5917 | 8852 | 282428.5917
[6 empty] | 8853 | 285816.4564 | 8853 | 285816.4564
[6 empty] | 8854 | 3347636.4654 | 8854 | 0
[6 empty] | 8855 | 0 | 8855 | 0
[6 empty] | 8856 | 4622929.8306 | 8856 | 0
[6 empty] | 8857 | 0 | 8857 | 0
[6 empty] | 8858 | 0 | 8858 | 0
[6 empty] | 8859 | 0 | 8859 | 0
[6 empty] | 8860 | 0 | 8860 | 0
[6 empty] | 8861 | 0 | 8861 | 0
[6 empty] | 8862 | 812553.5983 | 8862 | 812553.5983
[6 empty] | 8863 | 0 | 8863 | 0
[6 empty] | 8864 | 0 | 8864 | 0
[6 empty] | 8865 | 34201502.7008 | 8865 | 0
[6 empty] | 8866 | 0 | 8866 | 0
[6 empty] | 8867 | 0 | 8867 | 0
[6 empty] | 8868 | 271768.3913 | 8868 | 271768.3913
[6 empty] | 8869 | 769432.2005 | 8869 | 769432.2005
[6 empty] | 8870 | 0 | 8870 | 0
[6 empty] | 8871 | 71120.1321 | 8871 | 71120.1321
[6 empty] | 8872 | 60230.765 | 8872 | 60230.765
[6 empty] | 8873 | 108798.9524 | 8873 | 108798.9524
[6 empty] | 8874 | 0 | 8874 | 0
[6 empty] | 8875 | 0 | 8875 | 0
[6 empty] | 8876 | 0 | 8876 | 0
[6 empty] | 8877 | 3858932.709 | 8877 | 3858932.709
[6 empty] | 8878 | 553931.3244 | 8878 | 553931.3244
[6 empty] | 8879 | 3984181.9438 | 8879 | 3984181.9438
[6 empty] | 8880 | 1427667.5148 | 8880 | 1427667.5148
[6 empty] | 8881 | 174694.8343 | 8881 | 0
[6 empty] | 8882 | 0 | 8882 | 0
[6 empty] | 8883 | 580883.9089 | 8883 | 161844.1129
[6 empty] | 8884 | 4325604.4664 | 8884 | 1681272.4663
[6 empty] | 8885 | 0 | 8885 | 0
[6 empty] | 8886 | 0 | 8886 | 0
[6 empty] | 8887 | 3426834.0113 | 8887 | 256003.2479
[6 empty] | 8888 | 628863.2915 | 8888 | 373184.2891
[6 empty] | 8889 | 0 | 8889 | 0
[6 empty] | 8890 | 458984.3952 | 8890 | 458984.3952
[6 empty] | 8891 | 2871576.542 | 8891 | 0
[6 empty] | 8892 | 0 | 8892 | 0
[6 empty] | 8893 | 2661992.6181 | 8893 | 2661992.6181
[6 empty] | 8894 | 3802258.9495 | 8894 | 0
[6 empty] | 8895 | 0 | 8895 | 0
[6 empty] | 8896 | 0 | 8896 | 0
[6 empty] | 8897 | 5651972.1056 | 8897 | 3489043.641
[6 empty] | 8898 | 182805.1023 | 8898 | 182805.1023
[6 empty] | 8899 | 924219.6905 | 8899 | 0
[6 empty] | 8900 | 0 | 8900 | 0
[6 empty] | 8901 | 0 | 8901 | 0
[6 empty] | 8902 | 0 | 8902 | 0
[6 empty] | 8903 | 210533.091 | 8903 | 210533.091
[6 empty] | 8904 | 607240.4136 | 8904 | 607240.4136
[6 empty] | 8905 | 0 | 8905 | 0
[6 empty] | 8906 | 0 | 8906 | 0
[6 empty] | 8907 | 247040.7753 | 8907 | 247040.7753
[6 empty] | 8908 | 440451.7156 | 8908 | 440451.7156
[6 empty] | 8909 | 192803.2118 | 8909 | 192803.2118
[6 empty] | 8910 | 0 | 8910 | 0
[6 empty] | 8911 | 4329711.5719 | 8911 | 4329711.5719
[6 empty] | 8912 | 0 | 8912 | 0
[6 empty] | 8913 | 264974.9065 | 8913 | 264974.9065
[6 empty] | 8914 | 0 | 8914 | 0
[6 empty] | 8915 | 0 | 8915 | 0
[6 empty] | 8916 | 0 | 8916 | 0
[6 empty] | 8917 | 5584629.3533 | 8917 | 0
[6 empty] | 8918 | 206875.1834 | 8918 | 206875.1834
[6 empty] | 8919 | 0 | 8919 | 0
[6 empty] | 8920 | 0 | 8920 | 0
[6 empty] | 8921 | 2382859.6346 | 8921 | 1242065.4865
[6 empty] | 8922 | 0 | 8922 | 0
[6 empty] | 8923 | 4195927.6532 | 8923 | 0
[6 empty] | 8924 | 5002283.0224 | 8924 | 5002283.0224
[6 empty] | 8925 | 3642739.2398 | 8925 | 0
[6 empty] | 8926 | 222741.4657 | 8926 | 222741.4657
[6 empty] | 8927 | 0 | 8927 | 0
[6 empty] | 8928 | 228894.4804 | 8928 | 228894.4804
[6 empty] | 8929 | 0 | 8929 | 0
[6 empty] | 8930 | 9319112.1238 | 8930 | 0
[6 empty] | 8931 | 0 | 8931 | 0
[6 empty] | 8932 | 0 | 8932 | 0
[6 empty] | 8933 | 145875.2012 | 8933 | 0
[6 empty] | 8934 | 3716737.9301 | 8934 | 0
[6 empty] | 8935 | 4502116.0323 | 8935 | 0
[6 empty] | 8936 | 4243980.0268 | 8936 | 139878.5636
[6 empty] | 8937 | 0 | 8937 | 0
[6 empty] | 8938 | 153200.6113 | 8938 | 153200.6113
[6 empty] | 8939 | 240703.0056 | 8939 | 240703.0056
[6 empty] | 8940 | 204789.8632 | 8940 | 204789.8632
[6 empty] | 8941 | 0 | 8941 | 0
[6 empty] | 8942 | 224820.9253 | 8942 | 224820.9253
[6 empty] | 8943 | 282828.1688 | 8943 | 282828.1688
[6 empty] | 8944 | 2521390.6407 | 8944 | 2521390.6407
[6 empty] | 8945 | 0 | 8945 | 0
[6 empty] | 8946 | 4387468.4781 | 8946 | 0
[6 empty] | 8947 | 2081812.3926 | 8947 | 2081812.3926
[6 empty] | 8948 | 143963.2258 | 8948 | 143963.2258
[6 empty] | 8949 | 0 | 8949 | 0
[6 empty] | 8950 | 558227.2907 | 8950 | 558227.2907
[6 empty] | 8951 | 2548193.65 | 8951 | 2548193.65
[6 empty] | 8952 | 0 | 8952 | 0
[6 empty] | 8953 | 208637.4039 | 8953 | 208637.4039
[6 empty] | 8954 | 7898195.9881 | 8954 | 7898195.9881
[6 empty] | 8955 | 3797214.6547 | 8955 | 3640943.4397
[6 empty] | 8956 | 0 | 8956 | 0
[6 empty] | 8957 | 0 | 8957 | 0
[6 empty] | 8958 | 1210719.9575 | 8958 | 0
[6 empty] | 8959 | 0 | 8959 | 0
[6 empty] | 8960 | 1229705.9156 | 8960 | 1229705.9156
[6 empty] | 8961 | 0 | 8961 | 0
[6 empty] | 8962 | 2958822.5888 | 8962 | 0
[6 empty] | 8963 | 152160.7345 | 8963 | 0
[6 empty] | 8964 | 0 | 8964 | 0
[6 empty] | 8965 | 204374.4873 | 8965 | 204374.4873
[6 empty] | 8966 | 0 | 8966 | 0
[6 empty] | 8967 | 0 | 8967 | 0
[6 empty] | 8968 | 8211402.1184 | 8968 | 8211402.1184
[6 empty] | 8969 | 6299189.3951 | 8969 | 689728.0179
[6 empty] | 8970 | 0 | 8970 | 0
[6 empty] | 8971 | 0 | 8971 | 0
[6 empty] | 8972 | 0 | 8972 | 0
[6 empty] | 8973 | 0 | 8973 | 0
[6 empty] | 8974 | 0 | 8974 | 0
[6 empty] | 8975 | 0 | 8975 | 0
[6 empty] | 8976 | 0 | 8976 | 0
[6 empty] | 8977 | 0 | 8977 | 0
[6 empty] | 8978 | 0 | 8978 | 0
[6 empty] | 8979 | 196218.8204 | 8979 | 196218.8204
[6 empty] | 8980 | 0 | 8980 | 0
[6 empty] | 8981 | 0 | 8981 | 0
[6 empty] | 8982 | 884429.7597 | 8982 | 884429.7597
[6 empty] | 8983 | 405185.6142 | 8983 | 0
[6 empty] | 8984 | 0 | 8984 | 0
[6 empty] | 8985 | 447072.9407 | 8985 | 447072.9407
[6 empty] | 8986 | 1268164.6652 | 8986 | 1268164.6652
[6 empty] | 8987 | 0 | 8987 | 0
[6 empty] | 8988 | 265838.807 | 8988 | 0
[6 empty] | 8989 | 187305.172 | 8989 | 0
[6 empty] | 8990 | 248588.6529 | 8990 | 0
[6 empty] | 8991 | 0 | 8991 | 0
[6 empty] | 8992 | 0 | 8992 | 0
[6 empty] | 8993 | 0 | 8993 | 0
[6 empty] | 8994 | 0 | 8994 | 0
[6 empty] | 8995 | 0 | 8995 | 0
[6 empty] | 8996 | 0 | 8996 | 0
[6 empty] | 8997 | 3628639.4837 | 8997 | 0
[6 empty] | 8998 | 3981773.4628 | 8998 | 255251.9165
[6 empty] | 8999 | 329499.1103 | 8999 | 329499.1103
[6 empty] | 9000 | 0 | 9000 | 0
[6 empty] | 9001 | 0 | 9001 | 0
[6 empty] | 9002 | 0 | 9002 | 0
[6 empty] | 9003 | 5071879.7918 | 9003 | 0
[6 empty] | 9004 | 226418.6268 | 9004 | 0
[6 empty] | 9005 | 223337.7112 | 9005 | 223337.7112
[6 empty] | 9006 | 0 | 9006 | 0
[6 empty] | 9007 | 0 | 9007 | 0
[6 empty] | 9008 | 0 | 9008 | 0
[6 empty] | 9009 | 0 | 9009 | 0
[6 empty] | 9010 | 0 | 9010 | 0
[6 empty] | 9011 | 202532.6107 | 9011 | 202532.6107
[6 empty] | 9012 | 489868.1279 | 9012 | 489868.1279
[6 empty] | 9013 | 0 | 9013 | 0
[6 empty] | 9014 | 1525002.9698 | 9014 | 0
[6 empty] | 9015 | 0 | 9015 | 0
[6 empty] | 9016 | 3603807.739 | 9016 | 0
[6 empty] | 9017 | 5759203.4985 | 9017 | 0
[6 empty] | 9018 | 2947963.9464 | 9018 | 0
[6 empty] | 9019 | 4572551.4398 | 9019 | 4572551.4398
[6 empty] | 9020 | 2959940.1356 | 9020 | 716461.178
[6 empty] | 9021 | 41372.5448 | 9021 | 41372.5448
[6 empty] | 9022 | 0 | 9022 | 0
[6 empty] | 9023 | 5493605.9571 | 9023 | 0
[6 empty] | 9024 | 0 | 9024 | 0
[6 empty] | 9025 | 468417.2621 | 9025 | 468417.2621
[6 empty] | 9026 | 376871.868 | 9026 | 0
[6 empty] | 9027 | 0 | 9027 | 0
[6 empty] | 9028 | 175036.1954 | 9028 | 0
[6 empty] | 9029 | 2371156.5999 | 9029 | 2371156.5999
[6 empty] | 9030 | 0 | 9030 | 0
[6 empty] | 9031 | 155109.8463 | 9031 | 155109.8463
[6 empty] | 9032 | 1780575.5712 | 9032 | 1463183.4888
[6 empty] | 9033 | 361296.1017 | 9033 | 361296.1017
[6 empty] | 9034 | 0 | 9034 | 0
[6 empty] | 9035 | 376583.5168 | 9035 | 376583.5168
[6 empty] | 9036 | 0 | 9036 | 0
[6 empty] | 9037 | 0 | 9037 | 0
[6 empty] | 9038 | 0 | 9038 | 0
[6 empty] | 9039 | 0 | 9039 | 0
[6 empty] | 9040 | 0 | 9040 | 0
[6 empty] | 9041 | 17293240.5831 | 9041 | 0
[6 empty] | 9042 | 0 | 9042 | 0
[6 empty] | 9043 | 1265332.6511 | 9043 | 0
[6 empty] | 9044 | 0 | 9044 | 0
[6 empty] | 9045 | 0 | 9045 | 0
[6 empty] | 9046 | 0 | 9046 | 0
[6 empty] | 9047 | 179975.1164 | 9047 | 179975.1164
[6 empty] | 9048 | 0 | 9048 | 0
[6 empty] | 9049 | 10059888.8779 | 9049 | 0
[6 empty] | 9050 | 2784495.2804 | 9050 | 2784495.2804
[6 empty] | 9051 | 648497.1532 | 9051 | 648497.1532
[6 empty] | 9052 | 11833409.7726 | 9052 | 0
[6 empty] | 9053 | 2324769.2829 | 9053 | 0
[6 empty] | 9054 | 2477999.8701 | 9054 | 105402.7854
[6 empty] | 9055 | 0 | 9055 | 0
[6 empty] | 9056 | 0 | 9056 | 0
[6 empty] | 9057 | 0 | 9057 | 0
[6 empty] | 9058 | 0 | 9058 | 0
[6 empty] | 9059 | 6317962.5421 | 9059 | 6317962.5421
[6 empty] | 9060 | 1795644.4168 | 9060 | 0
[6 empty] | 9061 | 0 | 9061 | 0
[6 empty] | 9062 | 1352106.3269 | 9062 | 1352106.3269
[6 empty] | 9063 | 0 | 9063 | 0
[6 empty] | 9064 | 0 | 9064 | 0
[6 empty] | 9065 | 0 | 9065 | 0
[6 empty] | 9066 | 4052157.1643 | 9066 | 0
[6 empty] | 9067 | 0 | 9067 | 0
[6 empty] | 9068 | 3090473.2431 | 9068 | 2249453.8313
[6 empty] | 9069 | 1292986.5347 | 9069 | 1292986.5347
[6 empty] | 9070 | 0 | 9070 | 0
[6 empty] | 9071 | 404780.6115 | 9071 | 404780.6115
[6 empty] | 9072 | 3381163.9327 | 9072 | 3381163.9327
[6 empty] | 9073 | 0 | 9073 | 0
[6 empty] | 9074 | 0 | 9074 | 0
[6 empty] | 9075 | 9639596.9958 | 9075 | 0
[6 empty] | 9076 | 2859863.2564 | 9076 | 2859863.2564
[6 empty] | 9077 | 4652265.4405 | 9077 | 4652265.4405
[6 empty] | 9078 | 432171.5861 | 9078 | 432171.5861
[6 empty] | 9079 | 0 | 9079 | 0
[6 empty] | 9080 | 3313774.5436 | 9080 | 0
[6 empty] | 9081 | 0 | 9081 | 0
[6 empty] | 9082 | 260798.4998 | 9082 | 260798.4998
[6 empty] | 9083 | 0 | 9083 | 0
[6 empty] | 9084 | 8928056.8802 | 9084 | 1129537.2155
[6 empty] | 9085 | 0 | 9085 | 0
[6 empty] | 9086 | 0 | 9086 | 0
[6 empty] | 9087 | 0 | 9087 | 0
[6 empty] | 9088 | 0 | 9088 | 0
[6 empty] | 9089 | 3227491.3026 | 9089 | 0
[6 empty] | 9090 | 0 | 9090 | 0
[6 empty] | 9091 | 2161346.8603 | 9091 | 2161346.8603
[6 empty] | 9092 | 3667645.2445 | 9092 | 0
[6 empty] | 9093 | 1381024.6751 | 9093 | 379981.2574
[6 empty] | 9094 | 2843438.5547 | 9094 | 2843438.5547
[6 empty] | 9095 | 0 | 9095 | 0
[6 empty] | 9096 | 0 | 9096 | 0
[6 empty] | 9097 | 3632752.9689 | 9097 | 0
[6 empty] | 9098 | 2492316.4102 | 9098 | 2492316.4102
[6 empty] | 9099 | 807421.382 | 9099 | 807421.382
[6 empty] | 9100 | 0 | 9100 | 0
[6 empty] | 9101 | 0 | 9101 | 0
[6 empty] | 9102 | 219588.5322 | 9102 | 219588.5322
[6 empty] | 9103 | 0 | 9103 | 0
[6 empty] | 9104 | 514321.5876 | 9104 | 514321.5876
[6 empty] | 9105 | 4071301.7246 | 9105 | 0
[6 empty] | 9106 | 442727.4682 | 9106 | 442727.4682
[6 empty] | 9107 | 218893.358 | 9107 | 218893.358
[6 empty] | 9108 | 0 | 9108 | 0
[6 empty] | 9109 | 0 | 9109 | 0
[6 empty] | 9110 | 0 | 9110 | 0
[6 empty] | 9111 | 4450618.0358 | 9111 | 4450618.0358
[6 empty] | 9112 | 897359.495 | 9112 | 0
[6 empty] | 9113 | 0 | 9113 | 0
[6 empty] | 9114 | 3179841.9242 | 9114 | 3179841.9242
[6 empty] | 9115 | 0 | 9115 | 0
[6 empty] | 9116 | 0 | 9116 | 0
[6 empty] | 9117 | 0 | 9117 | 0
[6 empty] | 9118 | 2482586.2415 | 9118 | 0
[6 empty] | 9119 | 211541.9874 | 9119 | 0
[6 empty] | 9120 | 188568.679 | 9120 | 188568.679
[6 empty] | 9121 | 0 | 9121 | 0
[6 empty] | 9122 | 261746.5762 | 9122 | 0
[6 empty] | 9123 | 616669.1461 | 9123 | 616669.1461
[6 empty] | 9124 | 3713976.3731 | 9124 | 3713976.3731
[6 empty] | 9125 | 790292.3702 | 9125 | 790292.3702
[6 empty] | 9126 | 239523.8813 | 9126 | 0
[6 empty] | 9127 | 0 | 9127 | 0
[6 empty] | 9128 | 0 | 9128 | 0
[6 empty] | 9129 | 0 | 9129 | 0
[6 empty] | 9130 | 0 | 9130 | 0
[6 empty] | 9131 | 0 | 9131 | 0
[6 empty] | 9132 | 151643.2432 | 9132 | 151643.2432
[6 empty] | 9133 | 0 | 9133 | 0
[6 empty] | 9134 | 0 | 9134 | 0
[6 empty] | 9135 | 3779858.7885 | 9135 | 0
[6 empty] | 9136 | 129037.0981 | 9136 | 0
[6 empty] | 9137 | 7402366.8799 | 9137 | 7402366.8799
[6 empty] | 9138 | 270547.6938 | 9138 | 0
[6 empty] | 9139 | 0 | 9139 | 0
[6 empty] | 9140 | 720372.5009 | 9140 | 490152.1395
[6 empty] | 9141 | 3312658.907 | 9141 | 3312658.907
[6 empty] | 9142 | 399634.7884 | 9142 | 399634.7884
[6 empty] | 9143 | 2352909.7056 | 9143 | 0
[6 empty] | 9144 | 0 | 9144 | 0
[6 empty] | 9145 | 3286914.2416 | 9145 | 3286914.2416
[6 empty] | 9146 | 0 | 9146 | 0
[6 empty] | 9147 | 232735.5849 | 9147 | 232735.5849
[6 empty] | 9148 | 774789.9697 | 9148 | 774789.9697
[6 empty] | 9149 | 0 | 9149 | 0
[6 empty] | 9150 | 529544.5348 | 9150 | 265572.1239
[6 empty] | 9151 | 200484.4859 | 9151 | 200484.4859
[6 empty] | 9152 | 962426.8495 | 9152 | 962426.8495
[6 empty] | 9153 | 0 | 9153 | 0
[6 empty] | 9154 | 0 | 9154 | 0
[6 empty] | 9155 | 6764973.5388 | 9155 | 3439303.0336
[6 empty] | 9156 | 263896.575 | 9156 | 0
[6 empty] | 9157 | 0 | 9157 | 0
[6 empty] | 9158 | 184642.6666 | 9158 | 184642.6666
[6 empty] | 9159 | 0 | 9159 | 0
[6 empty] | 9160 | 0 | 9160 | 0
[6 empty] | 9161 | 0 | 9161 | 0
[6 empty] | 9162 | 241235.9863 | 9162 | 241235.9863
[6 empty] | 9163 | 3165973.3066 | 9163 | 3165973.3066
[6 empty] | 9164 | 8814701.6936 | 9164 | 0
[6 empty] | 9165 | 0 | 9165 | 0
[6 empty] | 9166 | 0 | 9166 | 0
[6 empty] | 9167 | 148595.5537 | 9167 | 148595.5537
[6 empty] | 9168 | 351639.1686 | 9168 | 351639.1686
[6 empty] | 9169 | 0 | 9169 | 0
[6 empty] | 9170 | 2663618.5575 | 9170 | 0
[6 empty] | 9171 | 14268276.088 | 9171 | 0
[6 empty] | 9172 | 0 | 9172 | 0
[6 empty] | 9173 | 3543287.8906 | 9173 | 0
[6 empty] | 9174 | 5520134.5145 | 9174 | 0
[6 empty] | 9175 | 1328036.0394 | 9175 | 1090840.8718
[6 empty] | 9176 | 178102.1711 | 9176 | 0
[6 empty] | 9177 | 0 | 9177 | 0
[6 empty] | 9178 | 2291798.0003 | 9178 | 2291798.0003
[6 empty] | 9179 | 0 | 9179 | 0
[6 empty] | 9180 | 215986.2141 | 9180 | 0
[6 empty] | 9181 | 0 | 9181 | 0
[6 empty] | 9182 | 263269.006 | 9182 | 0
[6 empty] | 9183 | 0 | 9183 | 0
[6 empty] | 9184 | 0 | 9184 | 0
[6 empty] | 9185 | 3565491.7371 | 9185 | 0
[6 empty] | 9186 | 266877.2141 | 9186 | 266877.2141
[6 empty] | 9187 | 0 | 9187 | 0
[6 empty] | 9188 | 251250.5436 | 9188 | 251250.5436
[6 empty] | 9189 | 0 | 9189 | 0
[6 empty] | 9190 | 0 | 9190 | 0
[6 empty] | 9191 | 0 | 9191 | 0
[6 empty] | 9192 | 0 | 9192 | 0
[6 empty] | 9193 | 0 | 9193 | 0
[6 empty] | 9194 | 350354.6793 | 9194 | 350354.6793
[6 empty] | 9195 | 5798224.6826 | 9195 | 0
[6 empty] | 9196 | 0 | 9196 | 0
[6 empty] | 9197 | 1220022.5763 | 9197 | 921345.1704
[6 empty] | 9198 | 7907660.0762 | 9198 | 7907660.0762
[6 empty] | 9199 | 0 | 9199 | 0
[6 empty] | 9200 | 0 | 9200 | 0
[6 empty] | 9201 | 5710354.5755 | 9201 | 4148753.0038
[6 empty] | 9202 | 169172.7867 | 9202 | 169172.7867
[6 empty] | 9203 | 282503.924 | 9203 | 0
[6 empty] | 9204 | 0 | 9204 | 0
[6 empty] | 9205 | 0 | 9205 | 0
[6 empty] | 9206 | 0 | 9206 | 0
[6 empty] | 9207 | 2906236.5231 | 9207 | 0
[6 empty] | 9208 | 0 | 9208 | 0
[6 empty] | 9209 | 718440.3861 | 9209 | 469731.2193
[6 empty] | 9210 | 3552298.4604 | 9210 | 3330535.5306
[6 empty] | 9211 | 49144358.8744 | 9211 | 0
[6 empty] | 9212 | 265434.4382 | 9212 | 265434.4382
[6 empty] | 9213 | 0 | 9213 | 0
[6 empty] | 9214 | 0 | 9214 | 0
[6 empty] | 9215 | 198982.4459 | 9215 | 198982.4459
[6 empty] | 9216 | 268678.1119 | 9216 | 268678.1119
[6 empty] | 9217 | 0 | 9217 | 0
[6 empty] | 9218 | 0 | 9218 | 0
[6 empty] | 9219 | 0 | 9219 | 0
[6 empty] | 9220 | 0 | 9220 | 0
[6 empty] | 9221 | 0 | 9221 | 0
[6 empty] | 9222 | 0 | 9222 | 0
[6 empty] | 9223 | 3253702.7424 | 9223 | 3253702.7424
[6 empty] | 9224 | 2484405.3336 | 9224 | 259370.2465
[6 empty] | 9225 | 282141.2245 | 9225 | 282141.2245
[6 empty] | 9226 | 0 | 9226 | 0
[6 empty] | 9227 | 0 | 9227 | 0
[6 empty] | 9228 | 0 | 9228 | 0
[6 empty] | 9229 | 0 | 9229 | 0
[6 empty] | 9230 | 3123000.7624 | 9230 | 0
[6 empty] | 9231 | 451061.1149 | 9231 | 451061.1149
[6 empty] | 9232 | 0 | 9232 | 0
[6 empty] | 9233 | 0 | 9233 | 0
[6 empty] | 9234 | 367617.0909 | 9234 | 367617.0909
[6 empty] | 9235 | 1081205.3952 | 9235 | 0
[6 empty] | 9236 | 93630.8235 | 9236 | 93630.8235
[6 empty] | 9237 | 0 | 9237 | 0
[6 empty] | 9238 | 69176.837 | 9238 | 69176.837
[6 empty] | 9239 | 142165.1417 | 9239 | 142165.1417
[6 empty] | 9240 | 8129401.9353 | 9240 | 0
[6 empty] | 9241 | 0 | 9241 | 0
[6 empty] | 9242 | 0 | 9242 | 0
[6 empty] | 9243 | 0 | 9243 | 0
[6 empty] | 9244 | 0 | 9244 | 0
[6 empty] | 9245 | 3129874.9062 | 9245 | 3129874.9062
[6 empty] | 9246 | 1004045.6133 | 9246 | 1004045.6133
[6 empty] | 9247 | 572487.0287 | 9247 | 572487.0287
[6 empty] | 9248 | 519026.6454 | 9248 | 334399.8184
[6 empty] | 9249 | 0 | 9249 | 0
[6 empty] | 9250 | 0 | 9250 | 0
[6 empty] | 9251 | 0 | 9251 | 0
[6 empty] | 9252 | 0 | 9252 | 0
[6 empty] | 9253 | 0 | 9253 | 0
[6 empty] | 9254 | 0 | 9254 | 0
[6 empty] | 9255 | 0 | 9255 | 0
[6 empty] | 9256 | 330667.467 | 9256 | 330667.467
[6 empty] | 9257 | 4478091.4293 | 9257 | 187842.8219
[6 empty] | 9258 | 185965.7537 | 9258 | 185965.7537
[6 empty] | 9259 | 0 | 9259 | 0
[6 empty] | 9260 | 0 | 9260 | 0
[6 empty] | 9261 | 2650849.1125 | 9261 | 0
[6 empty] | 9262 | 5402127.0072 | 9262 | 185444.6187
[6 empty] | 9263 | 0 | 9263 | 0
[6 empty] | 9264 | 0 | 9264 | 0
[6 empty] | 9265 | 0 | 9265 | 0
[6 empty] | 9266 | 3213961.5453 | 9266 | 3213961.5453
[6 empty] | 9267 | 253898.6124 | 9267 | 0
[6 empty] | 9268 | 0 | 9268 | 0
[6 empty] | 9269 | 0 | 9269 | 0
[6 empty] | 9270 | 213495.5412 | 9270 | 0
[6 empty] | 9271 | 223986.4878 | 9271 | 0
[6 empty] | 9272 | 2513946.9207 | 9272 | 244484.7279
[6 empty] | 9273 | 0 | 9273 | 0
[6 empty] | 9274 | 1136597.8547 | 9274 | 1136597.8547
[6 empty] | 9275 | 168559.7676 | 9275 | 0
[6 empty] | 9276 | 178934.7726 | 9276 | 178934.7726
[6 empty] | 9277 | 0 | 9277 | 0
[6 empty] | 9278 | 0 | 9278 | 0
[6 empty] | 9279 | 4754235.5679 | 9279 | 4754235.5679
[6 empty] | 9280 | 0 | 9280 | 0
[6 empty] | 9281 | 5632788.1693 | 9281 | 0
[6 empty] | 9282 | 529082.7389 | 9282 | 529082.7389
[6 empty] | 9283 | 0 | 9283 | 0
[6 empty] | 9284 | 0 | 9284 | 0
[6 empty] | 9285 | 0 | 9285 | 0
[6 empty] | 9286 | 7655050.2393 | 9286 | 0
[6 empty] | 9287 | 1286100.4011 | 9287 | 0
[6 empty] | 9288 | 5765807.8691 | 9288 | 3021932.5321
[6 empty] | 9289 | 2317129.4726 | 9289 | 2317129.4726
[6 empty] | 9290 | 3324798.875 | 9290 | 3324798.875
[6 empty] | 9291 | 0 | 9291 | 0
[6 empty] | 9292 | 299986.104 | 9292 | 299986.104
[6 empty] | 9293 | 0 | 9293 | 0
[6 empty] | 9294 | 195081.4864 | 9294 | 0
[6 empty] | 9295 | 0 | 9295 | 0
[6 empty] | 9296 | 0 | 9296 | 0
[6 empty] | 9297 | 438866.5382 | 9297 | 271947.8734
[6 empty] | 9298 | 0 | 9298 | 0
[6 empty] | 9299 | 0 | 9299 | 0
[6 empty] | 9300 | 0 | 9300 | 0
[6 empty] | 9301 | 0 | 9301 | 0
[6 empty] | 9302 | 0 | 9302 | 0
[6 empty] | 9303 | 0 | 9303 | 0
[6 empty] | 9304 | 0 | 9304 | 0
[6 empty] | 9305 | 0 | 9305 | 0
[6 empty] | 9306 | 0 | 9306 | 0
[6 empty] | 9307 | 2699221.1184 | 9307 | 0
[6 empty] | 9308 | 0 | 9308 | 0
[6 empty] | 9309 | 0 | 9309 | 0
[6 empty] | 9310 | 0 | 9310 | 0
[6 empty] | 9311 | 3712229.6238 | 9311 | 0
[6 empty] | 9312 | 3331209.9558 | 9312 | 0
[6 empty] | 9313 | 0 | 9313 | 0
[6 empty] | 9314 | 3832867.7753 | 9314 | 3832867.7753
[6 empty] | 9315 | 2695060.5026 | 9315 | 0
[6 empty] | 9316 | 419115.8897 | 9316 | 0
[6 empty] | 9317 | 0 | 9317 | 0
[6 empty] | 9318 | 3508488.6623 | 9318 | 3508488.6623
[6 empty] | 9319 | 0 | 9319 | 0
[6 empty] | 9320 | 0 | 9320 | 0
[6 empty] | 9321 | 0 | 9321 | 0
[6 empty] | 9322 | 260754.1831 | 9322 | 0
[6 empty] | 9323 | 0 | 9323 | 0
[6 empty] | 9324 | 0 | 9324 | 0
[6 empty] | 9325 | 215128.472 | 9325 | 215128.472
[6 empty] | 9326 | 235529.0824 | 9326 | 0
[6 empty] | 9327 | 152321.6552 | 9327 | 152321.6552
[6 empty] | 9328 | 2852338.0548 | 9328 | 0
[6 empty] | 9329 | 0 | 9329 | 0
[6 empty] | 9330 | 0 | 9330 | 0
[6 empty] | 9331 | 6558596.7604 | 9331 | 2932634.951
[6 empty] | 9332 | 189274.6246 | 9332 | 0
[6 empty] | 9333 | 0 | 9333 | 0
[6 empty] | 9334 | 0 | 9334 | 0
[6 empty] | 9335 | 2612524.2097 | 9335 | 2612524.2097
[6 empty] | 9336 | 2710591.0591 | 9336 | 2710591.0591
[6 empty] | 9337 | 2027436.6684 | 9337 | 0
[6 empty] | 9338 | 1053515.0216 | 9338 | 294172.0858
[6 empty] | 9339 | 0 | 9339 | 0
[6 empty] | 9340 | 0 | 9340 | 0
[6 empty] | 9341 | 0 | 9341 | 0
[6 empty] | 9342 | 0 | 9342 | 0
[6 empty] | 9343 | 0 | 9343 | 0
[6 empty] | 9344 | 0 | 9344 | 0
[6 empty] | 9345 | 0 | 9345 | 0
[6 empty] | 9346 | 290909.7342 | 9346 | 290909.7342
[6 empty] | 9347 | 0 | 9347 | 0
[6 empty] | 9348 | 288563.32 | 9348 | 288563.32
[6 empty] | 9349 | 159891.778 | 9349 | 159891.778
[6 empty] | 9350 | 7962560.2353 | 9350 | 0
[6 empty] | 9351 | 0 | 9351 | 0
[6 empty] | 9352 | 0 | 9352 | 0
[6 empty] | 9353 | 483544.2416 | 9353 | 291238.5483
[6 empty] | 9354 | 0 | 9354 | 0
[6 empty] | 9355 | 0 | 9355 | 0
[6 empty] | 9356 | 8516118.6983 | 9356 | 0
[6 empty] | 9357 | 258623.3274 | 9357 | 258623.3274
[6 empty] | 9358 | 0 | 9358 | 0
[6 empty] | 9359 | 0 | 9359 | 0
[6 empty] | 9360 | 1264681.8085 | 9360 | 1264681.8085
[6 empty] | 9361 | 3593640.1607 | 9361 | 0
[6 empty] | 9362 | 0 | 9362 | 0
[6 empty] | 9363 | 2414073.1056 | 9363 | 0
[6 empty] | 9364 | 390947.7477 | 9364 | 390947.7477
[6 empty] | 9365 | 0 | 9365 | 0
[6 empty] | 9366 | 0 | 9366 | 0
[6 empty] | 9367 | 410827.6132 | 9367 | 410827.6132
[6 empty] | 9368 | 0 | 9368 | 0
[6 empty] | 9369 | 0 | 9369 | 0
[6 empty] | 9370 | 222411.7633 | 9370 | 0
[6 empty] | 9371 | 0 | 9371 | 0
[6 empty] | 9372 | 2932958.6518 | 9372 | 2932958.6518
[6 empty] | 9373 | 0 | 9373 | 0
[6 empty] | 9374 | 0 | 9374 | 0
[6 empty] | 9375 | 1090401.4632 | 9375 | 226462.5126
[6 empty] | 9376 | 3796004.9403 | 9376 | 3796004.9403
[6 empty] | 9377 | 278600.8642 | 9377 | 0
[6 empty] | 9378 | 370384.7999 | 9378 | 370384.7999
[6 empty] | 9379 | 0 | 9379 | 0
[6 empty] | 9380 | 0 | 9380 | 0
[6 empty] | 9381 | 0 | 9381 | 0
[6 empty] | 9382 | 0 | 9382 | 0
[6 empty] | 9383 | 3571583.3537 | 9383 | 440466.7991
[6 empty] | 9384 | 0 | 9384 | 0
[6 empty] | 9385 | 0 | 9385 | 0
[6 empty] | 9386 | 0 | 9386 | 0
[6 empty] | 9387 | 223637.3892 | 9387 | 223637.3892
[6 empty] | 9388 | 206861.2295 | 9388 | 206861.2295
[6 empty] | 9389 | 0 | 9389 | 0
[6 empty] | 9390 | 0 | 9390 | 0
[6 empty] | 9391 | 3424926.1211 | 9391 | 3424926.1211
[6 empty] | 9392 | 0 | 9392 | 0
[6 empty] | 9393 | 0 | 9393 | 0
[6 empty] | 9394 | 0 | 9394 | 0
[6 empty] | 9395 | 0 | 9395 | 0
[6 empty] | 9396 | 0 | 9396 | 0
[6 empty] | 9397 | 0 | 9397 | 0
[6 empty] | 9398 | 3208814.8038 | 9398 | 112926.5907
[6 empty] | 9399 | 218022.0113 | 9399 | 218022.0113
[6 empty] | 9400 | 0 | 9400 | 0
[6 empty] | 9401 | 343996.6562 | 9401 | 343996.6562
[6 empty] | 9402 | 0 | 9402 | 0
[6 empty] | 9403 | 3211433.5279 | 9403 | 0
[6 empty] | 9404 | 0 | 9404 | 0
[6 empty] | 9405 | 2459781.7169 | 9405 | 1388022.7614
[6 empty] | 9406 | 342044.3769 | 9406 | 342044.3769
[6 empty] | 9407 | 0 | 9407 | 0
[6 empty] | 9408 | 0 | 9408 | 0
[6 empty] | 9409 | 337897.5624 | 9409 | 0
[6 empty] | 9410 | 870611.7971 | 9410 | 0
[6 empty] | 9411 | 0 | 9411 | 0
[6 empty] | 9412 | 0 | 9412 | 0
[6 empty] | 9413 | 0 | 9413 | 0
[6 empty] | 9414 | 1448293.9664 | 9414 | 1448293.9664
[6 empty] | 9415 | 5203479.0331 | 9415 | 0
[6 empty] | 9416 | 0 | 9416 | 0
[6 empty] | 9417 | 0 | 9417 | 0
[6 empty] | 9418 | 0 | 9418 | 0
[6 empty] | 9419 | 0 | 9419 | 0
[6 empty] | 9420 | 0 | 9420 | 0
[6 empty] | 9421 | 0 | 9421 | 0
[6 empty] | 9422 | 0 | 9422 | 0
[6 empty] | 9423 | 12656780.8316 | 9423 | 0
[6 empty] | 9424 | 146622.4828 | 9424 | 146622.4828
[6 empty] | 9425 | 388119.2283 | 9425 | 388119.2283
[6 empty] | 9426 | 573895.414 | 9426 | 0
[6 empty] | 9427 | 2790672.8621 | 9427 | 404095.9524
[6 empty] | 9428 | 3789957.1684 | 9428 | 0
[6 empty] | 9429 | 0 | 9429 | 0
[6 empty] | 9430 | 1372239.8992 | 9430 | 0
[6 empty] | 9431 | 2309821.6513 | 9431 | 0
[6 empty] | 9432 | 4220885.7088 | 9432 | 4220885.7088
[6 empty] | 9433 | 9453563.5158 | 9433 | 9453563.5158
[6 empty] | 9434 | 154871.3886 | 9434 | 154871.3886
[6 empty] | 9435 | 0 | 9435 | 0
[6 empty] | 9436 | 388365.6083 | 9436 | 388365.6083
[6 empty] | 9437 | 1694226.5309 | 9437 | 1694226.5309
[6 empty] | 9438 | 252312.174 | 9438 | 252312.174
[6 empty] | 9439 | 2413278.2064 | 9439 | 0
[6 empty] | 9440 | 3123725.3838 | 9440 | 0
[6 empty] | 9441 | 1669711.4536 | 9441 | 0
[6 empty] | 9442 | 3410858.695 | 9442 | 3410858.695
[6 empty] | 9443 | 216516.6589 | 9443 | 216516.6589
[6 empty] | 9444 | 1927252.462 | 9444 | 0
[6 empty] | 9445 | 0 | 9445 | 0
[6 empty] | 9446 | 0 | 9446 | 0
[6 empty] | 9447 | 15520741.4283 | 9447 | 0
[6 empty] | 9448 | 247991.4451 | 9448 | 247991.4451
[6 empty] | 9449 | 202547.8668 | 9449 | 0
[6 empty] | 9450 | 0 | 9450 | 0
[6 empty] | 9451 | 0 | 9451 | 0
[6 empty] | 9452 | 416065.5188 | 9452 | 0
[6 empty] | 9453 | 0 | 9453 | 0
[6 empty] | 9454 | 687629.8942 | 9454 | 687629.8942
[6 empty] | 9455 | 24769.4835 | 9455 | 24769.4835
[6 empty] | 9456 | 1278680.1577 | 9456 | 1278680.1577
[6 empty] | 9457 | 3156853.3309 | 9457 | 0
[6 empty] | 9458 | 0 | 9458 | 0
[6 empty] | 9459 | 0 | 9459 | 0
[6 empty] | 9460 | 840578.8946 | 9460 | 840578.8946
[6 empty] | 9461 | 3593421.0562 | 9461 | 0
[6 empty] | 9462 | 344835.4833 | 9462 | 344835.4833
[6 empty] | 9463 | 0 | 9463 | 0
[6 empty] | 9464 | 3224932.9974 | 9464 | 0
[6 empty] | 9465 | 0 | 9465 | 0
[6 empty] | 9466 | 0 | 9466 | 0
[6 empty] | 9467 | 0 | 9467 | 0
[6 empty] | 9468 | 0 | 9468 | 0
[6 empty] | 9469 | 0 | 9469 | 0
[6 empty] | 9470 | 228634.8901 | 9470 | 228634.8901
[6 empty] | 9471 | 139043.6104 | 9471 | 0
[6 empty] | 9472 | 2411016.2636 | 9472 | 167933.4584
[6 empty] | 9473 | 0 | 9473 | 0
[6 empty] | 9474 | 0 | 9474 | 0
[6 empty] | 9475 | 210559.2983 | 9475 | 0
[6 empty] | 9476 | 230125.9111 | 9476 | 230125.9111
[6 empty] | 9477 | 0 | 9477 | 0
[6 empty] | 9478 | 3454352.6291 | 9478 | 3454352.6291
[6 empty] | 9479 | 0 | 9479 | 0
[6 empty] | 9480 | 0 | 9480 | 0
[6 empty] | 9481 | 0 | 9481 | 0
[6 empty] | 9482 | 128098.9683 | 9482 | 128098.9683
[6 empty] | 9483 | 0 | 9483 | 0
[6 empty] | 9484 | 507347.7133 | 9484 | 0
[6 empty] | 9485 | 0 | 9485 | 0
[6 empty] | 9486 | 454693.1161 | 9486 | 454693.1161
[6 empty] | 9487 | 4291384.4494 | 9487 | 1548859.6216
[6 empty] | 9488 | 0 | 9488 | 0
[6 empty] | 9489 | 0 | 9489 | 0
[6 empty] | 9490 | 0 | 9490 | 0
[6 empty] | 9491 | 2506440.1467 | 9491 | 2506440.1467
[6 empty] | 9492 | 0 | 9492 | 0
[6 empty] | 9493 | 0 | 9493 | 0
[6 empty] | 9494 | 4534462.4646 | 9494 | 4379675.5136
[6 empty] | 9495 | 240902.3866 | 9495 | 0
[6 empty] | 9496 | 0 | 9496 | 0
[6 empty] | 9497 | 873508.7194 | 9497 | 352887.753
[6 empty] | 9498 | 3954645.5585 | 9498 | 0
[6 empty] | 9499 | 0 | 9499 | 0
[6 empty] | 9500 | 0 | 9500 | 0
[6 empty] | 9501 | 0 | 9501 | 0
[6 empty] | 9502 | 0 | 9502 | 0
[6 empty] | 9503 | 3068043.3026 | 9503 | 3068043.3026
[6 empty] | 9504 | 1544830.5727 | 9504 | 0
[6 empty] | 9505 | 155033.823 | 9505 | 0
[6 empty] | 9506 | 0 | 9506 | 0
[6 empty] | 9507 | 411921.0736 | 9507 | 411921.0736
[6 empty] | 9508 | 0 | 9508 | 0
[6 empty] | 9509 | 783138.7066 | 9509 | 783138.7066
[6 empty] | 9510 | 1323394.7513 | 9510 | 163408.7478
[6 empty] | 9511 | 745162.3665 | 9511 | 745162.3665
[6 empty] | 9512 | 2336712.1019 | 9512 | 0
[6 empty] | 9513 | 13683228.807 | 9513 | 0
[6 empty] | 9514 | 0 | 9514 | 0
[6 empty] | 9515 | 765384.2192 | 9515 | 765384.2192
[6 empty] | 9516 | 0 | 9516 | 0
[6 empty] | 9517 | 260410.6868 | 9517 | 260410.6868
[6 empty] | 9518 | 0 | 9518 | 0
[6 empty] | 9519 | 0 | 9519 | 0
[6 empty] | 9520 | 1086125.5192 | 9520 | 171327.8504
[6 empty] | 9521 | 873452.1727 | 9521 | 873452.1727
[6 empty] | 9522 | 297215.504 | 9522 | 297215.504
[6 empty] | 9523 | 0 | 9523 | 0
[6 empty] | 9524 | 311556.4423 | 9524 | 0
[6 empty] | 9525 | 0 | 9525 | 0
[6 empty] | 9526 | 3406411.7963 | 9526 | 3406411.7963
[6 empty] | 9527 | 0 | 9527 | 0
[6 empty] | 9528 | 0 | 9528 | 0
[6 empty] | 9529 | 0 | 9529 | 0
[6 empty] | 9530 | 0 | 9530 | 0
[6 empty] | 9531 | 441675.5122 | 9531 | 441675.5122
[6 empty] | 9532 | 0 | 9532 | 0
[6 empty] | 9533 | 199799.413 | 9533 | 199799.413
[6 empty] | 9534 | 323471.4858 | 9534 | 323471.4858
[6 empty] | 9535 | 7355517.8869 | 9535 | 7355517.8869
[6 empty] | 9536 | 0 | 9536 | 0
[6 empty] | 9537 | 0 | 9537 | 0
[6 empty] | 9538 | 3112836.3294 | 9538 | 3112836.3294
[6 empty] | 9539 | 0 | 9539 | 0
[6 empty] | 9540 | 526973.3022 | 9540 | 526973.3022
[6 empty] | 9541 | 4943066.8652 | 9541 | 68753.1292
[6 empty] | 9542 | 0 | 9542 | 0
[6 empty] | 9543 | 182146.7785 | 9543 | 0
[6 empty] | 9544 | 0 | 9544 | 0
[6 empty] | 9545 | 0 | 9545 | 0
[6 empty] | 9546 | 140052.7523 | 9546 | 140052.7523
[6 empty] | 9547 | 3701344.6285 | 9547 | 0
[6 empty] | 9548 | 194824.7214 | 9548 | 0
[6 empty] | 9549 | 0 | 9549 | 0
[6 empty] | 9550 | 1235310.255 | 9550 | 1235310.255
[6 empty] | 9551 | 0 | 9551 | 0
[6 empty] | 9552 | 0 | 9552 | 0
[6 empty] | 9553 | 210715.0491 | 9553 | 210715.0491
[6 empty] | 9554 | 0 | 9554 | 0
[6 empty] | 9555 | 0 | 9555 | 0
[6 empty] | 9556 | 3257248.9099 | 9556 | 3257248.9099
[6 empty] | 9557 | 0 | 9557 | 0
[6 empty] | 9558 | 2354991.8461 | 9558 | 0
[6 empty] | 9559 | 0 | 9559 | 0
[6 empty] | 9560 | 106882.6341 | 9560 | 106882.6341
[6 empty] | 9561 | 0 | 9561 | 0
[6 empty] | 9562 | 4006411.5876 | 9562 | 291028.3378
[6 empty] | 9563 | 0 | 9563 | 0
[6 empty] | 9564 | 2441268.9094 | 9564 | 2441268.9094
[6 empty] | 9565 | 3287868.3361 | 9565 | 3287868.3361
[6 empty] | 9566 | 0 | 9566 | 0
[6 empty] | 9567 | 2129623.7282 | 9567 | 2129623.7282
[6 empty] | 9568 | 0 | 9568 | 0
[6 empty] | 9569 | 2755628.5902 | 9569 | 2403922.5121
[6 empty] | 9570 | 552545.2957 | 9570 | 552545.2957
[6 empty] | 9571 | 0 | 9571 | 0
[6 empty] | 9572 | 239722.0487 | 9572 | 239722.0487
[6 empty] | 9573 | 257709.5282 | 9573 | 0
[6 empty] | 9574 | 160227.2125 | 9574 | 160227.2125
[6 empty] | 9575 | 152293.6098 | 9575 | 152293.6098
[6 empty] | 9576 | 2699470.6126 | 9576 | 545818.7644
[6 empty] | 9577 | 0 | 9577 | 0
[6 empty] | 9578 | 2379704.9487 | 9578 | 0
[6 empty] | 9579 | 3429951.2765 | 9579 | 3429951.2765
[6 empty] | 9580 | 0 | 9580 | 0
[6 empty] | 9581 | 0 | 9581 | 0
[6 empty] | 9582 | 279007.9563 | 9582 | 0
[6 empty] | 9583 | 0 | 9583 | 0
[6 empty] | 9584 | 0 | 9584 | 0
[6 empty] | 9585 | 5036968.7673 | 9585 | 2394569.2619
[6 empty] | 9586 | 152825.2853 | 9586 | 152825.2853
[6 empty] | 9587 | 987094.366 | 9587 | 0
[6 empty] | 9588 | 2956605.0251 | 9588 | 0
[6 empty] | 9589 | 8324926.7258 | 9589 | 0
[6 empty] | 9590 | 0 | 9590 | 0
[6 empty] | 9591 | 671579.152 | 9591 | 0
[6 empty] | 9592 | 0 | 9592 | 0
[6 empty] | 9593 | 0 | 9593 | 0
[6 empty] | 9594 | 0 | 9594 | 0
[6 empty] | 9595 | 0 | 9595 | 0
[6 empty] | 9596 | 0 | 9596 | 0
[6 empty] | 9597 | 2306001.1509 | 9597 | 2306001.1509
[6 empty] | 9598 | 0 | 9598 | 0
[6 empty] | 9599 | 222578.4796 | 9599 | 0
[6 empty] | 9600 | 0 | 9600 | 0
[6 empty] | 9601 | 0 | 9601 | 0
[6 empty] | 9602 | 0 | 9602 | 0
[6 empty] | 9603 | 0 | 9603 | 0
[6 empty] | 9604 | 3767846.4057 | 9604 | 698521.8665
[6 empty] | 9605 | 536558.1608 | 9605 | 338660.8338
[6 empty] | 9606 | 191107.0296 | 9606 | 191107.0296
[6 empty] | 9607 | 0 | 9607 | 0
[6 empty] | 9608 | 0 | 9608 | 0
[6 empty] | 9609 | 10459345.9574 | 9609 | 0
[6 empty] | 9610 | 4491383.4168 | 9610 | 201782.2197
[6 empty] | 9611 | 247321.6709 | 9611 | 247321.6709
[6 empty] | 9612 | 0 | 9612 | 0
[6 empty] | 9613 | 0 | 9613 | 0
[6 empty] | 9614 | 3565316.1883 | 9614 | 0
[6 empty] | 9615 | 0 | 9615 | 0
[6 empty] | 9616 | 14796133.2574 | 9616 | 582461.2326
[6 empty] | 9617 | 199928.0369 | 9617 | 199928.0369
[6 empty] | 9618 | 863186.0632 | 9618 | 863186.0632
[6 empty] | 9619 | 35860620.2636 | 9619 | 0
[6 empty] | 9620 | 703911.6634 | 9620 | 703911.6634
[6 empty] | 9621 | 2375718.3715 | 9621 | 949468.8534
[6 empty] | 9622 | 0 | 9622 | 0
[6 empty] | 9623 | 0 | 9623 | 0
[6 empty] | 9624 | 2153360.6934 | 9624 | 0
[6 empty] | 9625 | 259922.7196 | 9625 | 0
[6 empty] | 9626 | 395358.3233 | 9626 | 156754.5815
[6 empty] | 9627 | 243360.394 | 9627 | 0
[6 empty] | 9628 | 320343.3679 | 9628 | 320343.3679
[6 empty] | 9629 | 198607.4088 | 9629 | 0
[6 empty] | 9630 | 0 | 9630 | 0
[6 empty] | 9631 | 0 | 9631 | 0
[6 empty] | 9632 | 2770818.4748 | 9632 | 2770818.4748
[6 empty] | 9633 | 0 | 9633 | 0
[6 empty] | 9634 | 0 | 9634 | 0
[6 empty] | 9635 | 226349.2947 | 9635 | 0
[6 empty] | 9636 | 0 | 9636 | 0
[6 empty] | 9637 | 0 | 9637 | 0
[6 empty] | 9638 | 0 | 9638 | 0
[6 empty] | 9639 | 0 | 9639 | 0
[6 empty] | 9640 | 0 | 9640 | 0
[6 empty] | 9641 | 0 | 9641 | 0
[6 empty] | 9642 | 3430993.3936 | 9642 | 3430993.3936
[6 empty] | 9643 | 0 | 9643 | 0
[6 empty] | 9644 | 0 | 9644 | 0
[6 empty] | 9645 | 192958.1503 | 9645 | 192958.1503
[6 empty] | 9646 | 0 | 9646 | 0
[6 empty] | 9647 | 2900603.0558 | 9647 | 372091.9765
[6 empty] | 9648 | 1086453.6646 | 9648 | 1086453.6646
[6 empty] | 9649 | 0 | 9649 | 0
[6 empty] | 9650 | 0 | 9650 | 0
[6 empty] | 9651 | 1551024.8804 | 9651 | 1551024.8804
[6 empty] | 9652 | 0 | 9652 | 0
[6 empty] | 9653 | 0 | 9653 | 0
[6 empty] | 9654 | 0 | 9654 | 0
[6 empty] | 9655 | 247967.8576 | 9655 | 247967.8576
[6 empty] | 9656 | 0 | 9656 | 0
[6 empty] | 9657 | 2016421.4419 | 9657 | 2016421.4419
[6 empty] | 9658 | 2735591.2423 | 9658 | 0
[6 empty] | 9659 | 0 | 9659 | 0
[6 empty] | 9660 | 183068.2514 | 9660 | 183068.2514
[6 empty] | 9661 | 509447.0288 | 9661 | 509447.0288
[6 empty] | 9662 | 0 | 9662 | 0
[6 empty] | 9663 | 0 | 9663 | 0
[6 empty] | 9664 | 0 | 9664 | 0
[6 empty] | 9665 | 0 | 9665 | 0
[6 empty] | 9666 | 4732181.5446 | 9666 | 3529580.6379
[6 empty] | 9667 | 220193.4971 | 9667 | 220193.4971
[6 empty] | 9668 | 3672987.5195 | 9668 | 3672987.5195
[6 empty] | 9669 | 2513608.8852 | 9669 | 2513608.8852
[6 empty] | 9670 | 2648730.0352 | 9670 | 2326525.3054
[6 empty] | 9671 | 0 | 9671 | 0
[6 empty] | 9672 | 409106.3126 | 9672 | 409106.3126
[6 empty] | 9673 | 501936.6039 | 9673 | 501936.6039
[6 empty] | 9674 | 0 | 9674 | 0
[6 empty] | 9675 | 0 | 9675 | 0
[6 empty] | 9676 | 3767600.0915 | 9676 | 3767600.0915
[6 empty] | 9677 | 0 | 9677 | 0
[6 empty] | 9678 | 5845971.5508 | 9678 | 5584756.4718
[6 empty] | 9679 | 678846.9468 | 9679 | 678846.9468
[6 empty] | 9680 | 108136.1835 | 9680 | 108136.1835
[6 empty] | 9681 | 0 | 9681 | 0
[6 empty] | 9682 | 172231.3324 | 9682 | 172231.3324
[6 empty] | 9683 | 0 | 9683 | 0
[6 empty] | 9684 | 342497.3016 | 9684 | 342497.3016
[6 empty] | 9685 | 0 | 9685 | 0
[6 empty] | 9686 | 262979.9994 | 9686 | 262979.9994
[6 empty] | 9687 | 235389.6886 | 9687 | 235389.6886
[6 empty] | 9688 | 3511201.0547 | 9688 | 3511201.0547
[6 empty] | 9689 | 8023861.6466 | 9689 | 3756721.9895
[6 empty] | 9690 | 0 | 9690 | 0
[6 empty] | 9691 | 0 | 9691 | 0
[6 empty] | 9692 | 0 | 9692 | 0
[6 empty] | 9693 | 0 | 9693 | 0
[6 empty] | 9694 | 0 | 9694 | 0
[6 empty] | 9695 | 466080.4045 | 9695 | 466080.4045
[6 empty] | 9696 | 8083132.1558 | 9696 | 8083132.1558
[6 empty] | 9697 | 563539.9724 | 9697 | 563539.9724
[6 empty] | 9698 | 0 | 9698 | 0
[6 empty] | 9699 | 3067472.1654 | 9699 | 0
[6 empty] | 9700 | 0 | 9700 | 0
[6 empty] | 9701 | 0 | 9701 | 0
[6 empty] | 9702 | 1685597.9626 | 9702 | 439139.6694
[6 empty] | 9703 | 194667.1175 | 9703 | 194667.1175
[6 empty] | 9704 | 0 | 9704 | 0
[6 empty] | 9705 | 1916751.7675 | 9705 | 88465.4024
[6 empty] | 9706 | 0 | 9706 | 0
[6 empty] | 9707 | 0 | 9707 | 0
[6 empty] | 9708 | 5700922.4799 | 9708 | 0
[6 empty] | 9709 | 0 | 9709 | 0
[6 empty] | 9710 | 1464419.2963 | 9710 | 1464419.2963
[6 empty] | 9711 | 997571.1622 | 9711 | 997571.1622
[6 empty] | 9712 | 453558.3129 | 9712 | 453558.3129
[6 empty] | 9713 | 2073735.4935 | 9713 | 2073735.4935
[6 empty] | 9714 | 3098389.5965 | 9714 | 158909.0646
[6 empty] | 9715 | 0 | 9715 | 0
[6 empty] | 9716 | 5949672.2069 | 9716 | 5949672.2069
[6 empty] | 9717 | 210747.781 | 9717 | 0
[6 empty] | 9718 | 0 | 9718 | 0
[6 empty] | 9719 | 162870.4229 | 9719 | 162870.4229
[6 empty] | 9720 | 0 | 9720 | 0
[6 empty] | 9721 | 4413425.0168 | 9721 | 296735.8524
[6 empty] | 9722 | 0 | 9722 | 0
[6 empty] | 9723 | 0 | 9723 | 0
[6 empty] | 9724 | 0 | 9724 | 0
[6 empty] | 9725 | 254766.3908 | 9725 | 254766.3908
[6 empty] | 9726 | 0 | 9726 | 0
[6 empty] | 9727 | 933983.7831 | 9727 | 933983.7831
[6 empty] | 9728 | 0 | 9728 | 0
[6 empty] | 9729 | 0 | 9729 | 0
[6 empty] | 9730 | 3971196.9815 | 9730 | 3971196.9815
[6 empty] | 9731 | 0 | 9731 | 0
[6 empty] | 9732 | 1555118.7751 | 9732 | 0
[6 empty] | 9733 | 171861.7192 | 9733 | 171861.7192
[6 empty] | 9734 | 3525657.5326 | 9734 | 297357.8688
[6 empty] | 9735 | 0 | 9735 | 0
[6 empty] | 9736 | 0 | 9736 | 0
[6 empty] | 9737 | 8374051.6914 | 9737 | 5866553.1477
[6 empty] | 9738 | 0 | 9738 | 0
[6 empty] | 9739 | 242719.7548 | 9739 | 0
[6 empty] | 9740 | 0 | 9740 | 0
[6 empty] | 9741 | 234986.2765 | 9741 | 234986.2765
[6 empty] | 9742 | 0 | 9742 | 0
[6 empty] | 9743 | 651691.047 | 9743 | 651691.047
[6 empty] | 9744 | 215045.8074 | 9744 | 0
[6 empty] | 9745 | 0 | 9745 | 0
[6 empty] | 9746 | 0 | 9746 | 0
[6 empty] | 9747 | 0 | 9747 | 0
[6 empty] | 9748 | 303944.8816 | 9748 | 303944.8816
[6 empty] | 9749 | 184287.9861 | 9749 | 184287.9861
[6 empty] | 9750 | 1902856.0704 | 9750 | 1902856.0704
[6 empty] | 9751 | 160881.5528 | 9751 | 160881.5528
[6 empty] | 9752 | 0 | 9752 | 0
[6 empty] | 9753 | 0 | 9753 | 0
[6 empty] | 9754 | 489058.4974 | 9754 | 489058.4974
[6 empty] | 9755 | 970566.2327 | 9755 | 970566.2327
[6 empty] | 9756 | 165722.2248 | 9756 | 165722.2248
[6 empty] | 9757 | 1474071.563 | 9757 | 1474071.563
[6 empty] | 9758 | 0 | 9758 | 0
[6 empty] | 9759 | 892118.8275 | 9759 | 892118.8275
[6 empty] | 9760 | 331533.6587 | 9760 | 174470.9189
[6 empty] | 9761 | 0 | 9761 | 0
[6 empty] | 9762 | 2703455.8621 | 9762 | 2703455.8621
[6 empty] | 9763 | 0 | 9763 | 0
[6 empty] | 9764 | 154823.1695 | 9764 | 154823.1695
[6 empty] | 9765 | 0 | 9765 | 0
[6 empty] | 9766 | 0 | 9766 | 0
[6 empty] | 9767 | 0 | 9767 | 0
[6 empty] | 9768 | 0 | 9768 | 0
[6 empty] | 9769 | 2977774.2376 | 9769 | 0
[6 empty] | 9770 | 2023659.612 | 9770 | 0
[6 empty] | 9771 | 0 | 9771 | 0
[6 empty] | 9772 | 1856953.1965 | 9772 | 0
[6 empty] | 9773 | 0 | 9773 | 0
[6 empty] | 9774 | 853083.7174 | 9774 | 0
[6 empty] | 9775 | 1767245.2639 | 9775 | 395506.4857
[6 empty] | 9776 | 8820866.152 | 9776 | 453579.6823
[6 empty] | 9777 | 4711971.5742 | 9777 | 4711971.5742
[6 empty] | 9778 | 194461.451 | 9778 | 194461.451
[6 empty] | 9779 | 521472.5027 | 9779 | 349340.4167
[6 empty] | 9780 | 0 | 9780 | 0
[6 empty] | 9781 | 0 | 9781 | 0
[6 empty] | 9782 | 2347351.6627 | 9782 | 2347351.6627
[6 empty] | 9783 | 0 | 9783 | 0
[6 empty] | 9784 | 0 | 9784 | 0
[6 empty] | 9785 | 0 | 9785 | 0
[6 empty] | 9786 | 0 | 9786 | 0
[6 empty] | 9787 | 0 | 9787 | 0
[6 empty] | 9788 | 3564301.5801 | 9788 | 0
[6 empty] | 9789 | 4264527.583 | 9789 | 0
[6 empty] | 9790 | 2622483.1826 | 9790 | 0
[6 empty] | 9791 | 0 | 9791 | 0
[6 empty] | 9792 | 0 | 9792 | 0
[6 empty] | 9793 | 0 | 9793 | 0
[6 empty] | 9794 | 3512866.1659 | 9794 | 3512866.1659
[6 empty] | 9795 | 0 | 9795 | 0
[6 empty] | 9796 | 0 | 9796 | 0
[6 empty] | 9797 | 2839220.0001 | 9797 | 0
[6 empty] | 9798 | 180121.0055 | 9798 | 180121.0055
[6 empty] | 9799 | 0 | 9799 | 0
[6 empty] | 9800 | 169191.4409 | 9800 | 169191.4409
[6 empty] | 9801 | 0 | 9801 | 0
[6 empty] | 9802 | 179349.7748 | 9802 | 0
[6 empty] | 9803 | 2034997.2771 | 9803 | 0
[6 empty] | 9804 | 0 | 9804 | 0
[6 empty] | 9805 | 0 | 9805 | 0
[6 empty] | 9806 | 0 | 9806 | 0
[6 empty] | 9807 | 3570287.9609 | 9807 | 0
[6 empty] | 9808 | 0 | 9808 | 0
[6 empty] | 9809 | 0 | 9809 | 0
[6 empty] | 9810 | 0 | 9810 | 0
[6 empty] | 9811 | 3233662.1708 | 9811 | 3233662.1708
[6 empty] | 9812 | 0 | 9812 | 0
[6 empty] | 9813 | 0 | 9813 | 0
[6 empty] | 9814 | 774156.7088 | 9814 | 137852.5047
[6 empty] | 9815 | 0 | 9815 | 0
[6 empty] | 9816 | 0 | 9816 | 0
[6 empty] | 9817 | 2674638.4466 | 9817 | 2674638.4466
[6 empty] | 9818 | 0 | 9818 | 0
[6 empty] | 9819 | 277525.8057 | 9819 | 277525.8057
[6 empty] | 9820 | 1130999.3319 | 9820 | 1130999.3319
[6 empty] | 9821 | 172518.8449 | 9821 | 172518.8449
[6 empty] | 9822 | 0 | 9822 | 0
[6 empty] | 9823 | 2048971.7843 | 9823 | 2048971.7843
[6 empty] | 9824 | 0 | 9824 | 0
[6 empty] | 9825 | 0 | 9825 | 0
[6 empty] | 9826 | 217273.8316 | 9826 | 217273.8316
[6 empty] | 9827 | 3744067.8472 | 9827 | 3744067.8472
[6 empty] | 9828 | 0 | 9828 | 0
[6 empty] | 9829 | 0 | 9829 | 0
[6 empty] | 9830 | 0 | 9830 | 0
[6 empty] | 9831 | 0 | 9831 | 0
[6 empty] | 9832 | 168567.742 | 9832 | 168567.742
[6 empty] | 9833 | 1441101.7529 | 9833 | 0
[6 empty] | 9834 | 0 | 9834 | 0
[6 empty] | 9835 | 454952.8669 | 9835 | 268317.7308
[6 empty] | 9836 | 0 | 9836 | 0
[6 empty] | 9837 | 1844717.3707 | 9837 | 0
[6 empty] | 9838 | 1250268.7156 | 9838 | 0
[6 empty] | 9839 | 2290682.6415 | 9839 | 2290682.6415
[6 empty] | 9840 | 0 | 9840 | 0
[6 empty] | 9841 | 1105328.249 | 9841 | 1105328.249
[6 empty] | 9842 | 0 | 9842 | 0
[6 empty] | 9843 | 0 | 9843 | 0
[6 empty] | 9844 | 0 | 9844 | 0
[6 empty] | 9845 | 0 | 9845 | 0
[6 empty] | 9846 | 0 | 9846 | 0
[6 empty] | 9847 | 0 | 9847 | 0
[6 empty] | 9848 | 0 | 9848 | 0
[6 empty] | 9849 | 375757.638 | 9849 | 375757.638
[6 empty] | 9850 | 3107718.0802 | 9850 | 3107718.0802
[6 empty] | 9851 | 1039467.1769 | 9851 | 1039467.1769
[6 empty] | 9852 | 0 | 9852 | 0
[6 empty] | 9853 | 137674.3588 | 9853 | 0
[6 empty] | 9854 | 0 | 9854 | 0
[6 empty] | 9855 | 0 | 9855 | 0
[6 empty] | 9856 | 0 | 9856 | 0
[6 empty] | 9857 | 0 | 9857 | 0
[6 empty] | 9858 | 3998903.5268 | 9858 | 699369.4513
[6 empty] | 9859 | 0 | 9859 | 0
[6 empty] | 9860 | 0 | 9860 | 0
[6 empty] | 9861 | 331616.5296 | 9861 | 331616.5296
[6 empty] | 9862 | 0 | 9862 | 0
[6 empty] | 9863 | 2556369.6833 | 9863 | 0
[6 empty] | 9864 | 0 | 9864 | 0
[6 empty] | 9865 | 0 | 9865 | 0
[6 empty] | 9866 | 0 | 9866 | 0
[6 empty] | 9867 | 10203041.6076 | 9867 | 0
[6 empty] | 9868 | 3947346.1433 | 9868 | 1950075.8337
[6 empty] | 9869 | 0 | 9869 | 0
[6 empty] | 9870 | 0 | 9870 | 0
[6 empty] | 9871 | 0 | 9871 | 0
[6 empty] | 9872 | 0 | 9872 | 0
[6 empty] | 9873 | 0 | 9873 | 0
[6 empty] | 9874 | 3248626.1688 | 9874 | 3022293.7431
[6 empty] | 9875 | 28542072.3641 | 9875 | 0
[6 empty] | 9876 | 389241.1236 | 9876 | 389241.1236
[6 empty] | 9877 | 319539.7978 | 9877 | 319539.7978
[6 empty] | 9878 | 0 | 9878 | 0
[6 empty] | 9879 | 0 | 9879 | 0
[6 empty] | 9880 | 355077.6152 | 9880 | 355077.6152
[6 empty] | 9881 | 0 | 9881 | 0
[6 empty] | 9882 | 0 | 9882 | 0
[6 empty] | 9883 | 0 | 9883 | 0
[6 empty] | 9884 | 3814492.2807 | 9884 | 3814492.2807
[6 empty] | 9885 | 2457475.3848 | 9885 | 2457475.3848
[6 empty] | 9886 | 575523.3987 | 9886 | 575523.3987
[6 empty] | 9887 | 591503.4066 | 9887 | 591503.4066
[6 empty] | 9888 | 121883.4327 | 9888 | 121883.4327
[6 empty] | 9889 | 0 | 9889 | 0
[6 empty] | 9890 | 0 | 9890 | 0
[6 empty] | 9891 | 0 | 9891 | 0
[6 empty] | 9892 | 341848.9392 | 9892 | 341848.9392
[6 empty] | 9893 | 0 | 9893 | 0
[6 empty] | 9894 | 3463979.2501 | 9894 | 3463979.2501
[6 empty] | 9895 | 0 | 9895 | 0
[6 empty] | 9896 | 972318.819 | 9896 | 972318.819
[6 empty] | 9897 | 179565.3386 | 9897 | 179565.3386
[6 empty] | 9898 | 268457.2153 | 9898 | 268457.2153
[6 empty] | 9899 | 12052970.64 | 9899 | 0
[6 empty] | 9900 | 3642940.255 | 9900 | 218292.596
[6 empty] | 9901 | 331016.4962 | 9901 | 331016.4962
[6 empty] | 9902 | 3174952.8942 | 9902 | 3174952.8942
[6 empty] | 9903 | 0 | 9903 | 0
[6 empty] | 9904 | 3925522.6936 | 9904 | 3925522.6936
[6 empty] | 9905 | 2512913.0872 | 9905 | 2512913.0872
[6 empty] | 9906 | 0 | 9906 | 0
[6 empty] | 9907 | 3847470.9253 | 9907 | 3847470.9253
[6 empty] | 9908 | 0 | 9908 | 0
[6 empty] | 9909 | 0 | 9909 | 0
[6 empty] | 9910 | 226123.1561 | 9910 | 226123.1561
[6 empty] | 9911 | 0 | 9911 | 0
[6 empty] | 9912 | 624610.5742 | 9912 | 624610.5742
[6 empty] | 9913 | 0 | 9913 | 0
[6 empty] | 9914 | 191307.793 | 9914 | 191307.793
[6 empty] | 9915 | 0 | 9915 | 0
[6 empty] | 9916 | 0 | 9916 | 0
[6 empty] | 9917 | 2279817.3449 | 9917 | 0
[6 empty] | 9918 | 11847535.9094 | 9918 | 11847535.9094
[6 empty] | 9919 | 0 | 9919 | 0
[6 empty] | 9920 | 1374198.8095 | 9920 | 1374198.8095
[6 empty] | 9921 | 0 | 9921 | 0
[6 empty] | 9922 | 319597.9291 | 9922 | 319597.9291
[6 empty] | 9923 | 0 | 9923 | 0
[6 empty] | 9924 | 2062650.8685 | 9924 | 2062650.8685
[6 empty] | 9925 | 0 | 9925 | 0
[6 empty] | 9926 | 4440158.5556 | 9926 | 0
[6 empty] | 9927 | 0 | 9927 | 0
[6 empty] | 9928 | 3010537.1375 | 9928 | 0
[6 empty] | 9929 | 452054.2057 | 9929 | 452054.2057
[6 empty] | 9930 | 5688201.8968 | 9930 | 0
[6 empty] | 9931 | 3148943.0135 | 9931 | 3148943.0135
[6 empty] | 9932 | 4051028.6053 | 9932 | 4051028.6053
[6 empty] | 9933 | 3107360.9415 | 9933 | 3107360.9415
[6 empty] | 9934 | 0 | 9934 | 0
[6 empty] | 9935 | 0 | 9935 | 0
[6 empty] | 9936 | 0 | 9936 | 0
[6 empty] | 9937 | 1432819.2603 | 9937 | 1432819.2603
[6 empty] | 9938 | 262220.6596 | 9938 | 262220.6596
[6 empty] | 9939 | 0 | 9939 | 0
[6 empty] | 9940 | 0 | 9940 | 0
[6 empty] | 9941 | 2790855.8957 | 9941 | 0
[6 empty] | 9942 | 4443137.1761 | 9942 | 324135.9546
[6 empty] | 9943 | 0 | 9943 | 0
[6 empty] | 9944 | 189658.0059 | 9944 | 189658.0059
[6 empty] | 9945 | 0 | 9945 | 0
[6 empty] | 9946 | 330875.857 | 9946 | 0
[6 empty] | 9947 | 217239.1454 | 9947 | 217239.1454
[6 empty] | 9948 | 0 | 9948 | 0
[6 empty] | 9949 | 0 | 9949 | 0
[6 empty] | 9950 | 562745.0843 | 9950 | 562745.0843
[6 empty] | 9951 | 508972.4496 | 9951 | 508972.4496
[6 empty] | 9952 | 3106678.21 | 9952 | 393094.3027
[6 empty] | 9953 | 13949389.5158 | 9953 | 0
[6 empty] | 9954 | 3345725.7131 | 9954 | 0
[6 empty] | 9955 | 201854.6543 | 9955 | 0
[6 empty] | 9956 | 537169.4857 | 9956 | 537169.4857
[6 empty] | 9957 | 3344910.5666 | 9957 | 3344910.5666
[6 empty] | 9958 | 0 | 9958 | 0
[6 empty] | 9959 | 4695647.3629 | 9959 | 4355739.941
[6 empty] | 9960 | 590336.2405 | 9960 | 448402.973
[6 empty] | 9961 | 7109744.2354 | 9961 | 7109744.2354
[6 empty] | 9962 | 266248.0185 | 9962 | 0
[6 empty] | 9963 | 3765084.7256 | 9963 | 3765084.7256
[6 empty] | 9964 | 0 | 9964 | 0
[6 empty] | 9965 | 0 | 9965 | 0
[6 empty] | 9966 | 0 | 9966 | 0
[6 empty] | 9967 | 0 | 9967 | 0
[6 empty] | 9968 | 0 | 9968 | 0
[6 empty] | 9969 | 0 | 9969 | 0
[6 empty] | 9970 | 1535492.756 | 9970 | 1535492.756
[6 empty] | 9971 | 3397507.0309 | 9971 | 3187885.4338
[6 empty] | 9972 | 7463658.1003 | 9972 | 0
[6 empty] | 9973 | 0 | 9973 | 0
[6 empty] | 9974 | 282704.6931 | 9974 | 282704.6931
[6 empty] | 9975 | 3081089.9697 | 9975 | 0
[6 empty] | 9976 | 1144092.829 | 9976 | 1144092.829
[6 empty] | 9977 | 237455.0404 | 9977 | 237455.0404
[6 empty] | 9978 | 0 | 9978 | 0
[6 empty] | 9979 | 0 | 9979 | 0
[6 empty] | 9980 | 565075.2496 | 9980 | 565075.2496
[6 empty] | 9981 | 12060705.136 | 9981 | 12060705.136
[6 empty] | 9982 | 7569909.9379 | 9982 | 0
[6 empty] | 9983 | 0 | 9983 | 0
[6 empty] | 9984 | 6981645.6646 | 9984 | 3127059.0207
[6 empty] | 9985 | 4234451.6565 | 9985 | 270173.6805
[6 empty] | 9986 | 526192.4055 | 9986 | 526192.4055
[6 empty] | 9987 | 0 | 9987 | 0
[6 empty] | 9988 | 8055579.6616 | 9988 | 6192521.2164
[6 empty] | 9989 | 3768799.6846 | 9989 | 0
[6 empty] | 9990 | 0 | 9990 | 0
[6 empty] | 9991 | 0 | 9991 | 0
[6 empty] | 9992 | 662433.0755 | 9992 | 662433.0755
[6 empty] | 9993 | 0 | 9993 | 0
[6 empty] | 9994 | 4480812.7788 | 9994 | 346004.3547
[6 empty] | 9995 | 0 | 9995 | 0
[6 empty] | 9996 | 427389.123 | 9996 | 427389.123
[6 empty] | 9997 | 3904150.5676 | 9997 | 2531589.2242
[6 empty] | 9998 | 0 | 9998 | 0
[6 empty] | 9999 | 0 | 9999 | 0
[6 empty] | 10000 | 0 | 10000 | 0

## Combining LECs
Combining Loss Exceedance Curves
|  |  | Contact HDR to develop custom quantitative methods for your firm. |  | Introduction: Loss Exceedance Curves of multiple portfolios can be combined into a single Loss Exceedance Curve for an aggregate portfolio. As before, this involves running thousands of portfolio simulations. For simplicity, only the total loss of a portfolio—not the individual events—is considered here. To aggregate results, simply add the simulated totals for each portfolio, as shown in “Total of All Portfolios” (column E). The combined total is then used to generate a Loss Exceedance Curve, just as was done for the original portfolios.
www.hubbardresearch.com
info@hubbardresearch.com
10,000 Simulations for Each Portfolio and Combined Portfolios | [5 empty] | Combined Loss Exceedance Curve Table |  |  |  |  | Loss Exceedance Curves for all Portfolios Combined
| Portfolio 1 | Portfolio 2 | Portfolio 3 | Total of All Portfolios |  |  | Portfolio 1 | Portfolio 2 | Portfolio 3 | Total of All Portfolios
1 | 3320373.5547 | 5412439.7616 | 2253677.099 | 10986490.4153 |  | 0 | 99.92% | 84.79% | 84.75% | 100%
2 | 2426332.675 | 0 | 1699252.6619 | 4125585.3369 |  | 500000 | 98.5% | 83.79% | 62.53% | 99.94%
3 | 12047530.4975 | 25589856.1589 | 913483.3015 | 38550869.9579 |  | 1000000 | 96.42% | 82.03% | 50.55% | 99.79%
4 | 5494637.4884 | 2468927.5742 | 2338470.7205 | 10302035.7831 |  | 1500000 | 93.57% | 79.69% | 41.64% | 99.59%
5 | 6942820.7899 | 0 | 147887.0161 | 7090707.8061 |  | 2000000 | 89.71% | 76.91% | 34.33% | 99.33%
6 | 6218603.3292 | 17801677.9953 | 2490713.2182 | 26510994.5427 |  | 2500000 | 85.35% | 73.47% | 28.54% | 98.94%
7 | 13701174.1053 | 4367783.5541 | 892685.0538 | 18961642.7132 |  | 3000000 | 81.06% | 69.32% | 24.16% | 98.4%
8 | 9956153.3858 | 2670997.4079 | 1050762.6022 | 13677913.3959 |  | 3500000 | 76.41% | 65.54% | 20.8% | 97.82%
9 | 20068517.9354 | 16246334.7433 | 2134062.642 | 38448915.3208 |  | 4000000 | 71.56% | 61.97% | 18.15% | 96.95%
10 | 3363733.055 | 5648085.322 | 1980188.8301 | 10992007.2071 |  | 4500000 | 66.71% | 58% | 16.13% | 95.85%
11 | 3743060.3291 | 0 | 315148.3106 | 4058208.6397 |  | 5000000 | 62.26% | 54.2% | 14.51% | 94.51%
12 | 3375384.8169 | 4610458.8447 | 0 | 7985843.6615 |  | 5500000 | 58.32% | 50.37% | 12.91% | 93.19%
13 | 5240835.71 | 3190102.7506 | 2416654.419 | 10847592.8797 |  | 6000000 | 54.23% | 46.97% | 11.67% | 91.89%
14 | 17792548.6811 | 7200271.8918 | 0 | 24992820.5729 |  | 6500000 | 50.87% | 43.77% | 10.64% | 90.14%
15 | 12333269.0749 | 11867792.5946 | 2032058.5797 | 26233120.2492 |  | 7000000 | 47.59% | 40.68% | 9.73% | 88.59%
16 | 4039843.3963 | 0 | 4671144.1666 | 8710987.563 |  | 7500000 | 44.19% | 37.77% | 8.85% | 86.77%
17 | 15458582.833 | 3495547.4407 | 152455.6356 | 19106585.9093 |  | 8000000 | 41.18% | 35.21% | 8.26% | 84.82%
18 | 4651972.2241 | 10647613.6135 | 0 | 15299585.8376 |  | 8500000 | 38.48% | 32.56% | 7.56% | 82.82%
19 | 5749025.5393 | 4819072.2875 | 4754833.0175 | 15322930.8443 |  | 9000000 | 36.12% | 30.48% | 6.87% | 80.82%
20 | 3333369.0129 | 13684348.9536 | 5601278.3599 | 22618996.3264 |  | 9500000 | 33.74% | 28.37% | 6.19% | 78.59%
21 | 4340537.1372 | 0 | 13180002.3183 | 17520539.4555 |  | 10000000 | 31.48% | 26.48% | 5.6% | 76.86%
22 | 1581763.8509 | 13917633.6046 | 3376128.7062 | 18875526.1617 |  | 10500000 | 29.29% | 24.77% | 5.08% | 74.67%
23 | 6566170.9481 | 3984735.6297 | 0 | 10550906.5778 |  | 11000000 | 27.33% | 23.19% | 4.69% | 72.56%
24 | 1768727.3975 | 0 | 1949206.8342 | 3717934.2317 |  | 11500000 | 25.25% | 21.58% | 4.29% | 70.4%
25 | 5222929.7318 | 17258578.6444 | 4031196.2162 | 26512704.5924 |  | 12000000 | 23.38% | 20.05% | 3.95% | 68.47%
26 | 8906945.1655 | 8557488.2094 | 8243271.9255 | 25707705.3004 |  | 12500000 | 21.81% | 18.63% | 3.68% | 66.37%
27 | 3174714.4172 | 0 | 2070363.1836 | 5245077.6007 |  | 13000000 | 20.24% | 17.36% | 3.35% | 64.29%
28 | 28137896.774 | 5906216.6067 | 1860007.9108 | 35904121.2915 |  | 13500000 | 18.8% | 16.1% | 3.07% | 62.2%
29 | 9779940.1254 | 0 | 3840.2459 | 9783780.3713 |  | 14000000 | 17.66% | 15.01% | 2.8% | 60.03%
30 | 2387088.3653 | 0 | 286972.909 | 2674061.2743 |  | 14500000 | 16.57% | 13.93% | 2.6% | 57.96%
31 | 9648659.7539 | 15679338.5272 | 3071392.2443 | 28399390.5254 |  | 15000000 | 15.49% | 13.01% | 2.44% | 55.95%
32 | 1107638.4997 | 5273118.5431 | 2706048.6458 | 9086805.6886 |  | 15500000 | 14.41% | 12.16% | 2.23% | 53.76%
33 | 8410106.5166 | 5206162.144 | 146272.9983 | 13762541.6589 |  | 16000000 | 13.35% | 11.21% | 2.04% | 51.62%
34 | 5959275.1328 | 5956256.0109 | 722441.5464 | 12637972.6901 |  | 16500000 | 12.45% | 10.1% | 1.87% | 49.62%
35 | 8860967.8775 | 4877469.8504 | 6571920.8704 | 20310358.5982 |  | 17000000 | 11.5% | 9.35% | 1.75% | 47.78%
36 | 6313825.7861 | 0 | 8710163.2884 | 15023989.0744 |  | 17500000 | 10.67% | 8.69% | 1.57% | 45.8%
37 | 5675476.7412 | 14695354.9526 | 5690062.9994 | 26060894.6932 |  | 18000000 | 9.92% | 8.03% | 1.39% | 43.92%
38 | 3032144.0907 | 0 | 126938.4172 | 3159082.5079 |  | 18500000 | 9.27% | 7.54% | 1.23% | 42.1%
39 | 2975672.1898 | 7726314.9293 | 60833.0874 | 10762820.2065 |  | 19000000 | 8.82% | 7.06% | 1.13% | 40.44%
40 | 6017082.2135 | 22280737.0049 | 943527.1809 | 29241346.3994 |  | 19500000 | 8.1% | 6.51% | 1.06% | 38.82%
41 | 976297.627 | 17030003.7638 | 1097816.3544 | 19104117.7453 |  | 20000000 | 7.51% | 6.13% | 1.01% | 37.26%
42 | 3987171.1194 | 0 | 251461.5115 | 4238632.6309 |  | 20500000 | 7.07% | 5.61% | 0.91% | 35.47%
43 | 10997706.5601 | 4355643.1044 | 3020961.3351 | 18374310.9996 |  | 21000000 | 6.65% | 5.3% | 0.82% | 34.06%
44 | 6676333.2509 | 1032952.053 | 1693514.0135 | 9402799.3175 |  | 21500000 | 6.18% | 4.98% | 0.74% | 32.53%
45 | 8769488.8922 | 0 | 5881149.7058 | 14650638.598 |  | 22000000 | 5.88% | 4.69% | 0.7% | 31.13%
46 | 2791735.1132 | 0 | 1717076.4307 | 4508811.5439 |  | 22500000 | 5.49% | 4.42% | 0.67% | 29.6%
47 | 7518949.0672 | 7350229.167 | 5316462.4609 | 20185640.6951 |  | 23000000 | 5.1% | 4.03% | 0.62% | 28.26%
48 | 23756176.3271 | 2824600.4592 | 191563.6945 | 26772340.4807 |  | 23500000 | 4.77% | 3.74% | 0.6% | 26.79%
49 | 9785047.2428 | 0 | 3615264.4258 | 13400311.6686 |  | 24000000 | 4.44% | 3.52% | 0.54% | 25.46%
50 | 8364827.469 | 2057247.9041 | 4051618.7993 | 14473694.1724 |  | 24500000 | 4.18% | 3.28% | 0.49% | 24.18%
51 | 16548072.1292 | 0 | 11200582.6694 | 27748654.7986 |  | 25000000 | 3.95% | 3.1% | 0.46% | 23.11%
52 | 2241619.0904 | 0 | 188856.5954 | 2430475.6857 |  | 25500000 | 3.68% | 2.8% | 0.43% | 22.08%
53 | 3099523.4577 | 0 | 0 | 3099523.4577 |  | 26000000 | 3.5% | 2.55% | 0.36% | 21.05%
54 | 10700082.4179 | 8427187.0667 | 1641501.3276 | 20768770.8122 |  | 26500000 | 3.25% | 2.32% | 0.33% | 20.11%
55 | 12048745.897 | 3151883.9948 | 545288.7722 | 15745918.6641 |  | 27000000 | 2.94% | 2.14% | 0.3% | 19.2%
56 | 5328875.4037 | 0 | 2132443.7345 | 7461319.1383 |  | 27500000 | 2.75% | 2.03% | 0.3% | 18.23%
57 | 3284568.8893 | 2676128.64 | 20743013.0626 | 26703710.5918 |  | 28000000 | 2.53% | 1.93% | 0.29% | 17.38%
58 | 3722177.225 | 5719983.3619 | 1718134.0601 | 11160294.647 |  | 28500000 | 2.39% | 1.79% | 0.25% | 16.51%
59 | 7399098.5963 | 4812098.9898 | 2432981.9341 | 14644179.5202 |  | 29000000 | 2.16% | 1.66% | 0.23% | 15.58%
60 | 12520071.6003 | 33040006.1758 | 0 | 45560077.7761 |  | 29500000 | 2% | 1.52% | 0.22% | 14.68%
61 | 9789657.5885 | 1935134.1326 | 4849263.442 | 16574055.1631 |  | 30000000 | 1.92% | 1.41% | 0.22% | 14.02%
62 | 10221926.2524 | 2051425.0807 | 8010795.8131 | 20284147.1461 |  | 30500000 | 1.75% | 1.36% | 0.21% | 13.42%
63 | 3581515.9669 | 19218865.5534 | 484432.0962 | 23284813.6164 |  | 31000000 | 1.66% | 1.29% | 0.2% | 12.58%
64 | 8133403.6252 | 6583510.0684 | 914415.2745 | 15631328.9681 |  | 31500000 | 1.49% | 1.15% | 0.16% | 11.96%
65 | 4335085.3793 | 8472652.8118 | 8721480.6889 | 21529218.88 |  | 32000000 | 1.44% | 1.07% | 0.14% | 11.39%
66 | 1697129.3317 | 5616343.7868 | 4644349.617 | 11957822.7356 |  | 32500000 | 1.37% | 0.98% | 0.14% | 10.73%
67 | 6162174.0302 | 0 | 181571.4115 | 6343745.4416 |  | 33000000 | 1.3% | 0.91% | 0.13% | 10.24%
68 | 2390283.8296 | 0 | 1628326.6548 | 4018610.4845 |  | 33500000 | 1.21% | 0.84% | 0.12% | 9.75%
69 | 24055235.6178 | 17337898.365 | 389445.5936 | 41782579.5764 |  | 34000000 | 1.12% | 0.77% | 0.12% | 9.2%
70 | 7925169.5308 | 0 | 3375476.142 | 11300645.6728 |  | 34500000 | 1.03% | 0.76% | 0.12% | 8.75%
71 | 2207473.0991 | 3123609.3618 | 559065.0589 | 5890147.5198 |  | 35000000 | 0.95% | 0.71% | 0.11% | 8.26%
72 | 3795325.4624 | 0 | 7574889.5165 | 11370214.9789 |  | 35500000 | 0.87% | 0.67% | 0.1% | 7.9%
73 | 9527466.9855 | 7399645.6707 | 545275.0925 | 17472387.7488 |  | 36000000 | 0.83% | 0.64% | 0.1% | 7.42%
74 | 7459591.6681 | 7415355.2069 | 1185154.1271 | 16060101.002 |  | 36500000 | 0.81% | 0.61% | 0.09% | 6.97%
75 | 5044968.847 | 3451197.0074 | 3269064.6566 | 11765230.511 |  | 37000000 | 0.77% | 0.57% | 0.08% | 6.67%
76 | 15657239.231 | 3134521.0321 | 55591.1679 | 18847351.431 |  | 37500000 | 0.73% | 0.56% | 0.07% | 6.3%
77 | 4848611.5797 | 3842557.5838 | 1487662.9579 | 10178832.1213 |  | 38000000 | 0.67% | 0.53% | 0.07% | 5.97%
78 | 10801204.8023 | 11275875.6498 | 82290.801 | 22159371.2531 |  | 38500000 | 0.65% | 0.48% | 0.06% | 5.62%
79 | 6025683.4507 | 5663388.6486 | 10069915.0091 | 21758987.1083 |  | 39000000 | 0.61% | 0.44% | 0.06% | 5.3%
80 | 3264006.4372 | 0 | 0 | 3264006.4372 |  | 39500000 | 0.57% | 0.44% | 0.06% | 5.05%
81 | 2260755.2716 | 10237644.7997 | 0 | 12498400.0712 |  | 40000000 | 0.53% | 0.4% | 0.06% | 4.85%
82 | 5290096.5107 | 11827893.6151 | 409557.938 | 17527548.0639 |  | 40500000 | 0.5% | 0.38% | 0.06% | 4.64%
83 | 11437769.6235 | 3054419.2632 | 782296.5875 | 15274485.4743 |  | 41000000 | 0.49% | 0.34% | 0.06% | 4.46%
84 | 10503835.3544 | 4070605.4606 | 1610086.1681 | 16184526.9831 |  | 41500000 | 0.48% | 0.32% | 0.06% | 4.2%
85 | 8453597.5055 | 0 | 243177.5187 | 8696775.0242 |  | 42000000 | 0.42% | 0.3% | 0.05% | 3.98%
86 | 22750114.1693 | 6376943.0415 | 1102544.9572 | 30229602.1679 |  | 42500000 | 0.42% | 0.29% | 0.05% | 3.76%
87 | 1866546.406 | 5358546.0688 | 3658380.4669 | 10883472.9417 |  | 43000000 | 0.39% | 0.28% | 0.05% | 3.54%
88 | 8435266.9616 | 3293801.4989 | 1628343.8042 | 13357412.2647 |  | 43500000 | 0.37% | 0.25% | 0.05% | 3.3%
89 | 14184134.1978 | 6142587.2109 | 1487913.4709 | 21814634.8795 |  | 44000000 | 0.35% | 0.24% | 0.05% | 3.1%
90 | 2197489.8204 | 0 | 159731.3607 | 2357221.1811 |  | 44500000 | 0.31% | 0.23% | 0.04% | 2.96%
91 | 3453027.6711 | 0 | 2602875.6231 | 6055903.2941 |  | 45000000 | 0.29% | 0.22% | 0.04% | 2.86%
92 | 66653.4979 | 11381989.8562 | 0 | 11448643.3541 |  | 45500000 | 0.27% | 0.22% | 0.04% | 2.71%
93 | 18375614.9763 | 4857664.7451 | 570575.2059 | 23803854.9273 |  | 46000000 | 0.25% | 0.22% | 0.02% | 2.52%
94 | 1505366.4755 | 0 | 71131.0389 | 1576497.5144 |  | 46500000 | 0.23% | 0.22% | 0.02% | 2.35%
95 | 10450487.4434 | 1359079.9853 | 1967799.525 | 13777366.9537 |  | 47000000 | 0.21% | 0.22% | 0.02% | 2.23%
96 | 12666968.0561 | 11715601.5478 | 21278922.2377 | 45661491.8415 |  | 47500000 | 0.21% | 0.21% | 0.02% | 2.14%
97 | 10777748.5886 | 0 | 0 | 10777748.5886 |  | 48000000 | 0.2% | 0.2% | 0.02% | 2.06%
98 | 12119164.2367 | 0 | 339844.9984 | 12459009.2351 |  | 48500000 | 0.18% | 0.2% | 0.02% | 1.94%
99 | 9470887.5018 | 4171101.0189 | 14398909.4931 | 28040898.0138 |  | 49000000 | 0.17% | 0.2% | 0.02% | 1.81%
100 | 4443098.4185 | 5675226.8928 | 2780306.9251 | 12898632.2363 |  | 49500000 | 0.16% | 0.2% | 0.02% | 1.73%
101 | 15142653.294 | 3025323.3398 | 0 | 18167976.6338 |  | 50000000 | 0.16% | 0.2% | 0.02% | 1.69%
102 | 8532718.3299 | 0 | 3490452.8174 | 12023171.1473 |  | 50500000 | 0.15% | 0.15% | 0.02% | 1.54%
103 | 32235562.8743 | 7683586.8893 | 138431.4657 | 40057581.2293 |  | 51000000 | 0.13% | 0.15% | 0.02% | 1.48%
104 | 15025850.881 | 11979930.971 | 2063165.249 | 29068947.101 |  | 51500000 | 0.13% | 0.15% | 0.02% | 1.39%
105 | 3401049.4447 | 0 | 6070.0061 | 3407119.4508 |  | 52000000 | 0.13% | 0.15% | 0.01% | 1.31%
106 | 7371315.4628 | 2625340.925 | 4502251.8864 | 14498908.2742 |  | 52500000 | 0.13% | 0.13% | 0.01% | 1.24%
107 | 1874750.9057 | 2927083.2463 | 0 | 4801834.1519 |  | 53000000 | 0.13% | 0.11% | 0.01% | 1.21%
108 | 17094697.0073 | 12082154.0374 | 589710.0497 | 29766561.0945 |  | 53500000 | 0.12% | 0.1% | 0.01% | 1.18%
109 | 14631562.4114 | 5532650.2036 | 134928.519 | 20299141.1339 |  | 54000000 | 0.12% | 0.1% | 0.01% | 1.12%
110 | 11225103.0892 | 11396250.9714 | 9102863.9229 | 31724217.9835 |  | 54500000 | 0.12% | 0.1% | 0.01% | 1.05%
111 | 2873852.9103 | 5496531.5448 | 95941.7038 | 8466326.1588 |  | 55000000 | 0.12% | 0.1% | 0.01% | 1%
112 | 1854844.6377 | 16871426.1331 | 0 | 18726270.7708 |  | 55500000 | 0.12% | 0.09% | 0.01% | 0.96%
113 | 7057634.461 | 5972208.1409 | 2403374.3864 | 15433216.9883 |  | 56000000 | 0.11% | 0.08% | 0.01% | 0.91%
114 | 13213069.7533 | 14835196.9561 | 13939578.4979 | 41987845.2073 |  | 56500000 | 0.11% | 0.08% | 0.01% | 0.87%
115 | 11035514.7572 | 15765380.4914 | 1967563.8539 | 28768459.1025 |  | 57000000 | 0.11% | 0.07% | 0.01% | 0.82%
116 | 15360691.3788 | 6322658.9713 | 1759996.2268 | 23443346.577 |  | 57500000 | 0.11% | 0.07% | 0.01% | 0.8%
117 | 6003549.2698 | 3586554.8183 | 813723.4535 | 10403827.5416 |  | 58000000 | 0.1% | 0.07% | 0.01% | 0.77%
118 | 3702238.5296 | 0 | 541836.9187 | 4244075.4483 |  | 58500000 | 0.09% | 0.06% | 0.01% | 0.76%
119 | 3311640.3254 | 0 | 5711553.4676 | 9023193.793 |  | 59000000 | 0.09% | 0.06% | 0.01% | 0.73%
120 | 24240897.0983 | 0 | 1469282.6444 | 25710179.7427 |  | 59500000 | 0.09% | 0.06% | 0.01% | 0.67%
121 | 5778396.9341 | 0 | 14870224.8395 | 20648621.7736 |  | 60000000 | 0.09% | 0.06% | 0.01% | 0.63%
122 | 3046106.2304 | 3953038.5548 | 811851.3374 | 7810996.1226
123 | 1003257.2244 | 7846911.3491 | 0 | 8850168.5735
124 | 4105517.6617 | 11573539.5276 | 2820170.3122 | 18499227.5015
125 | 5445015.8136 | 8448840.4439 | 107199.4583 | 14001055.7159
126 | 13087203.9538 | 0 | 0 | 13087203.9538
127 | 7256125.9358 | 5290946.0479 | 3563232.9119 | 16110304.8956
128 | 290660.0893 | 12532749.854 | 1784401.9977 | 14607811.9411
129 | 1390778.895 | 0 | 3216022.9556 | 4606801.8506
130 | 2139360.1037 | 4109802.3523 | 1650030.1881 | 7899192.6441
131 | 10738320.3708 | 5199911.5023 | 2309855.6266 | 18248087.4998
132 | 4026855.5418 | 0 | 708846.7501 | 4735702.2919
133 | 2663544.9793 | 0 | 1904444.612 | 4567989.5912
134 | 13623155.6371 | 7451833.5221 | 24438.9462 | 21099428.1054
135 | 5459432.9015 | 4386950.9049 | 2355496.2888 | 12201880.0952
136 | 667422.8808 | 5725743.0041 | 290922.7818 | 6684088.6667
137 | 9821489.6688 | 7444571.276 | 367642.0421 | 17633702.9869
138 | 25388437.0684 | 0 | 0 | 25388437.0684
139 | 9619508.0594 | 3635839.162 | 3011614.2627 | 16266961.4841
140 | 6667961.6628 | 9638505.7195 | 0 | 16306467.3823
141 | 14916417.2974 | 14181320.9467 | 5762464.3286 | 34860202.5726
142 | 3186277.7533 | 3264674.4558 | 0 | 6450952.2091
143 | 3448537.0602 | 21580542.5518 | 3656513.2107 | 28685592.8227
144 | 3034389.5065 | 9857302.7169 | 1908337.4999 | 14800029.7233
145 | 5065717.0935 | 7999055.3292 | 1954690.3588 | 15019462.7815
146 | 3105678.2459 | 6413141.8557 | 9845362.9187 | 19364183.0204
147 | 1319629.2001 | 50100884.5525 | 0 | 51420513.7526
148 | 8968596.8764 | 0 | 2765538.3761 | 11734135.2525
149 | 11800490.5982 | 0 | 4596041.2141 | 16396531.8123
150 | 5755508.5241 | 0 | 640703.5053 | 6396212.0293
151 | 2205796.1573 | 2478092.717 | 2507260.9439 | 7191149.8181
152 | 2888651.0869 | 11259369.8744 | 926538.512 | 15074559.4733
153 | 2398198.9008 | 5044044.9965 | 245736.214 | 7687980.1113
154 | 6702595.7228 | 947480.2645 | 9770725.0579 | 17420801.0452
155 | 23043883.5152 | 0 | 1085258.1837 | 24129141.6988
156 | 4023754.1743 | 14012214.1687 | 5616856.4589 | 23652824.8019
157 | 6458040.3448 | 11479999.9849 | 1810396.7306 | 19748437.0602
158 | 2880968.7622 | 4641354.8049 | 1228820.9017 | 8751144.4688
159 | 4277954.9149 | 19811848.9847 | 388912.1746 | 24478716.0741
160 | 4499787.8985 | 24210808.3511 | 1041049.727 | 29751645.9766
161 | 9031131.7827 | 5515569.9945 | 6535806.229 | 21082508.0062
162 | 979838.4283 | 2686510.9869 | 2523361.761 | 6189711.1762
163 | 15310102.8394 | 2601607.5616 | 723340.8175 | 18635051.2185
164 | 2297062.7292 | 0 | 0 | 2297062.7292
165 | 11175929.1748 | 6611575.3915 | 0 | 17787504.5663
166 | 6279493.5691 | 2861233.1175 | 3040429.7406 | 12181156.4273
167 | 2787079.0828 | 14578012.5319 | 9273080.2126 | 26638171.8272
168 | 23062667.1114 | 4464548.1728 | 65059.8748 | 27592275.1589
169 | 9192027.873 | 9472245.9898 | 1445225.5122 | 20109499.375
170 | 4924637.4522 | 6530737.5544 | 807228.4126 | 12262603.4192
171 | 5912726.6582 | 0 | 268387.2806 | 6181113.9388
172 | 3344501.5549 | 14749646.446 | 6971005.2486 | 25065153.2495
173 | 5797551.3963 | 2512383.2919 | 1805672.5411 | 10115607.2293
174 | 8293575.4762 | 4899175.3152 | 955094.0466 | 14147844.838
175 | 11322173.9991 | 4789955.6012 | 20290448.4337 | 36402578.0341
176 | 13300024.3331 | 2055814.4862 | 837559.9282 | 16193398.7475
177 | 2978278.3009 | 2366697.5405 | 1529909.0272 | 6874884.8686
178 | 3480487.1416 | 8162917.7819 | 524017.3759 | 12167422.2994
179 | 25272615.847 | 10107886.1549 | 85557.2377 | 35466059.2396
180 | 3349237.485 | 11141121.9517 | 17266206.5809 | 31756566.0176
181 | 719941.1269 | 2197543.4802 | 14585094.3337 | 17502578.9407
182 | 3990975.2661 | 2152907.9045 | 2311803.4622 | 8455686.6328
183 | 2974385.1156 | 2546997.558 | 981350.0685 | 6502732.7421
184 | 6061616.3363 | 10574215.2026 | 6971265.5469 | 23607097.0858
185 | 2457951.585 | 14477797.5503 | 1323124.5758 | 18258873.7111
186 | 5105985.3836 | 19663523.9602 | 905457.2413 | 25674966.585
187 | 3285836.7942 | 1349102.0995 | 2592622.4428 | 7227561.3365
188 | 17674569.5691 | 0 | 0 | 17674569.5691
189 | 3685484.368 | 3761510.6866 | 9265546.0363 | 16712541.0909
190 | 10881101.0521 | 4712977.3485 | 5607213.7402 | 21201292.1408
191 | 26168914.6081 | 5828656.4315 | 1326650.0763 | 33324221.1159
192 | 10340897.1475 | 9404476.3166 | 1307673.4793 | 21053046.9434
193 | 4158484.9385 | 24342208.9841 | 3872915.3438 | 32373609.2664
194 | 8499169.9803 | 7611119.6982 | 5389527.8222 | 21499817.5007
195 | 3619959.5781 | 6697916.0836 | 0 | 10317875.6617
196 | 3564816.1469 | 0 | 0 | 3564816.1469
197 | 2556897.2537 | 0 | 3537924.3865 | 6094821.6402
198 | 3538830.727 | 9297141.0604 | 0 | 12835971.7874
199 | 9795824.9526 | 4090653.2693 | 1172251.4287 | 15058729.6506
200 | 10058986.2107 | 3988788.2034 | 8364723.3137 | 22412497.7278
201 | 27842623.2781 | 5801427.9252 | 89380.2959 | 33733431.4991
202 | 7838131.2979 | 0 | 0 | 7838131.2979
203 | 17723677.4121 | 2723962.5 | 330144.8498 | 20777784.7619
204 | 9073609.2472 | 6270530.0424 | 1613396.9647 | 16957536.2543
205 | 764686.2659 | 15539257.4564 | 0 | 16303943.7222
206 | 31546400.6155 | 0 | 1811901.3748 | 33358301.9903
207 | 9193250.411 | 9374042.6717 | 1045762.2364 | 19613055.319
208 | 3179907.0831 | 2302882.0446 | 915346.7167 | 6398135.8445
209 | 1477599.2102 | 2506541.8649 | 159364.5406 | 4143505.6157
210 | 16731174.5249 | 12710234.3043 | 1087913.7415 | 30529322.5707
211 | 5874423.2813 | 5119435.3126 | 394332.1734 | 11388190.7674
212 | 218512.4831 | 0 | 0 | 218512.4831
213 | 16107447.1916 | 1387315.851 | 194805.2302 | 17689568.2727
214 | 7466572.9502 | 13837891.7681 | 2838907.5759 | 24143372.2943
215 | 1251416.4925 | 4527292.6823 | 2188543.955 | 7967253.1298
216 | 21650934.3957 | 29365421.0937 | 202581.6528 | 51218937.1422
217 | 15043768.2609 | 0 | 1210657.0372 | 16254425.298
218 | 5591109.0211 | 668746.8146 | 0 | 6259855.8357
219 | 3537916.6074 | 11147904.1011 | 214937.7415 | 14900758.4501
220 | 13849116.6694 | 8356595.3713 | 80874.2034 | 22286586.2441
221 | 3953554.4165 | 9742638.0444 | 611229.1721 | 14307421.6331
222 | 17677815.3772 | 2713560.2828 | 0 | 20391375.66
223 | 10106148.8999 | 10799820.0039 | 4626357.7551 | 25532326.6588
224 | 697881.027 | 696407.2907 | 1160319.9844 | 2554608.3021
225 | 19902550.8321 | 5668807.6609 | 439625.8451 | 26010984.3382
226 | 34493593.0359 | 24579151.3014 | 156843.6079 | 59229587.9451
227 | 7106826.7806 | 3080247.3515 | 4493534.2389 | 14680608.371
228 | 1010068.4378 | 1982725.6532 | 0 | 2992794.091
229 | 4611551.0524 | 0 | 11037303.2212 | 15648854.2736
230 | 7369067.97 | 14634948.1889 | 531073.0916 | 22535089.2505
231 | 4985841.5943 | 6816436.5027 | 1310051.0767 | 13112329.1737
232 | 22502967.8364 | 8119631.86 | 1687391.3027 | 32309990.9991
233 | 13945413.8579 | 0 | 0 | 13945413.8579
234 | 6085837.8036 | 4893300.3288 | 1165895.6649 | 12145033.7973
235 | 15803716.2683 | 6773384.3735 | 736281.0141 | 23313381.6559
236 | 6531471.6043 | 8180843.6952 | 1425182.6282 | 16137497.9277
237 | 5363442.8434 | 11857220.1666 | 124963.8007 | 17345626.8107
238 | 7564135.8847 | 0 | 17126728.7638 | 24690864.6484
239 | 25371731.0414 | 5570819.9636 | 0 | 30942551.005
240 | 2315486.2882 | 8331919.7738 | 636115.7862 | 11283521.8481
241 | 6708940.6444 | 610323.0549 | 898656.3616 | 8217920.0608
242 | 8963537.5833 | 19859614.8494 | 899937.9584 | 29723090.3911
243 | 2968583.6577 | 9255943.1992 | 683662.805 | 12908189.662
244 | 43473702.3269 | 2330383.7246 | 1275252.5961 | 47079338.6476
245 | 5700530.3427 | 9397849.0365 | 2674700.0448 | 17773079.4241
246 | 3163156.9163 | 0 | 15853279.5368 | 19016436.4532
247 | 3427231.3446 | 4653219.0171 | 0 | 8080450.3617
248 | 25009013.9123 | 13546850.4438 | 276666.8845 | 38832531.2405
249 | 34157745.6168 | 10996124.417 | 0 | 45153870.0338
250 | 10218670.2029 | 6788692.5758 | 12802.9403 | 17020165.719
251 | 5379840.8044 | 15925560.8756 | 151613.7435 | 21457015.4235
252 | 13120896.0398 | 7372656.3868 | 1297287.1074 | 21790839.5339
253 | 3754943.4428 | 2918104.5026 | 4860869.5406 | 11533917.486
254 | 6336412.97 | 4645774.8798 | 44049.6824 | 11026237.5323
255 | 3408366.9187 | 0 | 577460.8616 | 3985827.7803
256 | 5635865.3337 | 5526577.8504 | 320015.5853 | 11482458.7694
257 | 19233367.7723 | 5677419.6707 | 13067741.2624 | 37978528.7054
258 | 2167315.503 | 10286531.4323 | 0 | 12453846.9353
259 | 3837682.7318 | 18854591.4919 | 1550105.5045 | 24242379.7283
260 | 9443747.9085 | 791922.1589 | 14202006.1137 | 24437676.1811
261 | 4701283.9304 | 742677.4078 | 0 | 5443961.3382
262 | 7860531.326 | 7228420.2978 | 567534.5204 | 15656486.1442
263 | 11485251.1292 | 0 | 3923595.088 | 15408846.2173
264 | 9489820.9121 | 9216481.9709 | 0 | 18706302.8829
265 | 5879242.1437 | 8306074.5736 | 7703390.9164 | 21888707.6336
266 | 5836298.9903 | 0 | 366448.0208 | 6202747.0111
267 | 2119745.6508 | 11599635.2188 | 2794707.0027 | 16514087.8722
268 | 9458941.7373 | 6482787.799 | 1108549.3742 | 17050278.9105
269 | 5362361.6576 | 11676888.0037 | 263833.3325 | 17303082.9937
270 | 6279481.8026 | 13210077.337 | 515626.2453 | 20005185.3849
271 | 2143631.47 | 1036367.936 | 131861.333 | 3311860.7391
272 | 3270409.0659 | 16567399.9993 | 704623.7894 | 20542432.8545
273 | 3687982.3545 | 0 | 0 | 3687982.3545
274 | 3721815.7972 | 8807766.9028 | 11245577.2866 | 23775159.9866
275 | 2154888.4354 | 21058663.8833 | 0 | 23213552.3187
276 | 6620117.7224 | 9857420.0469 | 0 | 16477537.7693
277 | 2579993.9854 | 5252246.5604 | 511021.7815 | 8343262.3274
278 | 5192912.5553 | 9490085.5886 | 21270.1199 | 14704268.2638
279 | 7014339.8276 | 4710041.6722 | 1345867.2434 | 13070248.7432
280 | 6666852.0074 | 1887125.8384 | 1366206.2454 | 9920184.0911
281 | 3545028.7975 | 3224387.8826 | 1905590.4722 | 8675007.1523
282 | 14212083.4662 | 9420516.7893 | 0 | 23632600.2555
283 | 3222829.1787 | 3194840.6121 | 1470674.8211 | 7888344.6118
284 | 2759364.3554 | 0 | 2406641.6391 | 5166005.9946
285 | 914916.9441 | 5171798.5556 | 795715.9991 | 6882431.4987
286 | 20317218.7739 | 50271.5362 | 6634739.6769 | 27002229.9871
287 | 1413359.4851 | 984795.4007 | 2085509.1767 | 4483664.0624
288 | 5739472.1735 | 13654758.3022 | 8104253.7012 | 27498484.1769
289 | 4443443.2178 | 11953672.1076 | 12145591.6276 | 28542706.9529
290 | 1930631.0239 | 13200937.5656 | 60480.5442 | 15192049.1336
291 | 10690586.174 | 4646995.17 | 507680.5763 | 15845261.9203
292 | 9777431.3363 | 9919921.0055 | 261941.2111 | 19959293.5529
293 | 13396013.0634 | 12546852.6424 | 6349655.481 | 32292521.1868
294 | 2917584.2589 | 0 | 5139832.601 | 8057416.8599
295 | 6310091.0576 | 1996602.3484 | 2402392.4309 | 10709085.8368
296 | 6059339.2891 | 4307181.8519 | 459708.5174 | 10826229.6584
297 | 4628297.9275 | 7563517.8376 | 6270455.5102 | 18462271.2753
298 | 26330988.3009 | 8934575.3014 | 0 | 35265563.6023
299 | 26241418.4641 | 14390612.712 | 2298718.4097 | 42930749.5858
300 | 2623102.1175 | 16378235.3687 | 12255069.6695 | 31256407.1557
301 | 1804749.5849 | 6228259.3401 | 0 | 8033008.925
302 | 7928495.3563 | 12302977.0785 | 244003.8019 | 20475476.2367
303 | 2847938.2943 | 4332416.7891 | 116716.8441 | 7297071.9274
304 | 10809825.7214 | 3238512.2653 | 3431482.1576 | 17479820.1444
305 | 16336812.7678 | 6020844.1765 | 4039931.7678 | 26397588.7121
306 | 8059941.04 | 6699300.7205 | 4034968.2318 | 18794209.9923
307 | 9025029.2316 | 3795036.8165 | 2131856.3381 | 14951922.3863
308 | 9598059.6646 | 4512550.8743 | 150664.7507 | 14261275.2896
309 | 5043210.5754 | 6474303.6488 | 1469121.5722 | 12986635.7965
310 | 6461596.7623 | 0 | 274860.9627 | 6736457.7249
311 | 2410098.5681 | 4906761.9448 | 1043718.1247 | 8360578.6376
312 | 9246579.6583 | 0 | 3430519.3481 | 12677099.0064
313 | 4277626.1697 | 7716014.9808 | 240879.0098 | 12234520.1603
314 | 9314657.5344 | 1291762.6626 | 895768.4767 | 11502188.6737
315 | 23357806.0289 | 5409651.4334 | 77012.0328 | 28844469.4951
316 | 3073256.3976 | 626819.4619 | 590136.4226 | 4290212.2821
317 | 5136700.4295 | 26171035.9007 | 3229714.6136 | 34537450.9438
318 | 12713864.6816 | 1314468.4136 | 553026.6754 | 14581359.7706
319 | 6152276.8522 | 0 | 2210417.2812 | 8362694.1335
320 | 8151922.3178 | 9380903.1786 | 506468.8727 | 18039294.3692
321 | 3373100.3473 | 0 | 4810673.5782 | 8183773.9255
322 | 11882047.6128 | 2604817.7536 | 2093830.2083 | 16580695.5747
323 | 4186387.3925 | 16342899.5496 | 268335.7667 | 20797622.7088
324 | 7587368.4913 | 12253490.9637 | 842479.9603 | 20683339.4153
325 | 5729660.1953 | 0 | 47248.0829 | 5776908.2781
326 | 6849418.6633 | 13146143.2064 | 0 | 19995561.8697
327 | 10107852.1932 | 26186034.6143 | 6437050.3139 | 42730937.1213
328 | 5569956.3987 | 4388983.9961 | 0 | 9958940.3948
329 | 6234011.965 | 16047981.0984 | 1667300.624 | 23949293.6874
330 | 1937620.9866 | 6727261.9737 | 921744.2423 | 9586627.2026
331 | 7302835.3967 | 938232.1725 | 0 | 8241067.5692
332 | 3077890.6386 | 0 | 1247163.3239 | 4325053.9626
333 | 5544972.6868 | 0 | 1186095.5522 | 6731068.239
334 | 9479587.5788 | 1377075.5517 | 60291.6494 | 10916954.7799
335 | 3130825.6026 | 10300429.384 | 4727822.4235 | 18159077.4101
336 | 3742772.7245 | 5170175.5714 | 2956475.574 | 11869423.8699
337 | 8908901.6388 | 7054059.2393 | 241800.0101 | 16204760.8883
338 | 10351107.6576 | 1681190.1598 | 10283178.5822 | 22315476.3997
339 | 2089067.4841 | 3141348.4448 | 3894306.9376 | 9124722.8665
340 | 2376190.31 | 5592584.7625 | 0 | 7968775.0725
341 | 5123343.447 | 0 | 440340.8091 | 5563684.2561
342 | 30226598.1644 | 0 | 1274579.2117 | 31501177.3762
343 | 7857875.3185 | 2732338.9435 | 3471668.3117 | 14061882.5736
344 | 1981117.5948 | 12738320.0385 | 385527.9285 | 15104965.5617
345 | 11121314.549 | 0 | 234638.1247 | 11355952.6737
346 | 19616867.0612 | 17349347.268 | 1528524.4226 | 38494738.7518
347 | 26735703.6032 | 8885741.8345 | 0 | 35621445.4377
348 | 5058235.2978 | 8770194.5886 | 226027.3427 | 14054457.229
349 | 9851328.9479 | 8161698.1229 | 1396886.9437 | 19409914.0145
350 | 5616368.5244 | 3098000.5057 | 525414.7713 | 9239783.8014
351 | 4377376.1112 | 14195876.4902 | 1370415.5113 | 19943668.1126
352 | 27177957.8929 | 8113885.7199 | 9726679.6189 | 45018523.2317
353 | 9159555.1307 | 3163249.0845 | 1334956.5434 | 13657760.7586
354 | 1469164.8216 | 0 | 1343561.54 | 2812726.3617
355 | 16266945.0606 | 9900194.2251 | 12177101.0604 | 38344240.3461
356 | 2877600.2404 | 1348123.6396 | 1764523.7921 | 5990247.6721
357 | 2855377.3016 | 0 | 0 | 2855377.3016
358 | 11184584.0593 | 0 | 754205.6554 | 11938789.7147
359 | 26648952.5097 | 6670603.3923 | 2110525.0245 | 35430080.9265
360 | 3073481.0671 | 0 | 1755012.3043 | 4828493.3714
361 | 8296404.5726 | 0 | 850642.5331 | 9147047.1057
362 | 1949567.3447 | 4664946.5704 | 966262.483 | 7580776.3981
363 | 2491543.5809 | 3523551.3356 | 8747361.1842 | 14762456.1008
364 | 2100534.3018 | 15842952.9085 | 3961244.7904 | 21904732.0006
365 | 18462327.9077 | 14612933.6995 | 2638253.296 | 35713514.9032
366 | 2338697.0269 | 9299263.0113 | 2926115.3688 | 14564075.4069
367 | 13790667.3578 | 6918613.009 | 1948082.1064 | 22657362.4732
368 | 5425913.4584 | 8320961.9255 | 2203445.8979 | 15950321.2819
369 | 2884359.4167 | 7522311.5264 | 3387570.9804 | 13794241.9235
370 | 3821878.7886 | 7487439.7793 | 881205.3059 | 12190523.8738
371 | 5625341.6604 | 0 | 7583950.1025 | 13209291.7628
372 | 21201615.076 | 2311149.8219 | 1101283.283 | 24614048.1809
373 | 1249450.7615 | 11620331.5706 | 185201.7243 | 13054984.0564
374 | 5006255.6458 | 7961672.0754 | 414437.8759 | 13382365.5971
375 | 11369082.0825 | 4637694.11 | 2540997.573 | 18547773.7654
376 | 610675.4221 | 20535700.927 | 0 | 21146376.3491
377 | 847549.9246 | 4074417.852 | 0 | 4921967.7766
378 | 8456805.4335 | 19427332.1818 | 1427562.2687 | 29311699.8841
379 | 10897488.178 | 0 | 389880.6618 | 11287368.8399
380 | 10999612.1552 | 0 | 359288.0199 | 11358900.175
381 | 1542966.0919 | 6865355.8258 | 792183.0349 | 9200504.9526
382 | 1633796.1475 | 5903437.0499 | 8552537.5793 | 16089770.7768
383 | 10142551.3055 | 12277756.9984 | 665993.4022 | 23086301.7061
384 | 15817582.1461 | 6840704.9137 | 4850602.4042 | 27508889.4641
385 | 4042564.4445 | 1825003.0288 | 22925212.4892 | 28792779.9625
386 | 18605966.6273 | 16060695.6612 | 1248946.0095 | 35915608.298
387 | 709986.8502 | 8447944.0074 | 1165086.2744 | 10323017.132
388 | 1249431.6394 | 4798911.1998 | 2172578.3345 | 8220921.1738
389 | 11460213.1252 | 5798115.1581 | 0 | 17258328.2832
390 | 2625703.1123 | 9308258.3139 | 1782160.7515 | 13716122.1777
391 | 2398560.0932 | 690033.6632 | 910723.3801 | 3999317.1365
392 | 7059111.4854 | 8435909.8 | 227953.9586 | 15722975.2441
393 | 26997337.9331 | 15657288.7284 | 2078616.7344 | 44733243.3958
394 | 11979991.5109 | 8465061.7144 | 218742.0871 | 20663795.3124
395 | 5693665.6924 | 8601516.6455 | 1165094.2706 | 15460276.6085
396 | 12636637.9965 | 3553587.9984 | 3090858.9699 | 19281084.9648
397 | 3157808.0109 | 2310315.7626 | 2476555.2128 | 7944678.9864
398 | 5865570.5551 | 3141726.6122 | 25585.998 | 9032883.1653
399 | 20489778.7707 | 3470894.0533 | 0 | 23960672.824
400 | 4495090.4474 | 1778465.0195 | 761411.8285 | 7034967.2954
401 | 4511015.4552 | 0 | 1364725.5369 | 5875740.9921
402 | 3153950.877 | 16108700.4226 | 5088381.7603 | 24351033.0599
403 | 495771.0139 | 0 | 1641492.1077 | 2137263.1217
404 | 3559543.9832 | 5482991.1757 | 10589578.0739 | 19632113.2328
405 | 1824322.9802 | 0 | 239918.134 | 2064241.1142
406 | 10633863.1593 | 3448492.6257 | 659988.4201 | 14742344.2052
407 | 8508428.1051 | 0 | 12069873.0237 | 20578301.1288
408 | 11214841.8003 | 2015582.6732 | 285503.0054 | 13515927.4789
409 | 15845622.1008 | 14724282.3369 | 533250.6225 | 31103155.0602
410 | 7561110.9779 | 4041677.1974 | 219105.7539 | 11821893.9293
411 | 10658631.3508 | 0 | 2318693.9871 | 12977325.3379
412 | 18754125.0459 | 0 | 0 | 18754125.0459
413 | 8962872.9217 | 0 | 0 | 8962872.9217
414 | 4024513.0588 | 9513361.8362 | 5633768.902 | 19171643.7971
415 | 4185266.5789 | 19278032.2765 | 66108.5442 | 23529407.3996
416 | 6829506.0327 | 7937434.6344 | 1228317.5064 | 15995258.1735
417 | 4557414.2008 | 2517120.9947 | 1095255.2199 | 8169790.4154
418 | 25225584.3707 | 19127130.93 | 665523.1611 | 45018238.4618
419 | 28883030.6234 | 0 | 3169763.5823 | 32052794.2057
420 | 2346989.2472 | 2729189.2806 | 1184671.2816 | 6260849.8094
421 | 1328694.9077 | 6285120.6133 | 49447.4515 | 7663262.9725
422 | 10061407.7419 | 0 | 911951.851 | 10973359.5929
423 | 13505717.753 | 7869983.4084 | 1417118.2936 | 22792819.4551
424 | 5150584.7684 | 4023114.0165 | 858699.3489 | 10032398.1338
425 | 30086670.2742 | 0 | 421763.6342 | 30508433.9084
426 | 10735892.1862 | 6450880.066 | 577565.4436 | 17764337.6958
427 | 1370469.0932 | 2079239.1465 | 194662.5307 | 3644370.7704
428 | 1761613.3067 | 15086241.836 | 670961.322 | 17518816.4647
429 | 1804571.0367 | 6951464.7963 | 4045243.3038 | 12801279.1368
430 | 10166813.7407 | 2991250.0997 | 0 | 13158063.8404
431 | 7681274.795 | 2258509.879 | 1333666.8352 | 11273451.5092
432 | 38109551.0795 | 1559397.9169 | 1313341.6305 | 40982290.6269
433 | 7236546.6246 | 0 | 2370009.6744 | 9606556.299
434 | 1573259.7058 | 6826601.0354 | 785748.5854 | 9185609.3266
435 | 2412141.8068 | 0 | 1774107.5321 | 4186249.3389
436 | 670336.4469 | 773720.0362 | 619126.2484 | 2063182.7315
437 | 20296571.8752 | 11146101.7106 | 1158973.0334 | 32601646.6191
438 | 2677732.0714 | 13119323.4422 | 111785.8469 | 15908841.3604
439 | 7327982.2704 | 14104949.4171 | 9162892.9848 | 30595824.6724
440 | 13886367.8701 | 1264943.3857 | 762293.6294 | 15913604.8851
441 | 34040655.9556 | 7557088.3016 | 2275008.5493 | 43872752.8064
442 | 2422240.156 | 3363383.6354 | 1495823.7783 | 7281447.5697
443 | 3291736.7176 | 8261277.3206 | 207972.0031 | 11760986.0413
444 | 25919044.3807 | 20475227.3365 | 48728.8825 | 46443000.5998
445 | 3381830.2959 | 0 | 14257077.1613 | 17638907.4572
446 | 11809191.5914 | 16529156.956 | 90241.8165 | 28428590.364
447 | 10269036.743 | 2123259.9325 | 739412.104 | 13131708.7795
448 | 4178827.1719 | 8242226.6899 | 1583098.1277 | 14004151.9896
449 | 2255385.9561 | 15701488.9651 | 14498203.6502 | 32455078.5713
450 | 1017390.3793 | 4179062.7178 | 493336.0254 | 5689789.1225
451 | 8901110.9195 | 0 | 1725069.9779 | 10626180.8974
452 | 7601727.7494 | 22594171.5233 | 480527.0938 | 30676426.3666
453 | 2758195.1229 | 21907653.7414 | 9336106.1966 | 34001955.0608
454 | 3445927.8475 | 11775855.4615 | 0 | 15221783.309
455 | 8852284.4466 | 0 | 150919.1134 | 9003203.5599
456 | 7710494.6246 | 15381223.5277 | 220638.2441 | 23312356.3964
457 | 4798198.8404 | 0 | 635543.0095 | 5433741.8499
458 | 15530361.0397 | 5454338.4108 | 0 | 20984699.4505
459 | 4261649.048 | 1487445.7278 | 4258104.3475 | 10007199.1232
460 | 17915383.9593 | 7570709.6926 | 0 | 25486093.6518
461 | 13262851.4018 | 13300376.2364 | 607729.9924 | 27170957.6306
462 | 12690185.4471 | 11545691.6369 | 166229.2512 | 24402106.3352
463 | 2778255.6287 | 4417350.1167 | 1756296.2916 | 8951902.0371
464 | 14762464.6263 | 0 | 770333.4104 | 15532798.0367
465 | 11161546.566 | 1447166.0639 | 69513.5194 | 12678226.1493
466 | 8196579.0006 | 22744660.0432 | 6601028.1018 | 37542267.1455
467 | 3831002.3329 | 3055546.0846 | 1796216.8445 | 8682765.262
468 | 8444525.1734 | 5114553.287 | 8896373.7575 | 22455452.2179
469 | 8210758.474 | 0 | 586849.3503 | 8797607.8243
470 | 1853476.4303 | 0 | 0 | 1853476.4303
471 | 23777014.2423 | 3282338.8426 | 1154526.286 | 28213879.3709
472 | 5357413.5777 | 13076427.5692 | 428451.3517 | 18862292.4986
473 | 12333941.4045 | 8259134.1989 | 3950912.4168 | 24543988.0202
474 | 5480703.9121 | 11129035.6898 | 651561.6874 | 17261301.2893
475 | 276453.9547 | 0 | 937946.5681 | 1214400.5229
476 | 7208963.6492 | 0 | 0 | 7208963.6492
477 | 1074512.9107 | 2730810.6368 | 325194.3861 | 4130517.9336
478 | 4113658.9 | 7517780.5022 | 1827042.0556 | 13458481.4578
479 | 20962818.8573 | 9713786.7376 | 592529.4242 | 31269135.0192
480 | 7135045.1998 | 0 | 0 | 7135045.1998
481 | 10301524.6165 | 7218063.7034 | 1141235.4243 | 18660823.7442
482 | 3452503.6024 | 9751286.3491 | 1937491.9232 | 15141281.8746
483 | 5811903.7055 | 11908971.481 | 0 | 17720875.1865
484 | 2014847.6216 | 12899607.8301 | 0 | 14914455.4516
485 | 19203679.2428 | 14440570.0213 | 468915.7454 | 34113165.0095
486 | 10374984.972 | 3655665.3609 | 1924915.1777 | 15955565.5106
487 | 5998766.3497 | 8682398.2505 | 1206459.3676 | 15887623.9678
488 | 2862039.9379 | 5015292.3499 | 812231.5052 | 8689563.7929
489 | 738421.8802 | 3329909.5363 | 3129194.7559 | 7197526.1723
490 | 3644331.4267 | 2852611.9346 | 0 | 6496943.3613
491 | 4946398.207 | 0 | 141509.1425 | 5087907.3495
492 | 12971950.2912 | 2756297.2747 | 2212684.1517 | 17940931.7176
493 | 13339774.3016 | 21832037.9624 | 76676.4525 | 35248488.7166
494 | 11864.5568 | 7859212.1605 | 195519.4375 | 8066596.1548
495 | 4391966.6988 | 13440236.4617 | 1931244.1618 | 19763447.3223
496 | 5359154.9081 | 7777681.0083 | 924342.3504 | 14061178.2669
497 | 50691171.6755 | 9052726.426 | 13047260.9725 | 72791159.0741
498 | 19847328.11 | 5962995.7516 | 0 | 25810323.8616
499 | 10491872.8954 | 6063704.0133 | 248436.6612 | 16804013.5699
500 | 14369050.7319 | 14919421.5782 | 84234.7073 | 29372707.0175
501 | 4941764.0916 | 15129046.2449 | 0 | 20070810.3365
502 | 5244560.861 | 3407775.0937 | 4598911.9127 | 13251247.8674
503 | 6854374.5166 | 4025112.2222 | 12128603.9775 | 23008090.7163
504 | 4733105.7441 | 2432264.0599 | 193564.0009 | 7358933.8048
505 | 2533392.0259 | 11674858.0556 | 6845611.4195 | 21053861.5009
506 | 15220362.9721 | 12633768.2911 | 1271769.2909 | 29125900.5541
507 | 2223572.7348 | 18541802.0233 | 0 | 20765374.7581
508 | 1019609.983 | 4896551.124 | 471462.0029 | 6387623.1099
509 | 9365818.9657 | 11913743.0765 | 838888.6713 | 22118450.7135
510 | 2855666.5662 | 12470826.998 | 8178471.3468 | 23504964.911
511 | 2984221.3947 | 24166613.4418 | 0 | 27150834.8365
512 | 2110292.5471 | 4236500.9172 | 3747466.7064 | 10094260.1707
513 | 46190242.8128 | 8217553.7002 | 7434305.3089 | 61842101.8218
514 | 5874973.558 | 5965351.5399 | 944772.8013 | 12785097.8991
515 | 7498810.0115 | 3575350.8027 | 0 | 11074160.8142
516 | 6615178.5622 | 3802242.2243 | 320027.0452 | 10737447.8318
517 | 6815814.7063 | 1733295.294 | 1307260.1423 | 9856370.1426
518 | 966801.5965 | 16396876.7108 | 1132671.2584 | 18496349.5657
519 | 16907313.3474 | 0 | 3632896.7284 | 20540210.0758
520 | 10884625.6685 | 3054808.32 | 1767199.0108 | 15706632.9993
521 | 12257622.55 | 12610958.8724 | 740481.3407 | 25609062.7631
522 | 4218185.7831 | 17214655.1511 | 0 | 21432840.9342
523 | 12148061.4504 | 0 | 2005333.8657 | 14153395.3161
524 | 5244675.1273 | 6392249.778 | 1074462.8367 | 12711387.742
525 | 8031090.5484 | 4670829.5458 | 992013.1782 | 13693933.2723
526 | 6017648.0611 | 3633930.6774 | 268469.9782 | 9920048.7167
527 | 1555450.4977 | 4600603.7001 | 1724178.7134 | 7880232.9113
528 | 3262744.8862 | 8361217.2202 | 964438.6119 | 12588400.7182
529 | 3410758.2364 | 8838615.4589 | 42553.4692 | 12291927.1645
530 | 11058143.9937 | 18403758.9247 | 0 | 29461902.9184
531 | 3646278.5798 | 0 | 536599.1266 | 4182877.7064
532 | 4107132.4249 | 3707711.2891 | 17653785.9466 | 25468629.6606
533 | 8733438.6573 | 9267412.632 | 2352516.5256 | 20353367.8149
534 | 13063045.4978 | 16575041.0554 | 7475431.2804 | 37113517.8336
535 | 7011406.3954 | 163440.5277 | 3127276.9257 | 10302123.8488
536 | 1328504.2682 | 4366059.4844 | 103826.7248 | 5798390.4774
537 | 3212156.0992 | 9260971.9058 | 589699.9157 | 13062827.9208
538 | 5952199.5805 | 3064927.791 | 164237.3216 | 9181364.6931
539 | 187945.1557 | 11461615.7451 | 798150.8177 | 12447711.7185
540 | 6785445.4937 | 17088675.0612 | 0 | 23874120.5549
541 | 14772487.3539 | 4269889.9549 | 11686612.6314 | 30728989.9401
542 | 3154119.8996 | 0 | 12029632.1486 | 15183752.0482
543 | 3446416.7045 | 0 | 130521.3558 | 3576938.0603
544 | 6973381.297 | 0 | 724772.8582 | 7698154.1552
545 | 7727551.0677 | 2236988.2252 | 120280.7415 | 10084820.0344
546 | 10490782.0396 | 0 | 6376443.2726 | 16867225.3122
547 | 3216437.82 | 16197775.4017 | 7318.4923 | 19421531.714
548 | 8696236.1917 | 944970.6989 | 612558.7766 | 10253765.6672
549 | 6610014.7429 | 8954818.1558 | 131049.713 | 15695882.6117
550 | 4825443.2733 | 12463395.3951 | 0 | 17288838.6684
551 | 1489913.6193 | 0 | 2358592.1825 | 3848505.8018
552 | 7023652.002 | 7294779.7674 | 1241571.4782 | 15560003.2477
553 | 4693300.8778 | 4349473.3763 | 105313.1937 | 9148087.4478
554 | 14093283.9831 | 6486276.2785 | 15360547.0558 | 35940107.3174
555 | 12136855.7971 | 10075570.9793 | 0 | 22212426.7764
556 | 25926483.1466 | 19109865.2164 | 122679.6911 | 45159028.0541
557 | 11336047.2273 | 14056391.132 | 3603499.1338 | 28995937.4931
558 | 2889200.7605 | 0 | 0 | 2889200.7605
559 | 1690374.8987 | 2619070.9795 | 0 | 4309445.8781
560 | 4670370.2207 | 0 | 6680224.0581 | 11350594.2787
561 | 7330123.0006 | 11349148.8631 | 2313540.3388 | 20992812.2025
562 | 5802263.249 | 0 | 0 | 5802263.249
563 | 3738927.7108 | 14527921.7059 | 2040005.3831 | 20306854.7998
564 | 2899383.9057 | 0 | 693737.7106 | 3593121.6163
565 | 4950160.0581 | 4375093.3163 | 6779850.5044 | 16105103.8788
566 | 12730252.0082 | 0 | 4206411.3318 | 16936663.34
567 | 5247499.402 | 6693308.529 | 514221.5482 | 12455029.4791
568 | 3700929.7826 | 7131963.3946 | 3976204.4349 | 14809097.6122
569 | 4689457.1597 | 9855776.3259 | 0 | 14545233.4856
570 | 10189959.1722 | 2750180.0238 | 306349.8892 | 13246489.0852
571 | 1731493.9433 | 4741405.3282 | 4456711.5245 | 10929610.796
572 | 3844539.9656 | 10414716.4296 | 0 | 14259256.3952
573 | 3842444.796 | 1214928.6085 | 0 | 5057373.4044
574 | 2837828.711 | 12720598.777 | 402021.1157 | 15960448.6036
575 | 7398289.8802 | 2901154.4555 | 2908927.6595 | 13208371.9952
576 | 1689571.4603 | 0 | 0 | 1689571.4603
577 | 9807704.7485 | 8577991.9936 | 20183903.5249 | 38569600.267
578 | 156066.8731 | 2543421.9987 | 2889405.4537 | 5588894.3254
579 | 14302660.5661 | 2562244.4335 | 3968074.4704 | 20832979.47
580 | 7918265.3433 | 8789234.4928 | 203472.7803 | 16910972.6163
581 | 6184217.2011 | 5706432.8944 | 564798.2909 | 12455448.3864
582 | 2309144.0847 | 4709064.6415 | 9011.9523 | 7027220.6785
583 | 13101452.9417 | 8253233.0411 | 766086.1849 | 22120772.1676
584 | 10374786.8208 | 2034467.1529 | 412030.189 | 12821284.1627
585 | 14600782.3139 | 1582872.2086 | 1946451.9803 | 18130106.5028
586 | 4549360.7745 | 14794536.0772 | 0 | 19343896.8517
587 | 4414570.5186 | 1258256.3447 | 0 | 5672826.8632
588 | 32699726.8215 | 0 | 1747906.2012 | 34447633.0228
589 | 4902204.3408 | 2471346.4513 | 2135571.8495 | 9509122.6416
590 | 3454320.7215 | 9468006.5139 | 0 | 12922327.2354
591 | 11225312.9253 | 9239653.9523 | 206208.4732 | 20671175.3508
592 | 20882106.9049 | 10680772.6629 | 2363192.6298 | 33926072.1975
593 | 9180844.434 | 0 | 0 | 9180844.434
594 | 3225559.5801 | 3053129.0723 | 237400.0171 | 6516088.6696
595 | 8433113.5341 | 16366486.8137 | 18194739.718 | 42994340.0657
596 | 1571289.8945 | 11686281.9561 | 274513.3049 | 13532085.1556
597 | 7125721.3748 | 19692927.9277 | 1483556.8754 | 28302206.1779
598 | 3003170.3046 | 0 | 258775.704 | 3261946.0085
599 | 8407788.9254 | 22734105.0481 | 4323736.5819 | 35465630.5554
600 | 23879971.188 | 0 | 2673340.717 | 26553311.905
601 | 3515935.9433 | 5099196.2457 | 54595.3027 | 8669727.4917
602 | 9322078.0064 | 9665948.4168 | 1089279.822 | 20077306.2453
603 | 5478360.1186 | 3429898.1104 | 1234724.6479 | 10142982.877
604 | 864231.2058 | 9715566.2491 | 168405.0491 | 10748202.504
605 | 2941845.1148 | 4831151.0899 | 1508005.1237 | 9281001.3284
606 | 37604617.3286 | 0 | 351351.4794 | 37955968.808
607 | 2682703.4902 | 4319670.5643 | 0 | 7002374.0545
608 | 26220776.2026 | 3906242.1357 | 0 | 30127018.3384
609 | 5683718.4804 | 6188343.7677 | 2486175.1615 | 14358237.4096
610 | 3697823.2599 | 1882998.5392 | 150127.1528 | 5730948.9518
611 | 828796.588 | 7376211.6163 | 7722384.0998 | 15927392.3041
612 | 15445594.0119 | 834831.8005 | 260674.2258 | 16541100.0382
613 | 13586164.2902 | 17809996.4745 | 4760596.2474 | 36156757.0121
614 | 2036255.0724 | 6328969.0666 | 465269.3561 | 8830493.495
615 | 1135194.7444 | 12537342.4185 | 2247974.5203 | 15920511.6832
616 | 9369586.0732 | 10418403.0104 | 1136134.1616 | 20924123.2452
617 | 28262705.8092 | 7025430.7521 | 944626.219 | 36232762.7803
618 | 17113355.5965 | 0 | 23069.7348 | 17136425.3313
619 | 25909073.8796 | 9221828.8296 | 4926982.301 | 40057885.0102
620 | 1287506.7722 | 17849804.6373 | 0 | 19137311.4095
621 | 11410970.8219 | 740730.8746 | 676985.575 | 12828687.2714
622 | 1929374.8893 | 9765044.51 | 0 | 11694419.3993
623 | 893595.5296 | 1574783.6901 | 93300.4551 | 2561679.6748
624 | 2508764.583 | 5718210.8456 | 2131778.7927 | 10358754.2214
625 | 4569159.7942 | 3240774.3486 | 2323551.5283 | 10133485.671
626 | 3720343.8431 | 11851152.0574 | 1072962.9527 | 16644458.8532
627 | 2884946.7269 | 4705502.5059 | 3108539.0936 | 10698988.3264
628 | 1971396.4376 | 0 | 78082.1764 | 2049478.614
629 | 6476332.0974 | 4517115.8077 | 104201.5398 | 11097649.4448
630 | 11205575.4085 | 5063607.0403 | 1355088.867 | 17624271.3158
631 | 10074827.1292 | 4075936.8884 | 1198890.923 | 15349654.9406
632 | 4451145.7974 | 13822868.788 | 0 | 18274014.5853
633 | 27161186.6468 | 7072112.2839 | 8855631.3893 | 43088930.3199
634 | 12325087.782 | 12691662.1284 | 3586770.6432 | 28603520.5537
635 | 5566443.9571 | 14657968.5839 | 138856.837 | 20363269.3781
636 | 12753572.0438 | 18059788.412 | 4827218.1163 | 35640578.5721
637 | 20721601.7701 | 14818273.4379 | 8563436.1213 | 44103311.3293
638 | 38603943.1122 | 4060980.9499 | 4556636.231 | 47221560.2931
639 | 3461841.1858 | 11893538.0689 | 840906.1414 | 16196285.3961
640 | 3971594.8099 | 372093.1547 | 483683.5665 | 4827371.531
641 | 6119009.8668 | 9174860.8752 | 8110846.7905 | 23404717.5326
642 | 6621677.2563 | 0 | 697772.9114 | 7319450.1677
643 | 10847803.2993 | 3819497.4839 | 7759691.6712 | 22426992.4545
644 | 11736767.5387 | 6838957.7058 | 0 | 18575725.2444
645 | 1117198.1828 | 4093235.3521 | 325219.4637 | 5535652.9986
646 | 13973451.4223 | 8297722.3987 | 987412.6515 | 23258586.4725
647 | 2148515.0428 | 10941433.5296 | 0 | 13089948.5723
648 | 3845614.2536 | 16398127.1979 | 1832230.6446 | 22075972.0961
649 | 3996039.686 | 2250014.3093 | 691476.3903 | 6937530.3857
650 | 5365627.8813 | 18471183.3936 | 2568961.3564 | 26405772.6313
651 | 949238.6939 | 4516277.1346 | 2573270.1326 | 8038785.9611
652 | 21182744.0309 | 0 | 1567645.8077 | 22750389.8386
653 | 24730460.4061 | 1942026.2101 | 4751494.0116 | 31423980.6278
654 | 11078608.1957 | 6676147.5284 | 318693.573 | 18073449.2971
655 | 4392583.475 | 13716149.7675 | 0 | 18108733.2425
656 | 7877000.1417 | 0 | 254023.4926 | 8131023.6343
657 | 8221457.7854 | 3022331.869 | 98138.5677 | 11341928.2221
658 | 11120883.7599 | 2394968.8147 | 7124193.6793 | 20640046.254
659 | 3005690.2349 | 4307182.6261 | 22613.2849 | 7335486.1459
660 | 1541068.2892 | 4684126.3623 | 477455.5643 | 6702650.2158
661 | 1757395.8205 | 3000772.1444 | 2928989.9446 | 7687157.9094
662 | 28634565.8497 | 15812809.1267 | 2018249.2614 | 46465624.2378
663 | 18103457.8107 | 6755494.2035 | 183071.5179 | 25042023.5321
664 | 26940484.1305 | 0 | 1017081.9737 | 27957566.1042
665 | 8708239.0432 | 2662583.0509 | 486718.3501 | 11857540.4441
666 | 1883061.6467 | 0 | 1390774.4274 | 3273836.0741
667 | 13763366.7521 | 16622661.8638 | 1524820.0868 | 31910848.7028
668 | 15031774.0015 | 6928984.162 | 54631.3296 | 22015389.493
669 | 9801235.7421 | 4108281.3614 | 39258.8179 | 13948775.9214
670 | 12669019.2068 | 4517641.655 | 0 | 17186660.8618
671 | 9031618.6131 | 6968085.2465 | 3502588.1167 | 19502291.9762
672 | 14155719.8152 | 12244069.002 | 16495.0727 | 26416283.8899
673 | 18127290.4212 | 5281792.2448 | 2732048.2684 | 26141130.9344
674 | 3333491.6563 | 2694611.7311 | 442615.6891 | 6470719.0765
675 | 14709874.3007 | 6919517.2758 | 0 | 21629391.5765
676 | 25333933.8791 | 16049380.6562 | 206853.0158 | 41590167.5511
677 | 2682846.5768 | 0 | 1133927.4257 | 3816774.0025
678 | 6311111.074 | 4377543.1321 | 2295069.8982 | 12983724.1043
679 | 13103221.123 | 15514879.7865 | 0 | 28618100.9095
680 | 5159412.1411 | 1368212.994 | 0 | 6527625.1352
681 | 745892.1586 | 8390115.7292 | 250686.0801 | 9386693.9679
682 | 7131548.7348 | 12983412.5029 | 5095018.0652 | 25209979.3028
683 | 14965977.2319 | 18372836.7269 | 1162075.4219 | 34500889.3807
684 | 12944055.6341 | 4160609.8065 | 8920180.9869 | 26024846.4276
685 | 4083062.7599 | 4207151.2329 | 324618.1919 | 8614832.1846
686 | 2704356.3247 | 22720338.7565 | 31217.1382 | 25455912.2194
687 | 14410769.1364 | 0 | 0 | 14410769.1364
688 | 20205510.0218 | 4973445.8197 | 239000.5433 | 25417956.3848
689 | 12397554.6012 | 1103878.7526 | 2448446.8062 | 15949880.1599
690 | 13613313.9109 | 0 | 33352958.8055 | 46966272.7163
691 | 25313504.014 | 3398593.6607 | 761504.5817 | 29473602.2563
692 | 9025684.0463 | 655482.4859 | 8347503.2875 | 18028669.8198
693 | 6427922.3356 | 16585695.4478 | 0 | 23013617.7834
694 | 180735.3759 | 6228187.4061 | 3101834.8953 | 9510757.6773
695 | 5463493.737 | 26594283.4373 | 7437676.354 | 39495453.5283
696 | 14430416.1706 | 6464311.4815 | 563306.6846 | 21458034.3367
697 | 23761478.3297 | 6718606.4948 | 341415.5538 | 30821500.3783
698 | 982408.5312 | 13614630.6738 | 0 | 14597039.2051
699 | 11309896.8554 | 6473372.3837 | 4486045.1376 | 22269314.3767
700 | 2792210.6324 | 4953129.0731 | 444536.2276 | 8189875.9331
701 | 1468061.52 | 14863149.0939 | 0 | 16331210.6139
702 | 14907328.6166 | 0 | 443961.3929 | 15351290.0095
703 | 4217278.9556 | 2121331.7854 | 2745929.6693 | 9084540.4103
704 | 13238931.223 | 10163242.8748 | 17077923.321 | 40480097.4187
705 | 5243705.258 | 0 | 3366400.4465 | 8610105.7044
706 | 20552740.2207 | 1001615.6371 | 0 | 21554355.8578
707 | 1138736.463 | 1005382.4492 | 66298.5951 | 2210417.5073
708 | 997225.4528 | 4628597.9196 | 303896.1507 | 5929719.5231
709 | 1855705.7623 | 7475081.0139 | 953798.712 | 10284585.4882
710 | 3168734.858 | 5985119.4824 | 764058.9036 | 9917913.244
711 | 12536078.8702 | 5854380.3649 | 0 | 18390459.2351
712 | 11563977.5136 | 8616925.7564 | 8837372.3722 | 29018275.6422
713 | 7655593.6659 | 1792663.6823 | 740346.7663 | 10188604.1144
714 | 1769002.0239 | 0 | 3634282.866 | 5403284.8899
715 | 1552705.4566 | 3599278.2691 | 1835943.6207 | 6987927.3464
716 | 1136230.7016 | 8485365.5284 | 2223217.8021 | 11844814.032
717 | 16707307.5968 | 4839242.2907 | 4136483.0007 | 25683032.8882
718 | 3836184.6728 | 4459947.621 | 6849714.1004 | 15145846.3942
719 | 3614376.7041 | 0 | 695501.1098 | 4309877.8139
720 | 3660083.3094 | 8844428.3123 | 39272.361 | 12543783.9827
721 | 1038032.7544 | 5460255.4075 | 800933.5957 | 7299221.7575
722 | 2285036.7694 | 13214011.9928 | 0 | 15499048.7622
723 | 13050053.7792 | 39921065.0264 | 591314.9222 | 53562433.7278
724 | 17084144.2086 | 7118280.8285 | 0 | 24202425.0371
725 | 7444576.0198 | 6060032.7168 | 187686.2569 | 13692294.9935
726 | 5898784.9848 | 810973.33 | 1024972.9118 | 7734731.2266
727 | 1646812.2724 | 5546780.0934 | 42834.4566 | 7236426.8224
728 | 7210150.0763 | 3661869.7691 | 8786116.9525 | 19658136.7979
729 | 8434419.5886 | 12823084.1251 | 28405.674 | 21285909.3876
730 | 3868154.7137 | 5480913.9142 | 5723448.5217 | 15072517.1497
731 | 5696974.8546 | 0 | 1386358.5144 | 7083333.3691
732 | 5580321.5493 | 0 | 9934846.1204 | 15515167.6697
733 | 13037597.4277 | 7161662.5341 | 7456070.8379 | 27655330.7997
734 | 4230170.2834 | 5804581.8192 | 464335.625 | 10499087.7276
735 | 26268797.4068 | 9589717.213 | 17169359.9924 | 53027874.6123
736 | 7194791.8124 | 5702769.3828 | 1525409.4294 | 14422970.6246
737 | 8822335.2122 | 0 | 44672.217 | 8867007.4292
738 | 4250739.7574 | 7472219.0571 | 4787381.3252 | 16510340.1397
739 | 4398359.7616 | 27062641.431 | 769837.227 | 32230838.4196
740 | 14562233.8602 | 16441519.3677 | 1118842.1438 | 32122595.3716
741 | 18229830.2734 | 0 | 17794481.2659 | 36024311.5393
742 | 10877777.4832 | 7244071.5929 | 951374.8681 | 19073223.9442
743 | 5774892.3438 | 11030356.3492 | 8397683.7895 | 25202932.4825
744 | 14916391.268 | 15785777.4094 | 5621879.3585 | 36324048.0359
745 | 2731333.1718 | 7022771.6113 | 817995.5308 | 10572100.3139
746 | 12519687.2176 | 2652314.0032 | 1099920.6334 | 16271921.8542
747 | 334755.7891 | 1364999.1962 | 1286579.9384 | 2986334.9237
748 | 653716.0711 | 10393260.6828 | 3314666.7214 | 14361643.4753
749 | 16618886.5535 | 0 | 2810061.3485 | 19428947.902
750 | 13320744.5897 | 4376332.9172 | 12665708.004 | 30362785.5109
751 | 7978115.3297 | 13508406.7303 | 0 | 21486522.0601
752 | 10079436.7224 | 14088257.4444 | 10774545.9071 | 34942240.0739
753 | 9076772.4677 | 6723393.7125 | 0 | 15800166.1802
754 | 12827424.5502 | 20112311.4326 | 2231318.9656 | 35171054.9484
755 | 9089151.4288 | 12127870.3663 | 7193283.7841 | 28410305.5792
756 | 3882331.5514 | 0 | 201081.1819 | 4083412.7332
757 | 3625616.964 | 9464075.1047 | 251755.3903 | 13341447.459
758 | 15880038.4514 | 4721820.4312 | 1197138.7189 | 21798997.6016
759 | 7281601.7336 | 26786048.5094 | 0 | 34067650.243
760 | 3990781.323 | 759569.7547 | 5480523.5713 | 10230874.649
761 | 9144262.8383 | 16070801.272 | 2053837.2806 | 27268901.3909
762 | 28774234.776 | 5845903.4862 | 7486022.4062 | 42106160.6684
763 | 16962849.5845 | 22849080.2231 | 3546825.4492 | 43358755.2567
764 | 2847288.5327 | 6440243.334 | 7611995.9106 | 16899527.7773
765 | 10919905.7874 | 19237900.7866 | 2631857.345 | 32789663.9191
766 | 7342062.4086 | 9788522.987 | 0 | 17130585.3957
767 | 17384177.919 | 11061912.9049 | 174186.3098 | 28620277.1338
768 | 26887114.3637 | 3791330.7366 | 3048233.6099 | 33726678.7102
769 | 5575860.4294 | 8691668.5208 | 423282.6724 | 14690811.6227
770 | 9837158.4334 | 31155767.5343 | 282811.535 | 41275737.5027
771 | 2886193.6646 | 0 | 19936045.4476 | 22822239.1122
772 | 6054492.5604 | 6313693.5806 | 123135.6075 | 12491321.7485
773 | 11084669.7904 | 4854630.8482 | 973421.1633 | 16912721.8019
774 | 12880711.4636 | 14105351.3033 | 1774274.974 | 28760337.7409
775 | 5076893.6051 | 3712363.1761 | 1250642.8147 | 10039899.5959
776 | 2205535.9673 | 5339601.3233 | 4343089.96 | 11888227.2506
777 | 3482387.4432 | 1069294.5266 | 0 | 4551681.9698
778 | 29146077.502 | 10579757.0496 | 210599.9361 | 39936434.4877
779 | 10867378.8892 | 2078572.8664 | 0 | 12945951.7556
780 | 1660265.7572 | 1313993.5438 | 7370626.0635 | 10344885.3644
781 | 3753803.6984 | 8863910.9568 | 2473453.4719 | 15091168.1272
782 | 6127956.6345 | 12279427.6829 | 0 | 18407384.3173
783 | 6273192.9575 | 0 | 410833.0599 | 6684026.0175
784 | 9542692.6749 | 27555430.9768 | 15872039.6045 | 52970163.2561
785 | 2987479.6576 | 4213130.082 | 148652.6573 | 7349262.3969
786 | 1914468.8363 | 0 | 953784.3665 | 2868253.2027
787 | 2898644.7286 | 0 | 16608674.8181 | 19507319.5466
788 | 21668302.121 | 6451950.7694 | 2790316.5892 | 30910569.4796
789 | 19381882.5942 | 4383132.331 | 863222.6868 | 24628237.612
790 | 2920513.9825 | 0 | 1070708.5223 | 3991222.5048
791 | 9591562.6188 | 9263985.6388 | 8318072.1078 | 27173620.3653
792 | 8353563.7446 | 33988655.644 | 4343067.5601 | 46685286.9487
793 | 4478488.8637 | 7624815.8387 | 3395637.1911 | 15498941.8935
794 | 5597508.1081 | 4730058.4377 | 896033.6762 | 11223600.2221
795 | 13596594.725 | 16008921.8367 | 1649988.7672 | 31255505.3289
796 | 11800426.0421 | 3519836.1726 | 0 | 15320262.2147
797 | 2744300.6468 | 2870826.1517 | 0 | 5615126.7985
798 | 5464085.1602 | 4700089.3329 | 897132.1105 | 11061306.6036
799 | 7137953.0589 | 0 | 2522525.8023 | 9660478.8611
800 | 3450074.8952 | 0 | 903354.5326 | 4353429.4277
801 | 1629828.5538 | 41984698.4954 | 275992.9642 | 43890520.0134
802 | 5219234.3388 | 9600552.8611 | 2244260.7688 | 17064047.9687
803 | 1171837.4275 | 0 | 26831561.4624 | 28003398.8899
804 | 5852750.7663 | 0 | 0 | 5852750.7663
805 | 7430901.8686 | 8649897.6543 | 1871244.3772 | 17952043.9002
806 | 2907577.7809 | 1904847.6899 | 425634.25 | 5238059.7208
807 | 11165031.2889 | 12353132.943 | 66091.4972 | 23584255.7292
808 | 4262603.9607 | 11264126.1904 | 5041294.4673 | 20568024.6185
809 | 12150615.097 | 39094.2336 | 0 | 12189709.3306
810 | 7695592.6446 | 20500210.177 | 0 | 28195802.8216
811 | 8496057.0128 | 16210417.5806 | 0 | 24706474.5933
812 | 1072677.3623 | 6503255.3532 | 9262867.2197 | 16838799.9352
813 | 7736909.4262 | 3074137.2597 | 3140454.603 | 13951501.2889
814 | 1751153.0022 | 4539677.224 | 0 | 6290830.2262
815 | 8021746.1757 | 4533570.9607 | 6394845.6604 | 18950162.7968
816 | 1394876.9058 | 4271516.3794 | 3492846.5093 | 9159239.7946
817 | 8675012.9972 | 13466845.213 | 0 | 22141858.2102
818 | 3671295.033 | 0 | 1684510.8425 | 5355805.8755
819 | 7052737.6797 | 1260151.8461 | 12562528.9516 | 20875418.4773
820 | 5856244.4233 | 4033578.7482 | 3961089.5863 | 13850912.7578
821 | 912209.5476 | 3615454.4884 | 184101.3793 | 4711765.4153
822 | 12401419.7894 | 5467088.5565 | 11801086.7536 | 29669595.0996
823 | 11550656.3093 | 9313188.0373 | 11926853.1256 | 32790697.4722
824 | 7502537.082 | 20961869.3434 | 12903129.0949 | 41367535.5204
825 | 2952236.5961 | 0 | 2491108.4062 | 5443345.0023
826 | 21619438.4513 | 0 | 519368.8029 | 22138807.2542
827 | 2175400.8278 | 0 | 87763.8875 | 2263164.7153
828 | 4023146.2969 | 4908159.8016 | 5363569.6577 | 14294875.7563
829 | 3505317.6285 | 23094432.952 | 5892802.4091 | 32492552.9895
830 | 6139391.3308 | 6596951.5797 | 5170109.9737 | 17906452.8842
831 | 5549813.5387 | 1703804.7623 | 323291.3156 | 7576909.6165
832 | 4735953.943 | 3638294.6891 | 1556144.421 | 9930393.0532
833 | 2476167.56 | 12244428.6899 | 258458.7744 | 14979055.0243
834 | 31846101.4836 | 0 | 0 | 31846101.4836
835 | 9294930.2737 | 6364043.8215 | 2277177.1238 | 17936151.219
836 | 3914867.5158 | 6583301.9026 | 817371.9554 | 11315541.3739
837 | 809878.4165 | 1476665.9762 | 2575303.9987 | 4861848.3913
838 | 5366357.2849 | 0 | 999220.7841 | 6365578.0691
839 | 3313715.9072 | 7847188.1651 | 17018587.3404 | 28179491.4128
840 | 9221388.8326 | 1817069.4466 | 1967692.457 | 13006150.7362
841 | 5034951.0528 | 15705947.5119 | 49907.4568 | 20790806.0215
842 | 5712884.5338 | 1332289.2836 | 2890112.5015 | 9935286.3189
843 | 4793799.8452 | 11218186.2893 | 153797.8122 | 16165783.9468
844 | 18556092.8748 | 13126059.3988 | 761264.505 | 32443416.7786
845 | 438755.9717 | 13895717.7519 | 2281271.6614 | 16615745.3849
846 | 8265464.341 | 5494550.8611 | 169823.8838 | 13929839.086
847 | 28605512.8864 | 0 | 2377781.5971 | 30983294.4835
848 | 5324345.0393 | 6768615.3704 | 2594807.1262 | 14687767.5359
849 | 2540197.8945 | 8465628.2912 | 1901460.9954 | 12907287.1811
850 | 3526660.3759 | 0 | 100655.7231 | 3627316.099
851 | 11919596.3053 | 13499095.2804 | 946516.1518 | 26365207.7375
852 | 2871585.9429 | 0 | 3628589.008 | 6500174.9509
853 | 28943929.1755 | 23802417.3674 | 5060553.0044 | 57806899.5473
854 | 14119876.0704 | 15792763.2108 | 1210817.661 | 31123456.9422
855 | 3747471.817 | 3338839.9827 | 0 | 7086311.7997
856 | 43066639.2887 | 12223166.909 | 6538359.2894 | 61828165.487
857 | 9910834.4654 | 0 | 3595199.387 | 13506033.8524
858 | 5789829.9332 | 6228367.5379 | 0 | 12018197.471
859 | 14447636.5359 | 14293522.0698 | 786505.7822 | 29527664.3878
860 | 3555233.7801 | 7288405.1921 | 0 | 10843638.9722
861 | 6787892.6209 | 5538094.951 | 69769.4751 | 12395757.047
862 | 7820144.8414 | 5405978.8117 | 190138.9011 | 13416262.5541
863 | 3752691.8021 | 4411298.6771 | 2455662.8516 | 10619653.3309
864 | 13934424.9849 | 4412583.0615 | 1714704.5163 | 20061712.5627
865 | 2645476.8065 | 9779353.2698 | 1147276.3016 | 13572106.3779
866 | 9367452.3638 | 9372989.7469 | 2624266.2383 | 21364708.349
867 | 20960730.2777 | 3082725.8176 | 1080489.0508 | 25123945.1461
868 | 15263577.4254 | 0 | 223228.213 | 15486805.6383
869 | 3895344.4137 | 6021807.3252 | 0 | 9917151.7389
870 | 5262289.7894 | 10702903.6288 | 1032064.939 | 16997258.3571
871 | 19502244.7497 | 4651265.5933 | 5416861.098 | 29570371.441
872 | 5423672.2609 | 0 | 43006.4916 | 5466678.7525
873 | 17691257.4182 | 24069987.9847 | 4000108.8471 | 45761354.25
874 | 9395938.4619 | 0 | 0 | 9395938.4619
875 | 10666360.3207 | 12041955.411 | 0 | 22708315.7317
876 | 6657366.4609 | 11492634.103 | 0 | 18150000.564
877 | 3836115.5011 | 9606988.9693 | 496458.4633 | 13939562.9337
878 | 2911630.4821 | 18092923.8473 | 0 | 21004554.3294
879 | 7965110.1533 | 6979820.0519 | 5053797.1553 | 19998727.3605
880 | 3070125.1533 | 15423500.4745 | 751150.5891 | 19244776.2169
881 | 7811433.5875 | 5733783.1113 | 7730421.9516 | 21275638.6504
882 | 3097582.1748 | 5135049.7885 | 3242150.9316 | 11474782.8949
883 | 3355682.9584 | 0 | 2785077.3212 | 6140760.2797
884 | 22119605.911 | 0 | 13013888.8199 | 35133494.731
885 | 12120065.2658 | 4059392.9807 | 0 | 16179458.2465
886 | 5121840.1784 | 7477760.1991 | 0 | 12599600.3776
887 | 5584438.5877 | 5568963.8822 | 5757831.132 | 16911233.6019
888 | 4626159.2803 | 1851921.2032 | 880392.2218 | 7358472.7053
889 | 1882589.5921 | 8375710.4377 | 506114.9783 | 10764415.008
890 | 20974678.4518 | 2809599.0493 | 26448.1741 | 23810725.6752
891 | 4088304.4717 | 8158855.0292 | 3042288.7384 | 15289448.2392
892 | 2530461.5622 | 0 | 2637177.1777 | 5167638.7399
893 | 8557501.1733 | 4813766.926 | 1460054.7369 | 14831322.8362
894 | 24844181.9295 | 16255998.7798 | 1392174.6589 | 42492355.3682
895 | 10590076.3067 | 4044578.0969 | 2476764.7587 | 17111419.1623
896 | 681627.7378 | 24973791.5933 | 2291340.7997 | 27946760.1308
897 | 296396.1104 | 5960239.782 | 2728946.3299 | 8985582.2223
898 | 2227052.3266 | 5164940.9258 | 9777988.1445 | 17169981.397
899 | 8376251.2929 | 15043235.4299 | 0 | 23419486.7228
900 | 15037445.1251 | 5406099.2039 | 109154.3713 | 20552698.7003
901 | 18284923.6539 | 260526.2472 | 1965202.4532 | 20510652.3542
902 | 14504245.9715 | 10473886.6695 | 927629.2484 | 25905761.8894
903 | 4469102.6383 | 3777941.6 | 5403149.4677 | 13650193.706
904 | 16042014.5444 | 4531031.4347 | 1607491.8844 | 22180537.8635
905 | 1307649.8028 | 7575475.8201 | 80706.4783 | 8963832.1012
906 | 22131660.3441 | 0 | 0 | 22131660.3441
907 | 4909561.1255 | 4272380.6948 | 3160771.1983 | 12342713.0185
908 | 8308890.9895 | 5173137.9113 | 1096493.6904 | 14578522.5912
909 | 7786958.092 | 3259642.2196 | 1436000.0353 | 12482600.3469
910 | 5701626.9826 | 0 | 952071.5693 | 6653698.552
911 | 15077641.0482 | 0 | 2593369.5553 | 17671010.6035
912 | 10774308.8106 | 0 | 1725965.1375 | 12500273.9481
913 | 10960166.8316 | 23570927.7484 | 8215858.833 | 42746953.413
914 | 2134407.4285 | 2848752.3935 | 488737.8237 | 5471897.6457
915 | 15683327.2986 | 2160810.3093 | 12509893.6855 | 30354031.2934
916 | 3078727.0376 | 2351504.0635 | 3274222.1832 | 8704453.2843
917 | 9988298.5632 | 20282973.4112 | 293274.5952 | 30564546.5697
918 | 1841072.25 | 14343787.4724 | 1713244.758 | 17898104.4804
919 | 12630428.0703 | 0 | 1566019.1104 | 14196447.1807
920 | 2794111.0842 | 8623146.9416 | 767506.6222 | 12184764.6479
921 | 8925515.6375 | 8994627.7875 | 1687386.5739 | 19607529.9989
922 | 7441765.5874 | 26013955.9873 | 256991.366 | 33712712.9406
923 | 22038542.982 | 6282650.8818 | 0 | 28321193.8638
924 | 9304995.964 | 12961366.1407 | 288940.2057 | 22555302.3104
925 | 20349355.869 | 7101401.4903 | 3592356.3133 | 31043113.6726
926 | 3715571.2167 | 9655105.7523 | 221765.2088 | 13592442.1778
927 | 2099824.1649 | 29688521.9616 | 679818.4157 | 32468164.5421
928 | 3482610.7001 | 11734988.4315 | 1044257.7875 | 16261856.9191
929 | 8241615.2603 | 4349405.2042 | 268619.0746 | 12859639.5392
930 | 10020369.3332 | 9303174.6601 | 1960024.8785 | 21283568.8718
931 | 3631718.2429 | 11974454.0085 | 8554529.7469 | 24160701.9983
932 | 13939074.2562 | 13190199.3685 | 2777585.0156 | 29906858.6403
933 | 21337101.5866 | 11339210.5389 | 2990832.6962 | 35667144.8217
934 | 18635577.1422 | 0 | 204780.1529 | 18840357.2951
935 | 3607096.3854 | 8211533.4555 | 8457640.0916 | 20276269.9325
936 | 16883160.4343 | 3939686.8753 | 2440499.6296 | 23263346.9393
937 | 5940374.4044 | 5196787.9268 | 4729539.8142 | 15866702.1454
938 | 7025913.3714 | 0 | 58510.4713 | 7084423.8427
939 | 11914311.986 | 1811916.3062 | 0 | 13726228.2923
940 | 4531498.4199 | 2845477.9648 | 24775265.0904 | 32152241.475
941 | 5724083.0129 | 0 | 13611719.9362 | 19335802.9491
942 | 9879102.123 | 17275237.1398 | 787780.5734 | 27942119.8363
943 | 2092908.0762 | 2741034.6862 | 2529748.0267 | 7363690.7891
944 | 11559900.554 | 0 | 0 | 11559900.554
945 | 3688696.3846 | 0 | 772030.1139 | 4460726.4985
946 | 2216508.1385 | 11406060.8551 | 13515667.2896 | 27138236.2832
947 | 3685702.8333 | 11017867.2493 | 4354746.0685 | 19058316.1511
948 | 5106779.4744 | 9819957.456 | 2681210.0836 | 17607947.014
949 | 10285337.5012 | 4586646.7415 | 124071.2262 | 14996055.4689
950 | 6942830.2682 | 6913048.016 | 163167.8288 | 14019046.113
951 | 25759994.5502 | 4948273.6262 | 177824.2366 | 30886092.4131
952 | 10121799.392 | 2027625.0563 | 1604444.4686 | 13753868.917
953 | 8778170.086 | 4312264.8311 | 1596688.647 | 14687123.5641
954 | 20151145.5851 | 7521945.6116 | 1200890.2394 | 28873981.4361
955 | 7020009.5428 | 0 | 641024.7667 | 7661034.3096
956 | 5173646.2568 | 9388035.4683 | 458708.6634 | 15020390.3885
957 | 5122265.9406 | 4908055.648 | 8203278.5149 | 18233600.1035
958 | 3961148.8321 | 6513770.8767 | 12184.0789 | 10487103.7876
959 | 4329123.9053 | 4089149.4382 | 525959.4605 | 8944232.804
960 | 11371613.8207 | 17378350.9598 | 102045.89 | 28852010.6704
961 | 632405.7198 | 19818712.6082 | 3385145.9794 | 23836264.3074
962 | 10851262.0858 | 2569556.5167 | 2358725.6173 | 15779544.2198
963 | 10226623.9174 | 0 | 1356304.0912 | 11582928.0085
964 | 3053878.2399 | 22784203.8346 | 65521.7724 | 25903603.8469
965 | 31284346.3791 | 2555036.9728 | 13067015.2487 | 46906398.6005
966 | 4597485.4547 | 3886556.9482 | 0 | 8484042.403
967 | 3838301.4972 | 9442534.5436 | 7554884.8138 | 20835720.8547
968 | 27464824.7687 | 5622706.9756 | 592773.5595 | 33680305.3039
969 | 12561839.3655 | 8289910.2777 | 232978.4906 | 21084728.1337
970 | 11255970.2374 | 1913760.3867 | 555164.1012 | 13724894.7253
971 | 8398930.1584 | 0 | 4835737.3414 | 13234667.4998
972 | 10497767.6201 | 8790768.691 | 483395.3084 | 19771931.6194
973 | 23526630.7343 | 2002502.2213 | 2357718.165 | 27886851.1205
974 | 7739779.7306 | 23487079.4282 | 922181.7749 | 32149040.9337
975 | 1762759.803 | 5205157.6008 | 0 | 6967917.4038
976 | 6813417.0562 | 1099934.9534 | 0 | 7913352.0096
977 | 7494158.4403 | 4432603.8554 | 2101567.0653 | 14028329.361
978 | 10046914.6918 | 4157298.9765 | 0 | 14204213.6683
979 | 9075129.2401 | 4554775.0524 | 2798235.6876 | 16428139.9802
980 | 5352896.4718 | 9797602.4699 | 2719348.7837 | 17869847.7254
981 | 7191324.5382 | 21913202.1748 | 3118998.0783 | 32223524.7913
982 | 14343046.6478 | 4485021.6886 | 1907608.1254 | 20735676.4618
983 | 10358072.0584 | 5542646.6265 | 2676550.1365 | 18577268.8215
984 | 9220654.7927 | 5075705.8964 | 12517467.4098 | 26813828.0989
985 | 1554536.0598 | 19752697.8969 | 91635.4457 | 21398869.4024
986 | 7308569.4166 | 1979306.2516 | 915766.3093 | 10203641.9775
987 | 29317933.4867 | 8321274.8139 | 983943.3347 | 38623151.6353
988 | 3994779.3242 | 5422411.7143 | 14751301.5006 | 24168492.5392
989 | 11767498.3953 | 7908405.5188 | 0 | 19675903.914
990 | 7283765.7889 | 6027495.721 | 2760431.4982 | 16071693.0081
991 | 4516685.5584 | 0 | 42679.5955 | 4559365.1539
992 | 7368109.1063 | 8067054.4596 | 1635791.8179 | 17070955.3838
993 | 2216048.3283 | 2914187.4615 | 2011580.0781 | 7141815.8679
994 | 4248515.0134 | 1237328.754 | 669735.5409 | 6155579.3084
995 | 11149059.3733 | 723377.9209 | 3792642.4743 | 15665079.7685
996 | 11477806.4416 | 2098790.4276 | 715572.2738 | 14292169.143
997 | 2211323.3194 | 1236725.4334 | 1222812.938 | 4670861.6908
998 | 13195285.0207 | 1335686.3667 | 1000861.0334 | 15531832.4208
999 | 5492773.4869 | 7515597.7405 | 28478273.4735 | 41486644.7009
1000 | 3559204.4464 | 0 | 1194226.8108 | 4753431.2572
1001 | 17406776.1821 | 0 | 610441.2111 | 18017217.3931
1002 | 5651060.5005 | 6249661.0585 | 710659.0116 | 12611380.5706
1003 | 2877590.3384 | 7696429.486 | 48688.3638 | 10622708.1882
1004 | 10774206.1961 | 4457206.2137 | 758309.8326 | 15989722.2425
1005 | 11174771.8929 | 5113018.5736 | 2027662.9926 | 18315453.4591
1006 | 6531091.3691 | 10639744.2836 | 184314.5098 | 17355150.1624
1007 | 6123659.7033 | 3404266.8125 | 0 | 9527926.5158
1008 | 5371853.4396 | 7532796.8385 | 162923.7626 | 13067574.0406
1009 | 13015294.1342 | 1304362.5548 | 177713.314 | 14497370.003
1010 | 6852697.1079 | 16419690.0545 | 10095781.9328 | 33368169.0952
1011 | 10214613.979 | 0 | 0 | 10214613.979
1012 | 6195425.5814 | 5782141.9125 | 74092.8508 | 12051660.3447
1013 | 1673825.734 | 1309108.3019 | 3105839.6984 | 6088773.7344
1014 | 13001593.2701 | 4886095.5855 | 1646110.7373 | 19533799.593
1015 | 7001863.3075 | 2333631.1261 | 2225460.3521 | 11560954.7857
1016 | 4625375.4852 | 23057269.7976 | 4895754.2975 | 32578399.5804
1017 | 12644311.1174 | 0 | 3320376.4711 | 15964687.5885
1018 | 1376511.8703 | 5788193.6113 | 10724694.1269 | 17889399.6086
1019 | 26557105.7444 | 4813460.3959 | 5018625.3937 | 36389191.5341
1020 | 14410375.8448 | 4231662.8648 | 0 | 18642038.7096
1021 | 1950174.6409 | 7690446.4371 | 2200901.2175 | 11841522.2954
1022 | 16182499.1007 | 2225413.9869 | 0 | 18407913.0875
1023 | 11129649.0836 | 19571409.5462 | 6495307.8673 | 37196366.497
1024 | 33295262.3425 | 13518036.2748 | 158897.4873 | 46972196.1046
1025 | 7864826.4842 | 14732612.8803 | 3550927.4018 | 26148366.7663
1026 | 1807026.9836 | 5844641.6908 | 0 | 7651668.6745
1027 | 4868294.6246 | 14629468.2921 | 1016841.1447 | 20514604.0613
1028 | 4087847.2773 | 7222805.9823 | 2561889.193 | 13872542.4525
1029 | 17719047.4973 | 4306958.6103 | 0 | 22026006.1075
1030 | 16803784.4469 | 8087262.9135 | 1190221.0967 | 26081268.4571
1031 | 5172364.7277 | 6790830.3698 | 38498807.1236 | 50462002.2211
1032 | 9616283.1959 | 2941495.4419 | 3601405.0722 | 16159183.71
1033 | 31284087.4837 | 8838478.4957 | 9984549.2572 | 50107115.2366
1034 | 9410467.7643 | 0 | 119461.2171 | 9529928.9814
1035 | 6656814.7755 | 10026128.9128 | 1643660.1163 | 18326603.8046
1036 | 16951735.5968 | 15109896.2474 | 4565778.9567 | 36627410.8008
1037 | 4666417.0979 | 8084974.7898 | 3018380.7754 | 15769772.6631
1038 | 12036521.0167 | 23808623.6844 | 15671670.5305 | 51516815.2316
1039 | 16109460.1284 | 14532804.6205 | 5006869.7536 | 35649134.5025
1040 | 5417140.3597 | 0 | 4716718.6616 | 10133859.0213
1041 | 6137322.0042 | 13005546.0126 | 1390653.012 | 20533521.0288
1042 | 1998180.9555 | 686146.186 | 576912.8182 | 3261239.9597
1043 | 14959431.0077 | 10829884.7981 | 52885.5685 | 25842201.3742
1044 | 980767.0759 | 0 | 11147809.6807 | 12128576.7565
1045 | 1980109.4925 | 0 | 6986016.6552 | 8966126.1477
1046 | 1057876.8204 | 23149641.0557 | 0 | 24207517.8761
1047 | 2463802.5159 | 7726143.3554 | 182768.7001 | 10372714.5714
1048 | 7732655.9028 | 0 | 1358136.0618 | 9090791.9646
1049 | 34386888.2232 | 8103594.0992 | 773572.8113 | 43264055.1337
1050 | 2371929.4401 | 10080665.9033 | 137293.9704 | 12589889.3138
1051 | 30980128.1409 | 0 | 60280.2455 | 31040408.3864
1052 | 4097152.3417 | 24162385.8361 | 569081.907 | 28828620.0849
1053 | 3281005.6231 | 1838288.9545 | 2263754.7102 | 7383049.2879
1054 | 10395898.5015 | 7612182.3879 | 0 | 18008080.8893
1055 | 3997288.8104 | 9163570.7289 | 10723446.5906 | 23884306.1299
1056 | 11609866.0362 | 3130096.4102 | 4861370.4719 | 19601332.9182
1057 | 7700123.6995 | 6479250.5186 | 865642.1496 | 15045016.3676
1058 | 9593261.7319 | 6924983.3035 | 499391.091 | 17017636.1263
1059 | 10354219.8587 | 6339351.3282 | 2008525.263 | 18702096.4499
1060 | 10099135.7365 | 11289482.4073 | 16919479.1987 | 38308097.3425
1061 | 22137586.3891 | 376977.8219 | 2384794.6512 | 24899358.8622
1062 | 16605742.2164 | 4491459.3126 | 505625.8371 | 21602827.3661
1063 | 9940572.117 | 14743749.6471 | 0 | 24684321.7641
1064 | 7852627.527 | 21246073.3401 | 0 | 29098700.8672
1065 | 15402371.946 | 24518042.7549 | 511833.2929 | 40432247.9939
1066 | 3552770.8404 | 4523065.8303 | 17679.668 | 8093516.3386
1067 | 7065119.935 | 3289905.6819 | 0 | 10355025.6169
1068 | 19804492.6647 | 12498265.2809 | 8764750.4139 | 41067508.3595
1069 | 4306022.222 | 2723597.3302 | 3205302.164 | 10234921.7162
1070 | 21343166.4902 | 9528122.6113 | 81438.2823 | 30952727.3838
1071 | 16918849.5215 | 4439908.7996 | 5863056.2268 | 27221814.5479
1072 | 4035054.1987 | 2435328.9012 | 0 | 6470383.0999
1073 | 1049826.5713 | 0 | 790790.0594 | 1840616.6307
1074 | 6897135.2808 | 15796451.31 | 4000681.3271 | 26694267.9179
1075 | 26523244.3119 | 6012960.7821 | 276591.3203 | 32812796.4143
1076 | 2598147.1525 | 8033033.8032 | 659183.8794 | 11290364.8351
1077 | 18300153.2079 | 7677282.6185 | 988930.3872 | 26966366.2136
1078 | 16096142.9962 | 2736535.2509 | 1820434.9063 | 20653113.1534
1079 | 10721043.54 | 7133665.0842 | 221117.5122 | 18075826.1363
1080 | 7752236.8188 | 2548596.7268 | 9176241.8646 | 19477075.4102
1081 | 8469570.2892 | 0 | 246438.3591 | 8716008.6483
1082 | 3849454.2719 | 6902046.2438 | 5721648.7609 | 16473149.2766
1083 | 8528213.638 | 2275671.811 | 2074366.4382 | 12878251.8871
1084 | 5352274.9365 | 17488657.6477 | 0 | 22840932.5843
1085 | 11860087.7936 | 11566689.2102 | 8745340.7553 | 32172117.7591
1086 | 9381398.3362 | 12657676.7038 | 3365278.8523 | 25404353.8923
1087 | 3044952.0252 | 6152073.1856 | 227019.0843 | 9424044.2951
1088 | 2428831.8516 | 10358702.8593 | 456414.3942 | 13243949.1051
1089 | 6022989.9069 | 0 | 0 | 6022989.9069
1090 | 5229944.7654 | 13927264.5856 | 1320699.0454 | 20477908.3964
1091 | 6861562.9495 | 2018746.6808 | 3748115.9204 | 12628425.5507
1092 | 4620349.7642 | 12095667.4417 | 368769.1704 | 17084786.3763
1093 | 2813968.8317 | 0 | 1932022.8751 | 4745991.7068
1094 | 1234763.6138 | 2691566.3947 | 17058946.9612 | 20985276.9697
1095 | 14698332.2304 | 15986143.3565 | 40243.3818 | 30724718.9687
1096 | 3442603.8881 | 6352066.9322 | 1004998.9306 | 10799669.7509
1097 | 4576188.0039 | 3167954.8021 | 0 | 7744142.8059
1098 | 1777370.0625 | 13993477.9412 | 7274040.0701 | 23044888.0738
1099 | 4667997.2971 | 31308593.989 | 1282938.2842 | 37259529.5703
1100 | 2221822.9613 | 17797752.9348 | 0 | 20019575.896
1101 | 11496616.0353 | 8392897.3418 | 1374695.869 | 21264209.246
1102 | 2576832.6516 | 2009681.6933 | 370996.1296 | 4957510.4745
1103 | 5518878.5389 | 15334855.7828 | 1667793.4885 | 22521527.8101
1104 | 1714627.5422 | 16826999.7913 | 3962956.976 | 22504584.3096
1105 | 6973832.2427 | 18187610.6445 | 109426.7206 | 25270869.6079
1106 | 812577.5521 | 7109039.764 | 0 | 7921617.3161
1107 | 3151528.9901 | 0 | 18828583.5845 | 21980112.5746
1108 | 914168.7003 | 9205005.4891 | 1018967.4528 | 11138141.6421
1109 | 2653492.1254 | 21444359.646 | 0 | 24097851.7714
1110 | 10555810.2011 | 2229839.0245 | 2077577.0772 | 14863226.3028
1111 | 8460383.3332 | 0 | 3199682.5848 | 11660065.918
1112 | 10554472.5625 | 0 | 5021203.0082 | 15575675.5707
1113 | 22516185.916 | 5092826.2774 | 114790.2611 | 27723802.4544
1114 | 8591914.1099 | 6550730.8266 | 578373.9655 | 15721018.9019
1115 | 23074152.7681 | 9650173.5937 | 374553.9522 | 33098880.3141
1116 | 26835055.6007 | 10630053.4394 | 5265603.1879 | 42730712.2279
1117 | 1248130.7565 | 3246219.9777 | 1362888.9465 | 5857239.6806
1118 | 23475867.0978 | 10707796.4139 | 3006666.5878 | 37190330.0995
1119 | 4797587.8914 | 13553623.3433 | 16123717.5894 | 34474928.824
1120 | 5729625.1863 | 9540969.3096 | 0 | 15270594.4959
1121 | 5430651.1064 | 12509935.0315 | 0 | 17940586.1379
1122 | 1900308.8942 | 1533297.8685 | 424224.477 | 3857831.2397
1123 | 20354345.4022 | 32682950.7648 | 16283291.085 | 69320587.2519
1124 | 34070396.254 | 15882470.3948 | 4915107.8787 | 54867974.5275
1125 | 10214564.4121 | 825875.3086 | 906309.374 | 11946749.0948
1126 | 15376825.2131 | 12956561.0923 | 2121649.8302 | 30455036.1356
1127 | 7593611.6834 | 1467243.1217 | 2457738.2505 | 11518593.0556
1128 | 1872152.1507 | 6270413.5539 | 0 | 8142565.7046
1129 | 3464438.8346 | 14435824.2837 | 3722171.7696 | 21622434.8879
1130 | 17704993.577 | 5493599.5491 | 592714.5494 | 23791307.6756
1131 | 4285761.6621 | 24828295.6 | 8367461.8191 | 37481519.0812
1132 | 5377115.7293 | 3611853.5927 | 0 | 8988969.322
1133 | 16796598.1469 | 5261052.801 | 2627631.4298 | 24685282.3777
1134 | 14460266.3809 | 0 | 3730495.208 | 18190761.5889
1135 | 15434397.7504 | 538215.6604 | 1734333.1923 | 17706946.603
1136 | 8071566.2891 | 0 | 7356011.2326 | 15427577.5216
1137 | 9145077.7199 | 1493839.4972 | 25619881.2689 | 36258798.486
1138 | 13790834.0805 | 29195274.8845 | 8507853.1917 | 51493962.1567
1139 | 4054154.5636 | 10490660.4197 | 6646010.1517 | 21190825.135
1140 | 17245987.7554 | 14632957.1973 | 5612201.0009 | 37491145.9536
1141 | 8759003.9826 | 1670558.5419 | 181296.5858 | 10610859.1104
1142 | 1690149.2639 | 4188161.4362 | 86269.2374 | 5964579.9375
1143 | 1320915.3533 | 4209923.7811 | 0 | 5530839.1344
1144 | 9589623.1215 | 7819564.968 | 162521.1393 | 17571709.2288
1145 | 4667428.3315 | 5106551.1535 | 28623643.6523 | 38397623.1372
1146 | 778154.5543 | 3376375.1808 | 178293.166 | 4332822.901
1147 | 23031074.2619 | 0 | 8587300.2383 | 31618374.5002
1148 | 2812727.9734 | 0 | 346023.9818 | 3158751.9552
1149 | 25955382.9824 | 0 | 1823724.4843 | 27779107.4667
1150 | 1722622.3762 | 0 | 3235039.2319 | 4957661.6081
1151 | 15316412.7874 | 2575186.837 | 144093.1042 | 18035692.7286
1152 | 7072803.1409 | 10126507.1134 | 0 | 17199310.2543
1153 | 11837744.6632 | 0 | 721078.4359 | 12558823.0991
1154 | 44472638.1512 | 2431813.5988 | 911335.6353 | 47815787.3853
1155 | 4823666.966 | 8221651.4594 | 0 | 13045318.4254
1156 | 25523992.7752 | 0 | 4082354.3057 | 29606347.0809
1157 | 1547275.4814 | 4266583.0202 | 3097026.5753 | 8910885.0769
1158 | 12303506.6653 | 4010678.7303 | 3314540.5003 | 19628725.8959
1159 | 10588503.4662 | 4159447.6341 | 781616.3761 | 15529567.4763
1160 | 3631540.5254 | 5884733.5746 | 1209489.5673 | 10725763.6674
1161 | 19273343.5437 | 7021223.1003 | 88020.6059 | 26382587.2499
1162 | 31708391.7842 | 3174304.0818 | 0 | 34882695.8659
1163 | 386739.2209 | 0 | 3968512.3148 | 4355251.5358
1164 | 10620646.9012 | 24271196.5808 | 630934.0192 | 35522777.5012
1165 | 9986177.9098 | 4253239.0824 | 376526.0943 | 14615943.0866
1166 | 16636920.4602 | 5139829.4616 | 901478.0123 | 22678227.9341
1167 | 9937939.2713 | 0 | 2915621.4971 | 12853560.7684
1168 | 2413847.3128 | 9122634.8884 | 87150.6795 | 11623632.8807
1169 | 589133.9456 | 11880529.2127 | 4761569.0833 | 17231232.2417
1170 | 4069481.9621 | 18596152.7643 | 3122381.0052 | 25788015.7317
1171 | 24207691.5597 | 0 | 50643.9939 | 24258335.5536
1172 | 4790793.0485 | 2569345.3147 | 1563860.2239 | 8923998.5871
1173 | 172574.27 | 19286657.1526 | 112635.1744 | 19571866.5971
1174 | 3904109.4377 | 7627124.3778 | 385637.103 | 11916870.9185
1175 | 9664952.6059 | 0 | 83924.1323 | 9748876.7383
1176 | 3494572.9595 | 21227680.4383 | 5655507.2673 | 30377760.6651
1177 | 5739213.6825 | 8919350.5441 | 680239.7545 | 15338803.9811
1178 | 2056704.6592 | 12344235.1049 | 0 | 14400939.7641
1179 | 7020313.9547 | 7512815.6625 | 1576958.1486 | 16110087.7658
1180 | 33589296.5693 | 320518.6668 | 105920.7808 | 34015736.0169
1181 | 7419644.7341 | 18916925.4274 | 7110855.9852 | 33447426.1467
1182 | 16587006.0166 | 2815597.7363 | 2298524.6334 | 21701128.3863
1183 | 6163637.5972 | 7741303.3343 | 442869.0347 | 14347809.9663
1184 | 7692748.5105 | 3731710.5082 | 389103.4078 | 11813562.4265
1185 | 4358398.6642 | 871126.5321 | 4838672.6916 | 10068197.8879
1186 | 13489769.9357 | 3470586.6697 | 584911.3412 | 17545267.9465
1187 | 4403453.2051 | 5923917.9967 | 3880334.3154 | 14207705.5172
1188 | 2236430.9278 | 4182148.1764 | 0 | 6418579.1042
1189 | 15599012.2866 | 4906706.9475 | 2173371.1043 | 22679090.3384
1190 | 5778590.4559 | 3164616.1166 | 1740311.8459 | 10683518.4184
1191 | 3760647.9948 | 26112343.0698 | 3051611.6392 | 32924602.7038
1192 | 10379724.099 | 13136923.9143 | 843836.5969 | 24360484.6102
1193 | 3760171.2735 | 9698910.6963 | 2534744.1659 | 15993826.1357
1194 | 16106063.3806 | 0 | 174259.1154 | 16280322.496
1195 | 5799817.0725 | 7361053.8027 | 1458199.6629 | 14619070.5381
1196 | 3011682.4659 | 12464304.7052 | 345803.5344 | 15821790.7056
1197 | 16370905.2693 | 2593443.0652 | 2326439.8222 | 21290788.1566
1198 | 1753030.9606 | 3435679.4335 | 4190079.5112 | 9378789.9054
1199 | 16655078.6339 | 6257329.8032 | 1713215.1049 | 24625623.5421
1200 | 200415.087 | 16169356.7383 | 6466659.5421 | 22836431.3674
1201 | 7310126.4026 | 1085068.2382 | 2682779.2084 | 11077973.8493
1202 | 29889709.7921 | 11824556.5026 | 494119.2841 | 42208385.5787
1203 | 4484640.7571 | 3835987.9805 | 3457309.2815 | 11777938.0191
1204 | 1494154.388 | 6007185.2444 | 1513301.2236 | 9014640.856
1205 | 968924.8729 | 6284876.9899 | 114279.3643 | 7368081.2271
1206 | 5554410.1632 | 769171.1592 | 9380931.6906 | 15704513.013
1207 | 4783496.8375 | 14166100.2732 | 5928304.5471 | 24877901.6578
1208 | 6891200.2158 | 12282315.5416 | 13290.4476 | 19186806.2051
1209 | 14082568.2373 | 9217153.7441 | 1484111.4315 | 24783833.4129
1210 | 1173110.2515 | 8917374.1893 | 164259.1999 | 10254743.6406
1211 | 9337005.9116 | 3064717.208 | 0 | 12401723.1196
1212 | 9702594.5583 | 26693020.748 | 1428087.3671 | 37823702.6734
1213 | 6594299.6877 | 6444346.3847 | 0 | 13038646.0723
1214 | 12406433.4349 | 8213025.9498 | 5556829.361 | 26176288.7457
1215 | 4791434.1337 | 0 | 2707933.0015 | 7499367.1352
1216 | 7560935.1702 | 9835420.8676 | 0 | 17396356.0377
1217 | 14440032.2724 | 9402651.9454 | 30046.719 | 23872730.9367
1218 | 38255467.3059 | 0 | 4908235.049 | 43163702.3549
1219 | 6562599.6498 | 0 | 1803684.3107 | 8366283.9605
1220 | 8468304.4216 | 16675046.3662 | 2342361.0599 | 27485711.8476
1221 | 10039623.8532 | 5765834.7621 | 3315617.967 | 19121076.5824
1222 | 22301106.7463 | 0 | 8002953.5148 | 30304060.2611
1223 | 16077771.6571 | 0 | 137134.6444 | 16214906.3015
1224 | 6247295.1384 | 3976196.147 | 1032555.4868 | 11256046.7721
1225 | 7964497.6423 | 10942873.8154 | 286449.2901 | 19193820.7479
1226 | 6611917.4077 | 6444688.2182 | 2789643.2942 | 15846248.9202
1227 | 17239083.3119 | 3053787.5984 | 1226482.0844 | 21519352.9948
1228 | 2258717.3604 | 7116752.3802 | 644542.3442 | 10020012.0848
1229 | 5461148.1253 | 3524419.6141 | 0 | 8985567.7394
1230 | 5086269.5606 | 0 | 3035357.5961 | 8121627.1567
1231 | 8502988.2726 | 2524393.9921 | 1694434.5689 | 12721816.8337
1232 | 9479100.258 | 4271143.3084 | 294290.9517 | 14044534.5181
1233 | 1567026.527 | 6293550.0926 | 1964989.4825 | 9825566.1021
1234 | 7363532.2085 | 5140218.4459 | 0 | 12503750.6544
1235 | 2155844.3331 | 15571978.241 | 9825584.047 | 27553406.6211
1236 | 12071312.8407 | 12633941.3319 | 125907.8167 | 24831161.9894
1237 | 11815300.0352 | 3948041.699 | 730313.6437 | 16493655.3778
1238 | 2202480.0507 | 2720918.5777 | 6367684.564 | 11291083.1924
1239 | 3424617.4416 | 10867585.9884 | 3071651.2122 | 17363854.6422
1240 | 16654335.4661 | 5880747.8543 | 472568.4096 | 23007651.73
1241 | 16525369.9972 | 8301120.0669 | 645804.6232 | 25472294.6872
1242 | 8875370.6624 | 12557729.1007 | 49531.217 | 21482630.9801
1243 | 658790.2811 | 3813411.1995 | 958237.9802 | 5430439.4608
1244 | 12567188.5421 | 12907837.3351 | 740052.3011 | 26215078.1782
1245 | 1973479.6301 | 19143420.7555 | 0 | 21116900.3857
1246 | 1528879.0069 | 3088049.0527 | 2312488.2327 | 6929416.2923
1247 | 4118651.5226 | 8815313.0701 | 175006.8511 | 13108971.4438
1248 | 1299800.691 | 6588980.5322 | 340888.2487 | 8229669.4719
1249 | 10885113.125 | 496494.8999 | 1765277.4513 | 13146885.4762
1250 | 11186091.5166 | 8731406.1935 | 67278.4971 | 19984776.2072
1251 | 5239287.005 | 14150416.6021 | 77749.3228 | 19467452.93
1252 | 8719751.6746 | 2318610.6206 | 2104558.1277 | 13142920.4229
1253 | 8601244.8498 | 3823183.0109 | 1629495.4174 | 14053923.2781
1254 | 25405576.097 | 10163286.4779 | 1537533.2982 | 37106395.8731
1255 | 3805215.527 | 11538059.6615 | 985630.2026 | 16328905.3912
1256 | 10898316.3233 | 6052999.2174 | 0 | 16951315.5408
1257 | 24979552.2835 | 10366788.7569 | 759493.282 | 36105834.3223
1258 | 8000352.6528 | 4081747.35 | 2327327.3268 | 14409427.3296
1259 | 2715172.3965 | 582536.9287 | 636571.3631 | 3934280.6883
1260 | 13577824.2376 | 1385136.9146 | 75501.09 | 15038462.2421
1261 | 8146034.1525 | 9497965.5374 | 0 | 17643999.6898
1262 | 1916501.8606 | 13499105.0009 | 5575972.7794 | 20991579.6408
1263 | 11243496.1759 | 7037816.5912 | 523920.5068 | 18805233.2739
1264 | 1142232.3676 | 636738.1316 | 136734.9638 | 1915705.4631
1265 | 4671923.9535 | 4875542.1929 | 2325247.0616 | 11872713.208
1266 | 3123871.8212 | 26426089.4954 | 43895.744 | 29593857.0606
1267 | 58250607.1624 | 3498353.4019 | 9387649.3794 | 71136609.9437
1268 | 6119210.088 | 1451167.6688 | 826211.4306 | 8396589.1874
1269 | 9343866.9606 | 4024052.7345 | 1065068.2869 | 14432987.982
1270 | 4513573.4742 | 3062186.6361 | 1001800.7711 | 8577560.8814
1271 | 17111336.0042 | 2069344.4752 | 60606.9466 | 19241287.426
1272 | 593116.4401 | 13339244.4796 | 3797041.7269 | 17729402.6466
1273 | 4699698.4057 | 1268519.5063 | 1082772.8575 | 7050990.7695
1274 | 29489849.523 | 9640545.6842 | 0 | 39130395.2073
1275 | 33267551.9356 | 7112947.6049 | 1124044.6943 | 41504544.2349
1276 | 2312099.2967 | 19409555.4683 | 2085042.5862 | 23806697.3512
1277 | 3791096.2623 | 780524.0563 | 3548952.9033 | 8120573.2218
1278 | 7522159.7183 | 10861206.6606 | 1652551.0464 | 20035917.4253
1279 | 2366124.348 | 749582.8231 | 469813.9301 | 3585521.1013
1280 | 16346457.0574 | 19776193.9155 | 3447062.2523 | 39569713.2252
1281 | 6607866.641 | 11690369.6299 | 375222.3422 | 18673458.6131
1282 | 19443021.8358 | 2504870.6608 | 1022692.2598 | 22970584.7565
1283 | 2552534.5943 | 0 | 2633032.3199 | 5185566.9142
1284 | 1087078.1845 | 0 | 1045562.6471 | 2132640.8315
1285 | 2075204.5151 | 0 | 390345.3522 | 2465549.8673
1286 | 4944452.2922 | 15378842.5497 | 10533905.7789 | 30857200.6208
1287 | 9164044.4701 | 17159426.2479 | 11680642.6361 | 38004113.3541
1288 | 1520171.492 | 7284436.8899 | 11330191.1416 | 20134799.5234
1289 | 14864887.0298 | 7966012.6928 | 1089974.9085 | 23920874.6311
1290 | 8129532.8184 | 0 | 1285738.663 | 9415271.4814
1291 | 25095840.218 | 38332382.7327 | 104285.4501 | 63532508.4007
1292 | 28103511.3296 | 15595697.7369 | 6739394.6632 | 50438603.7297
1293 | 10125482.5887 | 2605535.904 | 7538606.5919 | 20269625.0846
1294 | 10661838.9073 | 0 | 449385.3434 | 11111224.2506
1295 | 19467183.2519 | 5776560.0589 | 6231691.0568 | 31475434.3675
1296 | 3172443.3256 | 320313.9369 | 620416.2742 | 4113173.5367
1297 | 4280188.3303 | 4244721.5423 | 3073073.7168 | 11597983.5894
1298 | 4428432.8225 | 4655152.6503 | 0 | 9083585.4727
1299 | 1393335.1902 | 14382414.8368 | 404602.4571 | 16180352.4841
1300 | 6171391.1598 | 5226379.5795 | 1126795.6634 | 12524566.4027
1301 | 3086900.4897 | 0 | 4700.114 | 3091600.6037
1302 | 622140.728 | 4975586.55 | 2526866.5059 | 8124593.7839
1303 | 19520086.168 | 10477690.7993 | 8557225.1233 | 38555002.0905
1304 | 15046901.0607 | 8490848.1684 | 9180422.3656 | 32718171.5947
1305 | 1953363.1837 | 2467556.2927 | 2027615.4629 | 6448534.9393
1306 | 1367358.9009 | 5189841.7026 | 0 | 6557200.6035
1307 | 6011138.2126 | 0 | 0 | 6011138.2126
1308 | 10227386.7045 | 2715495.7473 | 2094722.8865 | 15037605.3383
1309 | 19213965.4382 | 3349781.6291 | 4055608.5995 | 26619355.6669
1310 | 1354938.5242 | 2894413.2782 | 7836876.267 | 12086228.0694
1311 | 2267479.2463 | 10949681.7241 | 3976325.3882 | 17193486.3586
1312 | 3461517.9948 | 6568227.8258 | 7776058.7851 | 17805804.6057
1313 | 10242239.556 | 0 | 661848.7452 | 10904088.3013
1314 | 7724855.6219 | 94914.3396 | 0 | 7819769.9615
1315 | 11413344.881 | 4449053.3398 | 27963.8318 | 15890362.0526
1316 | 10698495.0266 | 2682400.8247 | 565678.9006 | 13946574.7519
1317 | 5355447.4395 | 1686802.9771 | 1033303.5397 | 8075553.9563
1318 | 6149739.7231 | 8087000.176 | 75052.5079 | 14311792.4071
1319 | 2056770.5217 | 4726526.6764 | 2084037.3363 | 8867334.5345
1320 | 3895053.209 | 4959358.8718 | 4030106.784 | 12884518.8648
1321 | 11432712.0537 | 25298571.271 | 13559942.0049 | 50291225.3296
1322 | 4880748.067 | 8132725.6127 | 126523.976 | 13139997.6557
1323 | 3897612.9618 | 5510788.8859 | 3880661.7836 | 13289063.6313
1324 | 5687156.7696 | 8571569.9018 | 0 | 14258726.6714
1325 | 1958628.8205 | 8397311.2145 | 1219673.1221 | 11575613.1571
1326 | 3091454.6899 | 3427977.4145 | 1523080.5434 | 8042512.6478
1327 | 17178836.0766 | 9166219.3502 | 4799605.8727 | 31144661.2995
1328 | 7935573.2409 | 0 | 160670.6144 | 8096243.8553
1329 | 3520104.941 | 2866162.064 | 186695.5622 | 6572962.5673
1330 | 7122281.4292 | 4772572.3696 | 2717930.4372 | 14612784.236
1331 | 1472875.5285 | 6575282.323 | 77342.7157 | 8125500.5672
1332 | 9386633.2945 | 9404626.5794 | 7638.6011 | 18798898.475
1333 | 40277184.4507 | 0 | 2470988.0038 | 42748172.4545
1334 | 13470456.3188 | 2819457.9529 | 431777.4929 | 16721691.7646
1335 | 4175880.6412 | 11771293.76 | 3257168.9901 | 19204343.3913
1336 | 6943392.3694 | 11864082.9419 | 12912895.0923 | 31720370.4035
1337 | 10688518.9069 | 6488341.4759 | 6060941.3713 | 23237801.7542
1338 | 2187809.5656 | 15399420.7141 | 1579371.1593 | 19166601.4389
1339 | 16732172.7461 | 15464035.2415 | 1363190.2494 | 33559398.2369
1340 | 13810836.1295 | 4154274.5618 | 2176124.7734 | 20141235.4646
1341 | 13829332.3907 | 0 | 0 | 13829332.3907
1342 | 3639982.205 | 7120482.9565 | 237030.1514 | 10997495.3129
1343 | 5778876.3635 | 1990790.2883 | 4734467.7397 | 12504134.3915
1344 | 2028859.316 | 21066517.9458 | 2853483.0092 | 25948860.271
1345 | 2162360.3894 | 4390088.9407 | 410847.3885 | 6963296.7186
1346 | 7347286.3051 | 23219556.1434 | 275036.198 | 30841878.6465
1347 | 16146676.6844 | 3820245.1004 | 1195715.5162 | 21162637.301
1348 | 2138722.8078 | 12912104.5019 | 0 | 15050827.3097
1349 | 6402022.3617 | 2535523.2119 | 2195744.1286 | 11133289.7022
1350 | 5618883.2445 | 3146888.8463 | 414886.6861 | 9180658.7769
1351 | 5892663.0632 | 2543554.8783 | 2389615.6327 | 10825833.5742
1352 | 13835383.1046 | 9073756.1602 | 5766369.8528 | 28675509.1177
1353 | 15863228.5629 | 9757523.0667 | 3029371.9324 | 28650123.5621
1354 | 3707182.9374 | 17639592.6952 | 5531080.3147 | 26877855.9472
1355 | 1176626.3241 | 7085636.5805 | 496368.5072 | 8758631.4118
1356 | 17876085.3707 | 16454867.5895 | 9589503.4206 | 43920456.3808
1357 | 2483793.9352 | 12035152.6243 | 91228.7221 | 14610175.2815
1358 | 13788149.7039 | 11415857.0753 | 0 | 25204006.7792
1359 | 2326422.5936 | 22813680.1364 | 8643579.8839 | 33783682.6139
1360 | 24926209.3152 | 2338778.0332 | 470252.8212 | 27735240.1696
1361 | 7681061.522 | 5159613.9312 | 1485194.4494 | 14325869.9026
1362 | 10360010.3383 | 7091235.577 | 332065.8513 | 17783311.7667
1363 | 44382254.3004 | 0 | 24487256.7438 | 68869511.0443
1364 | 6543766.7544 | 6278839.5924 | 3262446.373 | 16085052.7198
1365 | 5816811.2733 | 17545376.8336 | 788101.8389 | 24150289.9458
1366 | 13993731.4268 | 18519473.6616 | 1637156.696 | 34150361.7844
1367 | 2759686.0697 | 1180747.0173 | 30489993.1654 | 34430426.2524
1368 | 8770908.4334 | 5086779.6932 | 0 | 13857688.1266
1369 | 11137863.7492 | 10764920.0127 | 1589617.1741 | 23492400.936
1370 | 5517621.813 | 9377111.5705 | 5159594.4726 | 20054327.856
1371 | 1345390.9269 | 0 | 0 | 1345390.9269
1372 | 10011206.4491 | 768077.83 | 1722192.6519 | 12501476.9311
1373 | 4563737.001 | 0 | 3283730.0664 | 7847467.0674
1374 | 20445352.6537 | 5321395.0255 | 0 | 25766747.6792
1375 | 7886084.4675 | 25665202.6833 | 1737770.0186 | 35289057.1694
1376 | 8400735.791 | 0 | 957735.0351 | 9358470.8261
1377 | 3692890.3647 | 6023642.9736 | 267783.3816 | 9984316.7199
1378 | 12816530.8024 | 4703515.7701 | 5491677.3408 | 23011723.9133
1379 | 22046718.3707 | 11113991.226 | 1175431.6097 | 34336141.2064
1380 | 14770674.2923 | 7876063.7876 | 1972252.1114 | 24618990.1913
1381 | 28020623.0448 | 0 | 3222650.6769 | 31243273.7217
1382 | 17367855.216 | 1802552.7052 | 13269496.6362 | 32439904.5573
1383 | 13588485.1077 | 2628569.0707 | 1588318.6956 | 17805372.874
1384 | 10359379.2385 | 10365102.7803 | 648101.5443 | 21372583.5631
1385 | 15792373.2236 | 4103667.4603 | 10469549.3393 | 30365590.0231
1386 | 10444430.1182 | 6877021.5156 | 2390118.3701 | 19711570.0038
1387 | 10329586.1361 | 50219265.3157 | 10273929.1533 | 70822780.6051
1388 | 2525155.8857 | 0 | 1120585.193 | 3645741.0787
1389 | 19555782.523 | 3217896.3043 | 6988430.6443 | 29762109.4715
1390 | 878913.2488 | 11257109.0363 | 205826.6368 | 12341848.922
1391 | 1339740.116 | 19371682.8626 | 118110.3562 | 20829533.3348
1392 | 22386668.983 | 6496769.9897 | 183837.5068 | 29067276.4796
1393 | 6052785.5553 | 7075077.4783 | 436757.8796 | 13564620.9132
1394 | 2363744.6937 | 0 | 67504.4364 | 2431249.1301
1395 | 4115009.3715 | 13433916.7112 | 96206.3047 | 17645132.3874
1396 | 13315416.9686 | 12345975.8823 | 20792815.9066 | 46454208.7575
1397 | 4390435.0624 | 0 | 75027.3533 | 4465462.4157
1398 | 5577889.0216 | 0 | 3500327.2261 | 9078216.2477
1399 | 3780709.6458 | 28374329.1767 | 0 | 32155038.8225
1400 | 15194933.3723 | 8247405.2767 | 623957.4841 | 24066296.1331
1401 | 4469757.4447 | 2290790.2172 | 1006942.0139 | 7767489.6758
1402 | 3425366.4156 | 3523333.7971 | 218326.7353 | 7167026.948
1403 | 13947730.0853 | 1560104.1127 | 3807572.0486 | 19315406.2467
1404 | 23174768.6661 | 15918797.399 | 0 | 39093566.0651
1405 | 18531635.3163 | 0 | 1682159.2505 | 20213794.5668
1406 | 9785544.3398 | 7709919.742 | 51538.0025 | 17547002.0843
1407 | 15634417.6358 | 12036167.6967 | 746582.9995 | 28417168.332
1408 | 22956029.9238 | 10735499.631 | 59246.0773 | 33750775.6321
1409 | 4663003.0867 | 17082709.7507 | 2188958.3384 | 23934671.1758
1410 | 9778344.6652 | 0 | 805453.6133 | 10583798.2785
1411 | 6220689.6901 | 1432028.5812 | 1999765.1005 | 9652483.3718
1412 | 19888.186 | 2799966.1602 | 1849732.0831 | 4669586.4293
1413 | 9968336.9063 | 16565274.9703 | 3448929.5458 | 29982541.4224
1414 | 11465397.0573 | 1172468.2685 | 1079130.9748 | 13716996.3005
1415 | 3397711.2608 | 5955556.7991 | 1065301.0862 | 10418569.1462
1416 | 19937269.4548 | 21564238.4731 | 461657.1889 | 41963165.1167
1417 | 5239275.6339 | 13519243.5752 | 6151963.509 | 24910482.7181
1418 | 3999145.1736 | 0 | 511668.5702 | 4510813.7438
1419 | 4578107.1843 | 10638666.1868 | 0 | 15216773.3711
1420 | 14945200.8908 | 8340219.2123 | 1105950.2947 | 24391370.3978
1421 | 3785298.1057 | 5522596.8088 | 455926.0844 | 9763820.9988
1422 | 8421787.4965 | 2530243.3537 | 2459304.9225 | 13411335.7726
1423 | 4057310.4862 | 0 | 653649.3734 | 4710959.8596
1424 | 2805553.2318 | 7389371.5649 | 973777.164 | 11168701.9607
1425 | 22512026.6687 | 9352469.0726 | 4990072.211 | 36854567.9522
1426 | 12143048.146 | 26547864.9946 | 1708416.4481 | 40399329.5887
1427 | 2488552.6328 | 9386331.3272 | 0 | 11874883.96
1428 | 5691585.2489 | 7298494.4031 | 13056332.7631 | 26046412.4151
1429 | 2450725.1988 | 3626493.2087 | 2796313.7842 | 8873532.1916
1430 | 9891745.9605 | 0 | 6251855.723 | 16143601.6835
1431 | 17711591.3421 | 5987587.3766 | 280727.0099 | 23979905.7286
1432 | 2860995.5117 | 1117030.419 | 1238261.108 | 5216287.0387
1433 | 3692026.8146 | 1995638.4939 | 0 | 5687665.3085
1434 | 19403047.9597 | 19172716.4952 | 334589.1526 | 38910353.6075
1435 | 16455839.3043 | 3245790.2643 | 974803.0747 | 20676432.6433
1436 | 8140037.0307 | 8774841.0789 | 481006.2372 | 17395884.3467
1437 | 20042206.8104 | 4588380.2594 | 0 | 24630587.0698
1438 | 24333614.2848 | 4801431.341 | 4040348.7472 | 33175394.373
1439 | 776781.7072 | 13451888.8957 | 733423.579 | 14962094.1818
1440 | 1993444.9889 | 17085486.6863 | 589152.8086 | 19668084.4838
1441 | 3616235.883 | 15424932.2056 | 1076812.2231 | 20117980.3117
1442 | 2489357.9336 | 9642843.3945 | 824013.1549 | 12956214.4829
1443 | 8730421.7963 | 0 | 0 | 8730421.7963
1444 | 15070907.6672 | 3553461.3491 | 61984.3855 | 18686353.4017
1445 | 1832256.9424 | 10533487.8826 | 160567.4082 | 12526312.2332
1446 | 16315498.9136 | 13390656.773 | 3398939.4791 | 33105095.1656
1447 | 1560321.5801 | 0 | 0 | 1560321.5801
1448 | 5607975.2545 | 7131666.505 | 106881.5359 | 12846523.2954
1449 | 5271197.1601 | 2399435.5926 | 2847439.4608 | 10518072.2134
1450 | 5334595.9256 | 0 | 55506.542 | 5390102.4676
1451 | 12084458.4899 | 3745311.996 | 2008000.5224 | 17837771.0084
1452 | 3431404.1732 | 19407324.453 | 0 | 22838728.6262
1453 | 68676651.9788 | 0 | 3142270.7614 | 71818922.7402
1454 | 4700692.9395 | 5181215.712 | 3644619.3763 | 13526528.0278
1455 | 33491749.4436 | 13130698.9655 | 78319.9489 | 46700768.3581
1456 | 8963781.2904 | 2034865.2513 | 2345916.8042 | 13344563.3459
1457 | 12512112.7539 | 2984047.1867 | 0 | 15496159.9406
1458 | 4149449.3025 | 0 | 0 | 4149449.3025
1459 | 1220569.8547 | 5553497.795 | 76123.1164 | 6850190.7661
1460 | 20222685.0068 | 16667144.4388 | 2703965.6856 | 39593795.1311
1461 | 15943359.6376 | 8256328.5072 | 1286991.3151 | 25486679.4599
1462 | 1714219.7408 | 2829585.4966 | 11624058.9154 | 16167864.1527
1463 | 2355056.1013 | 5194702.7009 | 3769688.6312 | 11319447.4334
1464 | 20816433.1229 | 4470855.4332 | 5460017.0842 | 30747305.6402
1465 | 13668562.6435 | 0 | 2327817.6882 | 15996380.3317
1466 | 65667.5583 | 1680915.9483 | 7452244.9367 | 9198828.4434
1467 | 11831510.8549 | 8467290.1098 | 0 | 20298800.9647
1468 | 5908674.1391 | 0 | 3652124.5702 | 9560798.7092
1469 | 1700517.7383 | 10545488.2345 | 1712314.6479 | 13958320.6207
1470 | 1846546.7995 | 5156839.6307 | 0 | 7003386.4301
1471 | 6151921.6516 | 20027112.4728 | 11232606.1973 | 37411640.3217
1472 | 12103530.5329 | 2843566.4956 | 6906764.3769 | 21853861.4055
1473 | 4217979.8562 | 7727228.2436 | 18825654.6334 | 30770862.7332
1474 | 5843688.1775 | 0 | 339260.3529 | 6182948.5304
1475 | 3551875.4225 | 24335257.5752 | 994032.0291 | 28881165.0268
1476 | 3228816.5154 | 8478352.2518 | 6686247.6509 | 18393416.4181
1477 | 24577318.9783 | 3435438.5409 | 151329.2745 | 28164086.7937
1478 | 10053749.9808 | 12466431.3855 | 2602543.0807 | 25122724.447
1479 | 12527757.1842 | 1366344.1955 | 0 | 13894101.3797
1480 | 4761890.6605 | 5920622.6663 | 968854.1906 | 11651367.5174
1481 | 1534724.0918 | 17608155.147 | 253304.2736 | 19396183.5124
1482 | 1447637.9263 | 8797954.1439 | 2116450.5919 | 12362042.6621
1483 | 8652710.7999 | 0 | 179208.1555 | 8831918.9553
1484 | 7085012.2234 | 7419229.0575 | 0 | 14504241.2809
1485 | 3316898.9648 | 1298417.7755 | 147352.8054 | 4762669.5458
1486 | 13246897.6234 | 16039915.8893 | 766903.7385 | 30053717.2512
1487 | 0 | 5886672.8374 | 6857332.2822 | 12744005.1196
1488 | 4537040.5283 | 11994421.7911 | 594239.5355 | 17125701.8549
1489 | 1150045.0559 | 0 | 8812104.2589 | 9962149.3149
1490 | 206047.3968 | 2759330.0676 | 6391978.7421 | 9357356.2065
1491 | 12935523.8601 | 785870.3868 | 4663008.0387 | 18384402.2856
1492 | 27695740.1924 | 0 | 553737.7004 | 28249477.8928
1493 | 8288895.6361 | 4392533.4949 | 9947387.6238 | 22628816.7548
1494 | 17261617.5901 | 28080815.0895 | 482539.817 | 45824972.4966
1495 | 8374926.4876 | 12090597.4375 | 3047699.5536 | 23513223.4786
1496 | 6554131.9381 | 24113270.0536 | 7641632.3385 | 38309034.3301
1497 | 11117824.1488 | 8935892.296 | 0 | 20053716.4448
1498 | 1381752.0972 | 4578296.3709 | 82818.665 | 6042867.1331
1499 | 373114.709 | 3972669.5474 | 32844.7115 | 4378628.9679
1500 | 798999.993 | 0 | 5238165.2934 | 6037165.2865
1501 | 2918088.1737 | 8150040.8617 | 14445021.8563 | 25513150.8917
1502 | 15042691.9465 | 9433950.7435 | 168761.7937 | 24645404.4836
1503 | 3231378.3809 | 1989993.9861 | 721431.2294 | 5942803.5964
1504 | 16558708.1411 | 9052439.4864 | 2504046.0866 | 28115193.7141
1505 | 7320669.4841 | 2473883.9252 | 178640.6781 | 9973194.0873
1506 | 13058465.4543 | 5757250.1889 | 974764.6906 | 19790480.3338
1507 | 2234078.8917 | 15603405.7548 | 267931.891 | 18105416.5375
1508 | 6511297.8343 | 1074294.5275 | 259414.1526 | 7845006.5145
1509 | 7192637.4745 | 0 | 1031749.8779 | 8224387.3524
1510 | 11135371.0896 | 0 | 14706990.4386 | 25842361.5282
1511 | 15163021.2299 | 2107602.5145 | 1274019.6033 | 18544643.3477
1512 | 15559690.0953 | 22722329.609 | 4580163.1994 | 42862182.9038
1513 | 6476773.1018 | 16182646.4013 | 1821081.6481 | 24480501.1512
1514 | 9033985.6833 | 10017725.8951 | 1375873.1386 | 20427584.7171
1515 | 2439418.0554 | 5309924.3739 | 11305274.7843 | 19054617.2135
1516 | 11006615.2269 | 17888811.6708 | 1224197.8214 | 30119624.719
1517 | 15682762.2468 | 6701495.6595 | 32448.9256 | 22416706.832
1518 | 3434882.2792 | 7823493.8604 | 17522.4512 | 11275898.5908
1519 | 20844880.1351 | 2147112.8634 | 0 | 22991992.9985
1520 | 10808458.9192 | 5833493.3728 | 243416.3584 | 16885368.6505
1521 | 7753552.1861 | 5887983.9939 | 5229974.3965 | 18871510.5766
1522 | 21896660.5146 | 11706460.2992 | 1039785.1429 | 34642905.9567
1523 | 8885619.2805 | 7726899.5793 | 1362806.338 | 17975325.1977
1524 | 6951092.6513 | 9406026.9336 | 6721415.4922 | 23078535.0771
1525 | 5256211.0684 | 5396792.4294 | 182730.1186 | 10835733.6164
1526 | 17301457.7814 | 6312743.5811 | 4783119.1353 | 28397320.4979
1527 | 24287686.7975 | 2556215.3008 | 271146.7305 | 27115048.8287
1528 | 2140731.5367 | 0 | 391112.5057 | 2531844.0424
1529 | 3398055.7069 | 0 | 2932483.0176 | 6330538.7245
1530 | 10323355.9043 | 20092409.1803 | 986735.1705 | 31402500.2551
1531 | 10107136.6539 | 2461545.7933 | 510444.6841 | 13079127.1313
1532 | 5733176.4524 | 12834296.8892 | 0 | 18567473.3416
1533 | 16273290.2823 | 11936474.4992 | 187662.4768 | 28397427.2583
1534 | 6247470.7733 | 1205193.164 | 195279.6095 | 7647943.5468
1535 | 1985182.4314 | 0 | 8700120.196 | 10685302.6274
1536 | 9677974.5913 | 5978622.505 | 131037.9063 | 15787635.0026
1537 | 3023062.8354 | 0 | 1741911.9182 | 4764974.7536
1538 | 19035827.5618 | 4872284.5058 | 375147.4134 | 24283259.481
1539 | 12918903.0275 | 7273732.0779 | 157581.4557 | 20350216.5611
1540 | 7546912.8028 | 7959509.6235 | 4313890.0177 | 19820312.444
1541 | 4225520.064 | 5992895.3829 | 487589.9308 | 10706005.3777
1542 | 7834134.7722 | 25717325.5545 | 0 | 33551460.3267
1543 | 21748082.0182 | 2164911.7649 | 1892876.745 | 25805870.5281
1544 | 1172994.4806 | 13467637.102 | 2897946.3348 | 17538577.9174
1545 | 12820050.9042 | 32036967.4093 | 5178277.8061 | 50035296.1197
1546 | 3078607.752 | 0 | 216117.328 | 3294725.08
1547 | 33185233.7692 | 7356354.9792 | 392652.9554 | 40934241.7037
1548 | 25750386.4632 | 4402687.4929 | 975343.5194 | 31128417.4754
1549 | 3262513.2062 | 6888823.4832 | 81224.7352 | 10232561.4246
1550 | 9354076.118 | 3288338.3528 | 102110.012 | 12744524.4828
1551 | 4606461.1625 | 0 | 6637883.6277 | 11244344.7902
1552 | 5414580.7819 | 6279173.855 | 5213112.0899 | 16906866.7269
1553 | 6221079.7084 | 3707111.5544 | 1946063.2799 | 11874254.5428
1554 | 6121085.1896 | 9729006.7146 | 1117129.5546 | 16967221.4588
1555 | 3960178.656 | 22849773.4105 | 166135.2043 | 26976087.2708
1556 | 6572775.3958 | 11721250.7551 | 1853602.399 | 20147628.5499
1557 | 19001574.9781 | 10831900.1263 | 0 | 29833475.1044
1558 | 11947815.9914 | 507282.2402 | 13240228.3674 | 25695326.5989
1559 | 111132.2196 | 9518758.5138 | 10419173.4444 | 20049064.1778
1560 | 10376136.2686 | 3604653.6697 | 7918795.9663 | 21899585.9045
1561 | 17029053.9497 | 0 | 1569445.1349 | 18598499.0846
1562 | 22514564.1171 | 726420.1392 | 0 | 23240984.2563
1563 | 33693156.4172 | 8663451.5986 | 1332998.5263 | 43689606.5421
1564 | 3673320.4689 | 2343945.3877 | 961847.6457 | 6979113.5023
1565 | 14739564.44 | 0 | 0 | 14739564.44
1566 | 9073784.6986 | 6943921.8358 | 85456.4265 | 16103162.9608
1567 | 1424732.2393 | 4983743.6379 | 3246774.3107 | 9655250.1879
1568 | 3546532.8698 | 3337599.6268 | 47814.964 | 6931947.4606
1569 | 8772868.3095 | 13292474.7826 | 5847631.3213 | 27912974.4134
1570 | 8409218.1783 | 0 | 2623235.9899 | 11032454.1682
1571 | 11609615.169 | 26919767.932 | 3021603.4982 | 41550986.5991
1572 | 5617055.9309 | 15270498.913 | 4678363.3842 | 25565918.228
1573 | 1987711.626 | 0 | 3202366.6282 | 5190078.2542
1574 | 11791785.595 | 17199702.7645 | 5610475.7027 | 34601964.0622
1575 | 5673016.482 | 12055659.8901 | 394942.2975 | 18123618.6697
1576 | 3903893.1355 | 15099164.211 | 1371009.98 | 20374067.3266
1577 | 2931286.0553 | 15653992.0779 | 1383530.9732 | 19968809.1064
1578 | 3997697.8379 | 2678580.0886 | 2712338.2633 | 9388616.1899
1579 | 7231993.8915 | 5344295.0059 | 0 | 12576288.8974
1580 | 12104704.6874 | 0 | 1901213.0538 | 14005917.7413
1581 | 7016532.3086 | 13146009.2178 | 1288960.9716 | 21451502.498
1582 | 11901156.9602 | 5551468.8256 | 7019765.6992 | 24472391.485
1583 | 5340591.7672 | 0 | 1764301.0315 | 7104892.7986
1584 | 9654276.802 | 151450.6625 | 3574506.138 | 13380233.6025
1585 | 5064658.6169 | 10012526.5597 | 0 | 15077185.1766
1586 | 1786457.7151 | 24146673.8025 | 1458982.3673 | 27392113.885
1587 | 5094195.6994 | 0 | 0 | 5094195.6994
1588 | 7300263.0384 | 26346267.1154 | 17270201.0829 | 50916731.2367
1589 | 10725077.2874 | 0 | 1032950.7224 | 11758028.0098
1590 | 574064.6791 | 14416207.517 | 7598695.5103 | 22588967.7064
1591 | 34374707.7227 | 5031121.2367 | 898392.3442 | 40304221.3036
1592 | 20101242.8426 | 13681821.6528 | 1017807.9371 | 34800872.4326
1593 | 7898356.2752 | 3854149.5674 | 8013678.7719 | 19766184.6145
1594 | 7883971.6119 | 3343321.6457 | 2275110.0222 | 13502403.2798
1595 | 489569.1957 | 12696403.6138 | 2578235.4198 | 15764208.2293
1596 | 5506174.1933 | 8356844.7801 | 263686.5187 | 14126705.4921
1597 | 7033142.3423 | 1951694.0412 | 60348.8456 | 9045185.229
1598 | 2059202.5991 | 9699832.4858 | 6001510.2599 | 17760545.3448
1599 | 1235993.1076 | 7855104.487 | 211609.1491 | 9302706.7438
1600 | 2625286.8968 | 0 | 146805.28 | 2772092.1768
1601 | 16686671.9721 | 3095332.6755 | 0 | 19782004.6476
1602 | 7801396.3075 | 5617834.895 | 1615030.6445 | 15034261.8471
1603 | 5566380.3376 | 25427713.8947 | 5280581.9856 | 36274676.2179
1604 | 4528724.1514 | 2232095.4856 | 2564764.2151 | 9325583.8521
1605 | 2547315.8215 | 12924539.3253 | 1278147.0173 | 16750002.1641
1606 | 3697648.7921 | 3408701.8629 | 9340661.6268 | 16447012.2818
1607 | 4792580.2841 | 0 | 2240103.1788 | 7032683.4629
1608 | 10319570.7025 | 11178742.2215 | 1369082.8878 | 22867395.8117
1609 | 8309730.8284 | 0 | 18626.8001 | 8328357.6285
1610 | 13531418.6835 | 2554402.5979 | 724569.5661 | 16810390.8475
1611 | 202348.8278 | 3775191.4106 | 1517731.8982 | 5495272.1366
1612 | 1074865.4329 | 7383788.2725 | 3411330.2186 | 11869983.924
1613 | 17332607.8402 | 3495972.9409 | 0 | 20828580.7811
1614 | 9252130.575 | 3031779.8486 | 2732714.727 | 15016625.1506
1615 | 7976870.8699 | 4126631.1197 | 87148.9644 | 12190650.9539
1616 | 2197719.8131 | 0 | 80064.4326 | 2277784.2457
1617 | 10336881.1841 | 4744448.6193 | 1328661.8658 | 16409991.6692
1618 | 1747133.0962 | 0 | 7638020.5888 | 9385153.685
1619 | 7972698.7842 | 1766931.8832 | 2757484.8614 | 12497115.5288
1620 | 29196061.8585 | 8480499.4068 | 367334.4609 | 38043895.7263
1621 | 4217490.9361 | 3115895.3902 | 97822.1171 | 7431208.4435
1622 | 12837446.3118 | 18415024.0916 | 346962.6628 | 31599433.0661
1623 | 18210336.8213 | 1607015.649 | 95456.3668 | 19912808.8371
1624 | 17626138.5058 | 20841538.8142 | 5424418.7983 | 43892096.1183
1625 | 10209491.7104 | 1449610.6542 | 1151561.615 | 12810663.9796
1626 | 4160329.1727 | 20377374.61 | 1685671.9196 | 26223375.7023
1627 | 3110430.7436 | 0 | 1287913.3412 | 4398344.0848
1628 | 10137960.9915 | 2611649.1703 | 0 | 12749610.1618
1629 | 7360723.3332 | 1835785.0373 | 226585.4574 | 9423093.8279
1630 | 4735607.2066 | 9762353.4703 | 491747.2239 | 14989707.9008
1631 | 2307805.8967 | 17551822.9858 | 209103.3906 | 20068732.2731
1632 | 8284200.4904 | 4385429.0512 | 981738.6225 | 13651368.1642
1633 | 3669533.6703 | 31904505.7021 | 557472.0029 | 36131511.3754
1634 | 1523971.6063 | 5503789.0572 | 0 | 7027760.6635
1635 | 3686332.7215 | 7887091.028 | 0 | 11573423.7495
1636 | 7134108.9466 | 1364888.267 | 2599068.9172 | 11098066.1308
1637 | 2957756.8627 | 8348273.9962 | 0 | 11306030.8588
1638 | 6251703.4926 | 10155407.6732 | 18438787.3092 | 34845898.475
1639 | 3069830.0561 | 11704732.9182 | 852055.3958 | 15626618.3701
1640 | 2790162.8395 | 9364441.4154 | 4184388.0665 | 16338992.3214
1641 | 15968726.5587 | 28399975.0211 | 1660882.0071 | 46029583.5869
1642 | 7386528.1713 | 6736316.3713 | 8987611.1445 | 23110455.6871
1643 | 9824981.8861 | 3774512.6282 | 84642.0062 | 13684136.5205
1644 | 7685456.2938 | 29958464.7471 | 263895.4272 | 37907816.4682
1645 | 2608884.2963 | 6053500.3404 | 1812700.6993 | 10475085.3359
1646 | 3919317.2223 | 10695967.1769 | 31147511.8125 | 45762796.2117
1647 | 7439331.5794 | 22850509.5416 | 1650201.1039 | 31940042.2249
1648 | 18475949.2606 | 4797237.8358 | 0 | 23273187.0964
1649 | 5230056.1142 | 0 | 1408240.1473 | 6638296.2615
1650 | 474970.3603 | 1280712.8872 | 2897433.1497 | 4653116.3972
1651 | 8042096.1904 | 3523311.751 | 670558.8042 | 12235966.7456
1652 | 2059239.2169 | 2574226.4804 | 0 | 4633465.6973
1653 | 20661623.8368 | 0 | 1120057.7303 | 21781681.5671
1654 | 1002616.8277 | 6263143.8192 | 1227174.9953 | 8492935.6422
1655 | 18569314.491 | 1037167.6672 | 3245453.3437 | 22851935.502
1656 | 5863043.1348 | 0 | 1282308.8224 | 7145351.9572
1657 | 7220807.0463 | 7314229.8845 | 0 | 14535036.9308
1658 | 6217648.2046 | 15622349.336 | 67327.2247 | 21907324.7653
1659 | 11565840.4795 | 0 | 1733216.4209 | 13299056.9005
1660 | 8622858.6321 | 11070805.1678 | 3883588.15 | 23577251.9499
1661 | 25217962.6657 | 3181600.1697 | 2253944.725 | 30653507.5603
1662 | 1830569.2915 | 6019794.9454 | 48392.3193 | 7898756.5561
1663 | 3279815.3153 | 10297946.0545 | 118956.3602 | 13696717.73
1664 | 12043819.4667 | 2850832.577 | 247169.6271 | 15141821.6708
1665 | 7362141.4438 | 806524.0496 | 1592860.4294 | 9761525.9228
1666 | 1504847.8729 | 6893403.8897 | 2214334.4805 | 10612586.2431
1667 | 15163962.9627 | 22931886.0299 | 0 | 38095848.9926
1668 | 9130551.456 | 6088594.4889 | 759388.197 | 15978534.142
1669 | 9680264.275 | 0 | 2013361.6869 | 11693625.9619
1670 | 13132792.179 | 2898469.0459 | 4174847.2032 | 20206108.4281
1671 | 11232538.6513 | 21936683.8323 | 1744851.4397 | 34914073.9233
1672 | 12865416.0137 | 9901458.1534 | 606597.8795 | 23373472.0466
1673 | 3750974.3879 | 2910223.0171 | 1830953.6551 | 8492151.0601
1674 | 21198610.9023 | 7030826.157 | 2577231.7195 | 30806668.7788
1675 | 65417730.2022 | 11173551.0109 | 226796.6072 | 76818077.8203
1676 | 5096286.0917 | 2529167.6535 | 1330214.8035 | 8955668.5487
1677 | 5080635.0499 | 8347975.1497 | 1934716.8976 | 15363327.0972
1678 | 6215418.8471 | 6672744.6615 | 290901.0569 | 13179064.5655
1679 | 5963096.5868 | 10279791.3771 | 1009956.6401 | 17252844.6041
1680 | 11042400.3767 | 3483798.0775 | 9249367.2176 | 23775565.6718
1681 | 3323337.029 | 11353730.0937 | 301793.9533 | 14978861.0759
1682 | 4334698.708 | 1853369.8941 | 588163.9377 | 6776232.5398
1683 | 2250607.2087 | 13256509.7139 | 7237975.1593 | 22745092.0818
1684 | 4247239.5388 | 5502291.0401 | 7494258.0351 | 17243788.6139
1685 | 4320712.4875 | 10158782.0097 | 0 | 14479494.4972
1686 | 2517955.9595 | 8299951.9855 | 421640.4511 | 11239548.3961
1687 | 6606802.2505 | 7283156.8674 | 6315350.588 | 20205309.7059
1688 | 26473520.1379 | 0 | 638070.9541 | 27111591.092
1689 | 12177993.3855 | 5856080.8807 | 5126011.5883 | 23160085.8546
1690 | 442360.6849 | 18346220.3987 | 15033944.2935 | 33822525.3771
1691 | 5962387.6972 | 15139058.5911 | 1470041.7663 | 22571488.0547
1692 | 2423756.6619 | 0 | 0 | 2423756.6619
1693 | 5565523.0958 | 4730347.7266 | 478965.1253 | 10774835.9477
1694 | 11451660.3312 | 9085128.1536 | 252581.8343 | 20789370.3191
1695 | 6562270.7906 | 11449661.1228 | 1596409.2195 | 19608341.1328
1696 | 40077840.7017 | 3256624.5695 | 18200146.9426 | 61534612.2138
1697 | 15404487.6117 | 8954604.5741 | 3073960.6914 | 27433052.8772
1698 | 79787.6864 | 5343980.1014 | 4237659.3406 | 9661427.1284
1699 | 1327944.4182 | 6399007.25 | 1317059.7079 | 9044011.3761
1700 | 4510076.0664 | 16748915.198 | 3422437.4036 | 24681428.6681
1701 | 23467833.0545 | 0 | 150044.2564 | 23617877.3109
1702 | 11044915.848 | 0 | 0 | 11044915.848
1703 | 11047153.4231 | 850836.0522 | 3364115.6084 | 15262105.0837
1704 | 8648938.7943 | 0 | 686709.0319 | 9335647.8262
1705 | 4778433.9328 | 5213505.4214 | 3643271.9824 | 13635211.3367
1706 | 1148659.958 | 3531001.8085 | 6301967.6125 | 10981629.379
1707 | 7559747.6069 | 0 | 1314113.5613 | 8873861.1682
1708 | 8841777.0754 | 5596189.4762 | 31748.0768 | 14469714.6284
1709 | 15901584.7278 | 6694993.2358 | 1505203.4786 | 24101781.4423
1710 | 3254628.2856 | 14030218.9974 | 497333.7826 | 17782181.0656
1711 | 2155529.3894 | 9754006.2629 | 30759.6093 | 11940295.2617
1712 | 14407540.8218 | 0 | 624228.4986 | 15031769.3205
1713 | 11098003.53 | 0 | 3594287.9165 | 14692291.4465
1714 | 2080426.0153 | 6677888.8323 | 47376.3768 | 8805691.2245
1715 | 10042020.1621 | 7491369.2137 | 771497.3682 | 18304886.744
1716 | 4721587.8379 | 13916999.5692 | 1386518.3593 | 20025105.7663
1717 | 5466800.5515 | 10218252.857 | 1817338.5337 | 17502391.9423
1718 | 5232978.885 | 3570020.4486 | 4738289.5658 | 13541288.8994
1719 | 2274321.302 | 0 | 1004805.4382 | 3279126.7402
1720 | 13539427.702 | 0 | 27568.4438 | 13566996.1458
1721 | 8559019.1906 | 0 | 5256822.0771 | 13815841.2676
1722 | 10870434.0882 | 4510429.8082 | 477896.8192 | 15858760.7156
1723 | 4892397.3466 | 10495689.9588 | 9929318.4409 | 25317405.7463
1724 | 3612623.6828 | 5454667.8107 | 1516978.4109 | 10584269.9043
1725 | 5721819.421 | 3515686.8747 | 256988.0497 | 9494494.3454
1726 | 3364227.5754 | 15154377.5549 | 10385484.377 | 28904089.5073
1727 | 14866059.1335 | 8065477.3474 | 5959666.46 | 28891202.9409
1728 | 3838419.816 | 23151838.1195 | 2079120.1353 | 29069378.0708
1729 | 6024912.2615 | 0 | 809217.3983 | 6834129.6598
1730 | 2498946.8199 | 17385887.2505 | 17399312.5456 | 37284146.616
1731 | 5392169.3887 | 2804570.6591 | 5763606.9917 | 13960347.0396
1732 | 17120723.7793 | 13493581.7715 | 8981955.9581 | 39596261.5089
1733 | 5993159.3622 | 8318556.4005 | 3500591.571 | 17812307.3337
1734 | 43714972.3562 | 13000779.993 | 3755150.4548 | 60470902.8039
1735 | 11571663.424 | 1488912.5074 | 0 | 13060575.9314
1736 | 10638154.0338 | 6617280.5598 | 2597928.2587 | 19853362.8523
1737 | 11409227.2166 | 1867988.3029 | 7917184.5794 | 21194400.0989
1738 | 9330662.2615 | 1573642.0996 | 1668010.9445 | 12572315.3057
1739 | 10354076.392 | 0 | 194048.7687 | 10548125.1607
1740 | 4175191.3013 | 18133085.2974 | 947157.1083 | 23255433.707
1741 | 9181040.4456 | 5866204.8033 | 540545.4168 | 15587790.6658
1742 | 4900202.2637 | 8017232.6054 | 10458447.823 | 23375882.6921
1743 | 5641616.8289 | 10253773.0828 | 7014658.1935 | 22910048.1051
1744 | 1650433.3712 | 310688.0948 | 2107336.1952 | 4068457.6611
1745 | 8831744.0242 | 25312564.0451 | 0 | 34144308.0693
1746 | 548804.1694 | 13268434.8179 | 0 | 13817238.9873
1747 | 1317451.6599 | 6015441.8116 | 2215302.031 | 9548195.5025
1748 | 32764374.7452 | 4202137.0987 | 8975404.8752 | 45941916.719
1749 | 11747554.283 | 10899487.728 | 354477.4013 | 23001519.4122
1750 | 14645045.8883 | 0 | 609534.7822 | 15254580.6706
1751 | 1290984.2285 | 1962381.6287 | 158922.83 | 3412288.6872
1752 | 5373607.6218 | 25357431.7024 | 0 | 30731039.3242
1753 | 8451899.52 | 0 | 14676834.8597 | 23128734.3797
1754 | 6875185.5373 | 9873148.8008 | 305287.7702 | 17053622.1083
1755 | 6314324.0934 | 18786653.5169 | 1758483.8473 | 26859461.4576
1756 | 1828008.702 | 4393593.2158 | 0 | 6221601.9178
1757 | 3653852.9254 | 2978685.0824 | 1885401.1568 | 8517939.1646
1758 | 38632615.6888 | 2885347.1272 | 566785.399 | 42084748.2149
1759 | 3881593.4374 | 0 | 73027.6187 | 3954621.056
1760 | 6386613.9805 | 10625811.4278 | 187241.1805 | 17199666.5888
1761 | 19007038.3311 | 0 | 720015.8268 | 19727054.1579
1762 | 1025880.5274 | 0 | 991143.86 | 2017024.3875
1763 | 19143299.9476 | 5367259.1215 | 613503.5505 | 25124062.6196
1764 | 10495600.7034 | 8243243.8251 | 237571.1151 | 18976415.6436
1765 | 8812611.4508 | 2686779.8946 | 3401379.4289 | 14900770.7743
1766 | 2384526.4278 | 2381618.0201 | 0 | 4766144.4479
1767 | 6841208.549 | 11534288.6831 | 6326739.3225 | 24702236.5546
1768 | 1340969.154 | 9271638.7739 | 0 | 10612607.9278
1769 | 4261006.3978 | 0 | 0 | 4261006.3978
1770 | 3735291.9194 | 0 | 5691367.602 | 9426659.5214
1771 | 5392434.5015 | 7578036.552 | 116819.828 | 13087290.8816
1772 | 4223607.9475 | 5511452.9612 | 4275403.6864 | 14010464.5951
1773 | 12669776.446 | 6786653.7137 | 221185.4476 | 19677615.6073
1774 | 8070364.4326 | 2150657.1722 | 143829.2401 | 10364850.8449
1775 | 8727468.6062 | 5443126.9102 | 165962.9842 | 14336558.5007
1776 | 5125214.7885 | 12326431.5787 | 2570463.6614 | 20022110.0286
1777 | 26674375.7747 | 9638942.1042 | 7063894.7448 | 43377212.6237
1778 | 8522362.6374 | 5830963.3833 | 1401884.2937 | 15755210.3145
1779 | 11676592.9391 | 14036377.6194 | 489937.3722 | 26202907.9307
1780 | 15357531.508 | 12257899.1735 | 1619694.362 | 29235125.0435
1781 | 28159034.0782 | 0 | 859706.5418 | 29018740.6199
1782 | 10389419.012 | 2262320.705 | 831188.6125 | 13482928.3295
1783 | 5698026.4312 | 6410090.9931 | 906690.7824 | 13014808.2067
1784 | 4840849.7379 | 0 | 159506.8014 | 5000356.5393
1785 | 228340.8574 | 12913399.7815 | 1417833.4017 | 14559574.0407
1786 | 2775973.1386 | 3414962.2397 | 219349.139 | 6410284.5173
1787 | 8351408.3693 | 9554935.6818 | 523927.7738 | 18430271.8249
1788 | 23161536.0584 | 4257044.5373 | 906761.5011 | 28325342.0968
1789 | 2033793.7159 | 2492022.8378 | 1625918.0867 | 6151734.6403
1790 | 17530979.1794 | 6853619.2239 | 0 | 24384598.4033
1791 | 4597455.2 | 0 | 1306682.4698 | 5904137.6698
1792 | 5506566.5648 | 0 | 163050.0726 | 5669616.6375
1793 | 9046629.2913 | 9749823.7502 | 16577901.9829 | 35374355.0245
1794 | 849501.5106 | 0 | 1160802.5105 | 2010304.0211
1795 | 3855560.4454 | 6555614.4936 | 1672786.058 | 12083960.9971
1796 | 3673580.6786 | 0 | 0 | 3673580.6786
1797 | 6940733.2293 | 33177689.38 | 11315631.8342 | 51434054.4436
1798 | 18472247.0655 | 13022090.0147 | 624601.7722 | 32118938.8524
1799 | 7160562.1102 | 69447268.7753 | 1189659.0801 | 77797489.9656
1800 | 3538186.3702 | 10547009.5527 | 11637.4398 | 14096833.3627
1801 | 1636032.767 | 0 | 80656.7164 | 1716689.4835
1802 | 2219592.873 | 20558099.7641 | 741190.7826 | 23518883.4198
1803 | 6895586.5714 | 14742382.1255 | 615097.0786 | 22253065.7754
1804 | 5145088.933 | 11026086.7496 | 410002.5694 | 16581178.252
1805 | 9729438.7553 | 23383850.0791 | 347146.8882 | 33460435.7227
1806 | 7150946.9364 | 66220.653 | 75370.4171 | 7292538.0065
1807 | 10317431.5838 | 5598595.4029 | 0 | 15916026.9868
1808 | 6274183.4253 | 2451850.1585 | 0 | 8726033.5839
1809 | 6618920.0914 | 13086800.8223 | 262390.5259 | 19968111.4396
1810 | 2984534.2268 | 7507205.3413 | 1773614.2645 | 12265353.8326
1811 | 5794409.0551 | 9530203.7659 | 39914.5143 | 15364527.3352
1812 | 1628852.7915 | 13177724.1468 | 301450.6152 | 15108027.5535
1813 | 3124905.2127 | 23982428.1507 | 6304859.3894 | 33412192.7528
1814 | 26110020.0927 | 14107234.4223 | 2803073.3306 | 43020327.8456
1815 | 13597897.608 | 6848632.8493 | 2088589.5526 | 22535120.0099
1816 | 8632167.0744 | 5120191.2424 | 3586003.0331 | 17338361.35
1817 | 10770699.3034 | 19418804.3854 | 585932.5306 | 30775436.2194
1818 | 3795616.4804 | 3917357.4354 | 3317276.4959 | 11030250.4118
1819 | 2152010.2762 | 4090219.2234 | 2476337.2333 | 8718566.7329
1820 | 1453316.0984 | 0 | 5379224.7864 | 6832540.8848
1821 | 16903283.5689 | 2617262.9127 | 24340637.2842 | 43861183.7658
1822 | 1982337.2329 | 10271153.0368 | 5481127.2281 | 17734617.4978
1823 | 3596781.3239 | 2969840.745 | 4129983.617 | 10696605.6859
1824 | 3197814.8907 | 4583473.0237 | 0 | 7781287.9144
1825 | 7580031.7141 | 0 | 0 | 7580031.7141
1826 | 6422011.771 | 22948833.9627 | 0 | 29370845.7336
1827 | 3539244.2015 | 12860053.4246 | 474306.0278 | 16873603.6538
1828 | 1790989.5362 | 19693172.4575 | 429636.9925 | 21913798.9862
1829 | 22685425.1322 | 3101919.1115 | 0 | 25787344.2437
1830 | 4735850.4872 | 6638943.0673 | 552635.7957 | 11927429.3502
1831 | 3065833.7703 | 3847269.0636 | 2675951.7296 | 9589054.5634
1832 | 5651843.1053 | 12668481.052 | 3131122.0933 | 21451446.2506
1833 | 13090817.5986 | 4988779.4893 | 0 | 18079597.088
1834 | 7906261.3701 | 982778.4898 | 513584.7473 | 9402624.6072
1835 | 2978520.499 | 8246211.952 | 1648945.7765 | 12873678.2274
1836 | 10251398.5593 | 0 | 751109.4131 | 11002507.9724
1837 | 14919816.9699 | 4094547.114 | 3584763.6662 | 22599127.7501
1838 | 14949829.5777 | 411753.2114 | 3839906.0654 | 19201488.8545
1839 | 5844723.5023 | 28826760.3264 | 0 | 34671483.8288
1840 | 10598070.2996 | 4155893.0726 | 5033208.4066 | 19787171.7788
1841 | 2332515.8085 | 12867062.6092 | 0 | 15199578.4177
1842 | 3590868.9077 | 0 | 0 | 3590868.9077
1843 | 1354848.0243 | 5197688.5242 | 3497689.4171 | 10050225.9656
1844 | 14864157.1065 | 3773304.464 | 798972.8277 | 19436434.3982
1845 | 12046084.4095 | 5352966.0866 | 74852.4082 | 17473902.9043
1846 | 7339778.7429 | 3917597.7687 | 2621895.3639 | 13879271.8755
1847 | 10366220.1115 | 15102702.6892 | 0 | 25468922.8007
1848 | 2090498.0769 | 3890683.4406 | 0 | 5981181.5175
1849 | 2354894.2225 | 1923260.0172 | 34482.587 | 4312636.8267
1850 | 5142993.9117 | 0 | 13682366.2807 | 18825360.1923
1851 | 1350567.613 | 3252765.9566 | 672551.3168 | 5275884.8865
1852 | 789916.0535 | 22730073.3521 | 877063.4151 | 24397052.8206
1853 | 35111849.9225 | 8756008.2032 | 36416.4813 | 43904274.6071
1854 | 8075087.0822 | 27847389.4113 | 7407615.2366 | 43330091.7302
1855 | 20074264.461 | 9049433.7217 | 87280.9036 | 29210979.0863
1856 | 12369439.4675 | 20256476.9003 | 8710287.4102 | 41336203.7781
1857 | 6475043.7999 | 4298362.7783 | 1791729.2854 | 12565135.8637
1858 | 5719239.7738 | 25036928.5174 | 173038.4816 | 30929206.7728
1859 | 15083050.1611 | 7018744.8518 | 940966.4395 | 23042761.4524
1860 | 13239619.1389 | 21094319.4561 | 4030832.0817 | 38364770.6768
1861 | 14293674.367 | 3740441.9392 | 444097.7745 | 18478214.0807
1862 | 7917914.5659 | 8513617.4236 | 0 | 16431531.9895
1863 | 12804037.9405 | 6094912.0575 | 69329.2913 | 18968279.2894
1864 | 21363690.6324 | 0 | 1665132.8411 | 23028823.4736
1865 | 4801202.3791 | 9266282.5089 | 0 | 14067484.888
1866 | 8802468.3774 | 13314892.3636 | 106194.545 | 22223555.2859
1867 | 9181823.8687 | 6999798.792 | 2580642.5391 | 18762265.1998
1868 | 12060070.4004 | 2868366.3645 | 3488107.8453 | 18416544.6102
1869 | 1433441.1565 | 4471673.0769 | 256564.6431 | 6161678.8766
1870 | 6607619.941 | 8520596.7111 | 469522.1376 | 15597738.7897
1871 | 10249851.7814 | 13978194.4179 | 1945392.2863 | 26173438.4856
1872 | 8985597.1144 | 0 | 0 | 8985597.1144
1873 | 7287482.0114 | 0 | 2368630.0463 | 9656112.0577
1874 | 8703129.5072 | 1702829.3411 | 9376043.0983 | 19782001.9466
1875 | 11870174.0131 | 288884.4921 | 176195.8938 | 12335254.399
1876 | 7387190.2925 | 5741161.9712 | 2075845.0884 | 15204197.3521
1877 | 2844092.3976 | 0 | 265042.6967 | 3109135.0942
1878 | 8774539.427 | 4933426.1548 | 3005685.2331 | 16713650.8149
1879 | 17921055.3109 | 2981382.563 | 1029117.9355 | 21931555.8094
1880 | 4671803.0912 | 154870.5178 | 2827064.5999 | 7653738.2089
1881 | 7756711.1713 | 1809402.9622 | 414779.2612 | 9980893.3946
1882 | 5189107.8676 | 2353766.993 | 8946909.9573 | 16489784.818
1883 | 3594610.0508 | 10477493.3577 | 252364.2828 | 14324467.6914
1884 | 21334411.8473 | 3487001.2921 | 754385.8306 | 25575798.97
1885 | 13095594.8889 | 1132489.0778 | 646912.7883 | 14874996.755
1886 | 2192701.8635 | 3971445.1259 | 1464624.7997 | 7628771.7891
1887 | 1481537.0499 | 16943848.4172 | 1194333.7842 | 19619719.2513
1888 | 9403923.4004 | 6994189.2126 | 0 | 16398112.613
1889 | 22229220.8602 | 16877124.1427 | 1261635.2275 | 40367980.2304
1890 | 4278711.8008 | 3044461.6595 | 77934.3469 | 7401107.8072
1891 | 9997953.6842 | 17076647.477 | 4895214.2526 | 31969815.4138
1892 | 7415672.028 | 9629263.136 | 202661.9564 | 17247597.1203
1893 | 2768158.3536 | 2741962.9088 | 123315.0166 | 5633436.279
1894 | 4099197.2605 | 1786309.2007 | 1143755.4529 | 7029261.9141
1895 | 6325795.4891 | 5075522.7613 | 1930015.942 | 13331334.1924
1896 | 7316206.8167 | 3697070.2956 | 981270.7688 | 11994547.8811
1897 | 16851752.9126 | 3499279.155 | 0 | 20351032.0677
1898 | 7298658.0214 | 9637438.9751 | 9454996.6906 | 26391093.6871
1899 | 3524922.8293 | 8439282.6902 | 2410334.7077 | 14374540.2271
1900 | 3912430.2669 | 1179073.1814 | 1747537.39 | 6839040.8383
1901 | 1283421.7135 | 25418035.7784 | 508435.385 | 27209892.8769
1902 | 14545532.2523 | 7206421.8668 | 746894.3756 | 22498848.4948
1903 | 31487256.3683 | 18990074.7201 | 6544024.6178 | 57021355.7062
1904 | 3666853.6566 | 2455323.6361 | 2067532.9577 | 8189710.2504
1905 | 23842212.0784 | 17137523.3335 | 0 | 40979735.4119
1906 | 7562532.3222 | 2089698.1211 | 2734444.2917 | 12386674.735
1907 | 4659150.2286 | 6309699.2078 | 0 | 10968849.4364
1908 | 28964686.9912 | 2365392.6317 | 0 | 31330079.6229
1909 | 3917697.2438 | 8086129.0027 | 206412.6864 | 12210238.9329
1910 | 9407697.6289 | 4557655.2926 | 3364010.3371 | 17329363.2586
1911 | 3747675.8861 | 12085267.893 | 0 | 15832943.7791
1912 | 1502453.7768 | 2533180.2484 | 0 | 4035634.0252
1913 | 14547064.1416 | 12873296.0791 | 5369192.412 | 32789552.6327
1914 | 2217584.9421 | 38045065.6628 | 1548510.1536 | 41811160.7585
1915 | 8521275.3939 | 8489105.4567 | 103660.0966 | 17114040.9473
1916 | 8042560.6424 | 5670147.3338 | 36485.3928 | 13749193.3691
1917 | 4949469.2051 | 10456688.2215 | 2364969.6602 | 17771127.0869
1918 | 4774451.8348 | 9759473.4335 | 0 | 14533925.2683
1919 | 5169682.1984 | 1690493.4762 | 365125.9328 | 7225301.6074
1920 | 11320405.2581 | 0 | 1465753.3556 | 12786158.6138
1921 | 10902480.0707 | 17373310.2301 | 9337042.596 | 37612832.8968
1922 | 1526713.3222 | 4089397.6965 | 2573352.7439 | 8189463.7626
1923 | 3914929.7126 | 6139194.6227 | 671868.5887 | 10725992.9241
1924 | 4330753.8187 | 5162907.9972 | 23776.3674 | 9517438.1833
1925 | 6293053.6678 | 4115177.529 | 3701191.5299 | 14109422.7267
1926 | 2710911.4828 | 8840050.6912 | 259094.5012 | 11810056.6752
1927 | 3880170.9782 | 0 | 11721.244 | 3891892.2222
1928 | 5261738.1249 | 7671684.9343 | 888399.4057 | 13821822.465
1929 | 7291994.5111 | 12522805.894 | 6242107.0514 | 26056907.4565
1930 | 3108429.54 | 11201960.3442 | 814059.0026 | 15124448.8867
1931 | 7903945.312 | 47245908.1502 | 1882440.484 | 57032293.9463
1932 | 4445674.2536 | 0 | 1287826.0749 | 5733500.3285
1933 | 11668992.1659 | 7415459.048 | 876856.3917 | 19961307.6055
1934 | 5789572.2209 | 9506686.1519 | 542755.3196 | 15839013.6925
1935 | 10913743.2712 | 3576263.445 | 48203.5898 | 14538210.306
1936 | 3693032.7323 | 9014113.9719 | 114031.057 | 12821177.7612
1937 | 9142493.0456 | 0 | 110874.5313 | 9253367.5769
1938 | 3738894.9514 | 2397941.9943 | 3761134.2285 | 9897971.1741
1939 | 1053053.6777 | 0 | 79307.1491 | 1132360.8268
1940 | 4949018.2251 | 11596313.2015 | 17603118.0485 | 34148449.4751
1941 | 2992878.0888 | 0 | 3130435.7274 | 6123313.8163
1942 | 17992579.7243 | 624292.8939 | 0 | 18616872.6182
1943 | 5697918.8666 | 5273887.7541 | 286320.1485 | 11258126.7691
1944 | 7184200.5484 | 0 | 0 | 7184200.5484
1945 | 39660842.8867 | 6866631.9955 | 31632.6707 | 46559107.5528
1946 | 4044932.9578 | 2725763.76 | 71160.9207 | 6841857.6385
1947 | 11254658.4267 | 2765716.624 | 0 | 14020375.0506
1948 | 15166675.8925 | 9411466.5857 | 1445745.0106 | 26023887.4888
1949 | 11791756.0829 | 7752526.22 | 0 | 19544282.3029
1950 | 7906197.7326 | 3035291.7662 | 0 | 10941489.4988
1951 | 16526865.3188 | 0 | 26533.3538 | 16553398.6726
1952 | 8676039.1044 | 1869623.8295 | 1670866.6423 | 12216529.5762
1953 | 5879534.2812 | 23597600.8002 | 0 | 29477135.0815
1954 | 4941448.6189 | 1959063.0498 | 13779968.9259 | 20680480.5946
1955 | 6891128.6147 | 3162622.0031 | 75150.9752 | 10128901.593
1956 | 10026243.5354 | 0 | 2247427.4086 | 12273670.944
1957 | 22377191.2505 | 5596750.4568 | 3249340.0752 | 31223281.7825
1958 | 8301733.3983 | 205075.1264 | 4784696.5467 | 13291505.0714
1959 | 25459791.3186 | 11186444.9308 | 1846299.8113 | 38492536.0608
1960 | 18487343.4824 | 14628759.1167 | 519276.8879 | 33635379.487
1961 | 4081023.2841 | 5313381.2274 | 0 | 9394404.5115
1962 | 4817065.6121 | 8278644.6533 | 1966684.1962 | 15062394.4617
1963 | 7140134.2354 | 4144246.1894 | 93519.4402 | 11377899.865
1964 | 4303363.4883 | 11052296.8077 | 0 | 15355660.296
1965 | 22884756.8456 | 2405140.7351 | 0 | 25289897.5806
1966 | 432212.9913 | 19999891.7329 | 51273.0444 | 20483377.7686
1967 | 8951961.2176 | 7375554.5407 | 101800.8467 | 16429316.605
1968 | 4175625.771 | 1726066.3044 | 592683.1852 | 6494375.2606
1969 | 1266325.1556 | 6872609.5726 | 239175.535 | 8378110.2633
1970 | 3528771.8858 | 3020370.1613 | 273850.4092 | 6822992.4563
1971 | 6847540.2621 | 38634365.2589 | 1054042.953 | 46535948.4741
1972 | 13022684.0847 | 5268197.5724 | 2582252.389 | 20873134.0462
1973 | 1493535.6882 | 6054983.5687 | 0 | 7548519.2569
1974 | 7733669.2826 | 0 | 3967990.3827 | 11701659.6653
1975 | 22424116.6818 | 12316252.9804 | 23400.385 | 34763770.0472
1976 | 12924123.3335 | 15961022.828 | 4063585.8309 | 32948731.9925
1977 | 12005040.4327 | 2408076.1456 | 0 | 14413116.5783
1978 | 4690986.454 | 3239714.5906 | 1359237.1021 | 9289938.1466
1979 | 31350541.3323 | 10727144.1031 | 1373607.9458 | 43451293.3812
1980 | 11810658.7617 | 8733514.8888 | 2396905.2409 | 22941078.8915
1981 | 2085649.502 | 4136173.3274 | 832068.94 | 7053891.7693
1982 | 10373781.1106 | 6714488.6323 | 646215.298 | 17734485.0409
1983 | 1065754.1374 | 3990963.4509 | 7233129.4873 | 12289847.0756
1984 | 6553885.7491 | 12016249.973 | 6929813.2485 | 25499948.9707
1985 | 2214133.3969 | 1829927.1729 | 820006.1533 | 4864066.7231
1986 | 16526314.3661 | 2845205.3361 | 0 | 19371519.7022
1987 | 35432372.3461 | 19605311.6054 | 19174898.3857 | 74212582.3372
1988 | 6083528.3176 | 11532789.1321 | 6398541.8744 | 24014859.3241
1989 | 16607718.716 | 7831875.0402 | 6264495.6249 | 30704089.3811
1990 | 2751170.7667 | 9542924.2767 | 1413543.1992 | 13707638.2425
1991 | 17578554.6097 | 10902151.1602 | 2446302.7608 | 30927008.5307
1992 | 4459199.2848 | 11116950.5192 | 1834585.4176 | 17410735.2216
1993 | 9228789.346 | 1158649.7956 | 77782.7554 | 10465221.8969
1994 | 12809946.1591 | 934549.4451 | 212164.7873 | 13956660.3914
1995 | 1309847.9551 | 7387848.2343 | 430444.3381 | 9128140.5275
1996 | 5836224.8982 | 11925552.9888 | 5120808.8265 | 22882586.7135
1997 | 11832266.3632 | 16467374.2713 | 17745504.7541 | 46045145.3886
1998 | 3198878.0096 | 4878185.5132 | 1325932.6867 | 9402996.2095
1999 | 14588694.0233 | 2705867.9947 | 1969733.9367 | 19264295.9547
2000 | 14540639.1122 | 6739659.252 | 208837.3462 | 21489135.7103
2001 | 928986.8686 | 13026237.9713 | 773569.3724 | 14728794.2123
2002 | 3602385.4923 | 0 | 0 | 3602385.4923
2003 | 3188138.6021 | 9902038.2719 | 0 | 13090176.8741
2004 | 4018503.3397 | 5386922.4542 | 9620320.0162 | 19025745.8101
2005 | 3477806.0641 | 5535590.1614 | 1120002.0969 | 10133398.3224
2006 | 11416842.3566 | 3771895.099 | 153939.1893 | 15342676.6449
2007 | 7356044.7426 | 17782649.4765 | 1259950.3989 | 26398644.618
2008 | 10713841.5312 | 22871118.0436 | 0 | 33584959.5748
2009 | 12723714.1156 | 6782272.9306 | 8333207.6417 | 27839194.6879
2010 | 1504811.2827 | 3687341.0319 | 239853.324 | 5432005.6386
2011 | 6070852.0278 | 7530222.3799 | 114847.1291 | 13715921.5368
2012 | 15529633.0939 | 9134303.2268 | 355666.8187 | 25019603.1395
2013 | 15984264.7574 | 5304011.7271 | 3433913.6457 | 24722190.1301
2014 | 18711496.1894 | 2051857.2757 | 1686579.9746 | 22449933.4398
2015 | 7160204.2736 | 0 | 0 | 7160204.2736
2016 | 1565344.0382 | 3675643.0533 | 577183.4496 | 5818170.541
2017 | 10984579.7319 | 4848628.3906 | 1882047.1097 | 17715255.2322
2018 | 36738893.1569 | 20560842.0941 | 649991.8986 | 57949727.1496
2019 | 1527295.9593 | 4515607.623 | 11513393.3864 | 17556296.9687
2020 | 4574606.9434 | 0 | 259601.271 | 4834208.2145
2021 | 37697078.9027 | 10918725.3983 | 213052.2139 | 48828856.5149
2022 | 14982057.9586 | 6981865.7588 | 819409.8134 | 22783333.5308
2023 | 7349426.1307 | 9668447.3276 | 1075520.0297 | 18093393.488
2024 | 877887.8481 | 6712925.1202 | 3299097.68 | 10889910.6484
2025 | 450531.3726 | 3897451.4158 | 2619286.3687 | 6967269.1572
2026 | 17083602.5822 | 0 | 6380327.7288 | 23463930.3109
2027 | 11820196.5334 | 0 | 454878.1538 | 12275074.6872
2028 | 3879920.3231 | 9265337.6459 | 0 | 13145257.9689
2029 | 11800682.4792 | 7992554.9072 | 2241115.993 | 22034353.3794
2030 | 1145654.327 | 0 | 0 | 1145654.327
2031 | 2416021.6084 | 395351.8194 | 15972305.3452 | 18783678.773
2032 | 1687181.6622 | 5609890.7923 | 1195128.0595 | 8492200.5141
2033 | 6713777.4202 | 0 | 646193.4102 | 7359970.8304
2034 | 13611529.6181 | 4572154.5499 | 153938.4918 | 18337622.6599
2035 | 8401038.8532 | 19236790.6146 | 9875348.2503 | 37513177.7182
2036 | 1634670.9976 | 14551769.8632 | 0 | 16186440.8608
2037 | 5434697.0941 | 4225092.2321 | 0 | 9659789.3261
2038 | 5942765.9287 | 1315600.387 | 5093705.8746 | 12352072.1904
2039 | 2273879.7389 | 5652510.3416 | 573753.7894 | 8500143.87
2040 | 29257049.3312 | 33882475.0928 | 1584413.4283 | 64723937.8523
2041 | 7176379.3578 | 13062060.45 | 1033531.6955 | 21271971.5033
2042 | 16489145.3614 | 0 | 6210523.1322 | 22699668.4936
2043 | 24485876.5744 | 24527061.6163 | 1042171.9023 | 50055110.093
2044 | 6423042.3395 | 0 | 1220432.8636 | 7643475.2031
2045 | 7803744.4222 | 4054488.6973 | 1734462.0012 | 13592695.1208
2046 | 5573607.0029 | 31753.3384 | 0 | 5605360.3412
2047 | 5375136.8807 | 8942231.0318 | 763224.5282 | 15080592.4406
2048 | 2414086.8059 | 9838679.8428 | 5793103.5422 | 18045870.1908
2049 | 11604808.1292 | 8328196.41 | 12565395.0782 | 32498399.6174
2050 | 10345127.8755 | 33522646.7579 | 357743.2354 | 44225517.8689
2051 | 13812477.5493 | 0 | 504149.2703 | 14316626.8196
2052 | 6833281.7826 | 2505603.1259 | 610561.6167 | 9949446.5252
2053 | 2026920.364 | 0 | 683757.1489 | 2710677.5129
2054 | 9953532.6525 | 3070919.0222 | 0 | 13024451.6747
2055 | 5589419.7206 | 12301366.2794 | 769736.8315 | 18660522.8315
2056 | 13637049.0573 | 14555718.4699 | 678693.8887 | 28871461.4158
2057 | 7553229.8672 | 19627335.6072 | 1128362.5657 | 28308928.04
2058 | 2535874.0264 | 18424923.732 | 1115605.6929 | 22076403.4512
2059 | 12495063.9208 | 7354771.2778 | 2001654.723 | 21851489.9216
2060 | 8110677.5534 | 12058828.5714 | 2920939.3513 | 23090445.4761
2061 | 7839188.5365 | 1697599.1148 | 2118418.6318 | 11655206.2831
2062 | 11661234.8453 | 8132731.7119 | 2244120.5609 | 22038087.118
2063 | 7415985.8245 | 8092766.0922 | 1257540.5739 | 16766292.4906
2064 | 5029647.166 | 6115781.3754 | 640924.0379 | 11786352.5792
2065 | 9670938.2593 | 5781590.9908 | 0 | 15452529.2501
2066 | 14827500.4475 | 12277955.0977 | 554970.4827 | 27660426.0279
2067 | 3140483.9413 | 13095768.5784 | 4551327.1226 | 20787579.6424
2068 | 1402805.0284 | 9716051.8006 | 2437924.8144 | 13556781.6435
2069 | 14302666.7878 | 13129507.5709 | 0 | 27432174.3587
2070 | 12839161.8079 | 5203880.2334 | 14119.2323 | 18057161.2735
2071 | 4626666.8307 | 3918293.9036 | 0 | 8544960.7342
2072 | 1365529.3223 | 4865956.0354 | 0 | 6231485.3577
2073 | 7101669.6496 | 0 | 0 | 7101669.6496
2074 | 7456706.0231 | 0 | 540422.1229 | 7997128.146
2075 | 3216683.327 | 5512428.7507 | 8626227.2434 | 17355339.3211
2076 | 14273253.16 | 9451346.027 | 2687743.5741 | 26412342.7611
2077 | 12705085.9077 | 0 | 106126.9921 | 12811212.8998
2078 | 6137903.8616 | 2904950.2225 | 0 | 9042854.0841
2079 | 4116837.7047 | 4920393.4686 | 1124317.9051 | 10161549.0784
2080 | 8530654.4668 | 2434966.2261 | 0 | 10965620.6929
2081 | 6294249.0937 | 15503552.1463 | 486155.0688 | 22283956.3088
2082 | 14996583.8042 | 5843209.1846 | 1444212.2596 | 22284005.2484
2083 | 6459068.0241 | 0 | 3170398.4757 | 9629466.4998
2084 | 4000363.5166 | 3908661.443 | 0 | 7909024.9596
2085 | 9635706.0856 | 2551177.2128 | 2629853.8513 | 14816737.1497
2086 | 8982330.1412 | 4834064.0532 | 464198.8521 | 14280593.0465
2087 | 4420704.932 | 20242619.7504 | 5763516.8172 | 30426841.4996
2088 | 3495083.0489 | 0 | 1261876.7903 | 4756959.8392
2089 | 45895396.1998 | 0 | 13510302.8852 | 59405699.0851
2090 | 2950407.5407 | 10575230.5814 | 483911.124 | 14009549.2461
2091 | 10987990.2629 | 0 | 0 | 10987990.2629
2092 | 27826299.8137 | 9434579.086 | 3952093.3816 | 41212972.2813
2093 | 11847712.0703 | 0 | 6669429.4382 | 18517141.5086
2094 | 3424843.174 | 9802856.6365 | 95319.4371 | 13323019.2476
2095 | 5133239.1665 | 22286860.2469 | 713449.5735 | 28133548.9869
2096 | 3347856.6882 | 15891101.2062 | 0 | 19238957.8944
2097 | 8418280.7331 | 5304928.7234 | 2456471.2346 | 16179680.6911
2098 | 20144616.5269 | 3069370.6316 | 1462847.775 | 24676834.9334
2099 | 1643442.0362 | 1497233.406 | 977556.006 | 4118231.4482
2100 | 16786009.2094 | 1146189.5313 | 51523200.2946 | 69455399.0353
2101 | 15306191.1628 | 6469562.4993 | 16967.631 | 21792721.2931
2102 | 3825460.806 | 3743754.8352 | 0 | 7569215.6412
2103 | 8228214.7431 | 0 | 1804759.6374 | 10032974.3804
2104 | 3443066.0177 | 1946239.7846 | 4639396.1035 | 10028701.9058
2105 | 12258313.4274 | 20812338.3836 | 0 | 33070651.811
2106 | 16547068.1957 | 6861723.5507 | 1419681.8597 | 24828473.6061
2107 | 4267247.8429 | 7000851.9842 | 0 | 11268099.8271
2108 | 10437766.198 | 5700517.0074 | 9647030.7347 | 25785313.9401
2109 | 5191790.2707 | 7825868.5472 | 6268095.7414 | 19285754.5593
2110 | 3270560.8189 | 4105497.7184 | 10712729.316 | 18088787.8532
2111 | 3946118.4986 | 19140030.0872 | 5615189.8019 | 28701338.3877
2112 | 2213618.424 | 36280922.4588 | 950929.3456 | 39445470.2284
2113 | 4746651.9995 | 14072136.0541 | 4580446.884 | 23399234.9376
2114 | 4329179.228 | 17115289.5344 | 3715066.326 | 25159535.0884
2115 | 2930193.1861 | 17203078.8119 | 525244.6205 | 20658516.6184
2116 | 8796805.6634 | 1935218.5354 | 0 | 10732024.1988
2117 | 2473311.4738 | 3382953.9164 | 1491985.4504 | 7348250.8405
2118 | 2396402.4722 | 6828880.5222 | 2477684.237 | 11702967.2314
2119 | 5366569.3763 | 932498.1284 | 2941723.6621 | 9240791.1668
2120 | 4979366.512 | 8673349.1963 | 11094791.5265 | 24747507.2348
2121 | 4618074.5092 | 8542027.0246 | 1811282.3199 | 14971383.8538
2122 | 13497299.5158 | 5623712.4116 | 67688.3183 | 19188700.2457
2123 | 4613325.2479 | 4639159.5908 | 2779490.9408 | 12031975.7795
2124 | 12474003.5412 | 0 | 171010.7832 | 12645014.3243
2125 | 4063170.1083 | 2238141.3127 | 21727205.4751 | 28028516.8961
2126 | 7139670.7744 | 11121724.6581 | 5182302.933 | 23443698.3654
2127 | 3531633.3821 | 6202492.1577 | 0 | 9734125.5398
2128 | 5045377.8577 | 0 | 249561.8112 | 5294939.6689
2129 | 19582244.9871 | 10814657.2263 | 1209718.1782 | 31606620.3917
2130 | 11082009.077 | 5555573.1621 | 2153780.9559 | 18791363.1951
2131 | 5051383.6067 | 8335981.7014 | 440787.5371 | 13828152.8452
2132 | 5819016.156 | 20526031.446 | 0 | 26345047.602
2133 | 17288823.6373 | 9510170.1006 | 0 | 26798993.738
2134 | 26488228.826 | 8019255.7109 | 2089876.7566 | 36597361.2934
2135 | 20952039.7773 | 0 | 693331.3351 | 21645371.1124
2136 | 2998937.78 | 0 | 67017.1124 | 3065954.8924
2137 | 3572157.1362 | 1858151.6783 | 176002.2847 | 5606311.0993
2138 | 16478696.3481 | 0 | 0 | 16478696.3481
2139 | 4071681.9878 | 2979834.8951 | 5777295.453 | 12828812.3358
2140 | 4148449.5669 | 0 | 1395306.8096 | 5543756.3765
2141 | 3122483.7324 | 12344829.7908 | 0 | 15467313.5232
2142 | 9020719.667 | 10066250.3581 | 4769157.9342 | 23856127.9594
2143 | 3139161.4031 | 2387012.8732 | 4117290.796 | 9643465.0724
2144 | 11293450.0651 | 24318429.6366 | 7285568.8272 | 42897448.5289
2145 | 23063835.568 | 13379729.8188 | 449900.3724 | 36893465.7593
2146 | 8513131.1472 | 8906875.3112 | 8242339.9366 | 25662346.395
2147 | 26228827.4155 | 18140803.1351 | 0 | 44369630.5506
2148 | 3238295.6467 | 4229987.3543 | 0 | 7468283.001
2149 | 12681676.6534 | 4032005.1194 | 7713716.9812 | 24427398.754
2150 | 12883575.8081 | 1899016.1062 | 101115.8249 | 14883707.7392
2151 | 1795645.068 | 13216335.8506 | 2578465.4607 | 17590446.3794
2152 | 1919482.4167 | 0 | 3917324.8619 | 5836807.2787
2153 | 1892739.9444 | 52022929.0464 | 1121918.4985 | 55037587.4892
2154 | 13158838.4211 | 17487862.2458 | 183593.1203 | 30830293.7872
2155 | 9023501.3333 | 0 | 6551667.0003 | 15575168.3336
2156 | 10494716.7382 | 7497291.7913 | 2593065.867 | 20585074.3964
2157 | 18446570.3914 | 10635520.2998 | 9580595.7347 | 38662686.4259
2158 | 9767500.0093 | 0 | 7933832.8129 | 17701332.8222
2159 | 7182377.4717 | 2375134.896 | 1239153.7653 | 10796666.1331
2160 | 5816717.4754 | 5047397.2962 | 528303.0105 | 11392417.7822
2161 | 4705707.2276 | 5001961.2451 | 87500.3343 | 9795168.8069
2162 | 8098360.7901 | 20066296.6627 | 283129.8488 | 28447787.3015
2163 | 5596950.4714 | 5597805.6443 | 549773.146 | 11744529.2618
2164 | 2175133.9436 | 5751485.0864 | 13524097.3138 | 21450716.3437
2165 | 6238987.6294 | 6471771.3926 | 11650414.8017 | 24361173.8238
2166 | 11664364.2007 | 4317386.738 | 1471489.7298 | 17453240.6684
2167 | 9232396.2057 | 0 | 1000020.2294 | 10232416.4352
2168 | 3875919.9544 | 5597885.2803 | 1511850.0533 | 10985655.2879
2169 | 3886705.8096 | 6356765.7828 | 949975.1407 | 11193446.7332
2170 | 14384038.8495 | 6797148.2987 | 1470978.0701 | 22652165.2182
2171 | 5171701.8255 | 2585696.3259 | 2202754.3337 | 9960152.4852
2172 | 3754254.6064 | 18170450.6286 | 0 | 21924705.235
2173 | 6795993.3783 | 27175351.4662 | 234651.3017 | 34205996.1461
2174 | 903013.7896 | 0 | 522881.0426 | 1425894.8322
2175 | 6316370.2171 | 2644835.5625 | 13182077.9327 | 22143283.7123
2176 | 3341081.3921 | 1434520.6026 | 49102.7916 | 4824704.7863
2177 | 15730438.3468 | 11282655.2858 | 0 | 27013093.6325
2178 | 583140.9633 | 8493001.1296 | 4873467.891 | 13949609.9839
2179 | 6118991.4144 | 3679763.1587 | 1960028.7997 | 11758783.3728
2180 | 1955719.3274 | 5394059.9985 | 9646205.1484 | 16995984.4744
2181 | 4155058.6645 | 11252825.5494 | 520912.2518 | 15928796.4658
2182 | 141552.1438 | 2550654.5843 | 1332999.9297 | 4025206.6578
2183 | 6352325.0604 | 16815989.0098 | 1007886.3008 | 24176200.3709
2184 | 12983260.479 | 5098045.3836 | 300302.2943 | 18381608.1568
2185 | 2638774.4574 | 0 | 4112389.5556 | 6751164.013
2186 | 14727265.6211 | 3161941.502 | 172210.423 | 18061417.5462
2187 | 14456385.3599 | 4289104.6439 | 0 | 18745490.0038
2188 | 5695052.1295 | 7598730.4317 | 1802982.441 | 15096765.0022
2189 | 7875163.5508 | 13586694.9231 | 0 | 21461858.4739
2190 | 1933732.6268 | 12377289.7445 | 4007107.7304 | 18318130.1017
2191 | 7256502.1971 | 602927.4731 | 2244148.0661 | 10103577.7363
2192 | 23869071.5534 | 13190555.9234 | 1355214.7741 | 38414842.2509
2193 | 7022350.1341 | 18286726.4005 | 2650981.6704 | 27960058.205
2194 | 18864017.771 | 10183142.8016 | 45639.9146 | 29092800.4873
2195 | 3715274.9932 | 5190431.3995 | 2295456.048 | 11201162.4407
2196 | 2834209.5289 | 0 | 0 | 2834209.5289
2197 | 4544871.1163 | 7021394.5329 | 1280784.3936 | 12847050.0428
2198 | 12086781.3031 | 1974497.899 | 7415028.3859 | 21476307.588
2199 | 3208296.6192 | 4704431.084 | 4256859.1388 | 12169586.8421
2200 | 5515668.6042 | 4439768.2096 | 1621592.5742 | 11577029.388
2201 | 6386567.0392 | 1979545.6957 | 729788.5072 | 9095901.2421
2202 | 19920909.4333 | 10888897.452 | 11547843.9725 | 42357650.8579
2203 | 15121431.2724 | 17207873.9046 | 1317033.8593 | 33646339.0363
2204 | 5385207.7809 | 10442050.8831 | 2339736.5541 | 18166995.2182
2205 | 4393162.7544 | 6506305.6238 | 294017.8895 | 11193486.2677
2206 | 6922895.9586 | 20003757.4872 | 14222989.1148 | 41149642.5606
2207 | 3435305.7716 | 13018104.1556 | 0 | 16453409.9272
2208 | 6792513.8461 | 0 | 0 | 6792513.8461
2209 | 4302323.4854 | 6340440.4771 | 238686.4463 | 10881450.4088
2210 | 14266662.1125 | 2647856.4984 | 782309.8537 | 17696828.4646
2211 | 2467196.6895 | 11852231.8606 | 223327.6208 | 14542756.1709
2212 | 19065843.1176 | 0 | 492833.4405 | 19558676.5582
2213 | 9565687.9797 | 2743353.8613 | 8743276.8198 | 21052318.6608
2214 | 1239033.0695 | 20253224.4374 | 0 | 21492257.5069
2215 | 2429760.9346 | 5917912.784 | 3336261.4981 | 11683935.2167
2216 | 2100789.5623 | 3067566.9755 | 12704609.1896 | 17872965.7275
2217 | 1289823.0022 | 1641620.6384 | 677960.6151 | 3609404.2557
2218 | 5544362.7779 | 11921159.4082 | 2358272.4853 | 19823794.6715
2219 | 27180867.929 | 1102425.798 | 4079405.7386 | 32362699.4656
2220 | 9585160.4216 | 9241120.2279 | 0 | 18826280.6495
2221 | 4115659.6307 | 9968402.1952 | 2629375.9177 | 16713437.7436
2222 | 13043143.3333 | 3359061.8751 | 3135964.9404 | 19538170.1488
2223 | 12813708.0848 | 18226260.3995 | 1960213.5532 | 33000182.0374
2224 | 12773631.9362 | 2009650.6835 | 70717.9959 | 14854000.6155
2225 | 2432643.8322 | 23461852.5992 | 1335668.5142 | 27230164.9456
2226 | 2785819.6811 | 16840061.4775 | 185741.8114 | 19811622.9699
2227 | 1923692.7164 | 7328776.3086 | 0 | 9252469.0249
2228 | 9337926.4604 | 0 | 1241283.9123 | 10579210.3727
2229 | 7209548.7418 | 22794152.5804 | 740758.7012 | 30744460.0234
2230 | 2729171.7814 | 0 | 0 | 2729171.7814
2231 | 9930800.1349 | 18824032.3157 | 7058219.9647 | 35813052.4152
2232 | 24948628.5599 | 4942009.5422 | 649873.4114 | 30540511.5135
2233 | 3800225.8542 | 18081904.4234 | 2289650.5787 | 24171780.8563
2234 | 40826973.7341 | 10475810.9676 | 2754552.0604 | 54057336.7622
2235 | 4859571.9116 | 14735578.302 | 23885626.3566 | 43480776.5701
2236 | 3508105.228 | 4678312.0386 | 284957.2372 | 8471374.5037
2237 | 10388829.8395 | 6466925.5568 | 1665016.4534 | 18520771.8498
2238 | 6068785.5713 | 15675509.4302 | 80788.8466 | 21825083.8481
2239 | 669528.3053 | 0 | 0 | 669528.3053
2240 | 12312248.7362 | 1610575.6457 | 2287201.7541 | 16210026.136
2241 | 5130355.8364 | 8997191.8641 | 8417214.1127 | 22544761.8132
2242 | 3461172.0903 | 0 | 2843110.3107 | 6304282.401
2243 | 7153967.9259 | 4480276.8279 | 7544908.9619 | 19179153.7157
2244 | 7670218.2742 | 15414992.6644 | 510266.0882 | 23595477.0267
2245 | 7202180.6422 | 3645215.0089 | 1097704.7285 | 11945100.3797
2246 | 2813302.6027 | 10716866.9908 | 119540.6994 | 13649710.2928
2247 | 6410221.5549 | 10424024.2085 | 2056568.1872 | 18890813.9505
2248 | 3356298.2215 | 9433495.7336 | 13254573.3094 | 26044367.2645
2249 | 9581249.2358 | 7965652.4522 | 0 | 17546901.688
2250 | 14539233.5396 | 1439674.9676 | 4480146.6429 | 20459055.15
2251 | 6342141.3247 | 31338701.4397 | 185749.5725 | 37866592.3369
2252 | 12290177.0357 | 3146701.6368 | 4469161.3012 | 19906039.9738
2253 | 9670175.5581 | 7276682.4885 | 2779047.9232 | 19725905.9698
2254 | 829671.8783 | 22066474.2012 | 0 | 22896146.0795
2255 | 7351681.4821 | 9531556.1079 | 418041.1907 | 17301278.7807
2256 | 7780347.8765 | 15839265.1954 | 268071.0381 | 23887684.1099
2257 | 4442483.0078 | 12133902.4119 | 27490.2932 | 16603875.7129
2258 | 1242585.5664 | 19747287.3374 | 11955143.0356 | 32945015.9394
2259 | 8901124.113 | 10305276.6179 | 3658161.9293 | 22864562.6602
2260 | 16935376.6305 | 8261170.9861 | 766947.4593 | 25963495.0759
2261 | 20547772.6999 | 5238364.5404 | 3608750.3229 | 29394887.5632
2262 | 7500406.7922 | 7250067.3714 | 379656.1939 | 15130130.3575
2263 | 3337262.6881 | 5057054.6122 | 620339.0691 | 9014656.3694
2264 | 1867761.6359 | 2959898.3196 | 2974258.802 | 7801918.7575
2265 | 2913672.7019 | 4902339.9031 | 2432784.8036 | 10248797.4086
2266 | 5080128.2194 | 14454008.1521 | 0 | 19534136.3715
2267 | 3351289.0466 | 12206834.816 | 764563.587 | 16322687.4496
2268 | 7394482.1898 | 4133308.5906 | 3385045.5041 | 14912836.2844
2269 | 5595094.4291 | 0 | 2008892.6658 | 7603987.0949
2270 | 7975542.6285 | 0 | 918883.609 | 8894426.2374
2271 | 7416106.5794 | 9747023.4867 | 234344.4444 | 17397474.5106
2272 | 8748065.2439 | 6183852.0124 | 2773498.851 | 17705416.1073
2273 | 3152111.3103 | 2916223.829 | 291290.3126 | 6359625.4518
2274 | 1992558.5502 | 0 | 189886.1638 | 2182444.7141
2275 | 1596699.7894 | 1237524.5598 | 16350.4937 | 2850574.8429
2276 | 19706821.8227 | 10446701.103 | 9681528.6922 | 39835051.6179
2277 | 2444727.844 | 3237326.4352 | 5909978.3112 | 11592032.5904
2278 | 4179151.8879 | 11171287.7198 | 1532630.2662 | 16883069.8738
2279 | 2346886.5195 | 13443410.8385 | 1319846.8247 | 17110144.1828
2280 | 8200921.4327 | 3734749.7756 | 19467437.5626 | 31403108.7708
2281 | 4069999.5413 | 11324091.3988 | 1762061.2861 | 17156152.2263
2282 | 10407514.8745 | 4509794.7918 | 149387.9541 | 15066697.6205
2283 | 12304931.6515 | 31697175.4235 | 741607.1317 | 44743714.2067
2284 | 9551600.376 | 3488467.6515 | 346401.1394 | 13386469.1668
2285 | 5240056.708 | 4814610.1709 | 14199419.443 | 24254086.3218
2286 | 9373418.1819 | 11130638.8829 | 0 | 20504057.0648
2287 | 6483860.361 | 2524786.1956 | 3513793.5775 | 12522440.1341
2288 | 13378940.2226 | 21147889.6257 | 623915.7838 | 35150745.6321
2289 | 4685980.2762 | 6024218.0328 | 3944463.7726 | 14654662.0816
2290 | 5130540.8864 | 14095962.554 | 1623427.7993 | 20849931.2397
2291 | 19668376.6374 | 2797585.158 | 936151.6526 | 23402113.4481
2292 | 4179137.7268 | 0 | 3173855.9228 | 7352993.6496
2293 | 5667023.6036 | 3094987.6082 | 344921.9233 | 9106933.1351
2294 | 3385727.4182 | 0 | 7243953.1598 | 10629680.5779
2295 | 730996.9905 | 0 | 186214.538 | 917211.5285
2296 | 11339523.3348 | 6062182.5172 | 12082917.737 | 29484623.589
2297 | 4475796.3269 | 8401627.4333 | 131260.3263 | 13008684.0865
2298 | 5287286.925 | 1526226.2285 | 0 | 6813513.1535
2299 | 6261686.3114 | 5402812.3955 | 0 | 11664498.7069
2300 | 7382293.3121 | 4147842.8185 | 1766249.7514 | 13296385.882
2301 | 4049142.5652 | 472553.2689 | 0 | 4521695.8341
2302 | 3975788.1335 | 4718853.4526 | 0 | 8694641.5861
2303 | 21966566.4884 | 5057849.9028 | 526851.2952 | 27551267.6864
2304 | 6462546.1817 | 9738177.1782 | 939776.6847 | 17140500.0446
2305 | 2329790.8967 | 8771485.5022 | 3728854.0919 | 14830130.4908
2306 | 17842492.4931 | 2908147.4075 | 1244550.8111 | 21995190.7117
2307 | 11636993.4242 | 3800016.5197 | 0 | 15437009.9439
2308 | 4520415.2397 | 9440495.684 | 352592.5976 | 14313503.5213
2309 | 37131.8324 | 0 | 7128308.5214 | 7165440.3538
2310 | 5614997.8396 | 7587559.0569 | 0 | 13202556.8966
2311 | 7423916.9558 | 7780017.0746 | 0 | 15203934.0304
2312 | 8449030.9922 | 4891590.1408 | 930862.7819 | 14271483.915
2313 | 3002396.6623 | 11630288.2324 | 11701564.1463 | 26334249.041
2314 | 4208456.2641 | 1176785.8048 | 1301396.6862 | 6686638.7551
2315 | 13839012.4132 | 7454268.8167 | 339287.2643 | 21632568.4942
2316 | 8521332.5077 | 0 | 172856.2852 | 8694188.793
2317 | 9534244.822 | 8436188.4266 | 96571.336 | 18067004.5846
2318 | 30372059.0664 | 12914754.468 | 1107085.6984 | 44393899.2328
2319 | 4610414.6546 | 16599945.1838 | 217654.5447 | 21428014.3831
2320 | 7664124.283 | 9724564.3753 | 394156.2385 | 17782844.8968
2321 | 0 | 4500169.9113 | 100270.3842 | 4600440.2955
2322 | 5646640.1745 | 4216803.2709 | 1072493.0976 | 10935936.5429
2323 | 3649225.2165 | 0 | 0 | 3649225.2165
2324 | 5574398.1793 | 2704000.8767 | 3378516.7316 | 11656915.7876
2325 | 6044398.0174 | 3966296.7853 | 104588.8326 | 10115283.6354
2326 | 7273178.8935 | 1235044.5955 | 873014.9077 | 9381238.3967
2327 | 4178049.9969 | 9534927.3104 | 1694644.3323 | 15407621.6395
2328 | 29295029.5976 | 7807078.368 | 901868.5827 | 38003976.5483
2329 | 22932736.1646 | 10955385.9492 | 91198.5397 | 33979320.6535
2330 | 5568961.6317 | 0 | 0 | 5568961.6317
2331 | 8675909.2139 | 10313398.8221 | 8593455.5999 | 27582763.6358
2332 | 12299238.5047 | 17404262.0807 | 4137227.9483 | 33840728.5337
2333 | 2583281.8167 | 0 | 735207.1441 | 3318488.9609
2334 | 4486529.6726 | 2638162.5724 | 3740573.9357 | 10865266.1808
2335 | 6611498.6288 | 3630550.0574 | 3408206.2604 | 13650254.9466
2336 | 2963609.0649 | 1539052.1864 | 6617730.6677 | 11120391.919
2337 | 4195141.2052 | 6776734.6051 | 7348860.9387 | 18320736.749
2338 | 17424771.9281 | 7569205.779 | 191905.1279 | 25185882.835
2339 | 19741134.8169 | 8926990.2123 | 2691864.7563 | 31359989.7854
2340 | 2859249.8509 | 20755284.9451 | 2661749.7895 | 26276284.5856
2341 | 11385045.1844 | 1492006.2616 | 39556.2761 | 12916607.722
2342 | 1439765.1336 | 23764750.4327 | 3810230.8411 | 29014746.4075
2343 | 5821168.0266 | 15494109.5956 | 1165743.6442 | 22481021.2664
2344 | 7203958.6309 | 21567639.1376 | 917843.6856 | 29689441.454
2345 | 18422021.1982 | 0 | 0 | 18422021.1982
2346 | 3910611.2262 | 8380523.584 | 0 | 12291134.8103
2347 | 15180634.164 | 18950135.2115 | 2251114.876 | 36381884.2515
2348 | 2132317.0846 | 9271667.4854 | 785726.1618 | 12189710.7318
2349 | 8877420.2043 | 5067574.8473 | 152547.4724 | 14097542.5241
2350 | 14814565.5074 | 6325833.5976 | 1174467.7243 | 22314866.8294
2351 | 13500914.5182 | 7523145.7921 | 1071421.7451 | 22095482.0554
2352 | 11073385.2713 | 2364108.6585 | 83435.0879 | 13520929.0178
2353 | 1801491.0025 | 5315616.5682 | 670987.0772 | 7788094.6478
2354 | 6684286.5771 | 9369160.967 | 922405.3614 | 16975852.9055
2355 | 11758417.7292 | 10040051.497 | 2355842.8807 | 24154312.1069
2356 | 4077466.9687 | 0 | 9107002.7736 | 13184469.7423
2357 | 7519930.7573 | 0 | 58954.3887 | 7578885.146
2358 | 3921418.4119 | 17818882.0361 | 0 | 21740300.448
2359 | 6254148.1306 | 8481423.0724 | 4443233.4295 | 19178804.6325
2360 | 4775263.6118 | 0 | 5388700.9302 | 10163964.542
2361 | 1255034.3096 | 0 | 1063590.1774 | 2318624.487
2362 | 17514656.0218 | 10429715.3858 | 0 | 27944371.4076
2363 | 30431060.5033 | 11533238.5264 | 198207.6495 | 42162506.6793
2364 | 12236684.0183 | 2064559.6602 | 0 | 14301243.6784
2365 | 8797644.0873 | 13276804.5609 | 214243.6123 | 22288692.2605
2366 | 13797088.9846 | 4091918.0862 | 0 | 17889007.0708
2367 | 5154974.5078 | 11393093.3966 | 10257319.3964 | 26805387.3009
2368 | 18234904.6057 | 8378671.9877 | 0 | 26613576.5934
2369 | 4041572.6289 | 13769472.0582 | 285051.4738 | 18096096.1609
2370 | 506720.5584 | 0 | 850782.9693 | 1357503.5277
2371 | 1709225.5484 | 7830374.6156 | 67279.6954 | 9606879.8595
2372 | 3131253.3224 | 1621953.1059 | 3012410.6316 | 7765617.0599
2373 | 8336420.7934 | 0 | 0 | 8336420.7934
2374 | 8492209.6585 | 5601486.9625 | 329880.9617 | 14423577.5828
2375 | 5762329.2333 | 4600043.9239 | 0 | 10362373.1572
2376 | 2237479.2751 | 9593314.2425 | 1621290.4943 | 13452084.0119
2377 | 4350674.5997 | 5780515.8856 | 4125674.4843 | 14256864.9697
2378 | 17204294.0952 | 13181105.7069 | 730031.5314 | 31115431.3335
2379 | 7953248.1409 | 0 | 2736902.2515 | 10690150.3925
2380 | 3818785.8408 | 29506348.2386 | 93206.5115 | 33418340.5909
2381 | 3690265.8514 | 0 | 1372956.405 | 5063222.2565
2382 | 5544251.9082 | 15977899.1438 | 2671260.2439 | 24193411.296
2383 | 2969593.5524 | 0 | 2365387.2152 | 5334980.7676
2384 | 11233768.9816 | 5685619.5397 | 0 | 16919388.5213
2385 | 5342548.465 | 14200545.3973 | 5092741.8629 | 24635835.7252
2386 | 3607753.3508 | 2373305.6774 | 951082.8573 | 6932141.8855
2387 | 9797810.4766 | 5318225.0086 | 6640303.2979 | 21756338.783
2388 | 3055880.8391 | 10109937.1624 | 3137956.0419 | 16303774.0434
2389 | 14520253.139 | 16029303.1071 | 0 | 30549556.2461
2390 | 10291605.272 | 5197128.4581 | 1696363.4713 | 17185097.2015
2391 | 2360514.9704 | 27900628.5966 | 5395706.416 | 35656849.9829
2392 | 10840020.2643 | 10392450.4456 | 950700.3118 | 22183171.0217
2393 | 5341608.3767 | 13789748.4629 | 2841413.0625 | 21972769.9021
2394 | 11637404.5774 | 5589528.1886 | 0 | 17226932.766
2395 | 6507228.0415 | 0 | 1146701.3621 | 7653929.4036
2396 | 2394088.9307 | 0 | 391261.168 | 2785350.0987
2397 | 19868986.2948 | 5073598.2681 | 0 | 24942584.563
2398 | 5254769.3298 | 0 | 822318.2109 | 6077087.5407
2399 | 8567429.3294 | 0 | 342749.9709 | 8910179.3003
2400 | 10751915.4795 | 16958994.3916 | 2080895.8757 | 29791805.7468
2401 | 27439851.5674 | 9570034.1917 | 261562.9962 | 37271448.7553
2402 | 7619432.3209 | 3648963.8201 | 5664305.7806 | 16932701.9217
2403 | 328166.459 | 15895738.4356 | 896404.5221 | 17120309.4167
2404 | 15080229.5233 | 1926095.757 | 507182.7359 | 17513508.0162
2405 | 9480157.5987 | 5781122.5318 | 10817413.6295 | 26078693.76
2406 | 5952918.4602 | 0 | 6629524.0814 | 12582442.5416
2407 | 8832214.6111 | 6165801.1263 | 5608856.6805 | 20606872.4179
2408 | 3119108.4217 | 1850337.5962 | 35730.7644 | 5005176.7823
2409 | 4314567.5242 | 4315394.562 | 0 | 8629962.0862
2410 | 9678690.2676 | 12222070.3646 | 5466998.6842 | 27367759.3164
2411 | 19608031.1204 | 5049407.3412 | 50056.0422 | 24707494.5038
2412 | 4567461.9804 | 0 | 1494491.8354 | 6061953.8158
2413 | 11931631.5034 | 18806334.5057 | 653161.4955 | 31391127.5047
2414 | 2201286.7554 | 28856817.8142 | 1067224.1646 | 32125328.7342
2415 | 3898963.4402 | 0 | 0 | 3898963.4402
2416 | 23825360.9635 | 7312223.1107 | 5505739.3931 | 36643323.4673
2417 | 21147632.2649 | 23846976.0875 | 3014375.7672 | 48008984.1196
2418 | 5954138.4089 | 0 | 490336.9209 | 6444475.3298
2419 | 2223342.6787 | 7506344.6248 | 782569.1412 | 10512256.4447
2420 | 4881608.9865 | 7249185.0963 | 87673.4187 | 12218467.5014
2421 | 30320767.2413 | 6144716.5788 | 0 | 36465483.8201
2422 | 3759771.1313 | 6537932.6983 | 387412.4181 | 10685116.2478
2423 | 11626081.7547 | 7625877.4395 | 991293.6212 | 20243252.8155
2424 | 13533989.9117 | 0 | 0 | 13533989.9117
2425 | 2050227.4347 | 5438901.1436 | 90526.1181 | 7579654.6964
2426 | 28660543.0559 | 3917609.843 | 0 | 32578152.8988
2427 | 6299680.9337 | 0 | 9580370.8354 | 15880051.7691
2428 | 5002068.0942 | 2359322.4837 | 161857.6671 | 7523248.245
2429 | 5653149.0841 | 0 | 1028924.4931 | 6682073.5772
2430 | 5784147.4661 | 3350634.2234 | 2787691.7022 | 11922473.3917
2431 | 17121144.8893 | 10681245.9444 | 4420921.8825 | 32223312.7162
2432 | 3002011.3092 | 828475.3449 | 1305926.8382 | 5136413.4923
2433 | 12654050.7123 | 11462674.576 | 4418592.8806 | 28535318.1688
2434 | 7886822.5796 | 3242501.0455 | 1679174.0653 | 12808497.6904
2435 | 16165389.411 | 5063852.0063 | 6000363.9928 | 27229605.4102
2436 | 22298388.0634 | 4567956.8487 | 2476055.9825 | 29342400.8947
2437 | 4880060.1491 | 1944957.1228 | 2123698.2196 | 8948715.4916
2438 | 1832052.6707 | 5100255.4946 | 1885454.687 | 8817762.8523
2439 | 7710211.9341 | 9637289.2898 | 1650006.7508 | 18997507.9747
2440 | 3343637.1077 | 10118876.7336 | 42355.9202 | 13504869.7615
2441 | 2144944.5861 | 0 | 276256.7649 | 2421201.351
2442 | 15751443.8951 | 4817186.3329 | 669386.2412 | 21238016.4692
2443 | 4142871.2083 | 5501477.0453 | 748923.8525 | 10393272.106
2444 | 5446982.4114 | 0 | 2571665.5875 | 8018647.9989
2445 | 25155195.7813 | 15958445.3728 | 460355.0856 | 41573996.2397
2446 | 2009406.403 | 4643976.8181 | 563160.7972 | 7216544.0183
2447 | 10562955.279 | 14915724.4999 | 6928392.6239 | 32407072.4028
2448 | 7214296.9148 | 9769397.7431 | 62846.4502 | 17046541.1081
2449 | 4245148.0869 | 11812120.0713 | 1645531.5434 | 17702799.7016
2450 | 8882509.2393 | 10597043.1643 | 282737.7842 | 19762290.1878
2451 | 593669.5933 | 538308.2275 | 108470.7716 | 1240448.5925
2452 | 4431064.5896 | 9703036.4065 | 1945543.6452 | 16079644.6412
2453 | 2303175.3939 | 1106071.1712 | 2177930.9726 | 5587177.5377
2454 | 6734583.6641 | 6844030.9079 | 0 | 13578614.572
2455 | 6901733.5583 | 10674035.944 | 6187675.248 | 23763444.7503
2456 | 13884735.5141 | 11277553.5282 | 0 | 25162289.0423
2457 | 2699493.8434 | 0 | 0 | 2699493.8434
2458 | 7734974.4205 | 1010858.4773 | 1233222.2947 | 9979055.1925
2459 | 2910149.6668 | 8002066.0112 | 23658.7367 | 10935874.4147
2460 | 5477637.6419 | 5390245.2924 | 1651791.8434 | 12519674.7777
2461 | 6873009.0486 | 1799198.7248 | 491795.4421 | 9164003.2155
2462 | 4865443.6596 | 6589418.3324 | 6590373.7467 | 18045235.7388
2463 | 4535976.4016 | 11027702.1937 | 48348.1858 | 15612026.7811
2464 | 16506753.7168 | 4301188.9352 | 13739920.1042 | 34547862.7562
2465 | 2701144.3374 | 4107197.3593 | 560214.7791 | 7368556.4759
2466 | 11803053.2291 | 3521014.8901 | 10152064.8319 | 25476132.9511
2467 | 8335288.36 | 0 | 58080.5819 | 8393368.9419
2468 | 15339738.3808 | 21295462.9433 | 5656680.1245 | 42291881.4486
2469 | 3649630.6055 | 3393278.5187 | 826884.2357 | 7869793.3599
2470 | 5738978.6575 | 2594188.9081 | 5136749.7688 | 13469917.3344
2471 | 495195.3892 | 4880127.5721 | 7051051.4926 | 12426374.4539
2472 | 7661261.2943 | 13218669.9016 | 4193113.7998 | 25073044.9957
2473 | 6029650.7372 | 3881381.6855 | 0 | 9911032.4227
2474 | 10225023.8536 | 26995534.9234 | 5168386.4657 | 42388945.2427
2475 | 12199206.8824 | 0 | 0 | 12199206.8824
2476 | 10140483.1998 | 27330776.6922 | 857766.2034 | 38329026.0954
2477 | 16584227.1509 | 26347641.0496 | 2591622.6604 | 45523490.8609
2478 | 6728921.6799 | 12779904.2132 | 1853196.2926 | 21362022.1857
2479 | 19089184.9615 | 0 | 0 | 19089184.9615
2480 | 4137201.1654 | 3439353.3993 | 9037448.0391 | 16614002.6038
2481 | 8543988.2516 | 1582289.2756 | 0 | 10126277.5272
2482 | 11995406.8993 | 12082604.4446 | 0 | 24078011.3439
2483 | 8497785.8417 | 11905387.459 | 29085.1602 | 20432258.4609
2484 | 275535.6647 | 4211285.1669 | 659882.5825 | 5146703.4142
2485 | 2825524.6115 | 9704773.1994 | 0 | 12530297.811
2486 | 2242066.5083 | 3500651.2149 | 1181193.115 | 6923910.8382
2487 | 6561568.3884 | 26880966.8077 | 3618520.5554 | 37061055.7515
2488 | 2839544.6032 | 17256717.3124 | 41601.7275 | 20137863.6431
2489 | 732283.3164 | 5858898.9466 | 0 | 6591182.263
2490 | 6909423.2479 | 1979394.6256 | 25831563.8361 | 34720381.7096
2491 | 10562803.3232 | 7440082.4941 | 9920020.0642 | 27922905.8815
2492 | 5695766.396 | 10490769.1446 | 505213.448 | 16691748.9887
2493 | 11566361.9255 | 2434267.1412 | 2561010.4834 | 16561639.55
2494 | 7342129.3987 | 6581639.6757 | 133636.2743 | 14057405.3488
2495 | 4742218.313 | 9817400.0755 | 0 | 14559618.3885
2496 | 769159.9828 | 5788506.7397 | 1009454.4389 | 7567121.1614
2497 | 5109060.0355 | 0 | 672739.8459 | 5781799.8814
2498 | 5531152.942 | 16006088.6145 | 2687684.0212 | 24224925.5777
2499 | 3824257.718 | 0 | 9704547.2332 | 13528804.9512
2500 | 3718962.1331 | 0 | 55332.9503 | 3774295.0834
2501 | 22706042.205 | 6414296.5904 | 724795.9174 | 29845134.7127
2502 | 11878861.7736 | 5052737.8459 | 1367377.0451 | 18298976.6646
2503 | 4182066.4214 | 9510927.2583 | 1687359.2496 | 15380352.9293
2504 | 17537151.2121 | 2497148.7114 | 582283.9174 | 20616583.8408
2505 | 15591587.3039 | 5415931.7234 | 1537405.7223 | 22544924.7496
2506 | 8693173.3262 | 8189698.8435 | 11596623.13 | 28479495.2997
2507 | 1880252.8395 | 0 | 3118401.2992 | 4998654.1387
2508 | 14428152.9176 | 0 | 2555110.8392 | 16983263.7568
2509 | 7055792.9635 | 14453812.2229 | 13073248.6111 | 34582853.7975
2510 | 2227086.115 | 7276343.6523 | 509002.4731 | 10012432.2405
2511 | 7525952.4928 | 10546325.4385 | 0 | 18072277.9313
2512 | 5531699.1516 | 3174051.7331 | 1668690.4307 | 10374441.3153
2513 | 8050698.3534 | 5964850.5246 | 2216792.0786 | 16232340.9566
2514 | 14746552.9874 | 5717395.9964 | 568856.1396 | 21032805.1233
2515 | 14549497.16 | 13872601.8943 | 0 | 28422099.0544
2516 | 2214589.6981 | 3440434.3248 | 165687.689 | 5820711.7119
2517 | 12040325.0691 | 5277229.8101 | 0 | 17317554.8792
2518 | 6774707.5566 | 9217487.6449 | 1068737.8776 | 17060933.0792
2519 | 5757243.8878 | 1437406.5041 | 0 | 7194650.3918
2520 | 2033640.4401 | 17589158.9674 | 0 | 19622799.4075
2521 | 2001236.6309 | 1450768.081 | 2737101.0038 | 6189105.7157
2522 | 3574701.3194 | 10357301.05 | 236570.7117 | 14168573.0811
2523 | 1618459.3775 | 7973023.2678 | 0 | 9591482.6453
2524 | 3509324.0105 | 21740184.2223 | 228166.6066 | 25477674.8395
2525 | 4681150.7318 | 0 | 0 | 4681150.7318
2526 | 8490287.5286 | 13625283.1092 | 0 | 22115570.6377
2527 | 11339.8378 | 3751084.0448 | 116559.2347 | 3878983.1173
2528 | 25715453.6807 | 0 | 0 | 25715453.6807
2529 | 6138969.7196 | 17142532.7553 | 0 | 23281502.4749
2530 | 8597973.4004 | 0 | 756650.309 | 9354623.7094
2531 | 3031040.9315 | 0 | 836756.4804 | 3867797.412
2532 | 15809861.4886 | 5007608.6189 | 1454676.4485 | 22272146.556
2533 | 32525385.3281 | 6337494.8687 | 1186381.6163 | 40049261.8131
2534 | 3115123.1459 | 1391943.622 | 7801389.3906 | 12308456.1586
2535 | 10022418.7057 | 4894894.2071 | 25675.2651 | 14942988.1779
2536 | 3820913.8697 | 655112.4246 | 3963799.6523 | 8439825.9467
2537 | 16319113.7378 | 13251940.1006 | 7314.448 | 29578368.2863
2538 | 1371223.6119 | 18683540.8232 | 91228.5175 | 20145992.9526
2539 | 7002647.4508 | 13852251.4959 | 0 | 20854898.9468
2540 | 17131715.3358 | 743853.72 | 5643651.7655 | 23519220.8213
2541 | 16305417.9032 | 3757556.3567 | 280156.5467 | 20343130.8067
2542 | 14035974.3378 | 12972127.8209 | 0 | 27008102.1587
2543 | 11489592.5235 | 14321515.0453 | 709945.9627 | 26521053.5314
2544 | 14236403.1726 | 0 | 241404.6561 | 14477807.8287
2545 | 3255212.667 | 10482962.5162 | 4638026.8257 | 18376202.0089
2546 | 12350416.8402 | 1349007.1653 | 4417320.8065 | 18116744.812
2547 | 6807012.876 | 0 | 6445047.0988 | 13252059.9749
2548 | 5004386.433 | 15237086.463 | 1617429.7383 | 21858902.6344
2549 | 23312692.0748 | 2520012.7061 | 794034.1192 | 26626738.9001
2550 | 9186213.8313 | 17850269.1916 | 4207691.008 | 31244174.0308
2551 | 17601754.1292 | 9293809.8976 | 333463.4438 | 27229027.4706
2552 | 12760289.3385 | 0 | 2353545.5567 | 15113834.8952
2553 | 6588285.0071 | 11249826.2541 | 1593914.454 | 19432025.7152
2554 | 3065590.151 | 2368786.236 | 0 | 5434376.3871
2555 | 3129296.4977 | 4949893.2401 | 128088.3929 | 8207278.1307
2556 | 13216119.6867 | 13191996.7151 | 1241445.3428 | 27649561.7446
2557 | 1548632.5954 | 25270409.4962 | 2457005.0715 | 29276047.163
2558 | 1845165.4329 | 0 | 1709239.5525 | 3554404.9854
2559 | 19825452.4884 | 8957693.1424 | 2619166.3522 | 31402311.983
2560 | 4895570.4662 | 20397781.5339 | 0 | 25293352
2561 | 1547980.7073 | 8221625.726 | 731555.0996 | 10501161.5329
2562 | 6406383.7545 | 9149542.161 | 1451681.8858 | 17007607.8013
2563 | 6417409.7235 | 7915638.0443 | 2830819.6318 | 17163867.3996
2564 | 7308079.9319 | 3041724.2363 | 394884.0563 | 10744688.2245
2565 | 3447843.4013 | 8703062.319 | 1371403.7283 | 13522309.4486
2566 | 4001072.9676 | 10709661.445 | 525524.4442 | 15236258.8569
2567 | 4147831.9054 | 6538346.5625 | 0 | 10686178.4679
2568 | 21412855.6736 | 30975985.974 | 2109096.8179 | 54497938.4654
2569 | 5705432.7305 | 3490919.0882 | 65609.9063 | 9261961.725
2570 | 3896371.0105 | 4843679.0986 | 407106.3832 | 9147156.4923
2571 | 4313190.0984 | 4792942.8096 | 25156.4325 | 9131289.3404
2572 | 7297063.882 | 1862817.3967 | 904073.2702 | 10063954.5489
2573 | 7293670.468 | 8268203.6606 | 1012981.5556 | 16574855.6841
2574 | 14094533.8047 | 5713316.9077 | 1439208.7373 | 21247059.4498
2575 | 20621566.1879 | 8996651.3147 | 0 | 29618217.5026
2576 | 8119839.0709 | 0 | 10052751.988 | 18172591.0589
2577 | 12201205.444 | 8633363.0727 | 10944648.0935 | 31779216.6102
2578 | 15860575.5001 | 18782840.1616 | 243237.0822 | 34886652.744
2579 | 6883722.8412 | 9456616.2238 | 8548575.7236 | 24888914.7887
2580 | 3124026.2139 | 3373373.6831 | 4423366.4012 | 10920766.2982
2581 | 6721847.3255 | 0 | 601775.2698 | 7323622.5953
2582 | 8530272.9476 | 13589969.2275 | 133327.1693 | 22253569.3445
2583 | 5465266.0612 | 17335460.7115 | 1322373.8933 | 24123100.666
2584 | 15593189.1836 | 4187681.2456 | 5122400.6453 | 24903271.0745
2585 | 4775503.6552 | 9572914.7736 | 874689.3535 | 15223107.7823
2586 | 3443508.7407 | 6074837.8888 | 3232450.5603 | 12750797.1897
2587 | 2691173.2869 | 12636206.8317 | 5879135.7 | 21206515.8185
2588 | 3674571.8743 | 2705428.7164 | 2202371.0641 | 8582371.6548
2589 | 6407009.832 | 14747909.532 | 2570393.9516 | 23725313.3155
2590 | 1274190.3777 | 1722841.7981 | 573227.6056 | 3570259.7813
2591 | 12241834.3168 | 4516690.4696 | 2323020.1808 | 19081544.9672
2592 | 7925045.8971 | 0 | 707312.7781 | 8632358.6753
2593 | 12459851.4702 | 10358306.9984 | 572374.5401 | 23390533.0088
2594 | 5931743.6234 | 2365054.8793 | 2938893.4613 | 11235691.964
2595 | 3022951.732 | 4059632.741 | 2227668.5642 | 9310253.0372
2596 | 4880929.314 | 14712690.3709 | 2934733.667 | 22528353.3519
2597 | 3419368.5823 | 0 | 0 | 3419368.5823
2598 | 11886570.2316 | 3914874.079 | 2673728.6705 | 18475172.9811
2599 | 19515495.9919 | 6836933.1078 | 743329.4938 | 27095758.5935
2600 | 14797404.8588 | 3363257.9585 | 4267360.8972 | 22428023.7145
2601 | 6883383.7738 | 6763948.9345 | 0 | 13647332.7083
2602 | 6468072.3776 | 1360352.3004 | 198923.6811 | 8027348.3591
2603 | 3246568.6833 | 3834299.6242 | 1310787.3187 | 8391655.6262
2604 | 14382299.6004 | 8424845.3994 | 9766179.8753 | 32573324.8751
2605 | 185859.4836 | 14167909.4043 | 2034624.5868 | 16388393.4747
2606 | 12641370.8375 | 16149753.7883 | 2364079.8374 | 31155204.4632
2607 | 18337145.2495 | 2572063.2468 | 14832839.5216 | 35742048.0179
2608 | 6405551.51 | 5597549.7413 | 0 | 12003101.2512
2609 | 12081055.6422 | 5025515.2138 | 9925572.4743 | 27032143.3303
2610 | 18177413.3329 | 17423635.5287 | 6156486.5207 | 41757535.3823
2611 | 4863073.0355 | 10175669.8786 | 0 | 15038742.9141
2612 | 27642061.5649 | 8303358.7192 | 0 | 35945420.2842
2613 | 3079808.7869 | 5187931.6741 | 44736.1371 | 8312476.5981
2614 | 5105311.6489 | 2700128.6344 | 3451728.0339 | 11257168.3172
2615 | 32408763.9532 | 3417383.7872 | 7970308.9258 | 43796456.6662
2616 | 2657736.7326 | 4569920.6253 | 5501424.787 | 12729082.1449
2617 | 3096732.562 | 18759409.4045 | 1463150.3716 | 23319292.3381
2618 | 10408623.2744 | 5734379.3479 | 0 | 16143002.6223
2619 | 8760935.6568 | 1399196.9649 | 2599565.0212 | 12759697.6429
2620 | 15028413.6473 | 0 | 135940.1108 | 15164353.7581
2621 | 5206159.2623 | 28678564.5278 | 52844.9836 | 33937568.7737
2622 | 3068545.9252 | 8776018.8332 | 0 | 11844564.7585
2623 | 15371481.584 | 9271307.6949 | 131681.971 | 24774471.2499
2624 | 6054615.2456 | 5427086.3802 | 784180.7815 | 12265882.4073
2625 | 8095600.7934 | 0 | 7925178.8047 | 16020779.5981
2626 | 6025701.199 | 7222454.0137 | 1348284.3762 | 14596439.5889
2627 | 3756836.3682 | 18050196.7612 | 2077612.9933 | 23884646.1227
2628 | 3283355.9714 | 15814243.9548 | 893402.8178 | 19991002.744
2629 | 24677312.3215 | 3652601.1609 | 0 | 28329913.4824
2630 | 15439589.6351 | 5677530.8123 | 590169.1414 | 21707289.5887
2631 | 13310689.2441 | 0 | 1658792.0877 | 14969481.3318
2632 | 144485.288 | 10362365.3627 | 1388205.5323 | 11895056.183
2633 | 40012713.9411 | 5026234.0524 | 953481.8401 | 45992429.8336
2634 | 7917677.054 | 2655928.2792 | 397414.1711 | 10971019.5042
2635 | 6719577.578 | 0 | 1571575.6386 | 8291153.2166
2636 | 8038971.2155 | 7300530.2297 | 1580275.7612 | 16919777.2063
2637 | 24112947.2192 | 1578906.5264 | 2045378.5103 | 27737232.2559
2638 | 5500949.4781 | 8953874.6863 | 0 | 14454824.1645
2639 | 19370501.6665 | 4299025.8044 | 1920531.8131 | 25590059.2839
2640 | 3964412.9716 | 3204822.049 | 2804388.5491 | 9973623.5697
2641 | 4762425.2881 | 1557441.1138 | 126703.4596 | 6446569.8615
2642 | 2877954.368 | 4384140.6731 | 13680775.3441 | 20942870.3852
2643 | 21056172.9778 | 0 | 119610.5966 | 21175783.5744
2644 | 8319474.291 | 0 | 3740205.5737 | 12059679.8647
2645 | 4615632.9865 | 449920.2099 | 271717.4396 | 5337270.636
2646 | 2079620.2245 | 35614016.0772 | 21803.3268 | 37715439.6285
2647 | 690295.247 | 4072985.1201 | 1381605.6133 | 6144885.9804
2648 | 20318724.249 | 0 | 405884.122 | 20724608.371
2649 | 15962222.5702 | 6501980.9723 | 14040235.7064 | 36504439.249
2650 | 7971965.9462 | 3626899.2976 | 3619446.2028 | 15218311.4466
2651 | 273144.0465 | 6407673.4083 | 453425.1926 | 7134242.6473
2652 | 3649049.4224 | 1204260.8218 | 746369.0229 | 5599679.2671
2653 | 2046610.2546 | 10956224.1358 | 282995.2602 | 13285829.6506
2654 | 1631493.71 | 15506536.8796 | 457575.0908 | 17595605.6804
2655 | 7752383.8319 | 16532201.1278 | 0 | 24284584.9597
2656 | 4221417.9126 | 6858004.643 | 817066.7189 | 11896489.2745
2657 | 14943298.2035 | 2061496.5821 | 262037.7571 | 17266832.5427
2658 | 2373283.4659 | 8162071.4135 | 823973.2716 | 11359328.151
2659 | 11186868.1377 | 1616453.7168 | 207284.3576 | 13010606.2121
2660 | 22320019.6304 | 3072699.8503 | 0 | 25392719.4807
2661 | 10519101.55 | 3207224.2931 | 6458491.4983 | 20184817.3413
2662 | 5496470.3012 | 9323677.2935 | 68968.5028 | 14889116.0975
2663 | 9691843.4928 | 22537963.0114 | 3856599.5704 | 36086406.0745
2664 | 627294.2399 | 16725187.4156 | 89829.7014 | 17442311.357
2665 | 10143885.5148 | 2588709.5826 | 944857.3204 | 13677452.4177
2666 | 4371662.6822 | 0 | 559579.2384 | 4931241.9206
2667 | 14858243.2563 | 0 | 8149849.1509 | 23008092.4072
2668 | 8164146.1537 | 12634000.0022 | 2481466.7625 | 23279612.9184
2669 | 8432982.6585 | 4729326.4113 | 1083076.5324 | 14245385.6021
2670 | 2829230.205 | 23447774.0742 | 244593.8857 | 26521598.165
2671 | 9875085.2233 | 60614403.7667 | 2642178.946 | 73131667.936
2672 | 1507266.2218 | 5034571.7343 | 1612609.0256 | 8154446.9817
2673 | 12474712.5022 | 16057013.3957 | 2000921.9689 | 30532647.8667
2674 | 4012618.5323 | 0 | 57273.9695 | 4069892.5018
2675 | 11892410.0902 | 0 | 0 | 11892410.0902
2676 | 6592484.9343 | 10324769.9069 | 2308109.5902 | 19225364.4315
2677 | 4138252.5608 | 7770259.519 | 1271049.9737 | 13179562.0535
2678 | 7168071.8178 | 0 | 4018367.559 | 11186439.3768
2679 | 32788851.1574 | 15308047.4386 | 676275.4369 | 48773174.0329
2680 | 5521135.5515 | 10789561.9521 | 0 | 16310697.5037
2681 | 9521391.0459 | 17518230.4869 | 14009705.2622 | 41049326.7951
2682 | 7113268.8273 | 4862763.0137 | 356499.5866 | 12332531.4276
2683 | 7919677.0808 | 1911671.0642 | 157087.0471 | 9988435.1921
2684 | 20208080.3798 | 11530762.496 | 18009184.4685 | 49748027.3443
2685 | 3383825.6237 | 6541035.696 | 271204.8263 | 10196066.146
2686 | 14990878.0463 | 6652974.7434 | 170486.3563 | 21814339.146
2687 | 3569040.2779 | 0 | 0 | 3569040.2779
2688 | 9723407.6658 | 0 | 1755559.3859 | 11478967.0517
2689 | 4324330.3251 | 1990141.9211 | 2126417.4035 | 8440889.6497
2690 | 11723655.0528 | 7584499.3816 | 6665975.6759 | 25974130.1104
2691 | 4652785.1729 | 2145401.2466 | 438427.6049 | 7236614.0244
2692 | 5823264.925 | 7847707.2649 | 1129963.1144 | 14800935.3043
2693 | 12956639.9323 | 78436607.1092 | 478756.0565 | 91872003.098
2694 | 2450992.2245 | 0 | 11561206.4639 | 14012198.6884
2695 | 3429096.3447 | 4328485.4748 | 3793459.9472 | 11551041.7667
2696 | 493537.8539 | 11108846.848 | 3232416.7679 | 14834801.4699
2697 | 3030145.1922 | 2586783.0075 | 9975163.5697 | 15592091.7694
2698 | 11803173.0977 | 2632034.8908 | 2856335.2429 | 17291543.2314
2699 | 8855655.6124 | 5423181.8646 | 1050018.9006 | 15328856.3776
2700 | 2877717.3748 | 7468703.5497 | 8196176.9544 | 18542597.8789
2701 | 4772885.1094 | 8813464.8366 | 1623182.1509 | 15209532.0969
2702 | 3831802.8492 | 22549993.3233 | 1061687.9145 | 27443484.087
2703 | 1353596.524 | 6305902.263 | 1779716.3395 | 9439215.1264
2704 | 18937691.2583 | 2608385.6745 | 1593078.2503 | 23139155.1831
2705 | 4028245.174 | 10063327.9519 | 13124782.9629 | 27216356.0888
2706 | 11007271.743 | 488517.6566 | 150189.5667 | 11645978.9663
2707 | 5412039.44 | 0 | 0 | 5412039.44
2708 | 3838363.5873 | 4428819.1871 | 5477892.5505 | 13745075.3249
2709 | 7650751.0679 | 7052124.7243 | 1337221.7525 | 16040097.5447
2710 | 7293828.4353 | 16774318.0561 | 0 | 24068146.4914
2711 | 5820668.9732 | 25722926.6667 | 3169384.4234 | 34712980.0633
2712 | 12531616.4288 | 4048764.1693 | 0 | 16580380.5981
2713 | 6960060.4047 | 25435514.4491 | 2520256.2002 | 34915831.054
2714 | 6598994.0483 | 0 | 2769364.5867 | 9368358.635
2715 | 2090251.1483 | 0 | 2160616.85 | 4250867.9983
2716 | 3452947.7087 | 0 | 3425785.5337 | 6878733.2424
2717 | 6159053.1234 | 0 | 709234.2051 | 6868287.3286
2718 | 883612.0059 | 11130338.0239 | 603024.2527 | 12616974.2826
2719 | 16986554.9938 | 9352544.6402 | 1076492.1469 | 27415591.7808
2720 | 7680796.7053 | 7437336.7788 | 8034051.8153 | 23152185.2993
2721 | 1623160.1729 | 7647856.1107 | 44177.277 | 9315193.5606
2722 | 5706764.4745 | 3966573.1594 | 32345.0959 | 9705682.7299
2723 | 5373448.2382 | 0 | 0 | 5373448.2382
2724 | 11808564.6089 | 8767119.5425 | 344802.1126 | 20920486.2639
2725 | 6249837.5469 | 0 | 17916102.0977 | 24165939.6446
2726 | 8265944.132 | 2751052.2391 | 133792.762 | 11150789.1331
2727 | 7750845.3393 | 503761.5111 | 2137686.7607 | 10392293.6111
2728 | 1517531.2767 | 1950473.5723 | 28772.7918 | 3496777.6408
2729 | 13443767.5503 | 2605155.0262 | 9101257.3546 | 25150179.9311
2730 | 5771329.9945 | 2750922.6453 | 2941159.2329 | 11463411.8727
2731 | 10022570.4389 | 8190876.0982 | 44941.4792 | 18258388.0162
2732 | 2989894.2386 | 8931726.9238 | 0 | 11921621.1624
2733 | 21399324.7689 | 2442615.0103 | 1867520.356 | 25709460.1352
2734 | 23058148.2571 | 3863856.4573 | 0 | 26922004.7145
2735 | 3660079.5374 | 7516866.3279 | 9490001.1948 | 20666947.06
2736 | 14113571.2734 | 4820735.0487 | 75542.1835 | 19009848.5056
2737 | 15546397.8952 | 5911281.8348 | 411204.4899 | 21868884.22
2738 | 7404129.3201 | 9405515.2359 | 1741843.4128 | 18551487.9688
2739 | 2576416.5047 | 8587629.1823 | 319091.6571 | 11483137.3441
2740 | 1906864.169 | 8212585.9954 | 11737903.8272 | 21857353.9915
2741 | 46650545.0129 | 4244870.5719 | 8676621.5961 | 59572037.1809
2742 | 4358476.6868 | 6021654.8807 | 76929.0269 | 10457060.5944
2743 | 3876245.4761 | 6082515.8798 | 5274871.9147 | 15233633.2706
2744 | 2719704.5804 | 19025563.2623 | 569866.5429 | 22315134.3856
2745 | 15989186.3135 | 3695839.0087 | 0 | 19685025.3222
2746 | 19293456.0695 | 10269850.7713 | 4816610.7838 | 34379917.6247
2747 | 26624857.7593 | 10297122.8607 | 2717704.5021 | 39639685.1221
2748 | 3409388.1019 | 4067985.8183 | 0 | 7477373.9201
2749 | 4971762.7872 | 7107866.846 | 1135767.5747 | 13215397.2079
2750 | 1395645.6499 | 7581216.6796 | 401054.0158 | 9377916.3453
2751 | 1393627.3164 | 2590374.3455 | 56584.0819 | 4040585.7438
2752 | 10922695.9314 | 3520281.4061 | 67575.6297 | 14510552.9672
2753 | 9727202.4636 | 16203493.8736 | 810012.2829 | 26740708.6202
2754 | 5289092.889 | 0 | 23327692.6652 | 28616785.5543
2755 | 4781277.5464 | 0 | 0 | 4781277.5464
2756 | 10365824.3314 | 2457202.2163 | 0 | 12823026.5477
2757 | 8703752.6001 | 10501505.1242 | 0 | 19205257.7243
2758 | 9213709.9978 | 0 | 738061.8784 | 9951771.8762
2759 | 15040804.3275 | 12611704.6321 | 2967747.734 | 30620256.6936
2760 | 15110630.3323 | 1566807.3401 | 164400.1915 | 16841837.8639
2761 | 8729589.1175 | 8017892.6049 | 2197489.6484 | 18944971.3708
2762 | 10628078.3777 | 9508119.6334 | 21727716.2004 | 41863914.2116
2763 | 7260986.7649 | 0 | 253881.756 | 7514868.521
2764 | 1646625.9985 | 7888589.5592 | 10099260.4062 | 19634475.9639
2765 | 17365214.6461 | 4945076.6325 | 4954561.9084 | 27264853.1871
2766 | 13998354.7378 | 17681235.8251 | 97503.2275 | 31777093.7903
2767 | 8999945.7866 | 13717738.1586 | 2159683.8245 | 24877367.7698
2768 | 16190847.3512 | 3349697.4968 | 2199525.3763 | 21740070.2242
2769 | 7522483.5922 | 5320951.9863 | 0 | 12843435.5785
2770 | 1069597.5674 | 0 | 1585555.7024 | 2655153.2698
2771 | 8513809.4228 | 0 | 374663.2146 | 8888472.6374
2772 | 8542631.8629 | 3177949.4045 | 2903862.3421 | 14624443.6095
2773 | 2348354.5448 | 0 | 1443402.1842 | 3791756.729
2774 | 4757736.6824 | 0 | 5036336.3691 | 9794073.0515
2775 | 1272074.336 | 0 | 991851.2392 | 2263925.5752
2776 | 2508635.2541 | 0 | 1633286.0761 | 4141921.3302
2777 | 4928441.7173 | 3990273.6065 | 8132954.6677 | 17051669.9915
2778 | 7780282.5866 | 14972872.8996 | 322234.1894 | 23075389.6756
2779 | 4655668.4879 | 1060267.0922 | 431486.6606 | 6147422.2407
2780 | 15796673.9814 | 0 | 1582147.6521 | 17378821.6335
2781 | 5845948.5477 | 9038650.1522 | 652444.63 | 15537043.33
2782 | 15115819.5326 | 0 | 2240733.9081 | 17356553.4407
2783 | 2153750.7042 | 0 | 922243.6289 | 3075994.333
2784 | 2598533.6396 | 11926936.3424 | 0 | 14525469.9819
2785 | 9904854.9627 | 1837800.5754 | 745394.2397 | 12488049.7778
2786 | 3377845.7993 | 15593292.333 | 1404195.5395 | 20375333.6718
2787 | 4300787.4766 | 0 | 552078.8973 | 4852866.374
2788 | 10890221.67 | 0 | 2875995.9593 | 13766217.6293
2789 | 21415271.4051 | 2421287.991 | 3929182.0354 | 27765741.4316
2790 | 6664165.3066 | 18892125.903 | 3467855.3407 | 29024146.5503
2791 | 5245605.3436 | 16014772.5942 | 5487701.0967 | 26748079.0345
2792 | 36878014.6714 | 813758.7332 | 377662.2834 | 38069435.6879
2793 | 3491992.4267 | 16207099.5552 | 93908.4665 | 19793000.4484
2794 | 6808502.5546 | 0 | 0 | 6808502.5546
2795 | 15543633.369 | 3818449.4659 | 3388944.4815 | 22751027.3164
2796 | 4531683.4255 | 2293898.6978 | 290868.0434 | 7116450.1667
2797 | 20024227.7246 | 18283618.5447 | 317406.9301 | 38625253.1994
2798 | 0 | 22033157.5132 | 818768.6553 | 22851926.1684
2799 | 6534939.0326 | 7428965.771 | 0 | 13963904.8036
2800 | 6369432.0632 | 5802273.4182 | 3022534.5302 | 15194240.0116
2801 | 4192863.9997 | 7992756.3168 | 0 | 12185620.3166
2802 | 12252769.4865 | 6199119.0783 | 3610398.0955 | 22062286.6603
2803 | 3168206.8316 | 3302692.0927 | 1623212.7318 | 8094111.6561
2804 | 4566909.5156 | 6243625.4631 | 3259466.0975 | 14070001.0762
2805 | 35686342.2127 | 0 | 1838140.247 | 37524482.4596
2806 | 1903829.5421 | 4527467.499 | 1678993.2685 | 8110290.3096
2807 | 3224732.9375 | 10920553.9239 | 0 | 14145286.8614
2808 | 8169735.5677 | 8696619.2359 | 1102591.2136 | 17968946.0172
2809 | 2076980.8245 | 1038340.6999 | 0 | 3115321.5244
2810 | 5365820.2215 | 6624532.9076 | 1961798.6596 | 13952151.7887
2811 | 1870458.8579 | 8252728.5135 | 556172.7419 | 10679360.1132
2812 | 25651105.2008 | 0 | 0 | 25651105.2008
2813 | 2552054.2279 | 17096215.1556 | 45788.9178 | 19694058.3013
2814 | 14525512.629 | 4661755.2461 | 227927.9968 | 19415195.8719
2815 | 8721693.7483 | 11950416.7828 | 93976.5788 | 20766087.1099
2816 | 12452432.6643 | 15327330.5159 | 602542.1124 | 28382305.2926
2817 | 13982773.5865 | 18780544.0342 | 1902928.8535 | 34666246.4743
2818 | 2953143.3048 | 3901093.5244 | 636897.5574 | 7491134.3866
2819 | 5986485.8332 | 11848027.4007 | 1425425.2658 | 19259938.4997
2820 | 2291796.2452 | 5949905.8312 | 1391693.3536 | 9633395.43
2821 | 817489.7893 | 2855597.3419 | 179545.1314 | 3852632.2626
2822 | 5448245.9092 | 1249936.302 | 350142.9434 | 7048325.1547
2823 | 4538352.4778 | 8816823.8706 | 0 | 13355176.3484
2824 | 6374044.1655 | 0 | 4798331.6564 | 11172375.8219
2825 | 7156442.4387 | 2863327.2427 | 36427.7402 | 10056197.4217
2826 | 13369517.9552 | 23980180.0068 | 4797483.242 | 42147181.2041
2827 | 8197316.2008 | 4078746.8603 | 1743746.7474 | 14019809.8084
2828 | 6198138.7478 | 0 | 2776083.6538 | 8974222.4017
2829 | 6147594.376 | 10765006.4788 | 477935.176 | 17390536.0308
2830 | 7813915.3073 | 1594066.4399 | 755043.3824 | 10163025.1297
2831 | 5200714.399 | 0 | 0 | 5200714.399
2832 | 9969693.813 | 17731718.6454 | 3903305.6106 | 31604718.069
2833 | 8186862.6937 | 8169343.8496 | 6546885.5648 | 22903092.1081
2834 | 2173079.7105 | 12304432.8908 | 498683.4263 | 14976196.0275
2835 | 4699659.3423 | 0 | 21039808.9035 | 25739468.2458
2836 | 2518450.1856 | 1741966.8781 | 599360.6375 | 4859777.7012
2837 | 15540505.6303 | 0 | 296699.396 | 15837205.0263
2838 | 1962772.2239 | 4609951.1737 | 1527584.757 | 8100308.1546
2839 | 3632424.3373 | 3556840.9444 | 1826530.7818 | 9015796.0635
2840 | 8020175.9216 | 277632.5983 | 4618430.3393 | 12916238.8592
2841 | 6267605.5539 | 4793690.4598 | 999407.7907 | 12060703.8044
2842 | 2013843.7769 | 11266553.6622 | 10148075.4532 | 23428472.8923
2843 | 16414898.2015 | 8214621.3088 | 2693869.4899 | 27323389.0001
2844 | 5434679.5659 | 22176204.097 | 191602.3005 | 27802485.9634
2845 | 4064615.0744 | 0 | 286309.0658 | 4350924.1401
2846 | 275917.6193 | 4107520.8463 | 686639.7681 | 5070078.2337
2847 | 11460753.5128 | 12204513.4469 | 3575103.5117 | 27240370.4714
2848 | 5127065.3677 | 7604490.9897 | 2672655.9482 | 15404212.3056
2849 | 1041363.0124 | 5471755.9244 | 307691.2801 | 6820810.2169
2850 | 16028293.0856 | 6218711.4655 | 130012.0129 | 22377016.5641
2851 | 1994195.8528 | 0 | 5202179.7839 | 7196375.6367
2852 | 5576566.3314 | 0 | 0 | 5576566.3314
2853 | 10801812.8484 | 5810224.4733 | 373239.3165 | 16985276.6382
2854 | 4259735.8213 | 3629651.1257 | 1159893.6374 | 9049280.5844
2855 | 3020241.9595 | 6043049.3005 | 1440728.8021 | 10504020.0622
2856 | 3149295.2531 | 7590000.9429 | 9224708.1768 | 19964004.3728
2857 | 1737503.9131 | 30337078.5207 | 193701.6713 | 32268284.1051
2858 | 18452140.3085 | 8774089.3244 | 2414226.4092 | 29640456.0422
2859 | 12782042.1155 | 14308326.2812 | 0 | 27090368.3967
2860 | 27175353.0947 | 19237114.4652 | 302131.4654 | 46714599.0253
2861 | 825941.2007 | 0 | 10068733.718 | 10894674.9187
2862 | 4743428.4381 | 5007846.2105 | 1770850.4863 | 11522125.135
2863 | 1312251.1042 | 8662185.6626 | 477406.8284 | 10451843.5952
2864 | 4996272.7563 | 9620313.0385 | 3267492.7117 | 17884078.5065
2865 | 497392.8568 | 2511750.0241 | 297114.6665 | 3306257.5475
2866 | 7318637.3292 | 1077339.0514 | 2413637.6413 | 10809614.0219
2867 | 7783561.5722 | 1437555.4141 | 5288154.3831 | 14509271.3694
2868 | 7046155.62 | 9341737.9796 | 561549.5915 | 16949443.191
2869 | 2939419.1663 | 23997475.6912 | 3296513.3452 | 30233408.2027
2870 | 15083557.6828 | 4563510.1314 | 458137.4487 | 20105205.2629
2871 | 17040068.4901 | 589746.8148 | 1301908.1393 | 18931723.4442
2872 | 765615.0924 | 0 | 0 | 765615.0924
2873 | 8158690.6643 | 8263080.9046 | 1435114.9393 | 17856886.5082
2874 | 9662816.9113 | 11605714.4432 | 1732270.6143 | 23000801.9688
2875 | 8093851.9258 | 8134732.744 | 271982.3749 | 16500567.0447
2876 | 29214576.7332 | 4777002.8367 | 891530.6804 | 34883110.2503
2877 | 8287340.3265 | 0 | 872787.6242 | 9160127.9507
2878 | 19921983.1698 | 14384437.5242 | 1695959.1091 | 36002379.8031
2879 | 9187548.7803 | 7770733.293 | 0 | 16958282.0734
2880 | 15821534.5755 | 14981269.2542 | 263560.4944 | 31066364.3241
2881 | 4094018.7162 | 1613173.613 | 406021.308 | 6113213.6373
2882 | 15656743.2247 | 29334632.113 | 3558290.3598 | 48549665.6975
2883 | 9782519.7895 | 3802577.0141 | 559761.3117 | 14144858.1153
2884 | 1277488.8631 | 2893835.5218 | 975446.1719 | 5146770.5568
2885 | 15417171.2523 | 16834978.84 | 2108318.4372 | 34360468.5295
2886 | 9068151.5295 | 3179424.4871 | 0 | 12247576.0166
2887 | 2856046.786 | 2788690.9218 | 148074.1227 | 5792811.8305
2888 | 17060043.5508 | 0 | 9226627.6625 | 26286671.2133
2889 | 3993383.9449 | 11977818.5483 | 792314.3721 | 16763516.8652
2890 | 10878269.1598 | 9981198.8808 | 6738398.4051 | 27597866.4457
2891 | 5791374.6996 | 5723429.4484 | 598899.912 | 12113704.06
2892 | 2758153.0836 | 4471583.2538 | 131622.7956 | 7361359.133
2893 | 7750719.9958 | 4190667.378 | 2330828.5884 | 14272215.9622
2894 | 3870104.5102 | 0 | 305811.3715 | 4175915.8817
2895 | 12480913.8137 | 5778388.8526 | 0 | 18259302.6663
2896 | 963196.0465 | 1934586.2077 | 360083.3929 | 3257865.647
2897 | 4732404.3538 | 2949742.7424 | 693854.6368 | 8376001.733
2898 | 17962184.3175 | 0 | 0 | 17962184.3175
2899 | 8059460.9294 | 11058241.6273 | 0 | 19117702.5567
2900 | 12212346.6886 | 6488841.6346 | 5050396.9845 | 23751585.3077
2901 | 8826423.7234 | 14367442.7731 | 1647722.1839 | 24841588.6804
2902 | 21715784.8943 | 19971969.565 | 0 | 41687754.4594
2903 | 15283975.6764 | 4375757.9264 | 0 | 19659733.6028
2904 | 4700541.0193 | 5896631.728 | 8523922.1107 | 19121094.8581
2905 | 8231987.0195 | 3642179.8716 | 507749.653 | 12381916.5441
2906 | 8108591.898 | 19528565.0681 | 46465.5397 | 27683622.5058
2907 | 9645602.1517 | 5122006.2476 | 0 | 14767608.3993
2908 | 6430432.4093 | 4449884.2366 | 0 | 10880316.6459
2909 | 3681442.2876 | 3451073.4231 | 2589425.1608 | 9721940.8714
2910 | 4546946.2267 | 3823242.5937 | 359607.0354 | 8729795.8559
2911 | 4315321.1747 | 883337.135 | 5654760.6755 | 10853418.9852
2912 | 13560854.4974 | 9896229.3734 | 8524144.1745 | 31981228.0452
2913 | 17857748.8497 | 25775447.6109 | 25734916.274 | 69368112.7346
2914 | 12239554.237 | 6218988.9013 | 3633324.0444 | 22091867.1827
2915 | 10116002.9822 | 6864102.8451 | 4057215.4762 | 21037321.3035
2916 | 2910586.1244 | 4353067.3285 | 1556628.102 | 8820281.5548
2917 | 7024536.0726 | 1291896.0731 | 0 | 8316432.1457
2918 | 7014845.6111 | 0 | 11069470.6692 | 18084316.2804
2919 | 4032288.1026 | 7888553.9905 | 1572896.8276 | 13493738.9208
2920 | 7427457.0137 | 8487090.3608 | 2541893.8203 | 18456441.1948
2921 | 12683898.9693 | 4904749.8764 | 10086213.8813 | 27674862.7271
2922 | 330141.7601 | 3829715.2495 | 240411.5438 | 4400268.5534
2923 | 10112593.6454 | 1933108.9816 | 3309400.2453 | 15355102.8723
2924 | 7428353.9542 | 11211437.0949 | 0 | 18639791.0491
2925 | 1924800.7313 | 10221464.4132 | 2546175.3957 | 14692440.5402
2926 | 1330348.1427 | 5635308.443 | 540666.0163 | 7506322.602
2927 | 4112346.6921 | 10802986.6192 | 400332.9916 | 15315666.3029
2928 | 5471842.9707 | 9453500.8287 | 932293.5367 | 15857637.3362
2929 | 2468360.5573 | 3591909.8816 | 755151.1101 | 6815421.549
2930 | 2609262.3989 | 4993572.6125 | 0 | 7602835.0114
2931 | 350848.0889 | 950168.2386 | 3017370.5098 | 4318386.8372
2932 | 3108300.7712 | 2219118.6915 | 2961755.239 | 8289174.7016
2933 | 7605683.7302 | 3605544.4324 | 245479.1037 | 11456707.2663
2934 | 2141022.2623 | 0 | 77249.5261 | 2218271.7884
2935 | 1453965.3212 | 6061452.0283 | 1293491.5797 | 8808908.9293
2936 | 15875842.5159 | 2433556.955 | 41654941.5094 | 59964340.9803
2937 | 9280986.0112 | 4520741.1578 | 53202.0281 | 13854929.197
2938 | 12618828.3236 | 8465345.0742 | 2405845.6993 | 23490019.0971
2939 | 31053091.6949 | 0 | 64176.3563 | 31117268.0511
2940 | 3457624.1776 | 0 | 2165819.5436 | 5623443.7213
2941 | 3578676.1186 | 2852891.4612 | 125728.4101 | 6557295.9899
2942 | 17113739.7793 | 10672591.3244 | 2546859.257 | 30333190.3607
2943 | 4558470.4239 | 5113494.9061 | 6411648.5173 | 16083613.8472
2944 | 16470902.5503 | 1627430.85 | 4094417.2706 | 22192750.671
2945 | 7757358.8735 | 4134697.5906 | 14979558.9666 | 26871615.4307
2946 | 7477517.6968 | 0 | 8564538.3866 | 16042056.0833
2947 | 4708190.3404 | 922731.2038 | 162938.4917 | 5793860.0359
2948 | 7155141.8209 | 7459364.4139 | 0 | 14614506.2348
2949 | 22231831.6944 | 13041784.4873 | 356269.8634 | 35629886.0451
2950 | 3002815.2723 | 3999420.3683 | 0 | 7002235.6406
2951 | 36895008.6392 | 6366906.9064 | 14176.5037 | 43276092.0493
2952 | 7121614.7876 | 13013329.2274 | 5795164.3825 | 25930108.3975
2953 | 12496276.4402 | 10670633.9664 | 450880.3273 | 23617790.7338
2954 | 16731893.7213 | 12427489.7637 | 1681205.2105 | 30840588.6954
2955 | 5038663.6847 | 6989357.1951 | 1627625.1008 | 13655645.9806
2956 | 39466375.3739 | 2120071.6442 | 5556065.7112 | 47142512.7293
2957 | 2970098.7343 | 11490832.1756 | 2039668.2396 | 16500599.1495
2958 | 12821950.024 | 13849332.0182 | 3335110.8641 | 30006392.9064
2959 | 5581390.7964 | 13125283.9642 | 4705498.8757 | 23412173.6362
2960 | 7648847.0696 | 5346302.7166 | 507325.5531 | 13502475.3392
2961 | 11700129.9584 | 2874513.7506 | 2976868.3566 | 17551512.0656
2962 | 19209971.3148 | 34358835.61 | 3321347.0012 | 56890153.9261
2963 | 15566362.5271 | 4150204.7816 | 403189.9575 | 20119757.2662
2964 | 4580516.3803 | 8366001.7918 | 159430.8017 | 13105948.9737
2965 | 5925199.2201 | 0 | 2943714.7377 | 8868913.9578
2966 | 7332256.0741 | 3138489.3409 | 1410653.5509 | 11881398.9659
2967 | 10271593.8595 | 21014110.1244 | 3763583.0651 | 35049287.049
2968 | 3591211.4446 | 2559724.2279 | 43943.592 | 6194879.2645
2969 | 6929709.3032 | 1438586.6493 | 1077785.2954 | 9446081.2479
2970 | 9094181.3442 | 2180922.8471 | 4975203.3028 | 16250307.4941
2971 | 915494.665 | 3369701.9317 | 5902156.6094 | 10187353.2061
2972 | 6770672.6066 | 5788563.9997 | 1347712.2711 | 13906948.8775
2973 | 6652424.6577 | 0 | 478927.6756 | 7131352.3332
2974 | 2266210.9101 | 0 | 488647.3556 | 2754858.2657
2975 | 10273442.3206 | 0 | 0 | 10273442.3206
2976 | 1426061.2567 | 4775220.8215 | 0 | 6201282.0782
2977 | 8849400.1604 | 11282721.4242 | 0 | 20132121.5846
2978 | 166324.1737 | 0 | 804518.1569 | 970842.3306
2979 | 14222959.0271 | 6360243.8747 | 13884592.9875 | 34467795.8893
2980 | 4183810.2391 | 6726387.8755 | 372238.7346 | 11282436.8492
2981 | 2572481.4928 | 6965272.7593 | 1756671.9227 | 11294426.1748
2982 | 9272371.1163 | 8324622.7715 | 5335311.2592 | 22932305.147
2983 | 2086297.9583 | 18188672.9137 | 192232.9446 | 20467203.8167
2984 | 2941989.9355 | 0 | 2134082.7856 | 5076072.7211
2985 | 3761670.4192 | 0 | 101341.4525 | 3863011.8717
2986 | 8472792.329 | 6789304.7042 | 5529689.0242 | 20791786.0574
2987 | 4419431.6766 | 6690880.5199 | 61628.4446 | 11171940.641
2988 | 16090734.0666 | 10144727.6415 | 416154.5313 | 26651616.2394
2989 | 2472024.1312 | 5511808.2309 | 2843204.9104 | 10827037.2725
2990 | 10611336.9902 | 5923501.0711 | 372190.9406 | 16907029.0019
2991 | 24285194.0866 | 2639203.3711 | 0 | 26924397.4577
2992 | 11338038.4919 | 3312472.6594 | 496281.184 | 15146792.3353
2993 | 2944273.8842 | 4463859.6373 | 95749.5124 | 7503883.0339
2994 | 560034.6647 | 14835813.596 | 1096760.2545 | 16492608.5153
2995 | 2955142.3707 | 8337531.3002 | 2977378.5764 | 14270052.2472
2996 | 5793651.2352 | 15596827.011 | 2161970.0502 | 23552448.2964
2997 | 1614339.8039 | 8185405.2207 | 4337745.9417 | 14137490.9663
2998 | 1324708.7143 | 2716469.6927 | 871026.7908 | 4912205.1979
2999 | 5015911.598 | 2264246.9051 | 646208.4023 | 7926366.9054
3000 | 3952638.109 | 1036979.5326 | 120391.9862 | 5110009.6279
3001 | 11925817.4206 | 16214252.5708 | 0 | 28140069.9914
3002 | 7645780.6495 | 2930940.935 | 814735.0151 | 11391456.5996
3003 | 11090384.2284 | 3176028.9293 | 2698124.1143 | 16964537.272
3004 | 777685.6814 | 3344108.8033 | 77839.9811 | 4199634.4658
3005 | 15597925.5799 | 6460981.1023 | 680698.8458 | 22739605.528
3006 | 14134068.0119 | 4982687.3393 | 9026568.9694 | 28143324.3206
3007 | 3884592.889 | 7479132.9137 | 2683550.5568 | 14047276.3595
3008 | 4053215.3235 | 6973997.0356 | 0 | 11027212.3591
3009 | 5695803.9347 | 9202307.0034 | 0 | 14898110.9381
3010 | 9548672.3068 | 3034880.3894 | 1232770.4298 | 13816323.126
3011 | 19697647.6425 | 0 | 0 | 19697647.6425
3012 | 17634149.9981 | 1130754.7258 | 0 | 18764904.7239
3013 | 3709910.4984 | 6970685.8286 | 1264837.9534 | 11945434.2803
3014 | 24583729.3716 | 8325855.4949 | 2592637.2476 | 35502222.1141
3015 | 10583012.9474 | 3847735.0128 | 0 | 14430747.9602
3016 | 622101.3613 | 12942637.0421 | 2567611.022 | 16132349.4254
3017 | 5593630.228 | 6597084.083 | 67555.3932 | 12258269.7042
3018 | 6651545.99 | 13256391.3069 | 420828.5978 | 20328765.8947
3019 | 8272813.3438 | 2117209.8756 | 1453213.5728 | 11843236.7923
3020 | 826154.3616 | 8893306.2848 | 1289904.9953 | 11009365.6417
3021 | 3504295.9557 | 2253659.8043 | 1506580.3064 | 7264536.0664
3022 | 8901100.2172 | 1295392.3544 | 0 | 10196492.5716
3023 | 7514674.3371 | 9495367.2913 | 0 | 17010041.6284
3024 | 17474033.5493 | 11870314.1718 | 3721611.3154 | 33065959.0365
3025 | 16977544.072 | 0 | 1546031.6142 | 18523575.6862
3026 | 7811020.1701 | 0 | 3589838.4581 | 11400858.6282
3027 | 13171395.7955 | 8401612.8124 | 12020585.0907 | 33593593.6987
3028 | 6087896.2532 | 17516832.5886 | 1988896.0757 | 25593624.9175
3029 | 16813558.7493 | 1310717.374 | 8651117.0859 | 26775393.2092
3030 | 6266514.3023 | 638748.2063 | 1011927.6398 | 7917190.1484
3031 | 15534415.186 | 24792998.1547 | 0 | 40327413.3407
3032 | 12937123.1396 | 7135940.8827 | 5761258.711 | 25834322.7333
3033 | 11433843.8563 | 7188915.5655 | 5671250.9182 | 24294010.34
3034 | 1855857.8115 | 7735852.9227 | 76077.0876 | 9667787.8218
3035 | 4555754.2378 | 44849978.96 | 42898.6972 | 49448631.8951
3036 | 16292155.1908 | 9889505.3012 | 1225438.9081 | 27407099.4001
3037 | 6721147.8748 | 0 | 1189982.4877 | 7911130.3624
3038 | 10499680.543 | 6177681.6517 | 75764.2858 | 16753126.4805
3039 | 1105184.9105 | 0 | 0 | 1105184.9105
3040 | 2580625.5963 | 4069086.522 | 605996.2443 | 7255708.3626
3041 | 6670847.4934 | 8909712.6235 | 1654672.7941 | 17235232.911
3042 | 3104903.6825 | 3442951.0509 | 6577232.9257 | 13125087.6591
3043 | 3779375.787 | 16227826.8765 | 2195180.1236 | 22202382.787
3044 | 2729427.811 | 4986951.4622 | 133011.9908 | 7849391.264
3045 | 17886343.1446 | 31172951.7184 | 487490.0829 | 49546784.9459
3046 | 1901735.8847 | 3684630.0301 | 1207549.1388 | 6793915.0536
3047 | 4820179.6551 | 4939392.9545 | 259952.5535 | 10019525.1631
3048 | 17535326.3879 | 13977918.0446 | 307258.6415 | 31820503.0739
3049 | 4441119.7639 | 16994714.0696 | 242282.4927 | 21678116.3262
3050 | 3919944.0685 | 5863569.0716 | 14782352.9778 | 24565866.1179
3051 | 11686211.6482 | 15496848.2374 | 1574915.6349 | 28757975.5205
3052 | 7722895.7817 | 0 | 0 | 7722895.7817
3053 | 8120789.8688 | 5776530.7071 | 319893.8122 | 14217214.388
3054 | 2111198.451 | 4217030.3393 | 2620219.3566 | 8948448.1469
3055 | 4147047.9863 | 6980258.3479 | 2012550.8442 | 13139857.1784
3056 | 1895472.4518 | 6381453.3025 | 619116.8385 | 8896042.5928
3057 | 14224176.2822 | 17351703.3094 | 1160628.6083 | 32736508.1999
3058 | 5471337.4707 | 0 | 0 | 5471337.4707
3059 | 4018237.992 | 7036793.57 | 0 | 11055031.5621
3060 | 5031025.0457 | 4504569.5076 | 1119514.6555 | 10655109.2088
3061 | 14147598.4676 | 10606704.5077 | 3896737.4571 | 28651040.4325
3062 | 5171325.0119 | 0 | 2051609.8258 | 7222934.8377
3063 | 1918368.7402 | 4166963.3091 | 362124.7372 | 6447456.7865
3064 | 9339576.1149 | 3895893.9321 | 8148447.0885 | 21383917.1355
3065 | 11770830.6059 | 5784039.4084 | 339343.1189 | 17894213.1332
3066 | 6784464.953 | 14458806.4724 | 10612427.8095 | 31855699.2349
3067 | 2788353.6451 | 9208250.3905 | 3948973.7283 | 15945577.7639
3068 | 8138041.0141 | 3443466.9054 | 154866.8679 | 11736374.7875
3069 | 4967872.5196 | 0 | 1500122.1054 | 6467994.625
3070 | 2304559.7703 | 6740343.3579 | 290445.573 | 9335348.7012
3071 | 2111383.9657 | 4111377.9579 | 2850515.4948 | 9073277.4184
3072 | 18302972.1523 | 1845306.7114 | 53396.8197 | 20201675.6833
3073 | 6955353.3453 | 6634521.7353 | 96068.4067 | 13685943.4873
3074 | 1843413.2478 | 15212284.1165 | 982312.8096 | 18038010.1739
3075 | 3331873.8624 | 4822252.5191 | 3829325.2679 | 11983451.6493
3076 | 7688620.844 | 0 | 1471987.347 | 9160608.1911
3077 | 3453599.6811 | 0 | 1345332.5576 | 4798932.2388
3078 | 14173485.6992 | 7169535.1762 | 0 | 21343020.8753
3079 | 7471141.0728 | 40727040.9598 | 3974232.0263 | 52172414.0589
3080 | 10171059.7796 | 0 | 207449.6392 | 10378509.4188
3081 | 9776510.0816 | 15471847.5578 | 592579.8035 | 25840937.4429
3082 | 10187311.4041 | 15757059.2286 | 426268.2924 | 26370638.9252
3083 | 5427957.8976 | 11573895.8733 | 1197664.1404 | 18199517.9113
3084 | 1829739.6308 | 31397232.4844 | 2002719.13 | 35229691.2452
3085 | 8962214.9996 | 17702682.9281 | 21105830.4132 | 47770728.3409
3086 | 1666483.4231 | 8354862.2486 | 1376137.2275 | 11397482.8993
3087 | 8643562.9053 | 2865758.0292 | 8417484.2492 | 19926805.1836
3088 | 14116865.8297 | 6318294.9459 | 1276708.8973 | 21711869.6729
3089 | 5198062.9318 | 0 | 4472885.3175 | 9670948.2493
3090 | 8615719.2935 | 0 | 2996566.5593 | 11612285.8528
3091 | 8791296.7858 | 16065958.7154 | 476880.1285 | 25334135.6296
3092 | 2374084.5347 | 2815111.8939 | 24871.7832 | 5214068.2118
3093 | 3423635.9127 | 4357683.2766 | 814835.4622 | 8596154.6515
3094 | 3204733.596 | 3781825.845 | 0 | 6986559.441
3095 | 12223672.9819 | 0 | 4293914.8179 | 16517587.7998
3096 | 9995831.2315 | 63262.2501 | 2439299.4806 | 12498392.9622
3097 | 2652947.4594 | 19733999.059 | 4425744.9505 | 26812691.4689
3098 | 5337892.4765 | 4463308.0857 | 4347576.3584 | 14148776.9206
3099 | 11367330.2133 | 5335274.6484 | 0 | 16702604.8617
3100 | 7583841.3378 | 19079108.3918 | 4122131.1237 | 30785080.8533
3101 | 6346512.304 | 4453940.7282 | 142019.6352 | 10942472.6674
3102 | 14309828.2304 | 3309093.7104 | 0 | 17618921.9408
3103 | 5399162.4172 | 6243985.9133 | 436479.2243 | 12079627.5547
3104 | 6680485.2243 | 24833709.8943 | 0 | 31514195.1186
3105 | 6557035.7455 | 5419897.8428 | 465622.6648 | 12442556.2531
3106 | 476996.7055 | 5797533.1877 | 8834985.7226 | 15109515.6158
3107 | 6987927.3257 | 0 | 1405111.5531 | 8393038.8788
3108 | 6861032.6244 | 4848570.343 | 1563217.3215 | 13272820.2889
3109 | 15955518.8236 | 11070140.5545 | 3454133.046 | 30479792.4241
3110 | 18691305.3572 | 38672947.0301 | 3819279.6769 | 61183532.0642
3111 | 7469323.5424 | 11152576.2019 | 4914822.8986 | 23536722.6428
3112 | 3718345.1814 | 1328347.9498 | 0 | 5046693.1312
3113 | 11702417.5914 | 10131546.9524 | 924533.3592 | 22758497.9029
3114 | 16577752.8259 | 3879205.2501 | 973284.5899 | 21430242.6659
3115 | 5342518.9759 | 0 | 1616319.0168 | 6958837.9927
3116 | 3490984.516 | 6454767.0389 | 2335440.9535 | 12281192.5084
3117 | 1490473.002 | 8917839.7704 | 551788.8642 | 10960101.6366
3118 | 13582787.1168 | 4816466.4597 | 121467.0932 | 18520720.6697
3119 | 2056671.8318 | 10514363.9571 | 77094.5275 | 12648130.3164
3120 | 18647722.5004 | 5078187.4208 | 380370.3861 | 24106280.3073
3121 | 14138633.5219 | 0 | 6763057.3874 | 20901690.9093
3122 | 17975462.7942 | 13303558.8555 | 5081309.8987 | 36360331.5484
3123 | 4928036.2384 | 0 | 898416.833 | 5826453.0713
3124 | 13919514.1088 | 3494291.7676 | 1038826.1847 | 18452632.0611
3125 | 7908876.8877 | 0 | 2293479.9591 | 10202356.8468
3126 | 7161797.9859 | 0 | 4220993.7192 | 11382791.7051
3127 | 7748085.6512 | 22510451.0554 | 6590892.1984 | 36849428.905
3128 | 8223408.4537 | 0 | 2134918.4174 | 10358326.8712
3129 | 6238739.5408 | 25719138.5848 | 780895.6065 | 32738773.732
3130 | 5371203.7199 | 2295997.3248 | 324044.1513 | 7991245.1959
3131 | 9056771.786 | 4685558.4003 | 0 | 13742330.1863
3132 | 6939644.7973 | 4920346.1382 | 594632.843 | 12454623.7785
3133 | 10905693.6517 | 5760548.6433 | 265930.3768 | 16932172.6718
3134 | 2679155.1674 | 3917718.4937 | 0 | 6596873.661
3135 | 30281330.2414 | 17547315.0626 | 430754.2368 | 48259399.5408
3136 | 3498758.3164 | 2867160.5155 | 831639.1769 | 7197558.0088
3137 | 10297236.0127 | 10931513.9268 | 0 | 21228749.9395
3138 | 1030370.198 | 7323675.7996 | 1350121.8868 | 9704167.8844
3139 | 1130723.4392 | 9072731.2206 | 0 | 10203454.6598
3140 | 1904080.7674 | 19867846.7403 | 2793800.9205 | 24565728.4281
3141 | 12827271.2928 | 53097095.744 | 2559981.1537 | 68484348.1905
3142 | 1141450.0117 | 2940212.554 | 3835673.0998 | 7917335.6655
3143 | 18048855.915 | 3811230.8486 | 2863256.714 | 24723343.4775
3144 | 18243536.05 | 19354048.4609 | 5530628.5098 | 43128213.0207
3145 | 5873599.1213 | 4669834.6089 | 360979.7467 | 10904413.4769
3146 | 6598210.4318 | 1115207.7542 | 2540074.1813 | 10253492.3672
3147 | 3187007.5929 | 2714172.1772 | 711707.5781 | 6612887.3482
3148 | 3833659.8015 | 0 | 169076.7796 | 4002736.5811
3149 | 1810735.4815 | 14137663.7425 | 3651990.7514 | 19600389.9754
3150 | 12563361.2667 | 8333045.8426 | 473542.978 | 21369950.0873
3151 | 3740747.6596 | 14128919.1628 | 224914.0425 | 18094580.8649
3152 | 3344040.1328 | 2841347.5721 | 226555.1576 | 6411942.8625
3153 | 7593689.6179 | 10500992.491 | 617338.5494 | 18712020.6584
3154 | 3493621.9951 | 11413486.6484 | 179960.4078 | 15087069.0514
3155 | 2988868.1099 | 0 | 0 | 2988868.1099
3156 | 22645633.2761 | 4621870.5625 | 2944316.8045 | 30211820.6432
3157 | 387091.4411 | 0 | 467952.5115 | 855043.9526
3158 | 1698591.7092 | 22728940.2065 | 750287.7458 | 25177819.6615
3159 | 1263007.1015 | 5613674.6807 | 0 | 6876681.7822
3160 | 10827521.1485 | 4160296.0998 | 0 | 14987817.2483
3161 | 14436533.5521 | 9354539.3721 | 3505108.8515 | 27296181.7757
3162 | 12749856.8309 | 3495791.894 | 319298.1031 | 16564946.828
3163 | 6816550.4304 | 32395919.1454 | 0 | 39212469.5758
3164 | 12625397.2547 | 4964591.7161 | 0 | 17589988.9708
3165 | 17096898.1083 | 15611360.1632 | 6433431.2282 | 39141689.4997
3166 | 14579578.9274 | 0 | 478047.3927 | 15057626.3201
3167 | 25267415.493 | 3252240.4072 | 167521.7541 | 28687177.6544
3168 | 1629418.8183 | 0 | 2166784.5475 | 3796203.3658
3169 | 3986673.7018 | 3227224.8806 | 14841418.6462 | 22055317.2286
3170 | 10508361.5057 | 6808554.3564 | 0 | 17316915.8622
3171 | 2022507.9518 | 10129782.4728 | 18807204.5872 | 30959495.0118
3172 | 6703582.5643 | 2958229.1354 | 5260256.3465 | 14922068.0462
3173 | 3257803.6967 | 1949139.5472 | 0 | 5206943.2438
3174 | 8440121.4099 | 0 | 0 | 8440121.4099
3175 | 6351511.2907 | 6430076.773 | 0 | 12781588.0637
3176 | 12785279.6524 | 3058598.3617 | 87706.9011 | 15931584.9152
3177 | 4745649.4315 | 16878774.0956 | 0 | 21624423.5271
3178 | 2781481.6445 | 15858847.9204 | 6539946.2556 | 25180275.8205
3179 | 1114046.7171 | 0 | 88805.4683 | 1202852.1854
3180 | 21489024.2112 | 33475543.7293 | 1447858.3351 | 56412426.2757
3181 | 5662863.3359 | 17521163.4409 | 3262837.4032 | 26446864.18
3182 | 37342179.3034 | 17211531.605 | 2201784.3358 | 56755495.2442
3183 | 10534656.6799 | 2031805.8871 | 20420089.1945 | 32986551.7615
3184 | 25008752.6364 | 26562197.0147 | 886957.8598 | 52457907.5109
3185 | 3694327.2316 | 3324712.7535 | 937603.4712 | 7956643.4564
3186 | 4262843.1797 | 29504944.2719 | 1600001.057 | 35367788.5085
3187 | 25991282.4533 | 5596902.4039 | 7578118.9475 | 39166303.8048
3188 | 12028311.9049 | 4346527.0359 | 52076.627 | 16426915.5678
3189 | 3339809.3392 | 19995473.6761 | 7503641.5348 | 30838924.55
3190 | 7800666.0396 | 9180312.9725 | 122047.6243 | 17103026.6363
3191 | 5434069.6203 | 10657233.8985 | 24813779.4723 | 40905082.9911
3192 | 20443956.1668 | 5357006.2771 | 8025979.345 | 33826941.789
3193 | 9759844.9701 | 5229804.7236 | 6689678.9389 | 21679328.6327
3194 | 1796645.5088 | 12418381.091 | 2271672.2401 | 16486698.8399
3195 | 4192271.6402 | 8159002.0551 | 21370177.6256 | 33721451.3209
3196 | 5406659.3441 | 6029592.6723 | 536789.9643 | 11973041.9808
3197 | 4276322.7751 | 14470462.9023 | 47713.7228 | 18794499.4002
3198 | 4622296.4353 | 4359364.9443 | 742523.0228 | 9724184.4023
3199 | 18357933.5884 | 11620632.5455 | 0 | 29978566.1339
3200 | 28857357.7916 | 7948934.215 | 259467.4868 | 37065759.4935
3201 | 6654356.3476 | 25603134.0907 | 201202.1287 | 32458692.567
3202 | 12927119.151 | 12890581.9842 | 3282623.0657 | 29100324.2009
3203 | 3743516.8036 | 5081751.2498 | 0 | 8825268.0535
3204 | 3611298.7496 | 6602596.6883 | 10692213.8064 | 20906109.2443
3205 | 9780580.2814 | 7406290.4816 | 936525.0513 | 18123395.8142
3206 | 16203949.0285 | 1495452.176 | 17943562.486 | 35642963.6905
3207 | 4342820.1025 | 2306555.8603 | 1003978.5745 | 7653354.5373
3208 | 13571704.1121 | 17284714.8283 | 1081516.0425 | 31937934.9829
3209 | 7399471.2559 | 0 | 1514995.1108 | 8914466.3667
3210 | 13082258.1547 | 9517710.4175 | 1551492.5 | 24151461.0722
3211 | 3024591.1697 | 5899437.3169 | 0 | 8924028.4866
3212 | 3528631.2582 | 8239086.953 | 339652.5425 | 12107370.7537
3213 | 17588151.8515 | 4671648.5502 | 0 | 22259800.4017
3214 | 18716636.3491 | 9922439.7364 | 0 | 28639076.0855
3215 | 4092725.2201 | 0 | 1121508.4495 | 5214233.6696
3216 | 3166048.0731 | 12974464.288 | 1977487.084 | 18117999.4451
3217 | 4884627.8902 | 7188689.9945 | 15527174.1779 | 27600492.0625
3218 | 3350659.7247 | 11320243.2107 | 1684523.4856 | 16355426.4211
3219 | 1841537.3911 | 7887440.2215 | 2703790.7563 | 12432768.3689
3220 | 11342725.6525 | 12007957.9445 | 103782.5344 | 23454466.1315
3221 | 1567695.7241 | 0 | 3424279.1116 | 4991974.8357
3222 | 17580936.7207 | 0 | 26668681.3961 | 44249618.1168
3223 | 14633668.3168 | 4660068.2502 | 0 | 19293736.567
3224 | 11542959.3027 | 14434201.4068 | 2764124.3212 | 28741285.0307
3225 | 8921711.4882 | 2343210.4533 | 1896269.1854 | 13161191.127
3226 | 4794778.3496 | 13632076.9898 | 816218.9973 | 19243074.3368
3227 | 2740683.7127 | 6947867.6554 | 1376191.2994 | 11064742.6675
3228 | 7455144.7919 | 7613499.454 | 1841878.8579 | 16910523.1038
3229 | 17098093.9156 | 0 | 0 | 17098093.9156
3230 | 2262897.5148 | 323061.4764 | 594553.9326 | 3180512.9239
3231 | 4746807.17 | 6292268.0883 | 178236.6276 | 11217311.8859
3232 | 5734088.7745 | 1094819.4523 | 0 | 6828908.2267
3233 | 11109101.4078 | 1040637.2692 | 0 | 12149738.6769
3234 | 1530168.5888 | 0 | 1683488.7406 | 3213657.3294
3235 | 9936505.8027 | 8571785.3798 | 3510169.0439 | 22018460.2264
3236 | 2256699.7443 | 5512640.3534 | 2489514.9987 | 10258855.0964
3237 | 14132707.7894 | 11962479.428 | 0 | 26095187.2174
3238 | 6570916.9688 | 6209082.1988 | 1414197.3564 | 14194196.524
3239 | 9062551.2791 | 3168748.666 | 2207748.6476 | 14439048.5927
3240 | 10622143.0176 | 20096330.4824 | 4089988.4974 | 34808461.9974
3241 | 4269270.0785 | 0 | 0 | 4269270.0785
3242 | 37485053.8913 | 5214114.6579 | 0 | 42699168.5492
3243 | 6367374.6478 | 11949789.2346 | 2006326.7945 | 20323490.6769
3244 | 3589201.6481 | 9364480.8528 | 106476.4707 | 13060158.9716
3245 | 7185107.1867 | 20169428.4059 | 210435.9254 | 27564971.518
3246 | 13321329.2889 | 8499481.2073 | 2173294.4708 | 23994104.9669
3247 | 4897416.1988 | 7033198.5751 | 2153359.3539 | 14083974.1278
3248 | 1928107.6963 | 5972162.8321 | 591254.5337 | 8491525.0621
3249 | 4170893.7161 | 0 | 2774449.5022 | 6945343.2182
3250 | 15937873.5185 | 8242142.4599 | 7211693.8263 | 31391709.8047
3251 | 7596531.921 | 0 | 6159883.7494 | 13756415.6704
3252 | 23360360.2224 | 16431090.4696 | 1715538.2125 | 41506988.9045
3253 | 9330156.3696 | 4866230.6178 | 0 | 14196386.9873
3254 | 5752841.1043 | 8233278.2795 | 1879960.7061 | 15866080.0899
3255 | 1472314.1628 | 0 | 3286859.4821 | 4759173.6449
3256 | 4098715.1714 | 1409375.0542 | 657703.1113 | 6165793.3369
3257 | 11932480.9843 | 24008976.623 | 144853.1271 | 36086310.7344
3258 | 13486296.7564 | 7434986.5257 | 253967.7425 | 21175251.0246
3259 | 5340000.4244 | 1102371.9307 | 648582.6398 | 7090954.995
3260 | 4305460.3586 | 8051196.2592 | 292929.0998 | 12649585.7176
3261 | 2269726.6468 | 12176182.8793 | 6097240.4301 | 20543149.9562
3262 | 8035768.5261 | 9914623.7493 | 0 | 17950392.2754
3263 | 7543271.2698 | 3215808.61 | 1481391.7916 | 12240471.6715
3264 | 7028563.7656 | 0 | 1245443.2295 | 8274006.9952
3265 | 6320455.1144 | 0 | 0 | 6320455.1144
3266 | 5719297.5692 | 13984944.106 | 3868666.7601 | 23572908.4353
3267 | 21781584.1355 | 2842762.8788 | 811447.1057 | 25435794.12
3268 | 8344115.0963 | 7903699.2778 | 14108352.2361 | 30356166.6103
3269 | 7203816.8476 | 1388029.4694 | 4055023.2069 | 12646869.5239
3270 | 1083166.4136 | 13588955.3094 | 1359831.4126 | 16031953.1356
3271 | 9872080.0221 | 4197786.0385 | 2461530.6871 | 16531396.7477
3272 | 4346213.1102 | 6537603.1822 | 302188.7337 | 11186005.0261
3273 | 5460779.9218 | 0 | 3607750.5334 | 9068530.4552
3274 | 12590810.0131 | 7734071.652 | 23457.7119 | 20348339.377
3275 | 6299336.0446 | 5677828.5204 | 80758.6738 | 12057923.2389
3276 | 33697804.4291 | 9547266.543 | 126695.991 | 43371766.9632
3277 | 3244494.5033 | 3224853.6682 | 1012975.8918 | 7482324.0633
3278 | 2267594.2927 | 0 | 0 | 2267594.2927
3279 | 2964669.0882 | 19465553.7094 | 1666648.2587 | 24096871.0563
3280 | 12657285.7911 | 0 | 0 | 12657285.7911
3281 | 11325598.3992 | 7408459.7592 | 1218481.87 | 19952540.0284
3282 | 7703477.3838 | 10339198.1907 | 0 | 18042675.5745
3283 | 6011549.4133 | 6314027.2292 | 2173825.0267 | 14499401.6692
3284 | 4004463.4762 | 18090866.2455 | 197149.489 | 22292479.2107
3285 | 8082310.1301 | 1856559.3688 | 38379.185 | 9977248.6838
3286 | 12545638.9835 | 2352489.4546 | 1221181.2023 | 16119309.6404
3287 | 11100071.0397 | 11237594.7603 | 2071473.4435 | 24409139.2435
3288 | 15694617.4362 | 8672547.9136 | 0 | 24367165.3497
3289 | 8606409.5505 | 614756.9874 | 3434406.1134 | 12655572.6513
3290 | 821110.6948 | 10839083.1782 | 1944255.9402 | 13604449.8132
3291 | 11502754.2823 | 3328336.0656 | 328540.9505 | 15159631.2984
3292 | 2906393.6256 | 2849902.6845 | 22779.0426 | 5779075.3526
3293 | 5392282.948 | 0 | 1039424.5854 | 6431707.5333
3294 | 3522482.8693 | 8774609.1382 | 524578.4676 | 12821670.4751
3295 | 5561558.7579 | 6000382.569 | 362650.6989 | 11924592.0258
3296 | 24488450.3255 | 7105331.8151 | 774632.8178 | 32368414.9583
3297 | 7846526.112 | 0 | 159151.0909 | 8005677.2029
3298 | 8576998.8112 | 3561900.8047 | 0 | 12138899.6159
3299 | 26806749.1544 | 2714612.2209 | 1456902.2779 | 30978263.6532
3300 | 6933650.3946 | 3345450.5593 | 5160386.3411 | 15439487.295
3301 | 2941588.2062 | 8683001.6117 | 2736516.7862 | 14361106.6041
3302 | 11596805.3611 | 574585.802 | 310057.5228 | 12481448.6859
3303 | 2419680.6119 | 4719776.6192 | 160842.288 | 7300299.5191
3304 | 13197784.9056 | 0 | 2029479.8528 | 15227264.7584
3305 | 9021407.5766 | 0 | 1338915.2694 | 10360322.846
3306 | 20570821.5324 | 18817993.4481 | 0 | 39388814.9805
3307 | 11660799.4778 | 3732590.0257 | 272235.8607 | 15665625.3642
3308 | 16850558.6552 | 4832329.1196 | 4503065.9591 | 26185953.7338
3309 | 14009672.5867 | 3140474.6379 | 1756407.8473 | 18906555.0719
3310 | 10246149.6599 | 0 | 0 | 10246149.6599
3311 | 7106852.8993 | 3529820.233 | 14342222.2587 | 24978895.391
3312 | 2186788.5556 | 0 | 6750023.405 | 8936811.9607
3313 | 12302909.4142 | 8901665.6204 | 7499141.0147 | 28703716.0492
3314 | 3212333.7222 | 1935838.5642 | 9844576.5777 | 14992748.8641
3315 | 9275908.9481 | 16882272.8216 | 3210227.7633 | 29368409.533
3316 | 11201487.243 | 0 | 1099924.5994 | 12301411.8423
3317 | 7649746.3983 | 0 | 0 | 7649746.3983
3318 | 20068188.4115 | 0 | 2044623.4129 | 22112811.8244
3319 | 6088503.5126 | 14220031.1499 | 52877.766 | 20361412.4285
3320 | 12506919.5318 | 4310677.4184 | 1641516.7543 | 18459113.7046
3321 | 12219859.0739 | 8060501.8621 | 2963969.2819 | 23244330.2179
3322 | 4648029.3709 | 16203757.7739 | 1306475.7858 | 22158262.9306
3323 | 2002181.1333 | 19069879.4312 | 2392011.3828 | 23464071.9474
3324 | 25275304.2834 | 2329145.7545 | 239317.1928 | 27843767.2307
3325 | 4874574.2172 | 13723659.6765 | 4591784.2224 | 23190018.1162
3326 | 3084132.8105 | 4272501.7029 | 1212920.4077 | 8569554.921
3327 | 24114990.521 | 2223149.2322 | 1415492.674 | 27753632.4272
3328 | 3124836.5212 | 3120193.1607 | 18235988.8474 | 24481018.5294
3329 | 236485.2541 | 20516242.0695 | 0 | 20752727.3236
3330 | 173834.3286 | 4220171.1489 | 1217843.3033 | 5611848.7808
3331 | 10148285.8318 | 16841068.8649 | 903060.8584 | 27892415.5552
3332 | 1187112.5508 | 0 | 2779040.3941 | 3966152.945
3333 | 23605292.4504 | 0 | 0 | 23605292.4504
3334 | 3052286.4199 | 7834072.4957 | 590125.673 | 11476484.5885
3335 | 18348074.754 | 7807750.4558 | 2049762.9981 | 28205588.2079
3336 | 3266229.4892 | 9582950.1878 | 702138.8384 | 13551318.5154
3337 | 12704120.2489 | 13270287.0162 | 2622377.0974 | 28596784.3625
3338 | 13633942.51 | 0 | 278087.0768 | 13912029.5868
3339 | 2950744.5297 | 8924464.5665 | 1317414.747 | 13192623.8432
3340 | 19185984.8157 | 2560460.2221 | 170060.2295 | 21916505.2673
3341 | 19364030.8942 | 2934201.9034 | 6445813.9361 | 28744046.7337
3342 | 1467135.5337 | 5702697.2637 | 381806.5706 | 7551639.368
3343 | 14092374.8563 | 0 | 749579.7053 | 14841954.5616
3344 | 5500839.0064 | 0 | 2009414.4186 | 7510253.425
3345 | 1972818.5367 | 6907386.6891 | 1913129.0542 | 10793334.28
3346 | 8251716.2823 | 2088250.7963 | 2091934.9435 | 12431902.022
3347 | 5343424.5654 | 16179328.3682 | 8584964.0407 | 30107716.9743
3348 | 3126036.5768 | 0 | 7434738.5524 | 10560775.1292
3349 | 53479598.0677 | 2376641.9277 | 1772632.1712 | 57628872.1666
3350 | 7015619.5221 | 14915213.8093 | 235888.6309 | 22166721.9623
3351 | 5347571.5472 | 0 | 1477045.2 | 6824616.7472
3352 | 8487401.3462 | 4862280.4638 | 0 | 13349681.81
3353 | 10825369.6985 | 8779783.9385 | 188254.7083 | 19793408.3454
3354 | 647823.29 | 3484650.932 | 2300652.1016 | 6433126.3236
3355 | 17286259.6287 | 3299649.318 | 1582565.4323 | 22168474.379
3356 | 3203590.2288 | 0 | 115145.8003 | 3318736.0291
3357 | 14065492.0059 | 5428227.423 | 3571030.069 | 23064749.498
3358 | 15783415.1742 | 8298006.6155 | 1969571.6165 | 26050993.4061
3359 | 6591069.8926 | 4065907.6338 | 823447.416 | 11480424.9424
3360 | 13632101.5822 | 9245500.0742 | 57508.0146 | 22935109.671
3361 | 5533108.6158 | 5714702.2237 | 2355716.753 | 13603527.5925
3362 | 14860755.8847 | 8630728.8398 | 111387.6047 | 23602872.3292
3363 | 1096286.4106 | 4797481.7978 | 1655169.8658 | 7548938.0743
3364 | 3751776.5781 | 7887743.4476 | 4607423.8953 | 16246943.921
3365 | 17353853.3274 | 0 | 1399818.8982 | 18753672.2256
3366 | 8914246.2696 | 5023759.5347 | 3639649.0905 | 17577654.8949
3367 | 7268088.1375 | 2154726.3262 | 6551964.2461 | 15974778.7098
3368 | 2550707.1719 | 4051259.0027 | 960950.1114 | 7562916.286
3369 | 4783772.0827 | 9919796.4761 | 1838784.5148 | 16542353.0737
3370 | 3633627.8071 | 1081813.0497 | 936173.5779 | 5651614.4347
3371 | 2580045.6595 | 2768161.9235 | 441506.9539 | 5789714.5369
3372 | 6445134.2389 | 9315567.4971 | 0 | 15760701.736
3373 | 5647989.9997 | 25370260.6949 | 235695.173 | 31253945.8676
3374 | 15152006.314 | 7832005.0073 | 861280.6665 | 23845291.9877
3375 | 3222012.8418 | 1219119.451 | 1860166.7337 | 6301299.0265
3376 | 3646683.8246 | 3870547.5133 | 0 | 7517231.3379
3377 | 14594277.5913 | 0 | 1523899.2591 | 16118176.8504
3378 | 12215848.3584 | 0 | 2512721.4771 | 14728569.8355
3379 | 513016.7584 | 4769353.9965 | 8360215.1684 | 13642585.9233
3380 | 2187601.8994 | 6001442.8683 | 0 | 8189044.7678
3381 | 11769354.2549 | 8065520.128 | 13071092.6797 | 32905967.0626
3382 | 7569130.6111 | 6521377.5976 | 5008341.2205 | 19098849.4292
3383 | 1678933.9125 | 2301398.2909 | 4480752.2213 | 8461084.4247
3384 | 19667746.2039 | 5424746.5942 | 212175.1985 | 25304667.9965
3385 | 5928087.5863 | 0 | 60535.4767 | 5988623.063
3386 | 26061152.8851 | 1220806.0245 | 531367.6175 | 27813326.5271
3387 | 2696004.8103 | 2972282.6374 | 265174.5205 | 5933461.9682
3388 | 11534970.2557 | 11519998.9972 | 7086083.6877 | 30141052.9406
3389 | 1810286.0261 | 6847231.7298 | 4028345.5369 | 12685863.2928
3390 | 13266637.8753 | 16368518.9519 | 1148953.9112 | 30784110.7384
3391 | 2766391.1217 | 0 | 2371071.3385 | 5137462.4602
3392 | 4923289.4968 | 12289234.7721 | 3381407.0842 | 20593931.3532
3393 | 7953693.8801 | 12830294.2423 | 0 | 20783988.1224
3394 | 13322136.9219 | 0 | 614290.9411 | 13936427.8629
3395 | 5554830.6329 | 6724474.9668 | 2766654.1993 | 15045959.7991
3396 | 9499354.7329 | 1111989.1577 | 4829142.5814 | 15440486.472
3397 | 3007426.2536 | 6004944.6067 | 2773894.1925 | 11786265.0528
3398 | 3191296.9296 | 0 | 1098288.9829 | 4289585.9125
3399 | 10150928.3178 | 0 | 440625.6254 | 10591553.9432
3400 | 5109298.4128 | 0 | 6937014.4663 | 12046312.8791
3401 | 10187666.7454 | 6210902.0596 | 850639.2795 | 17249208.0845
3402 | 7310139.3552 | 16232163.1499 | 294421.5405 | 23836724.0456
3403 | 14417660.5557 | 4716234.1295 | 0 | 19133894.6852
3404 | 1429996.5938 | 5921733.1737 | 5535203.5205 | 12886933.288
3405 | 4787135.1399 | 235602.91 | 452457.5127 | 5475195.5627
3406 | 10097134.9943 | 0 | 108109.3206 | 10205244.3149
3407 | 18287651.164 | 13654750.1218 | 1295036.0846 | 33237437.3705
3408 | 14843994.1766 | 4399799.2119 | 0 | 19243793.3886
3409 | 4085001.461 | 0 | 2159684.2855 | 6244685.7465
3410 | 4470442.1881 | 8985013.8885 | 129265.8775 | 13584721.9541
3411 | 3988788.0286 | 2764677.8148 | 6780310.4999 | 13533776.3433
3412 | 11547141.6434 | 10089840.8821 | 0 | 21636982.5254
3413 | 12268406.2861 | 12489105.842 | 0 | 24757512.1281
3414 | 93593.8093 | 8145049.1251 | 715811.1689 | 8954454.1032
3415 | 1737722.1653 | 19367509.5961 | 1645485.0495 | 22750716.8109
3416 | 16493321.3089 | 2183138.2367 | 587194.0221 | 19263653.5676
3417 | 6286106.9647 | 4872484.9026 | 529961.9033 | 11688553.7706
3418 | 11221632.8135 | 650416.7956 | 0 | 11872049.6091
3419 | 15325165.6457 | 11249195.792 | 4339409.6976 | 30913771.1352
3420 | 15926639.0182 | 3018007.0829 | 1000575.1627 | 19945221.2639
3421 | 5343086.2444 | 7544363.3043 | 1569803.2733 | 14457252.8221
3422 | 6976596.6186 | 3415659.824 | 0 | 10392256.4426
3423 | 3964511.2795 | 18414659.2808 | 25943.297 | 22405113.8573
3424 | 4964033.5582 | 0 | 1691386.5391 | 6655420.0973
3425 | 15761804.976 | 1936945.7515 | 644875.3186 | 18343626.0461
3426 | 21644856.177 | 31776385.2012 | 2498737.4141 | 55919978.7923
3427 | 2926540.1529 | 5865907.1216 | 3517593.0262 | 12310040.3007
3428 | 2809481.1099 | 2637905.2639 | 5357559.5023 | 10804945.8761
3429 | 9216656.6489 | 0 | 4101092.5321 | 13317749.181
3430 | 4009950.5726 | 9721088.4886 | 68188.6487 | 13799227.7099
3431 | 1294638.871 | 2956436.3676 | 1893185.7735 | 6144261.0122
3432 | 15056135.8075 | 5608424.2974 | 0 | 20664560.1049
3433 | 5652266.3992 | 3860162.6949 | 959571.9945 | 10472001.0886
3434 | 1887617.3004 | 18757048.0519 | 2704745.5884 | 23349410.9406
3435 | 744971.4059 | 0 | 1794499.7396 | 2539471.1455
3436 | 12797046.4727 | 2521874.4237 | 1262451.5666 | 16581372.4631
3437 | 4026624.214 | 3513640.5492 | 1765995.4721 | 9306260.2353
3438 | 15962806.6577 | 7497850.0795 | 6531552.7164 | 29992209.4536
3439 | 6941050.5909 | 12372154.0681 | 10609226.2219 | 29922430.881
3440 | 6368453.8332 | 11450691.4607 | 52555.0771 | 17871700.371
3441 | 1599014.6939 | 890581.8409 | 1119933.9643 | 3609530.4991
3442 | 16016108.7049 | 6884056.8457 | 757336.1108 | 23657501.6615
3443 | 138605.7985 | 9889012.12 | 1692174.3732 | 11719792.2917
3444 | 12825890.4661 | 16961231.3485 | 0 | 29787121.8147
3445 | 3515853.231 | 10925702.2583 | 310103.057 | 14751658.5462
3446 | 26626194.6938 | 0 | 533235.7674 | 27159430.4612
3447 | 3742569.559 | 0 | 1551134.0292 | 5293703.5883
3448 | 11548072.8926 | 10723865.5187 | 1379754.4761 | 23651692.8874
3449 | 576155.2215 | 10423708.2007 | 1007778.3276 | 12007641.7497
3450 | 8345629.8092 | 16927909.4867 | 0 | 25273539.2959
3451 | 13821470.4364 | 8001290.0594 | 96858.4756 | 21919618.9714
3452 | 8534680.7434 | 17048522.7516 | 0 | 25583203.495
3453 | 4472878.7999 | 5466489.1684 | 782791.0655 | 10722159.0338
3454 | 10174191.3427 | 24137730.4879 | 0 | 34311921.8305
3455 | 4289978.1567 | 0 | 5081759.5658 | 9371737.7225
3456 | 5595278.3156 | 8297220.3241 | 1407537.3242 | 15300035.9639
3457 | 3580987.7702 | 19031957.8642 | 671339.5184 | 23284285.1528
3458 | 31316875.7435 | 1879312.2083 | 1427748.2662 | 34623936.218
3459 | 1735206.6752 | 11858732.2846 | 5472488.2404 | 19066427.2002
3460 | 2033491.2446 | 7036675.2129 | 342906.2991 | 9413072.7566
3461 | 9371467.6712 | 26456541.154 | 2421119.2776 | 38249128.1028
3462 | 7976074.3699 | 5936548.2199 | 1052289.3806 | 14964911.9705
3463 | 5399024.5396 | 17650994.2757 | 17497455.3597 | 40547474.1749
3464 | 9398765.9484 | 5230464.4682 | 9256034.8134 | 23885265.23
3465 | 7790029.0158 | 13276763.2038 | 2127784.6357 | 23194576.8553
3466 | 6538843.6631 | 5608879.9067 | 12357176.3974 | 24504899.9673
3467 | 10079723.565 | 12023356.7563 | 3282027.2683 | 25385107.5896
3468 | 3426021.5691 | 0 | 2928685.2379 | 6354706.8071
3469 | 2351809.1251 | 3329084.3579 | 3665268.909 | 9346162.3919
3470 | 3478281.3066 | 11320824.6732 | 944987.9673 | 15744093.9471
3471 | 6579492.4369 | 15076246.9689 | 10028201.0371 | 31683940.443
3472 | 1053945.011 | 9198712.326 | 2140115.5166 | 12392772.8535
3473 | 6687235.3962 | 2417840.7147 | 0 | 9105076.1109
3474 | 10770486.7417 | 14123537.9978 | 1657984.4955 | 26552009.235
3475 | 20341093.7915 | 0 | 178290.5442 | 20519384.3356
3476 | 8844563.0349 | 0 | 0 | 8844563.0349
3477 | 5317912.2264 | 4812840.592 | 2124459.7264 | 12255212.5448
3478 | 4231948.2093 | 9370363.0183 | 0 | 13602311.2276
3479 | 23169000.8152 | 3712809.2318 | 7104629.7575 | 33986439.8045
3480 | 19767795.7391 | 3843761.1091 | 0 | 23611556.8482
3481 | 9742979.615 | 17454302.0561 | 1435600.5839 | 28632882.2549
3482 | 8719343.0183 | 1324715.5335 | 1477520.9551 | 11521579.5068
3483 | 447654.1101 | 2938604.9252 | 78397.8457 | 3464656.8811
3484 | 3957331.5129 | 1802542.7902 | 791232.3117 | 6551106.6147
3485 | 3983230.8428 | 3199356.5533 | 0 | 7182587.3962
3486 | 17156066.0682 | 6640035.9564 | 1121970.944 | 24918072.9687
3487 | 3625895.524 | 5774985.1344 | 398062.811 | 9798943.4695
3488 | 8321604.3417 | 2714180.4681 | 7415686.7749 | 18451471.5847
3489 | 6022944.5465 | 2801113.2485 | 8626427.3711 | 17450485.166
3490 | 3092510.621 | 6496969.3084 | 57186.1067 | 9646666.036
3491 | 14470797.6169 | 6395033.3119 | 80083.7685 | 20945914.6973
3492 | 4747151.1608 | 14847614.4968 | 1157572.9201 | 20752338.5777
3493 | 1014885.7487 | 4399118.1792 | 360734.7403 | 5774738.6681
3494 | 10382869.1532 | 7761064.1086 | 0 | 18143933.2618
3495 | 1635121.9464 | 36472420.1555 | 887984.4831 | 38995526.585
3496 | 12963292.5567 | 17369404.3571 | 1546246.478 | 31878943.3918
3497 | 1182918.5085 | 13577534.5847 | 0 | 14760453.0932
3498 | 5541887.5509 | 8721203.0795 | 6131245.4389 | 20394336.0693
3499 | 17740438.9876 | 7583764.9977 | 0 | 25324203.9853
3500 | 4656782.0226 | 16580043.6236 | 7135120.3685 | 28371946.0148
3501 | 4800378.8786 | 793071.0775 | 0 | 5593449.956
3502 | 10599737.1121 | 28695829.3439 | 0 | 39295566.456
3503 | 37622855.0381 | 2131476.7269 | 1530868.9596 | 41285200.7246
3504 | 6726919.3975 | 3143015.7722 | 455798.9852 | 10325734.155
3505 | 8580360.3893 | 18635766.3256 | 3531454.1545 | 30747580.8693
3506 | 3367615.4482 | 12964775.8482 | 0 | 16332391.2964
3507 | 11448397.8689 | 15800703.0711 | 302824.0144 | 27551924.9544
3508 | 8881268.8323 | 18205925.5523 | 1990541.1545 | 29077735.5391
3509 | 7526965.5558 | 14723941.6038 | 8456083.0005 | 30706990.1601
3510 | 4378541.6212 | 13732892.6449 | 0 | 18111434.2661
3511 | 18249676.0924 | 9170101.4626 | 1466615.1582 | 28886392.7131
3512 | 14851245.177 | 1763996.6193 | 166608.406 | 16781850.2023
3513 | 4482866.0705 | 7202882.7669 | 0 | 11685748.8375
3514 | 10672847.4168 | 11102279.366 | 12980661.7388 | 34755788.5216
3515 | 11821879.0575 | 3765361.5632 | 506283.5458 | 16093524.1665
3516 | 8746987.426 | 2280995.1644 | 0 | 11027982.5903
3517 | 17436559.5725 | 0 | 3748296.3058 | 21184855.8783
3518 | 3314949.1402 | 0 | 9902235.5923 | 13217184.7325
3519 | 8496973.056 | 17653685.2757 | 2084025.9151 | 28234684.2467
3520 | 7163952.5717 | 8320586.6478 | 132343.8106 | 15616883.0301
3521 | 12555480.2239 | 29855158.7155 | 268666.5174 | 42679305.4568
3522 | 3505422.2315 | 4071884.4917 | 2070345.0516 | 9647651.7748
3523 | 15236422.3044 | 13228583.4033 | 0 | 28465005.7077
3524 | 1644972.6362 | 2404571.3462 | 645223.8782 | 4694767.8606
3525 | 2064762.8317 | 7508860.9225 | 81696.7029 | 9655320.4571
3526 | 2405997.0515 | 6328589.8569 | 777080.6625 | 9511667.5709
3527 | 868003.0312 | 19363122.1466 | 369423.1681 | 20600548.3459
3528 | 6158666.9474 | 2715962.9942 | 2392417.3182 | 11267047.2598
3529 | 10633638.762 | 6113823.4477 | 474551.7823 | 17222013.992
3530 | 2755192.6919 | 0 | 0 | 2755192.6919
3531 | 35270786.2568 | 5236354.1897 | 1731059.2952 | 42238199.7416
3532 | 13919451.6889 | 5831089.8753 | 3551610.2507 | 23302151.8149
3533 | 4122500.5748 | 2262876.7477 | 61961.2692 | 6447338.5917
3534 | 8205389.1081 | 7329388.4134 | 0 | 15534777.5215
3535 | 8117780.9076 | 6294036.6134 | 1627658.5982 | 16039476.1192
3536 | 12496803.038 | 0 | 774075.6327 | 13270878.6707
3537 | 23997333.2906 | 23087728.7684 | 2359185.8974 | 49444247.9564
3538 | 20191015.6137 | 0 | 11392367.9445 | 31583383.5582
3539 | 26980451.2157 | 5569097.7592 | 8902632.6814 | 41452181.6563
3540 | 1802301.8186 | 13874396.5273 | 3977011.0481 | 19653709.3941
3541 | 7783576.7747 | 3809236.9282 | 229467.0247 | 11822280.7276
3542 | 1245796.1451 | 7661491.256 | 345732.9155 | 9253020.3166
3543 | 4021757.5303 | 12807647.8339 | 962915.1734 | 17792320.5376
3544 | 7279480.8181 | 15301367.2385 | 1718916.8611 | 24299764.9177
3545 | 18014140.115 | 5861993.4262 | 1914472.861 | 25790606.4022
3546 | 7236054.2552 | 4375576.4608 | 402922.1071 | 12014552.8231
3547 | 2306572.0743 | 4023141.5187 | 371642.8365 | 6701356.4295
3548 | 8435148.9649 | 0 | 876407.0429 | 9311556.0078
3549 | 4278438.9303 | 17808063.6332 | 53456.5664 | 22139959.1299
3550 | 12869567.4088 | 0 | 964460.8469 | 13834028.2557
3551 | 13652741.1563 | 2638312.2506 | 1947373.6925 | 18238427.0994
3552 | 6563600.3093 | 25664872.4386 | 2723993.9137 | 34952466.6616
3553 | 4624979.1715 | 13504851.8452 | 622487.4887 | 18752318.5054
3554 | 4035199.7456 | 3200601.9362 | 4174566.5323 | 11410368.2141
3555 | 10562729.8347 | 7776764.9418 | 1977380.515 | 20316875.2916
3556 | 2335940.5541 | 10839348.5135 | 1241047.8081 | 14416336.8757
3557 | 4407985.0929 | 9746445.2044 | 3702423.3782 | 17856853.6755
3558 | 9535730.9376 | 8986955.1886 | 1707055.4957 | 20229741.622
3559 | 2353917.86 | 3664513.4898 | 580753.3424 | 6599184.6922
3560 | 6971879.7315 | 1824727.5404 | 0 | 8796607.2718
3561 | 5896245.0243 | 0 | 1352565.3741 | 7248810.3984
3562 | 4329791.8772 | 14095332.7802 | 1301158.9922 | 19726283.6496
3563 | 20517816.6199 | 5122387.4122 | 1292133.9159 | 26932337.948
3564 | 3767719.8957 | 0 | 4162948.7363 | 7930668.632
3565 | 4869344.9398 | 3842922.9787 | 0 | 8712267.9185
3566 | 4257787.8251 | 413811.6815 | 1653027.9841 | 6324627.4907
3567 | 12461388.3994 | 110519.9187 | 0 | 12571908.3181
3568 | 10031421.5765 | 18426078.2267 | 500978.3222 | 28958478.1254
3569 | 9790255.0192 | 11582885.6515 | 4184454.0876 | 25557594.7582
3570 | 2985742.4224 | 2419372.617 | 12746410.5716 | 18151525.6109
3571 | 4243186.7419 | 4811479.1718 | 397765.8548 | 9452431.7685
3572 | 18824993.8562 | 242226.8635 | 4410783.7218 | 23478004.4414
3573 | 7897476.7886 | 0 | 3180073.7657 | 11077550.5543
3574 | 9275829.8324 | 10164195.2747 | 1739046.7455 | 21179071.8526
3575 | 35602235.3784 | 0 | 1848511.0778 | 37450746.4563
3576 | 31449827.7784 | 3432165.2212 | 789608.0192 | 35671601.0187
3577 | 18761321.8758 | 5933290.594 | 514832.8367 | 25209445.3065
3578 | 22327403.1678 | 5887606.9218 | 163835.0983 | 28378845.1879
3579 | 451652.2821 | 3185301.2103 | 0 | 3636953.4923
3580 | 6406297.2098 | 1934502.726 | 226415.8431 | 8567215.7789
3581 | 4222762.2571 | 17002757.3656 | 0 | 21225519.6227
3582 | 4583537.4007 | 4474233.085 | 192411.5811 | 9250182.0668
3583 | 2837966.8662 | 5870177.5175 | 0 | 8708144.3837
3584 | 18785065.1771 | 2327201.6571 | 793710.3591 | 21905977.1933
3585 | 11833273.2593 | 0 | 1436621.4384 | 13269894.6977
3586 | 9101383.5813 | 14823197.2121 | 271400.39 | 24195981.1835
3587 | 7851228.6834 | 0 | 11499197.6829 | 19350426.3662
3588 | 2033793.9732 | 0 | 4014771.8589 | 6048565.8321
3589 | 341768.9474 | 1556127.0422 | 500623.2459 | 2398519.2355
3590 | 8559593.0328 | 21646967.3148 | 82948.866 | 30289509.2136
3591 | 5536866.9915 | 8205666.6327 | 16935712.8571 | 30678246.4813
3592 | 2529202.6877 | 0 | 39040.5492 | 2568243.2369
3593 | 8422191.2831 | 0 | 380925.7722 | 8803117.0553
3594 | 706730.1592 | 0 | 0 | 706730.1592
3595 | 6016755.1473 | 17794094.0495 | 477131.5373 | 24287980.7341
3596 | 4286296.8147 | 17092293.5912 | 18581522.75 | 39960113.1558
3597 | 3851968.1417 | 10846945.9642 | 768880.2069 | 15467794.3128
3598 | 13856648.8925 | 4365881.1992 | 3572772.2027 | 21795302.2944
3599 | 14034917.4748 | 6982836.0678 | 1078549.5124 | 22096303.055
3600 | 2326388.0903 | 5095950.5619 | 168650.4929 | 7590989.1451
3601 | 10165299.1117 | 2118311.7976 | 73239.6831 | 12356850.5923
3602 | 1538405.0562 | 12490531.9765 | 299874.8142 | 14328811.8469
3603 | 12051020.7267 | 0 | 1116904.9268 | 13167925.6535
3604 | 4768872.5563 | 16897126.752 | 1933695.7689 | 23599695.0772
3605 | 3669950.4256 | 2423573.9949 | 366877.424 | 6460401.8445
3606 | 5349119.5105 | 10013378.4294 | 0 | 15362497.9399
3607 | 14599109.9828 | 4705452.5671 | 285198.9061 | 19589761.456
3608 | 10102682.2704 | 3475397.724 | 0 | 13578079.9944
3609 | 10427384.548 | 2696323.401 | 43736.7314 | 13167444.6803
3610 | 15346954.3779 | 0 | 146579.5076 | 15493533.8855
3611 | 5673547.4365 | 5323283.8789 | 944982.7221 | 11941814.0375
3612 | 8407618.8998 | 1423256.566 | 14765119.8029 | 24595995.2687
3613 | 7035784.982 | 10453340.9146 | 6165656.7173 | 23654782.614
3614 | 9024254.0009 | 15060875.0314 | 1585010.0506 | 25670139.0829
3615 | 17420641.3522 | 3466573.1866 | 4651323.2081 | 25538537.7468
3616 | 4988476.9636 | 26528972.7295 | 2067936.001 | 33585385.6941
3617 | 5767402.9559 | 0 | 2476752.6802 | 8244155.636
3618 | 3267696.784 | 7193426.3912 | 2864549.5959 | 13325672.7712
3619 | 2249925.6588 | 3771021.9242 | 6781251.0699 | 12802198.6528
3620 | 18058630.973 | 8986980.7778 | 0 | 27045611.7508
3621 | 3632616.1161 | 22094603.7492 | 0 | 25727219.8653
3622 | 15665828.1966 | 12535938.8394 | 985707.2443 | 29187474.2802
3623 | 4888134.3506 | 20548636.9015 | 0 | 25436771.252
3624 | 7261021.3742 | 11941931.2058 | 0 | 19202952.5799
3625 | 3638930.8875 | 2760304.0628 | 42993.0263 | 6442227.9767
3626 | 6584463.777 | 0 | 1427079.047 | 8011542.824
3627 | 12620227.9704 | 25144112.5893 | 954299.1886 | 38718639.7483
3628 | 7438688.7485 | 5146376.658 | 8344921.357 | 20929986.7635
3629 | 14407958.1249 | 6407501.1878 | 703809.2824 | 21519268.595
3630 | 15527716.6706 | 3378578.944 | 0 | 18906295.6146
3631 | 9684674.2261 | 0 | 541688.932 | 10226363.1581
3632 | 4052124.8706 | 7828382.0636 | 457187.0567 | 12337693.9909
3633 | 2640369.2675 | 3764023.8185 | 464204.0443 | 6868597.1303
3634 | 12409437.2618 | 24583335.6984 | 284107.5502 | 37276880.5105
3635 | 11478229.3904 | 3127535.8305 | 0 | 14605765.2209
3636 | 12704814.407 | 4322952.9798 | 6998616.4183 | 24026383.8051
3637 | 4350731.8765 | 10181536.5504 | 576720.9237 | 15108989.3506
3638 | 5707410.0172 | 4367503.8282 | 1993754.6639 | 12068668.5093
3639 | 9588174.4044 | 0 | 3007169.1764 | 12595343.5808
3640 | 4905477.2649 | 3149395.6608 | 105090.5884 | 8159963.5142
3641 | 1995059.4913 | 2893092.0092 | 67574.8153 | 4955726.3158
3642 | 3989958.5922 | 12956420.7954 | 2937366.8452 | 19883746.2328
3643 | 2946893.231 | 5849357.987 | 356878.6784 | 9153129.8964
3644 | 10056901.8765 | 17445488.4507 | 878972.1716 | 28381362.4987
3645 | 12117938.7654 | 3463605.4286 | 417810.4065 | 15999354.6006
3646 | 14865343.1665 | 9190126.6388 | 3084082.7183 | 27139552.5236
3647 | 15053251.3515 | 11074329.3149 | 2529796.2615 | 28657376.9279
3648 | 15717913.8867 | 0 | 1308378.4761 | 17026292.3629
3649 | 3658095.191 | 0 | 20356826.1828 | 24014921.3737
3650 | 12266854.4232 | 26926943.7885 | 2822769.9301 | 42016568.1418
3651 | 829654.113 | 4756633.2391 | 893077.5763 | 6479364.9284
3652 | 5310051.6465 | 1534341.807 | 2632870.4403 | 9477263.8938
3653 | 15157116.9951 | 2183900.8198 | 3113610.0478 | 20454627.8626
3654 | 9056524.0989 | 3322955.0919 | 2748918.8757 | 15128398.0665
3655 | 5431221.3783 | 4584863.2142 | 7447181.1381 | 17463265.7306
3656 | 1834355.5634 | 0 | 949274.449 | 2783630.0124
3657 | 11828653.6645 | 5157528.4903 | 300386.166 | 17286568.3209
3658 | 16160031.8792 | 6915970.2012 | 645131.2355 | 23721133.316
3659 | 2448704.3149 | 4519941.6802 | 11842043.4071 | 18810689.4022
3660 | 16858137.7043 | 0 | 213177.9327 | 17071315.637
3661 | 9329916.2312 | 17055777.5842 | 142152.031 | 26527845.8465
3662 | 14262307.0713 | 14082561.9373 | 1267839.3942 | 29612708.4028
3663 | 2752496.6994 | 25640498.7738 | 1958025.936 | 30351021.4093
3664 | 18767416.6884 | 20230528.5338 | 495283.1331 | 39493228.3553
3665 | 27444393.8962 | 8044522.7674 | 478263.9209 | 35967180.5845
3666 | 4364718.1597 | 21554183.4499 | 3619288.0844 | 29538189.694
3667 | 8352225.4238 | 0 | 30398.807 | 8382624.2309
3668 | 1832751.5345 | 10454693.793 | 254577.2225 | 12542022.55
3669 | 15325188.2825 | 7748095.1931 | 10611962.6145 | 33685246.0901
3670 | 3569872.091 | 7572927.913 | 4264251.6612 | 15407051.6652
3671 | 7264993.108 | 20676646.0519 | 1359262.7627 | 29300901.9226
3672 | 19996869.6402 | 3019863.4774 | 391292.423 | 23408025.5405
3673 | 9182987.6064 | 11577020.3525 | 847089.4328 | 21607097.3916
3674 | 19369511.7034 | 5732008.3206 | 2786222.57 | 27887742.594
3675 | 9736550.1917 | 22489642.4218 | 0 | 32226192.6134
3676 | 6087473.5851 | 16510449.2258 | 2930992.436 | 25528915.2469
3677 | 10367976.8181 | 9960971.3604 | 1224548.2738 | 21553496.4523
3678 | 12890946.1694 | 5124089.4523 | 0 | 18015035.6217
3679 | 2938450.7889 | 7931222.0988 | 114555.0024 | 10984227.89
3680 | 5533994.19 | 12774226.592 | 332601.2529 | 18640822.035
3681 | 1458563.9548 | 0 | 2694780.9386 | 4153344.8934
3682 | 25941671.8372 | 15882654.2366 | 12825591.8721 | 54649917.9459
3683 | 7847980.0794 | 22471577.0566 | 0 | 30319557.136
3684 | 4345667.5211 | 367539.7447 | 574846.9149 | 5288054.1807
3685 | 3218364.4823 | 16831715.1225 | 377064.0311 | 20427143.6359
3686 | 4529119.58 | 7836723.441 | 1554462.3815 | 13920305.4025
3687 | 13685964.7523 | 2829141.4333 | 4539649.1573 | 21054755.3429
3688 | 9264539.3214 | 4972943.562 | 1581126.1437 | 15818609.027
3689 | 580680.5457 | 10518639.6717 | 710663.3042 | 11809983.5215
3690 | 20644198.5909 | 3186914.4927 | 715255.4023 | 24546368.4859
3691 | 6540680.7338 | 7756625.5469 | 10071453.706 | 24368759.9867
3692 | 7552683.5823 | 2049142.216 | 247981.6885 | 9849807.4868
3693 | 9124118.2945 | 973029.7407 | 1847021.6792 | 11944169.7145
3694 | 4605159.958 | 6816565.6129 | 541485.4332 | 11963211.004
3695 | 3812088.1642 | 13685334.2219 | 2270284.8425 | 19767707.2286
3696 | 5308860.4227 | 9154644.4086 | 10151.05 | 14473655.8813
3697 | 8200976.1339 | 0 | 0 | 8200976.1339
3698 | 6561834.8457 | 14169572.1317 | 75621.5778 | 20807028.5552
3699 | 4517280.4805 | 4102355.1607 | 0 | 8619635.6412
3700 | 3622142.8561 | 6657931.5358 | 31746.1793 | 10311820.5712
3701 | 120627.068 | 7715888.2844 | 1189192.3582 | 9025707.7105
3702 | 9807755.3598 | 0 | 0 | 9807755.3598
3703 | 6644467.7602 | 1860426.5396 | 2329336.5393 | 10834230.839
3704 | 9593974.8663 | 2819194.7202 | 5098821.8166 | 17511991.4031
3705 | 6555758.5931 | 7418622.0288 | 12523.9302 | 13986904.5521
3706 | 4947634.3856 | 112175.6781 | 274859.5385 | 5334669.6022
3707 | 11112361.5216 | 36991677.3824 | 4165590.6692 | 52269629.5731
3708 | 4874560.9245 | 9658593.2988 | 693063.3999 | 15226217.6232
3709 | 7200590.7387 | 4753823.8537 | 15075210.5965 | 27029625.1889
3710 | 8766655.2631 | 5302477.8857 | 998493.9615 | 15067627.1103
3711 | 3868084.2071 | 58077498.7347 | 468353.5983 | 62413936.5401
3712 | 4433180.5324 | 0 | 2093289.2794 | 6526469.8117
3713 | 2845433.1891 | 6268631.9772 | 0 | 9114065.1663
3714 | 4245774.4585 | 13151012.7184 | 1477280.0499 | 18874067.2268
3715 | 4211461.9907 | 2095385.3323 | 119742.6293 | 6426589.9523
3716 | 5245369.9601 | 4994421.0339 | 0 | 10239790.994
3717 | 5456213.4306 | 20711031.6117 | 0 | 26167245.0424
3718 | 1921021.6073 | 2599851.3601 | 13944252.3193 | 18465125.2866
3719 | 11662871.6583 | 25514312.362 | 0 | 37177184.0203
3720 | 4701552.5898 | 28807170.7172 | 6543772.9127 | 40052496.2198
3721 | 10057506.6596 | 4220964.9688 | 691522.1904 | 14969993.8187
3722 | 28755245.0977 | 16068448.1955 | 3933282.102 | 48756975.3953
3723 | 3607912.7275 | 0 | 104069.064 | 3711981.7915
3724 | 3295717.1667 | 8502447.9428 | 3698101.8112 | 15496266.9206
3725 | 226709.7758 | 23323803.6018 | 2799035.9821 | 26349549.3597
3726 | 14991926.599 | 863735.1825 | 173328.0831 | 16028989.8646
3727 | 2862939.5321 | 0 | 0 | 2862939.5321
3728 | 3816771.2506 | 2442411.6855 | 2078965.264 | 8338148.2
3729 | 19483811.6145 | 13704507.5115 | 464711.9179 | 33653031.0439
3730 | 589837.6715 | 13012237.5595 | 2745356.5716 | 16347431.8026
3731 | 13325549.6917 | 31172042.9245 | 223338.7436 | 44720931.3597
3732 | 2525070.4953 | 5213674.103 | 338222.2124 | 8076966.8107
3733 | 15165296.5326 | 4052731.8916 | 648879.0706 | 19866907.4948
3734 | 3049705.8199 | 0 | 8177480.9297 | 11227186.7496
3735 | 2191662.6481 | 2642885.7315 | 1095434.1586 | 5929982.5382
3736 | 10124374.1817 | 0 | 292068.1191 | 10416442.3009
3737 | 2644311.2008 | 0 | 623339.168 | 3267650.3689
3738 | 8768143.723 | 9463443.9542 | 86272.6025 | 18317860.2798
3739 | 3229411.1296 | 2632009.1235 | 0 | 5861420.2531
3740 | 5987599.7748 | 13096813.5525 | 0 | 19084413.3273
3741 | 4109873.3296 | 6508217.4917 | 5756358.7094 | 16374449.5306
3742 | 4283879.0622 | 10947933.4485 | 25040319.2683 | 40272131.7791
3743 | 6497920.5562 | 479727.2414 | 0 | 6977647.7977
3744 | 5756063.745 | 1933990.572 | 1146702.1642 | 8836756.4812
3745 | 9431265.3227 | 4187030.6949 | 0 | 13618296.0176
3746 | 895971.0879 | 6457472.769 | 1519371.4825 | 8872815.3394
3747 | 5505206.4583 | 11283344.6358 | 17015579.1843 | 33804130.2784
3748 | 5988300.2612 | 2921732.6553 | 528616.1527 | 9438649.0693
3749 | 2021483.4003 | 2245104.1247 | 12615047.6194 | 16881635.1443
3750 | 2035939.2482 | 29986844.1738 | 664520.7802 | 32687304.2023
3751 | 11082351.9945 | 3751081.8469 | 2311640.6146 | 17145074.4559
3752 | 10462337.649 | 12395519.8946 | 3378498.0781 | 26236355.6217
3753 | 7247947.5058 | 0 | 825655.7861 | 8073603.2919
3754 | 16427502.8135 | 33256575.5027 | 365416.7315 | 50049495.0477
3755 | 3343654.6361 | 3913807.5506 | 14447488.8606 | 21704951.0474
3756 | 6519511.8534 | 3576132.2275 | 2091350.5189 | 12186994.5997
3757 | 12093290.6201 | 13285828.857 | 415139.1892 | 25794258.6662
3758 | 14961829.6786 | 264344.9416 | 0 | 15226174.6203
3759 | 5076239.0582 | 0 | 2070631.0195 | 7146870.0777
3760 | 18303760.9701 | 32084328.504 | 1822722.0439 | 52210811.518
3761 | 2470229.3615 | 0 | 3233427.7748 | 5703657.1363
3762 | 2733089.2286 | 0 | 12015822.478 | 14748911.7067
3763 | 8729549.4055 | 6863919.9737 | 78326.7519 | 15671796.1311
3764 | 9882671.66 | 6319536.77 | 0 | 16202208.43
3765 | 5334074.189 | 5777064.5508 | 159171.7264 | 11270310.4661
3766 | 3956042.2491 | 16642440.6643 | 1597708.9945 | 22196191.9079
3767 | 13856187.4486 | 0 | 7623136.6359 | 21479324.0845
3768 | 10643011.6528 | 8088564.5467 | 269202.8782 | 19000779.0778
3769 | 5230581.5749 | 493566.4512 | 15003911.4184 | 20728059.4445
3770 | 11680480.5709 | 1634361.3645 | 1706114.3149 | 15020956.2503
3771 | 4868792.606 | 0 | 0 | 4868792.606
3772 | 6509815.012 | 6163265.6831 | 3832320.6323 | 16505401.3274
3773 | 11362594.5854 | 6722945.932 | 1435147.1989 | 19520687.7163
3774 | 4375744.9907 | 0 | 310745.1385 | 4686490.1292
3775 | 817456.2601 | 9941634.7591 | 1166670.2249 | 11925761.2441
3776 | 573079.6962 | 0 | 1449092.2447 | 2022171.9409
3777 | 16795390.782 | 11626604.8954 | 4409054.8037 | 32831050.4811
3778 | 1762594.3874 | 20355403.3966 | 1426322.9441 | 23544320.7281
3779 | 5414986.7327 | 9053121.5413 | 0 | 14468108.274
3780 | 8082385.5093 | 15956593.0067 | 0 | 24038978.516
3781 | 4683554.5674 | 3626725.0923 | 8098791.5341 | 16409071.1938
3782 | 3339401.3393 | 0 | 2086960.8316 | 5426362.1709
3783 | 12815464.9862 | 11573828.8354 | 2469184.3317 | 26858478.1533
3784 | 6700004.6784 | 967775.3277 | 0 | 7667780.0061
3785 | 24041829.7832 | 17800383.9134 | 0 | 41842213.6966
3786 | 2391397.3646 | 15351029.9842 | 1427979.3729 | 19170406.7217
3787 | 8212029.5316 | 0 | 11253139.7329 | 19465169.2645
3788 | 11026290.2374 | 8089054.1417 | 675712.8289 | 19791057.208
3789 | 16602790.082 | 10322418.1699 | 7400844.2777 | 34326052.5296
3790 | 2360197.4003 | 6437108.2156 | 2041332.5156 | 10838638.1315
3791 | 11452408.1209 | 9757463.0777 | 5538751.6219 | 26748622.8204
3792 | 6691312.232 | 0 | 484809.5166 | 7176121.7485
3793 | 13487941.4631 | 2526904.6761 | 451772.6785 | 16466618.8178
3794 | 16172076.1503 | 20087598.2036 | 0 | 36259674.3539
3795 | 15423580.4464 | 11641151.2418 | 147220.8608 | 27211952.549
3796 | 13264768.4232 | 14563386.2632 | 6316001.0868 | 34144155.7733
3797 | 13508143.682 | 366025.8233 | 87768.2496 | 13961937.7549
3798 | 1687806.6203 | 0 | 260591.9601 | 1948398.5804
3799 | 5385939.4131 | 0 | 327922.5564 | 5713861.9695
3800 | 3925357.5111 | 8907497.5217 | 12041155.7701 | 24874010.8029
3801 | 693509.898 | 12375198.6697 | 864098.1862 | 13932806.7539
3802 | 4348332.5235 | 11959462.4688 | 988602.9323 | 17296397.9246
3803 | 6411825.4078 | 13222088.7678 | 43246.9356 | 19677161.1112
3804 | 10848773.9656 | 4366229.3023 | 3286655.2562 | 18501658.5241
3805 | 1955458.637 | 27256119.7079 | 604380.2112 | 29815958.556
3806 | 2699957.4082 | 5172448.4068 | 1058338.2594 | 8930744.0745
3807 | 31050869.7375 | 12607428.4456 | 6347934.4043 | 50006232.5875
3808 | 4448369.3822 | 2196863.9358 | 2134566.4584 | 8779799.7764
3809 | 4892046.7864 | 1163256.4548 | 0 | 6055303.2412
3810 | 2625886.9423 | 16113050.2198 | 1253021.6052 | 19991958.7673
3811 | 1796821.9402 | 0 | 342004.2674 | 2138826.2075
3812 | 5367779.9115 | 7523698.8254 | 2368637.2502 | 15260115.9871
3813 | 11401593.8254 | 14248786.8291 | 0 | 25650380.6545
3814 | 28278122.9181 | 4182831.8016 | 2356266.4456 | 34817221.1654
3815 | 11149104.878 | 4345128.984 | 960875.6017 | 16455109.4637
3816 | 291837.1906 | 6411239.9071 | 129647.2919 | 6832724.3896
3817 | 31409155.6013 | 1567731.8641 | 85419.5447 | 33062307.01
3818 | 4647254.1299 | 19309262.7248 | 1916435.1119 | 25872951.9667
3819 | 3564854.9991 | 14235045.0886 | 48845.4646 | 17848745.5523
3820 | 1672355.664 | 16388851.1455 | 6470505.5687 | 24531712.3782
3821 | 18646195.6144 | 256646.5023 | 297867.1809 | 19200709.2976
3822 | 3504106.9555 | 19404986.6191 | 1229434.7212 | 24138528.2959
3823 | 7427596.6715 | 3238258.2807 | 108462.3395 | 10774317.2917
3824 | 9285202.2273 | 3866515.7382 | 5927770.7968 | 19079488.7623
3825 | 9164181.4768 | 2884633.4759 | 1893981.1146 | 13942796.0674
3826 | 4507917.3557 | 0 | 705730.6123 | 5213647.9681
3827 | 5113896.7736 | 13543705.2671 | 425526.9606 | 19083129.0013
3828 | 923260.2919 | 0 | 0 | 923260.2919
3829 | 3011468.9926 | 8008100.1925 | 1765013.3722 | 12784582.5573
3830 | 5385011.7776 | 14647359.0915 | 3508336.2939 | 23540707.163
3831 | 13411494.074 | 3003893.0885 | 0 | 16415387.1625
3832 | 2871265.4767 | 8834304.0366 | 12015551.8356 | 23721121.3489
3833 | 5754090.1658 | 3481067.6881 | 0 | 9235157.854
3834 | 1037470.2263 | 7681245.4078 | 0 | 8718715.6341
3835 | 2746543.3038 | 5354027.5647 | 90383.4288 | 8190954.2972
3836 | 13446351.427 | 0 | 13342008.155 | 26788359.582
3837 | 2960009.452 | 11398995.5387 | 15150478.4048 | 29509483.3954
3838 | 6330388.614 | 11351784.5272 | 1542281.7674 | 19224454.9085
3839 | 19814938.8673 | 4187408.1378 | 1448693.9359 | 25451040.941
3840 | 8200962.4781 | 9879076.1737 | 3023469.7601 | 21103508.4119
3841 | 2159747.877 | 8879823.8975 | 8639169.4427 | 19678741.2172
3842 | 6864831.6777 | 0 | 33800.1345 | 6898631.8122
3843 | 2321017.3013 | 11099074.401 | 213623.1459 | 13633714.8482
3844 | 8470347.6357 | 8508540.6506 | 167657.5944 | 17146545.8807
3845 | 1815421.7331 | 7000562.8114 | 628665.2363 | 9444649.7808
3846 | 31387371.4749 | 0 | 1748312.7722 | 33135684.247
3847 | 1939181.8066 | 12569171.9585 | 10471240.9628 | 24979594.7279
3848 | 3712536.3953 | 1532607.0802 | 698974.7173 | 5944118.1929
3849 | 117237202.9915 | 43741964.2365 | 0 | 160979167.228
3850 | 2607308.2578 | 7704632.2159 | 1690837.846 | 12002778.3197
3851 | 7020279.653 | 0 | 5212401.3924 | 12232681.0454
3852 | 18065354.365 | 10663569.4361 | 312933.0894 | 29041856.8905
3853 | 20543814.8349 | 3758690.5485 | 37531.6828 | 24340037.0663
3854 | 12494847.6817 | 10428121.1198 | 496815.1191 | 23419783.9205
3855 | 48493127.7999 | 10386983.9035 | 150893.9858 | 59031005.6892
3856 | 2440617.8695 | 3238961.7498 | 2227647.5726 | 7907227.1919
3857 | 3436225.4023 | 18002444.7875 | 6460330.024 | 27899000.2138
3858 | 12104415.7118 | 0 | 1453544.4622 | 13557960.1741
3859 | 6486447.2889 | 29076684.8421 | 0 | 35563132.1309
3860 | 27522871.8272 | 1237933.4906 | 1757093.1642 | 30517898.4819
3861 | 9187221.4254 | 4830367.52 | 6361719.6529 | 20379308.5983
3862 | 14566460.6283 | 4610552.4212 | 1043752.8775 | 20220765.9271
3863 | 9595250.8209 | 8076607.0398 | 799467.4367 | 18471325.2974
3864 | 1822310.4864 | 9992175.9395 | 772470.7459 | 12586957.1717
3865 | 16599648.4315 | 4600957.4538 | 4656457.7001 | 25857063.5855
3866 | 1097243.9558 | 0 | 414794.9698 | 1512038.9256
3867 | 13026527.9722 | 9579613.8472 | 5101659.0084 | 27707800.8278
3868 | 47938765.8352 | 0 | 109124.6143 | 48047890.4495
3869 | 9134330.7287 | 10015809.3152 | 0 | 19150140.0439
3870 | 5894884.3188 | 11580081.9329 | 5643425.3204 | 23118391.5722
3871 | 4229709.4038 | 6759021.7346 | 436877.9449 | 11425609.0834
3872 | 7242060.6152 | 176056.1489 | 435319.0575 | 7853435.8216
3873 | 7168664.8841 | 6860313.7203 | 1953492.8819 | 15982471.4863
3874 | 3575177.8477 | 11271692.3158 | 1225207.251 | 16072077.4145
3875 | 4540117.3933 | 1739163.8013 | 556074.7345 | 6835355.9291
3876 | 12355423.4471 | 4148724.9554 | 958188.0469 | 17462336.4494
3877 | 3870523.0266 | 0 | 5669373.6101 | 9539896.6367
3878 | 4284221.8042 | 4693146.021 | 2467647.716 | 11445015.5412
3879 | 11945723.578 | 6073659.5985 | 5094567.5133 | 23113950.6899
3880 | 10769775.7848 | 9293771.2183 | 5236413.1573 | 25299960.1604
3881 | 3944605.1979 | 980253.8206 | 0 | 4924859.0185
3882 | 19420374.1819 | 7274480.702 | 173772.0743 | 26868626.9582
3883 | 2926507.1517 | 15372244.7108 | 633274.7644 | 18932026.6268
3884 | 14134133.3965 | 13158941.8065 | 608155.4537 | 27901230.6566
3885 | 7263672.6171 | 17902930.9288 | 5317.3469 | 25171920.8928
3886 | 3614828.998 | 3362154.1232 | 0 | 6976983.1212
3887 | 6732890.9001 | 10645620.6373 | 3527857.7354 | 20906369.2728
3888 | 13010214.1015 | 5547875.8306 | 1196892.3843 | 19754982.3165
3889 | 7103048.0331 | 2925180.3072 | 752025.5152 | 10780253.8556
3890 | 4366814.6244 | 0 | 2279277.8233 | 6646092.4477
3891 | 6899856.1971 | 22796028.2908 | 123631.6748 | 29819516.1627
3892 | 7567863.5994 | 7381021.7527 | 20768294.2975 | 35717179.6496
3893 | 37364916.3597 | 5071232.4785 | 1227611.2691 | 43663760.1073
3894 | 4749825.3686 | 7254596.9303 | 4262694.7328 | 16267117.0317
3895 | 3075503.5585 | 0 | 1538612.643 | 4614116.2016
3896 | 16985506.26 | 0 | 20160581.9154 | 37146088.1754
3897 | 4022943.7891 | 0 | 0 | 4022943.7891
3898 | 32884780.4837 | 15136652.6454 | 2390419.0926 | 50411852.2217
3899 | 9657908.2575 | 6992505.7809 | 1274419.6055 | 17924833.6439
3900 | 6895035.7054 | 6025185.9653 | 197885.2758 | 13118106.9466
3901 | 1886904.5882 | 3121447.6563 | 2137320.7745 | 7145673.019
3902 | 3716939.2946 | 2822507.585 | 3449743.8383 | 9989190.7179
3903 | 3017302.3148 | 4867190.4877 | 3674870.5742 | 11559363.3766
3904 | 4822819.3088 | 8241401.3667 | 4957833.7906 | 18022054.4662
3905 | 1043243.8677 | 24101983.9001 | 288414.506 | 25433642.2738
3906 | 2115979.0974 | 3702203.9545 | 63383.5216 | 5881566.5736
3907 | 2283313.2836 | 4389430.5696 | 0 | 6672743.8532
3908 | 6810258.0948 | 16005080.4455 | 3126841.7907 | 25942180.3311
3909 | 9876899.2969 | 0 | 2250210.0406 | 12127109.3376
3910 | 13337594.4003 | 14372286.6459 | 2074968.9777 | 29784850.0239
3911 | 13189359.5373 | 561382.9777 | 492549.5434 | 14243292.0584
3912 | 12044512.4876 | 0 | 2411582.7724 | 14456095.2601
3913 | 7494225.5603 | 7641006.0281 | 177977.7405 | 15313209.3289
3914 | 9368810.7873 | 18600029.3991 | 467754.1095 | 28436594.2959
3915 | 3678966.4577 | 11566569.0936 | 2564468.7346 | 17810004.2859
3916 | 10168627.0469 | 6730756.7877 | 1096246.968 | 17995630.8026
3917 | 2957594.9578 | 5900714.8476 | 8647050.1481 | 17505359.9535
3918 | 7351693.1358 | 24042.4657 | 5188972.4677 | 12564708.0692
3919 | 9976543.3598 | 5815940.2201 | 695875.5021 | 16488359.0819
3920 | 3945111.2894 | 6580728.193 | 10482682.7593 | 21008522.2417
3921 | 6793391.9818 | 5906848.2865 | 715081.0701 | 13415321.3384
3922 | 19190731.6977 | 5243680.6142 | 3038519.2575 | 27472931.5694
3923 | 11157827.3795 | 4037417.3866 | 10942092.5668 | 26137337.3329
3924 | 2305782.4265 | 12265546.1601 | 0 | 14571328.5867
3925 | 10726634.7053 | 9250947.4688 | 4171902.2626 | 24149484.4367
3926 | 2596543.2912 | 6721408.6852 | 10775.189 | 9328727.1653
3927 | 10242388.3394 | 6182215.2707 | 2296472.5063 | 18721076.1164
3928 | 2171938.5384 | 34732047.4677 | 1122030.7722 | 38026016.7782
3929 | 13096051.4398 | 0 | 7007653.9627 | 20103705.4025
3930 | 15788978.5335 | 6979117.0279 | 288817.2582 | 23056912.8196
3931 | 18836267.8548 | 3753897.7802 | 0 | 22590165.635
3932 | 1966765.7859 | 0 | 31076989.1529 | 33043754.9388
3933 | 7537543.1151 | 0 | 56253.4005 | 7593796.5156
3934 | 1838996.259 | 2938961.1875 | 776634.5463 | 5554591.9928
3935 | 11205515.6432 | 2351151.1455 | 7155623.5448 | 20712290.3336
3936 | 8727358.2035 | 22876879.1952 | 0 | 31604237.3986
3937 | 4830707.1987 | 0 | 0 | 4830707.1987
3938 | 1131553.4889 | 3021476.091 | 0 | 4153029.58
3939 | 3402855.1777 | 0 | 1112025.8653 | 4514881.043
3940 | 3980031.3422 | 9087454.2569 | 138349.8338 | 13205835.433
3941 | 5986592.1232 | 2139219.6935 | 0 | 8125811.8167
3942 | 9332003.0458 | 4728402.4488 | 1951977.6825 | 16012383.1771
3943 | 19096219.193 | 1408343.8521 | 2853132.0911 | 23357695.1362
3944 | 10781867.6814 | 0 | 759964.9182 | 11541832.5996
3945 | 2211103.9061 | 7750845.8497 | 0 | 9961949.7558
3946 | 5584040.5085 | 0 | 0 | 5584040.5085
3947 | 16692961.713 | 13334344.4641 | 1751297.645 | 31778603.8222
3948 | 7623258.3909 | 3858932.4234 | 0 | 11482190.8143
3949 | 9629066.2833 | 6020033.4994 | 1249680.3746 | 16898780.1574
3950 | 8408548.2026 | 0 | 1646813.8425 | 10055362.045
3951 | 9846468.6781 | 3671083.1526 | 1494128.8544 | 15011680.6851
3952 | 1890637.5206 | 6944701.4774 | 91321.8524 | 8926660.8504
3953 | 1614575.4112 | 2689794.929 | 0 | 4304370.3402
3954 | 13418347.7215 | 22128222.0352 | 2575933.0305 | 38122502.7872
3955 | 9709911.6151 | 6568787.8267 | 0 | 16278699.4418
3956 | 1594961.1971 | 4672862.1033 | 11523315.1078 | 17791138.4082
3957 | 2794960.3499 | 12239249.1155 | 79220.5032 | 15113429.9686
3958 | 6443501.4611 | 0 | 0 | 6443501.4611
3959 | 3414774.6017 | 3259352.6826 | 959655.6126 | 7633782.8969
3960 | 13516272.2117 | 0 | 0 | 13516272.2117
3961 | 1389435.1914 | 0 | 0 | 1389435.1914
3962 | 15557340.6395 | 6841172.3562 | 2323341.7425 | 24721854.7381
3963 | 2561698.836 | 13163316.1019 | 46049.3475 | 15771064.2854
3964 | 8649145.3343 | 15690551.7138 | 4369251.7807 | 28708948.8288
3965 | 11328588.0046 | 6532993.7681 | 0 | 17861581.7728
3966 | 4130069.6351 | 16152188.4992 | 308279.5526 | 20590537.6869
3967 | 5310319.0746 | 6618908.9217 | 2468834.7386 | 14398062.7349
3968 | 5612536.603 | 1672808.707 | 6199648.9002 | 13484994.2102
3969 | 1110145.121 | 12950521.6212 | 1818459.6127 | 15879126.3548
3970 | 5515433.2075 | 9873145.9421 | 75099.4795 | 15463678.6291
3971 | 6736542.8663 | 16374279.3712 | 0 | 23110822.2375
3972 | 16507190.5059 | 3854470.7211 | 3880340.886 | 24242002.1129
3973 | 832559.452 | 1332171.9374 | 0 | 2164731.3894
3974 | 6164776.0575 | 7430171.6097 | 1016628.5191 | 14611576.1863
3975 | 7262135.6271 | 6716156.3791 | 133738.935 | 14112030.9413
3976 | 16497555.1906 | 3531797.4213 | 698130.6618 | 20727483.2737
3977 | 1588081.0732 | 19741648.2367 | 4684974.4242 | 26014703.734
3978 | 4726976.9929 | 23451675.9923 | 0 | 28178652.9852
3979 | 4851667.9703 | 0 | 523017.5464 | 5374685.5167
3980 | 22156110.9588 | 11609723.0685 | 0 | 33765834.0273
3981 | 5988854.1866 | 0 | 921976.0687 | 6910830.2553
3982 | 4901650.8432 | 0 | 82264.9126 | 4983915.7558
3983 | 6795482.1871 | 14532073.4406 | 1096791.5756 | 22424347.2033
3984 | 19459411.5419 | 232711.1588 | 405216.6587 | 20097339.3593
3985 | 27281266.8237 | 8582871.3969 | 3111961.788 | 38976100.0086
3986 | 12545408.4088 | 28404166.7422 | 10864192.0577 | 51813767.2087
3987 | 2274020.2804 | 4566804.0068 | 951813.5713 | 7792637.8585
3988 | 12789220.9643 | 3632052.2994 | 108693.4228 | 16529966.6864
3989 | 12881293.6127 | 0 | 0 | 12881293.6127
3990 | 11258612.7091 | 2373995.7568 | 2057724.099 | 15690332.5648
3991 | 7204784.8199 | 0 | 937346.8265 | 8142131.6464
3992 | 20007546.8435 | 13592127.8192 | 0 | 33599674.6627
3993 | 8849111.4614 | 7400262.3487 | 14044.622 | 16263418.4322
3994 | 4203211.4323 | 3306577.7323 | 1756301.8507 | 9266091.0153
3995 | 9679279.2083 | 6589156.8873 | 4063066.7982 | 20331502.8939
3996 | 4859950.8268 | 8724620.6432 | 3936152.6562 | 17520724.1262
3997 | 3983318.3358 | 16556806.0201 | 35434.2375 | 20575558.5935
3998 | 2259062.1022 | 14960887.0452 | 1789095.0916 | 19009044.2389
3999 | 6188586.0742 | 6528193.4864 | 5326930.9632 | 18043710.5239
4000 | 2581366.0383 | 9854856.1146 | 1621025.911 | 14057248.064
4001 | 1025919.4591 | 0 | 22850958.3319 | 23876877.791
4002 | 3746870.675 | 8955926.7102 | 2427187.1745 | 15129984.5598
4003 | 8911149.5869 | 21251362.1339 | 5391142.068 | 35553653.7888
4004 | 18353897.3348 | 3026828.0056 | 1721546.2264 | 23102271.5668
4005 | 11677338.9823 | 8969235.8481 | 953851.8034 | 21600426.6337
4006 | 11716733.4747 | 4920924.9282 | 1149541.5473 | 17787199.9502
4007 | 6873446.9888 | 8992238.3475 | 331424.7891 | 16197110.1254
4008 | 13140477.0648 | 3214048.154 | 80863.9732 | 16435389.192
4009 | 1205208.6442 | 18805410.549 | 3799712.8417 | 23810332.0349
4010 | 28714913.9627 | 12749549.3614 | 103968.0866 | 41568431.4107
4011 | 4121982.1775 | 0 | 4059065.4742 | 8181047.6516
4012 | 14214312.2698 | 5654630.3325 | 520348.7708 | 20389291.3732
4013 | 3552810.9543 | 3918520.474 | 1056157.9369 | 8527489.3652
4014 | 10515314.2437 | 2462359.8939 | 0 | 12977674.1376
4015 | 4720753.6124 | 18668218.1655 | 534243.9456 | 23923215.7236
4016 | 4176495.7654 | 6357739.3852 | 6003529.009 | 16537764.1596
4017 | 10083990.511 | 13513806.8069 | 146607.1528 | 23744404.4706
4018 | 15221457.8805 | 5808690.6822 | 0 | 21030148.5628
4019 | 2949344.2584 | 1569554.3924 | 2757978.6642 | 7276877.315
4020 | 5026121.7536 | 2014157.2784 | 1178967.7292 | 8219246.7611
4021 | 8147950.8153 | 0 | 474892.2621 | 8622843.0774
4022 | 17473093.3711 | 0 | 0 | 17473093.3711
4023 | 2612412.5782 | 9992704.6027 | 982193.1942 | 13587310.3751
4024 | 1572848.7624 | 974016.9161 | 1094837.6952 | 3641703.3738
4025 | 10294038.5801 | 5153523.9753 | 898834.106 | 16346396.6614
4026 | 10214721.4902 | 5399755.0557 | 11208124.0236 | 26822600.5695
4027 | 7990582.9097 | 12206223.6323 | 2247417.0395 | 22444223.5814
4028 | 23561557.0856 | 7177719.9492 | 0 | 30739277.0348
4029 | 4029678.6407 | 3563677.8014 | 551988.3624 | 8145344.8044
4030 | 5861001.8997 | 10846569.8625 | 5765226.9086 | 22472798.6707
4031 | 15540087.6191 | 9896964.3001 | 181361.9006 | 25618413.8199
4032 | 13632405.8186 | 11382943.799 | 0 | 25015349.6176
4033 | 27675073.2369 | 16870012.983 | 6783586.3731 | 51328672.5931
4034 | 5461099.9206 | 4518741.4808 | 194394.1204 | 10174235.5217
4035 | 2018708.1879 | 7693946.8744 | 3467524.9407 | 13180180.003
4036 | 15629634.2226 | 0 | 0 | 15629634.2226
4037 | 1486061.0487 | 1315533.6992 | 3110257.9393 | 5911852.6872
4038 | 5863624.832 | 0 | 8958693.6668 | 14822318.4987
4039 | 10515676.6142 | 19423453.6245 | 0 | 29939130.2386
4040 | 3301151.1163 | 5752313.6159 | 16049704.833 | 25103169.5652
4041 | 8654542.1218 | 13079739.778 | 10269041.4357 | 32003323.3355
4042 | 11590983.4678 | 6134177.5877 | 1616974.1772 | 19342135.2327
4043 | 7573767.8466 | 2998416.4851 | 0 | 10572184.3317
4044 | 1552924.1812 | 3078044.6061 | 993633.4192 | 5624602.2065
4045 | 8193755.77 | 28127215.8094 | 991293.5195 | 37312265.0989
4046 | 15082033.8939 | 13483265.7072 | 452527.562 | 29017827.1631
4047 | 30839375.8052 | 5664723.685 | 847489.8328 | 37351589.3229
4048 | 4992138.6772 | 10987907.7216 | 9720742.5196 | 25700788.9184
4049 | 3627344.1155 | 11691634.466 | 2683057.5333 | 18002036.1148
4050 | 27117251.5685 | 8342080.5059 | 551893.592 | 36011225.6664
4051 | 10947757.0419 | 18414082.6048 | 15775774.562 | 45137614.2087
4052 | 2513188.6105 | 2820459.4155 | 498680.0869 | 5832328.1129
4053 | 31456962.5424 | 0 | 0 | 31456962.5424
4054 | 8977770.5658 | 17206480.7866 | 715122.8948 | 26899374.2472
4055 | 5890463.7641 | 16844140.13 | 5150568.6868 | 27885172.5809
4056 | 5935818.5471 | 15358723.1123 | 0 | 21294541.6594
4057 | 2437242.845 | 1619376.2817 | 149685.8533 | 4206304.98
4058 | 3444719.96 | 11824467.216 | 3598517.7878 | 18867704.9638
4059 | 4619148.5303 | 0 | 3694362.9451 | 8313511.4754
4060 | 5218958.0055 | 18526199.4741 | 3279289.9386 | 27024447.4182
4061 | 5653226.6714 | 2069876.7269 | 0 | 7723103.3983
4062 | 13166937.981 | 1528406.8012 | 849176.4619 | 15544521.244
4063 | 8040411.6351 | 23186539.935 | 761203.8876 | 31988155.4577
4064 | 10996074.577 | 7256456.866 | 259232.4768 | 18511763.9197
4065 | 9421490.1293 | 2703888.0098 | 2655807.7301 | 14781185.8692
4066 | 9599379.8714 | 4647921.2666 | 1252463.2382 | 15499764.3763
4067 | 3442059.913 | 0 | 1386100.7419 | 4828160.6549
4068 | 26257340.4988 | 1862995.9803 | 0 | 28120336.479
4069 | 11623901.0651 | 4473499.8761 | 306376.3321 | 16403777.2733
4070 | 18269331.4397 | 14339657.5267 | 4984904.8317 | 37593893.7981
4071 | 20506241.9174 | 3108177.2801 | 480842.7657 | 24095261.9632
4072 | 59926.7921 | 6241382.5736 | 1059160.746 | 7360470.1118
4073 | 525902.9701 | 8393202.1696 | 202182.3418 | 9121287.4815
4074 | 2969176.3432 | 7671161.3772 | 121826.3088 | 10762164.0292
4075 | 11185015.5435 | 15687293.6111 | 195541.3572 | 27067850.5118
4076 | 1251403.879 | 4077248.2713 | 4695055.0492 | 10023707.1994
4077 | 3683246.1114 | 1666241.3555 | 2672631.1727 | 8022118.6395
4078 | 1091133.9348 | 16468137.4903 | 837251.014 | 18396522.4391
4079 | 10341916.3971 | 16073798.0252 | 25333.9726 | 26441048.3949
4080 | 1208400.5142 | 0 | 2777263.1244 | 3985663.6386
4081 | 875379.756 | 3347004.703 | 6023549.5503 | 10245934.0093
4082 | 5989802.9363 | 21758912.9667 | 521168.3831 | 28269884.2862
4083 | 17288163.6001 | 6285626.4332 | 136277.493 | 23710067.5263
4084 | 9844009.696 | 21011366.0049 | 200863.4724 | 31056239.1734
4085 | 7436316.4726 | 14883137.0432 | 344933.3403 | 22664386.8561
4086 | 9431587.6631 | 0 | 1213901.6319 | 10645489.295
4087 | 6044403.8351 | 0 | 5737633.3079 | 11782037.143
4088 | 5778224.9062 | 0 | 0 | 5778224.9062
4089 | 5658887.6309 | 3348370.147 | 2795862.3143 | 11803120.0921
4090 | 3979954.9354 | 10777896.1264 | 0 | 14757851.0618
4091 | 4941044.8205 | 7539711.7098 | 0 | 12480756.5303
4092 | 3952257.0954 | 7294437.0558 | 1374062.0925 | 12620756.2438
4093 | 5482904.5665 | 6875622.889 | 502173.2176 | 12860700.6732
4094 | 17942189.3186 | 6093168.7356 | 226136.0124 | 24261494.0666
4095 | 10676616.068 | 6245544.9659 | 35388.1722 | 16957549.206
4096 | 8432927.9468 | 7039585.0874 | 3938374.9287 | 19410887.9628
4097 | 4040495.6533 | 3711705.2007 | 1430174.8911 | 9182375.7451
4098 | 23750603.8097 | 9812742.0886 | 1079147.56 | 34642493.4583
4099 | 8776038.4663 | 5101055.976 | 214054.5558 | 14091148.9981
4100 | 3302317.3842 | 6449658.4322 | 1558448.4593 | 11310424.2758
4101 | 35235313.7784 | 14061179.7728 | 11696434.6499 | 60992928.2011
4102 | 6666418.1279 | 4341044.2203 | 5003908.9752 | 16011371.3234
4103 | 17237120.1697 | 7804726.3368 | 5369478.8877 | 30411325.3941
4104 | 7843223.7992 | 6797895.3118 | 2339428.3234 | 16980547.4343
4105 | 4882567.1716 | 9334986.7442 | 0 | 14217553.9158
4106 | 926072.1408 | 7195384.377 | 556076.9112 | 8677533.429
4107 | 4382436.3977 | 3096462.2161 | 0 | 7478898.6138
4108 | 22244992.3691 | 16292896.236 | 1254448.534 | 39792337.1391
4109 | 22717716.9653 | 7398650.2233 | 1902214.9362 | 32018582.1248
4110 | 5523880.3343 | 6659363.8434 | 1785481.4661 | 13968725.6438
4111 | 12159516.7675 | 3710341.9059 | 1154785.9797 | 17024644.653
4112 | 9576794.423 | 0 | 1331182.6806 | 10907977.1036
4113 | 4397238.9292 | 949815.5658 | 3450442.0984 | 8797496.5934
4114 | 11361854.1807 | 2063935.3436 | 1509383.8213 | 14935173.3455
4115 | 2925020.4489 | 985815.0394 | 3205785.7578 | 7116621.2461
4116 | 15150332.5317 | 2141932.2007 | 10766222.9551 | 28058487.6876
4117 | 5632906.9404 | 3289045.9423 | 9146532.2431 | 18068485.1258
4118 | 8165322.9176 | 4246457.8413 | 1423105.5036 | 13834886.2625
4119 | 7268126.7506 | 2287913.4069 | 2275527.77 | 11831567.9275
4120 | 22503415.5106 | 0 | 1449673.9397 | 23953089.4503
4121 | 3084542.2541 | 11572356.2092 | 710929.2102 | 15367827.6735
4122 | 2241986.7576 | 3467850.9075 | 191639.6884 | 5901477.3534
4123 | 4577508.4291 | 10805351.3286 | 830418.3736 | 16213278.1313
4124 | 7437901.2495 | 9121852.2043 | 811971.2277 | 17371724.6815
4125 | 5939544.1562 | 26125163.9552 | 470695.8643 | 32535403.9757
4126 | 5161643.2076 | 4405802.4862 | 0 | 9567445.6939
4127 | 13236560.4967 | 3905604.8048 | 0 | 17142165.3015
4128 | 4901826.5476 | 0 | 688016.2792 | 5589842.8268
4129 | 3231427.4913 | 6762856.9307 | 234387.9081 | 10228672.3302
4130 | 3169288.8192 | 0 | 2170935.5806 | 5340224.3998
4131 | 3287766.7605 | 7931989.1521 | 2837445.3503 | 14057201.263
4132 | 7705964.9802 | 0 | 457953.8144 | 8163918.7945
4133 | 723102.4104 | 0 | 71417.8166 | 794520.2269
4134 | 9554759.8403 | 4225386.5024 | 1662153.4268 | 15442299.7695
4135 | 7238929.1749 | 1263893.3974 | 0 | 8502822.5723
4136 | 4262161.2004 | 27661933.0979 | 1552754.547 | 33476848.8453
4137 | 3992079.6818 | 4406812.8648 | 788614.948 | 9187507.4946
4138 | 2552367.9911 | 0 | 0 | 2552367.9911
4139 | 11610295.4395 | 1972349.7802 | 658880.3067 | 14241525.5265
4140 | 23367720.4988 | 9617361.0532 | 404491.4131 | 33389572.9651
4141 | 8659257.2123 | 3188772.7208 | 663495.9321 | 12511525.8652
4142 | 3846638.7608 | 13939635.8685 | 2074869.0366 | 19861143.6659
4143 | 605985.5057 | 0 | 3812021.5316 | 4418007.0373
4144 | 1567012.7273 | 19976777.76 | 487025.5582 | 22030816.0456
4145 | 18580106.4822 | 0 | 2079045.2556 | 20659151.7378
4146 | 10392150.7111 | 0 | 903863.0174 | 11296013.7285
4147 | 18490535.4174 | 5907251.3849 | 0 | 24397786.8023
4148 | 6210308.0443 | 5162774.3524 | 1175345.7161 | 12548428.1129
4149 | 17196340.5384 | 12541427.0664 | 5654774.2924 | 35392541.8973
4150 | 31011270.4813 | 1618375.6412 | 535917.3858 | 33165563.5082
4151 | 7030770.5652 | 5955388.6792 | 0 | 12986159.2444
4152 | 3276965.9797 | 1128138.1822 | 2899937.0363 | 7305041.1981
4153 | 14756434.7741 | 3782949.4361 | 2874508.2992 | 21413892.5094
4154 | 0 | 7404417.7934 | 3023955.4802 | 10428373.2736
4155 | 3519290.4075 | 0 | 894828.8371 | 4414119.2446
4156 | 2121326.6227 | 6890284.6834 | 1140569.6935 | 10152180.9995
4157 | 2724036.6917 | 2266203.3251 | 2161853.9785 | 7152093.9953
4158 | 2429039.1068 | 7438957.0025 | 44144.7799 | 9912140.8892
4159 | 1584148.339 | 0 | 124827.5597 | 1708975.8987
4160 | 14040384.4557 | 7007700.9131 | 7244.3182 | 21055329.6869
4161 | 1461406.8011 | 15998275.0644 | 0 | 17459681.8655
4162 | 17166633.1043 | 6466161.4545 | 836407.5621 | 24469202.1209
4163 | 3089257.6081 | 7736131.9707 | 11638889.3862 | 22464278.965
4164 | 11248723.3168 | 8841716.2412 | 262674.3583 | 20353113.9163
4165 | 1216528.0596 | 3778543.1211 | 420238.5104 | 5415309.6911
4166 | 6853531.664 | 7405313.576 | 0 | 14258845.24
4167 | 1579958.5795 | 2848047.3616 | 1822415.0946 | 6250421.0357
4168 | 22417914.152 | 6216057.9518 | 368778.7199 | 29002750.8238
4169 | 6106038.901 | 15547077.959 | 0 | 21653116.8601
4170 | 2818123.5312 | 0 | 946108.2893 | 3764231.8204
4171 | 9685845.0324 | 0 | 0 | 9685845.0324
4172 | 3558273.5117 | 5228682.188 | 1073760.3485 | 9860716.0482
4173 | 13159913.3662 | 3354490.4699 | 375508.8745 | 16889912.7106
4174 | 3534854.5549 | 9272921.9924 | 10336070.5909 | 23143847.1383
4175 | 16460334.8464 | 8987144.6247 | 68629.3983 | 25516108.8695
4176 | 2355643.8724 | 2925721.6631 | 0 | 5281365.5355
4177 | 9554945.7016 | 3650628.2974 | 10386514.9219 | 23592088.9209
4178 | 927065.332 | 0 | 191969.8497 | 1119035.1817
4179 | 14034122.3335 | 644741.771 | 1468946.9577 | 16147811.0622
4180 | 2441983.9867 | 6012152.0332 | 217890.833 | 8672026.8529
4181 | 30735676.1835 | 15981526.7152 | 478441.0388 | 47195643.9374
4182 | 6533951.8929 | 5118915.489 | 799752.2588 | 12452619.6406
4183 | 3276970.7773 | 6435386.7494 | 2835461.1002 | 12547818.6269
4184 | 3287945.4089 | 4064316.7962 | 846144.0823 | 8198406.2874
4185 | 5539612.844 | 13572744.2664 | 907837.3044 | 20020194.4148
4186 | 4638620.0146 | 14564496.2147 | 1977505.8974 | 21180622.1267
4187 | 9702095.7143 | 2904470.7789 | 0 | 12606566.4932
4188 | 1365816.0909 | 2399021.4498 | 0 | 3764837.5407
4189 | 4339672.3688 | 5927580.0563 | 2828518.1461 | 13095770.5712
4190 | 3556358.8623 | 1098195.2573 | 0 | 4654554.1196
4191 | 4783160.3853 | 4886387.7784 | 0 | 9669548.1637
4192 | 8194321.7764 | 2220457.6172 | 11550094.8124 | 21964874.206
4193 | 13779327.6911 | 4773314.4494 | 1021798.6561 | 19574440.7967
4194 | 21986970.0716 | 8429737.2523 | 858019.2084 | 31274726.5322
4195 | 6155350.7834 | 2822290.8439 | 0 | 8977641.6274
4196 | 16434147.1388 | 1459657.7544 | 393710.3961 | 18287515.2893
4197 | 16191786.5213 | 4404362.1599 | 4278551.6085 | 24874700.2897
4198 | 14406188.2921 | 24202439.2468 | 2231837.8282 | 40840465.3671
4199 | 4977930.5501 | 6486691.9809 | 492727.1534 | 11957349.6844
4200 | 4861605.3707 | 4710242.4652 | 0 | 9571847.8359
4201 | 4059086.0476 | 751909.4875 | 0 | 4810995.535
4202 | 16810580.5123 | 5584607.3156 | 864480.09 | 23259667.9178
4203 | 6338108.3611 | 7307978.0197 | 8919162.9004 | 22565249.2812
4204 | 10633751.7519 | 7245386.4548 | 254975.2536 | 18134113.4602
4205 | 3782061.5282 | 9919619.5548 | 8730347.0459 | 22432028.1289
4206 | 8657665.1852 | 4546902.9422 | 147213.8246 | 13351781.9521
4207 | 2275468.9862 | 1339930.2857 | 44210.9367 | 3659610.2086
4208 | 4191375.0892 | 3014920.4541 | 0 | 7206295.5434
4209 | 13170835.3898 | 7479538.5712 | 3691656.5528 | 24342030.5138
4210 | 5834251.4506 | 13595731.47 | 13174127.3828 | 32604110.3035
4211 | 10804696.3405 | 5403081.798 | 89007.17 | 16296785.3084
4212 | 3928826.3122 | 7630022.1983 | 0 | 11558848.5105
4213 | 13179770.0053 | 5280793.7087 | 347904.909 | 18808468.623
4214 | 620541.2554 | 10471447.3724 | 1444970.5105 | 12536959.1383
4215 | 2355787.1 | 0 | 2140524.0509 | 4496311.1508
4216 | 10068645.3363 | 4523315.1477 | 0 | 14591960.484
4217 | 7661613.2939 | 2000714.5814 | 1822256.6485 | 11484584.5238
4218 | 2376389.5253 | 698333.6723 | 4951115.8139 | 8025839.0116
4219 | 12294737.755 | 14542089.8988 | 125506.4077 | 26962334.0615
4220 | 7608268.7806 | 2987575.3515 | 429202.6418 | 11025046.7738
4221 | 12526872.8218 | 38142612.9732 | 750906.0379 | 51420391.8329
4222 | 13749805.2131 | 429329.47 | 0 | 14179134.6831
4223 | 27011844.8021 | 0 | 3193277.4137 | 30205122.2158
4224 | 35660220.0746 | 33843571.8618 | 1733670.412 | 71237462.3484
4225 | 5150449.9013 | 0 | 1367451.6751 | 6517901.5764
4226 | 32361138.2288 | 14596177.0141 | 1445006.5436 | 48402321.7865
4227 | 4436744.8209 | 1473625.9417 | 254167.4589 | 6164538.2216
4228 | 22841202.8426 | 779427.1066 | 0 | 23620629.9492
4229 | 8164730.1063 | 0 | 368441.6281 | 8533171.7344
4230 | 3938568.0936 | 22569052.7679 | 3370454.7571 | 29878075.6186
4231 | 7015132.123 | 3300244.3742 | 0 | 10315376.4972
4232 | 5000508.4205 | 4808432.0195 | 823204.0544 | 10632144.4945
4233 | 9901660.5118 | 10866906.0199 | 3016773.4501 | 23785339.9818
4234 | 5625215.7114 | 16104265.617 | 4534995.4017 | 26264476.7301
4235 | 2923365.0323 | 2225500.9251 | 0 | 5148865.9574
4236 | 3929555.0721 | 14039548.461 | 0 | 17969103.5331
4237 | 2989183.8583 | 5565826.4064 | 0 | 8555010.2648
4238 | 11654365.1951 | 1728973.3168 | 0 | 13383338.5119
4239 | 15500158.5629 | 2135979.608 | 1863814.9325 | 19499953.1034
4240 | 1719532.0773 | 6610979.6867 | 175319.8368 | 8505831.6008
4241 | 4068848.462 | 5587338.1723 | 1501529.8882 | 11157716.5225
4242 | 8838320.3828 | 8461263.8807 | 5793920.0793 | 23093504.3427
4243 | 14518251.1648 | 3968568.291 | 2205738.5927 | 20692558.0484
4244 | 9472013.439 | 4717248.5939 | 1300177.5327 | 15489439.5656
4245 | 7155193.9683 | 3846310.1944 | 104558.9738 | 11106063.1364
4246 | 8689867.809 | 16279548.9579 | 1238108.6658 | 26207525.4327
4247 | 5856870.2449 | 23111408.2218 | 2271324.6214 | 31239603.0881
4248 | 915225.9676 | 11245082.8668 | 50077.8404 | 12210386.6748
4249 | 27294968.2679 | 5728273.546 | 18527442.9919 | 51550684.8058
4250 | 4716054.1451 | 3484858.0765 | 2951811.7206 | 11152723.9422
4251 | 6292993.1222 | 0 | 190274.5336 | 6483267.6558
4252 | 11990699.4531 | 0 | 213376.647 | 12204076.1
4253 | 6989511.2968 | 580011.8875 | 2788481.2871 | 10358004.4714
4254 | 16178956.7548 | 6009377.8771 | 1972938.0378 | 24161272.6696
4255 | 3064501.4701 | 9908299.5863 | 3027845.2819 | 16000646.3383
4256 | 8154684.2383 | 6497752.4679 | 1560741.0143 | 16213177.7204
4257 | 3834324.2997 | 1473169.8278 | 0 | 5307494.1274
4258 | 11548020.7007 | 2221996.5504 | 2336224.4767 | 16106241.7278
4259 | 11622659.6928 | 4599759.5433 | 4900645.028 | 21123064.2641
4260 | 6515226.78 | 12005205.3872 | 3340922.7085 | 21861354.8757
4261 | 28885904.9158 | 4447509.9584 | 310606.3748 | 33644021.2491
4262 | 5900445.0505 | 1326912.5422 | 1492584.3159 | 8719941.9086
4263 | 4665745.0677 | 18237285.3331 | 0 | 22903030.4008
4264 | 26332777.2337 | 0 | 234065.9654 | 26566843.1991
4265 | 8455490.4983 | 18195547.5639 | 1382298.0678 | 28033336.1301
4266 | 1956162.8871 | 24733284.6005 | 443677.2967 | 27133124.7844
4267 | 5305840.9783 | 2889548.9965 | 594507.1464 | 8789897.1212
4268 | 3452751.0228 | 13528944.6796 | 744041.2769 | 17725736.9794
4269 | 381636.5035 | 6554589.2208 | 7689140.4188 | 14625366.1431
4270 | 4294918.1028 | 3039724.2931 | 276914.3106 | 7611556.7065
4271 | 8635567.586 | 5550467.8358 | 753231.5736 | 14939266.9954
4272 | 14404312.9375 | 28627979.1218 | 1142811.9963 | 44175104.0555
4273 | 7558231.9709 | 31023216.9339 | 9489999.8827 | 48071448.7875
4274 | 1124852.5889 | 1180901.758 | 0 | 2305754.3469
4275 | 3637399.5076 | 8954711.2754 | 917270.1763 | 13509380.9593
4276 | 11963991.9849 | 4266005.5003 | 7173227.5086 | 23403224.9938
4277 | 3111528.3211 | 0 | 854784.8741 | 3966313.1952
4278 | 9134754.4947 | 13452545.5594 | 328924.9043 | 22916224.9584
4279 | 7175029.0733 | 2216229.7755 | 4749963.8844 | 14141222.7332
4280 | 8526999.6131 | 4979850.8491 | 1253606.037 | 14760456.4992
4281 | 11376199.7909 | 20366289.6022 | 331551.5645 | 32074040.9576
4282 | 12516996.2189 | 4808399.9076 | 0 | 17325396.1265
4283 | 10261118.4819 | 52593378.7641 | 1599839.4763 | 64454336.7224
4284 | 6746267.1074 | 0 | 1165053.8106 | 7911320.9181
4285 | 604446.8225 | 13680883.6684 | 386114.7872 | 14671445.2781
4286 | 13245191.2631 | 7112879.946 | 0 | 20358071.2091
4287 | 6258715.5571 | 13958513.5184 | 54195.9046 | 20271424.9801
4288 | 1655965.6519 | 3334377.8729 | 0 | 4990343.5248
4289 | 7617934.7413 | 3610122.3637 | 174133.3444 | 11402190.4494
4290 | 13713505.8167 | 3000754.4405 | 1920940.3896 | 18635200.6468
4291 | 20683676.0186 | 16130809.9112 | 27989776.1849 | 64804262.1147
4292 | 6639329.5256 | 23944270.0467 | 0 | 30583599.5724
4293 | 4145463.0347 | 0 | 0 | 4145463.0347
4294 | 6049899.2692 | 24442213.2917 | 0 | 30492112.5609
4295 | 1172091.0579 | 4626516.9001 | 672995.6883 | 6471603.6463
4296 | 6696313.6933 | 18658605.8373 | 94836.6501 | 25449756.1807
4297 | 3217633.7208 | 27674851.2261 | 0 | 30892484.947
4298 | 11565107.6744 | 2163873.0032 | 15965.0857 | 13744945.7634
4299 | 4712739.7272 | 56576723.6403 | 0 | 61289463.3675
4300 | 12057237.4052 | 17214467.5541 | 2853008.0616 | 32124713.021
4301 | 3932006.7399 | 22182809.5867 | 3315729.4225 | 29430545.7491
4302 | 11835243.21 | 9824503.7528 | 1805691.0274 | 23465437.9903
4303 | 1895991.7666 | 0 | 0 | 1895991.7666
4304 | 14261957.8723 | 0 | 6449804.5763 | 20711762.4486
4305 | 7279859.3886 | 12043670.2419 | 9868459.6402 | 29191989.2707
4306 | 8526237.6745 | 5024031.891 | 126342.8907 | 13676612.4562
4307 | 8275811.1339 | 3725831.2513 | 3741431.9796 | 15743074.3649
4308 | 33314912.988 | 18538742.7117 | 0 | 51853655.6997
4309 | 22307136.8094 | 0 | 0 | 22307136.8094
4310 | 14919124.8116 | 4903263.2065 | 352342.1276 | 20174730.1458
4311 | 8113102.7705 | 12079109.2547 | 4487713.3135 | 24679925.3386
4312 | 49338823.8456 | 8035112.5782 | 637966.423 | 58011902.8468
4313 | 20032664.2356 | 6127924.8339 | 98333.7234 | 26258922.7928
4314 | 4883395.616 | 3580801.6541 | 122172.3513 | 8586369.6214
4315 | 13658652.3489 | 0 | 4043122.5341 | 17701774.883
4316 | 16417720.3221 | 0 | 634524.2002 | 17052244.5223
4317 | 12892003.6341 | 609142.8228 | 3678965.3448 | 17180111.8016
4318 | 14626590.8155 | 2295918.9267 | 1074082.6718 | 17996592.414
4319 | 6826037.2051 | 5282756.5077 | 6324732.3831 | 18433526.0959
4320 | 2587444.1523 | 3574239.0127 | 0 | 6161683.165
4321 | 9207500.3751 | 6245265.6838 | 1679320.8566 | 17132086.9156
4322 | 18197061.4723 | 6080057.9908 | 4103802.0492 | 28380921.5123
4323 | 12100037.0832 | 12779077.3146 | 4954965.9176 | 29834080.3155
4324 | 4444182.2131 | 2661330.3019 | 0 | 7105512.515
4325 | 3700457.59 | 13620676.7461 | 9972809.8797 | 27293944.2157
4326 | 11296928.4866 | 20022295.1315 | 2282416.948 | 33601640.5661
4327 | 5263417.7461 | 0 | 2901590.3778 | 8165008.1238
4328 | 4539601.0977 | 0 | 907644.3255 | 5447245.4232
4329 | 149762.9436 | 8668624.8513 | 2374497.7128 | 11192885.5077
4330 | 3244514.3055 | 0 | 706100.4158 | 3950614.7212
4331 | 34542801.1992 | 17496438.6697 | 2506469.2861 | 54545709.155
4332 | 15741816.5744 | 3589615.792 | 15527955.9071 | 34859388.2735
4333 | 8335614.4156 | 0 | 1072984.2361 | 9408598.6517
4334 | 16702237.8891 | 15929875.4957 | 29646.2177 | 32661759.6026
4335 | 6470754.9339 | 11802352.2079 | 214801.5484 | 18487908.6902
4336 | 13859603.9691 | 5932239.4417 | 2487032.618 | 22278876.0288
4337 | 10220398.889 | 10999873.3094 | 749180.846 | 21969453.0444
4338 | 4724081.6854 | 1776582.3502 | 4259577.9739 | 10760242.0095
4339 | 8658182.7533 | 17994621.4339 | 0 | 26652804.1872
4340 | 3118373.5222 | 7207946.3256 | 4008179.0781 | 14334498.9259
4341 | 5768706.2872 | 0 | 1263543.1575 | 7032249.4446
4342 | 2064528.9138 | 6408597.0843 | 3438617.4783 | 11911743.4765
4343 | 7491502.647 | 0 | 12170037.8418 | 19661540.4887
4344 | 26647790.5687 | 10251253.2475 | 1713918.871 | 38612962.6873
4345 | 1872444.3304 | 0 | 0 | 1872444.3304
4346 | 9022557.5029 | 7094026.3511 | 4367027.802 | 20483611.6561
4347 | 4964106.7668 | 2854943.9795 | 1632672.0477 | 9451722.794
4348 | 5031205.2347 | 1726758.0648 | 1790310.3895 | 8548273.6889
4349 | 3978504.8549 | 4878273.9774 | 10674058.8186 | 19530837.651
4350 | 4759409.6501 | 2811038.582 | 3874768.3861 | 11445216.6183
4351 | 8790883.0128 | 14939551.9582 | 900393.4249 | 24630828.396
4352 | 7490801.1464 | 13150009.3427 | 2093686.2343 | 22734496.7235
4353 | 4748859.2094 | 5515284.1891 | 2294091.8576 | 12558235.2561
4354 | 1901236.8652 | 3730153.2994 | 7657218.8155 | 13288608.9801
4355 | 2750659.2012 | 5426016.5079 | 110949.4249 | 8287625.1339
4356 | 2184678.6207 | 0 | 7476990.2893 | 9661668.9101
4357 | 1282802.3921 | 6096528.088 | 1720998.5159 | 9100328.996
4358 | 4998381.0874 | 7181848.817 | 20726896.6655 | 32907126.5699
4359 | 8544505.7802 | 0 | 654547.4902 | 9199053.2704
4360 | 6761192.1073 | 0 | 114832.2493 | 6876024.3566
4361 | 4769254.3952 | 5182849.3922 | 2289480.6135 | 12241584.401
4362 | 11852517.8344 | 0 | 0 | 11852517.8344
4363 | 1710224.5885 | 4106878.5383 | 1102654.9918 | 6919758.1186
4364 | 24250511.8183 | 2413599.4146 | 2634221.8475 | 29298333.0804
4365 | 5789955.3903 | 4956739.4917 | 0 | 10746694.882
4366 | 2524292.1602 | 20054848.6387 | 0 | 22579140.7989
4367 | 18452231.4145 | 1113785.9416 | 334451.0261 | 19900468.3822
4368 | 13318472.1596 | 6726654.6594 | 0 | 20045126.819
4369 | 6040171.3607 | 5644708.3567 | 840457.4186 | 12525337.136
4370 | 587572.0057 | 3059796.9736 | 4551781.5651 | 8199150.5445
4371 | 4290504.9603 | 27472500.5325 | 906480.4767 | 32669485.9695
4372 | 4139353.1774 | 582586.3258 | 2529226.8138 | 7251166.317
4373 | 5186299.1636 | 24169299.4901 | 0 | 29355598.6537
4374 | 16536148.044 | 0 | 13371.9978 | 16549520.0418
4375 | 4003338.3199 | 4711281.1025 | 5237605.7749 | 13952225.1974
4376 | 10568915.6176 | 7070580.5353 | 1718156.7831 | 19357652.9359
4377 | 10429806.3706 | 5464301.4833 | 4281224.8941 | 20175332.748
4378 | 7433071.6647 | 0 | 1961013.1772 | 9394084.842
4379 | 4010649.745 | 8556788.5736 | 104227.7091 | 12671666.0277
4380 | 5881916.3297 | 4490235.6745 | 350916.5635 | 10723068.5677
4381 | 25778822.4243 | 789057.0089 | 728802.8686 | 27296682.3018
4382 | 2020551.8689 | 12836223.3801 | 925775.8857 | 15782551.1347
4383 | 12435052.5808 | 5084056.895 | 0 | 17519109.4758
4384 | 8607875.8466 | 10057109.4941 | 6507641.6811 | 25172627.0218
4385 | 13653626.1203 | 8857962.873 | 4665771.356 | 27177360.3494
4386 | 9161565.0966 | 0 | 462225.5733 | 9623790.6699
4387 | 15395994.2468 | 19473540.4916 | 2296701.2287 | 37166235.9671
4388 | 22795709.8311 | 14733760.4546 | 222556.409 | 37752026.6947
4389 | 6083298.595 | 8450039.5971 | 0 | 14533338.192
4390 | 3759352.7654 | 2119362.8451 | 2199366.5262 | 8078082.1367
4391 | 5033953.0193 | 0 | 2997189.0766 | 8031142.096
4392 | 10140689.5206 | 2712884.4479 | 2005947.4939 | 14859521.4624
4393 | 8432630.0953 | 3998991.5642 | 109502.117 | 12541123.7764
4394 | 7349394.2406 | 5016640.6589 | 9213837.5891 | 21579872.4886
4395 | 2652815.21 | 2239007.1775 | 6349232.1218 | 11241054.5093
4396 | 3435688.4853 | 0 | 1708788.1803 | 5144476.6655
4397 | 4640210.0532 | 0 | 0 | 4640210.0532
4398 | 14011092.4066 | 5267309.8317 | 205919.9848 | 19484322.2231
4399 | 11987210.8026 | 0 | 3973049.1013 | 15960259.9038
4400 | 2619408.4307 | 3914327.1868 | 16139980.7861 | 22673716.4035
4401 | 8768641.951 | 3982105.2438 | 1480352.9066 | 14231100.1015
4402 | 3545242.4456 | 6161033.5047 | 3266667.2506 | 12972943.2009
4403 | 10681338.7254 | 5082704.2138 | 9488100.2599 | 25252143.199
4404 | 4631914.5797 | 4295560.2776 | 384184.1113 | 9311658.9686
4405 | 363583.2446 | 2623139.2429 | 904271.6034 | 3890994.0909
4406 | 1837157.4536 | 25717065.2115 | 90942.6512 | 27645165.3163
4407 | 11452853.0869 | 8153782.6422 | 0 | 19606635.7291
4408 | 9566424.5945 | 5830427.9255 | 142404.1595 | 15539256.6796
4409 | 5820192.1971 | 21448511.5763 | 636113.1624 | 27904816.9358
4410 | 9572156.8935 | 25027842.8451 | 12960012.0428 | 47560011.7814
4411 | 251068.5587 | 15306070.2473 | 937636.2701 | 16494775.0761
4412 | 6655427.7058 | 5696408.8791 | 22607396.9656 | 34959233.5505
4413 | 8998428.9216 | 11006662.3656 | 14838377.716 | 34843469.0032
4414 | 9283178.1589 | 16241764.2164 | 7001063.3806 | 32526005.7558
4415 | 8007854.6709 | 3633304.5882 | 4082817.4081 | 15723976.6671
4416 | 10329510.3427 | 4477179.5065 | 0 | 14806689.8492
4417 | 31429608.4984 | 979788.3101 | 5665629.8012 | 38075026.6097
4418 | 10535663.4789 | 2411718.2789 | 371049.5698 | 13318431.3276
4419 | 1512747.7078 | 4480894.5877 | 0 | 5993642.2955
4420 | 3231657.8469 | 6715084.6062 | 241500.4624 | 10188242.9154
4421 | 19580870.0089 | 0 | 0 | 19580870.0089
4422 | 17456981.0957 | 3398159.3967 | 1238563.2464 | 22093703.7388
4423 | 7108192.8592 | 8923609.0308 | 553372.6996 | 16585174.5897
4424 | 5363557.2225 | 5667201.4832 | 9743936.3523 | 20774695.0581
4425 | 6729059.4038 | 18111832.7235 | 54021.4198 | 24894913.5471
4426 | 3993258.4244 | 5087995.9733 | 5038522.1476 | 14119776.5453
4427 | 11706109.5262 | 0 | 17831267.114 | 29537376.6402
4428 | 5855928.7437 | 14047624.1925 | 387942.9025 | 20291495.8387
4429 | 10514490.819 | 5910985.9243 | 131927.4458 | 16557404.1892
4430 | 4487049.7874 | 0 | 621893.6837 | 5108943.4711
4431 | 10441699.7528 | 5988289.3736 | 0 | 16429989.1263
4432 | 3060752.9529 | 0 | 3767928.0604 | 6828681.0133
4433 | 15466578.9076 | 9506446.0167 | 126057.7377 | 25099082.662
4434 | 2527094.6991 | 8746498.1681 | 4834223.5568 | 16107816.4241
4435 | 3254172.7723 | 7353793.1171 | 0 | 10607965.8894
4436 | 7430267.6284 | 925286.7245 | 565821.5509 | 8921375.9038
4437 | 14945789.6102 | 6366468.8132 | 0 | 21312258.4235
4438 | 5060469.4927 | 2780589.8359 | 883086.2482 | 8724145.5769
4439 | 2812063.1442 | 2300569.7689 | 0 | 5112632.9131
4440 | 461819.9892 | 3963923.3854 | 12622374.7944 | 17048118.169
4441 | 6989372.9246 | 15331177.2655 | 788076.0155 | 23108626.2056
4442 | 4102373.4415 | 20574120.8731 | 1496130.8364 | 26172625.1511
4443 | 22649975.166 | 9275589.7838 | 2918152.7764 | 34843717.7262
4444 | 6489295.1304 | 12505280.1718 | 1221019.4351 | 20215594.7373
4445 | 41525159.3062 | 1979520.6069 | 7320073.1528 | 50824753.0659
4446 | 9555593.88 | 1795846.4321 | 969714.2726 | 12321154.5847
4447 | 5877175.9164 | 2674127.6963 | 780625.9609 | 9331929.5736
4448 | 3122188.4037 | 0 | 4842353.6134 | 7964542.0171
4449 | 19272783.3388 | 2581022.2627 | 25928.0478 | 21879733.6492
4450 | 29590464.087 | 6338919.0183 | 11106757.5757 | 47036140.681
4451 | 7373586.4017 | 5238251.9612 | 827283.722 | 13439122.0849
4452 | 69505.131 | 27025873.846 | 75380.365 | 27170759.3421
4453 | 8309463.492 | 3446665.4389 | 0 | 11756128.9309
4454 | 4046019.1168 | 0 | 80833.1425 | 4126852.2593
4455 | 1473071.6284 | 5793599.5145 | 480017.5951 | 7746688.738
4456 | 3911840.3874 | 0 | 4239205.5189 | 8151045.9064
4457 | 12061054.1401 | 17661728.5926 | 0 | 29722782.7327
4458 | 4791820.5623 | 7499590.0483 | 2269820.9331 | 14561231.5436
4459 | 1346611.8116 | 15399252.4934 | 5418887.9927 | 22164752.2976
4460 | 6169807.7119 | 7063332.2444 | 1992120.9735 | 15225260.9298
4461 | 6179015.1991 | 4120519.2577 | 1936090.4808 | 12235624.9376
4462 | 6431266.6188 | 0 | 938376.0969 | 7369642.7157
4463 | 3704260.2974 | 23912035.6147 | 2712702.0752 | 30328997.9872
4464 | 12917504.3551 | 0 | 1929384.0562 | 14846888.4113
4465 | 944955.6576 | 0 | 3602635.8095 | 4547591.4671
4466 | 4127180.5719 | 14746445.8616 | 108211.7026 | 18981838.1361
4467 | 7532638.1543 | 3482749.0307 | 1448162.0375 | 12463549.2225
4468 | 1897320.0143 | 1052555.4311 | 907620.1053 | 3857495.5507
4469 | 3980871.5784 | 6817875.39 | 9300232.5178 | 20098979.4861
4470 | 33298334.7222 | 7605010.7197 | 471917.4579 | 41375262.8998
4471 | 4819729.9458 | 0 | 103847.4608 | 4923577.4066
4472 | 7780104.3853 | 0 | 112722.6714 | 7892827.0567
4473 | 10984995.4287 | 6060182.432 | 3624044.2962 | 20669222.1569
4474 | 7352705.3725 | 5606365.2002 | 578431.6079 | 13537502.1806
4475 | 5871935.0307 | 5384358.7147 | 2055715.3301 | 13312009.0755
4476 | 55832054.4935 | 11856423.2438 | 5720672.8046 | 73409150.542
4477 | 6096038.7258 | 4484304.5981 | 460729.2322 | 11041072.5561
4478 | 2623315.1519 | 7331609.1507 | 1534054.4096 | 11488978.7121
4479 | 3517466.9589 | 7486853.8478 | 2020124.2393 | 13024445.046
4480 | 4576479.818 | 1905592.7853 | 17978645.4805 | 24460718.0838
4481 | 6811804.6759 | 6769277.0702 | 0 | 13581081.7462
4482 | 7529683.6929 | 24411828.9703 | 1190983.8077 | 33132496.4709
4483 | 8754185.2665 | 9966715.5616 | 566902.5055 | 19287803.3336
4484 | 39352008.1964 | 50009774.6736 | 1865978.1919 | 91227761.0619
4485 | 216716.4363 | 11435439.6885 | 17479275.2399 | 29131431.3647
4486 | 0 | 310032.0341 | 3299896.1304 | 3609928.1645
4487 | 15407332.6864 | 507042.627 | 3226036.6596 | 19140411.973
4488 | 20041817.9569 | 2880125.0264 | 0 | 22921942.9833
4489 | 29225424.9666 | 55163503.1873 | 354045.0813 | 84742973.2352
4490 | 11835893.141 | 4753749.2945 | 440388.4809 | 17030030.9164
4491 | 8427937.2982 | 4758236.6453 | 0 | 13186173.9435
4492 | 10312902.682 | 6248808.3468 | 1978774.3053 | 18540485.3341
4493 | 2399495.5164 | 15503081.3874 | 2542410.1118 | 20444987.0156
4494 | 7492996.2577 | 5838729.3734 | 2852058.5461 | 16183784.1772
4495 | 28329497.7217 | 1639792.6877 | 1816100.104 | 31785390.5134
4496 | 2103824.6303 | 12391481.9428 | 11954205.4472 | 26449512.0203
4497 | 7363697.8387 | 15028653.0417 | 799275.0763 | 23191625.9567
4498 | 11877916.9807 | 4469902.854 | 1304931.0748 | 17652750.9096
4499 | 9808824.4857 | 7205038.299 | 78817.5852 | 17092680.37
4500 | 1188775.2043 | 3942297.2966 | 1025723.3034 | 6156795.8043
4501 | 12176451.4634 | 2228898.9757 | 9196446.2301 | 23601796.6692
4502 | 6938603.4163 | 0 | 297340.9126 | 7235944.3288
4503 | 7671072.0431 | 2185895.2464 | 2998284.0229 | 12855251.3123
4504 | 1340500.7462 | 2001272.354 | 6919890.1357 | 10261663.2359
4505 | 2335763.1387 | 3152648.8379 | 1235052.7215 | 6723464.6981
4506 | 12245013.9268 | 1302102.2822 | 1690184.009 | 15237300.2179
4507 | 8150405.2226 | 10588334.1954 | 168604.7498 | 18907344.1678
4508 | 18004037.8235 | 14944232.8971 | 266208.7027 | 33214479.4233
4509 | 26576177.3513 | 1167884.977 | 102350.6812 | 27846413.0095
4510 | 2635750.204 | 3244187.1392 | 1770266.4209 | 7650203.764
4511 | 3316363.5278 | 5399576.4226 | 60846.8975 | 8776786.8479
4512 | 2849136.3499 | 15695414.5155 | 4486687.5122 | 23031238.3776
4513 | 16816619.4002 | 3923744.0198 | 2436249.5863 | 23176613.0063
4514 | 126988.5955 | 10712019.3365 | 1140237.9656 | 11979245.8976
4515 | 6987981.8901 | 9264180.257 | 0 | 16252162.1472
4516 | 1821255.3354 | 0 | 1743256.718 | 3564512.0534
4517 | 13939379.5829 | 2467972.754 | 5811038.3069 | 22218390.6438
4518 | 2199424.2396 | 2775271.9857 | 1668836.2815 | 6643532.5069
4519 | 5738583.4705 | 1132779.5568 | 1660904.4887 | 8532267.516
4520 | 5113892.5654 | 13159561.6622 | 18283492.237 | 36556946.4646
4521 | 3672622.0489 | 4136620.6256 | 2062240.3679 | 9871483.0424
4522 | 9866692.8042 | 1493229.8482 | 0 | 11359922.6523
4523 | 12189021.6749 | 12418935.6209 | 13349234.306 | 37957191.6018
4524 | 15271878.1648 | 6818966.5947 | 6199118.4807 | 28289963.2402
4525 | 18069454.2182 | 13633239.9121 | 6307788.2575 | 38010482.3878
4526 | 374517.2658 | 3543688.8837 | 3910949.2057 | 7829155.3553
4527 | 2391275.716 | 2449935.6476 | 450995.9389 | 5292207.3024
4528 | 24252174.0823 | 21170465.6231 | 416281.7244 | 45838921.4299
4529 | 17265698.4989 | 16941569.1632 | 0 | 34207267.6621
4530 | 2051425.631 | 0 | 2609102.2297 | 4660527.8607
4531 | 57599298.8874 | 5712653.1193 | 1015300.8989 | 64327252.9057
4532 | 7175099.3479 | 4117834.8773 | 17797214.7542 | 29090148.9794
4533 | 9565049.6702 | 10054017.7522 | 14200641.4247 | 33819708.8471
4534 | 6169549.3153 | 8042422.2579 | 1231517.8161 | 15443489.3893
4535 | 7316243.5265 | 7957603.561 | 330672.4223 | 15604519.5098
4536 | 5752747.3127 | 10179324.4849 | 20480665.2357 | 36412737.0334
4537 | 12705936.0954 | 10532560.4302 | 2354261.2744 | 25592757.8
4538 | 10002260.8929 | 0 | 37632.6525 | 10039893.5454
4539 | 25812948.5633 | 13698964.9584 | 0 | 39511913.5217
4540 | 10988696.6258 | 0 | 0 | 10988696.6258
4541 | 8131428.713 | 15922678.8497 | 0 | 24054107.5627
4542 | 6783202.9882 | 7651224.6877 | 12504184.2422 | 26938611.918
4543 | 5744404.7753 | 0 | 443342.877 | 6187747.6523
4544 | 2402143.6478 | 6092508.6247 | 0 | 8494652.2724
4545 | 4860913.3332 | 0 | 0 | 4860913.3332
4546 | 7530617.8838 | 193576.7929 | 0 | 7724194.6767
4547 | 15019343.8008 | 14996991.3137 | 3826768.5513 | 33843103.6658
4548 | 17804058.2659 | 5998587.8665 | 5445843.7824 | 29248489.9148
4549 | 4509618.4597 | 2505441.1314 | 136661.8681 | 7151721.4593
4550 | 5760369.8538 | 12207692.7347 | 0 | 17968062.5884
4551 | 15470987.6501 | 10695457.7522 | 30756.965 | 26197202.3673
4552 | 17988971.4155 | 13149181.6282 | 129960.0437 | 31268113.0874
4553 | 9339955.691 | 40233444.8615 | 9415706.6293 | 58989107.1819
4554 | 25219171.3983 | 2002481.5525 | 423770.7225 | 27645423.6733
4555 | 2336663.4858 | 0 | 2058392.6898 | 4395056.1756
4556 | 15520265.6993 | 2897598.0601 | 177032.8465 | 18594896.6059
4557 | 682614.4647 | 0 | 276605.5807 | 959220.0454
4558 | 8973603.2187 | 28882407.8829 | 564704.156 | 38420715.2576
4559 | 5352132.7323 | 0 | 2886486.3999 | 8238619.1322
4560 | 12065415.1638 | 3704640.5858 | 209243.7602 | 15979299.5098
4561 | 5395269.1933 | 7917319.9913 | 2949889.2327 | 16262478.4173
4562 | 5781159.0191 | 1977082.858 | 206675.8093 | 7964917.6864
4563 | 2087318.5456 | 5274324.3186 | 1395160.3933 | 8756803.2574
4564 | 4879887.4977 | 0 | 2135218.6759 | 7015106.1735
4565 | 14807186.0112 | 7693968.1885 | 1400903.2345 | 23902057.4341
4566 | 6342875.2971 | 5837521.4819 | 139853.1394 | 12320249.9184
4567 | 9728213.6026 | 2995257.6726 | 1566796.5126 | 14290267.7878
4568 | 9520902.0556 | 11621116.6171 | 0 | 21142018.6727
4569 | 5217364.1635 | 14245802.5023 | 996127.1581 | 20459293.8239
4570 | 7480761.6911 | 8663240.1555 | 787046.3471 | 16931048.1936
4571 | 3041864.9773 | 6088824.5225 | 966711.3603 | 10097400.8601
4572 | 261670.0573 | 3806509.1814 | 503874.9805 | 4572054.2191
4573 | 8106201.0854 | 13772068.0911 | 233781.5522 | 22112050.7287
4574 | 5586056.206 | 4941674.0671 | 0 | 10527730.2732
4575 | 21504647.0023 | 5395184.6144 | 113351.4142 | 27013183.031
4576 | 6671914.2881 | 21088179.4088 | 1740402.8789 | 29500496.5758
4577 | 13890952.8699 | 8716170.2414 | 1511999.678 | 24119122.7893
4578 | 8851875.2956 | 8756714.5758 | 1646779.7701 | 19255369.6415
4579 | 20176229.9994 | 7455143.5958 | 0 | 27631373.5952
4580 | 10330921.6786 | 6565717.7831 | 199710.3216 | 17096349.7833
4581 | 11963999.9226 | 38995802.1692 | 0 | 50959802.0918
4582 | 11129382.1479 | 11869581.1538 | 3277666.1361 | 26276629.4378
4583 | 5470955.4134 | 2374929.7253 | 639629.5185 | 8485514.6572
4584 | 26031295.5816 | 6710054.1914 | 310285.3338 | 33051635.1068
4585 | 1813337.4157 | 6001970.5358 | 0 | 7815307.9515
4586 | 9169597.2321 | 8938314.6235 | 14344415.9574 | 32452327.813
4587 | 15335622.7837 | 6006560.2398 | 2515618.6834 | 23857801.7069
4588 | 8225943.1546 | 0 | 0 | 8225943.1546
4589 | 18772920.1714 | 2687447.495 | 15638152.2084 | 37098519.8748
4590 | 2363429.2368 | 5350286.2144 | 14016.2736 | 7727731.7248
4591 | 5356348.8367 | 1461175.2177 | 2557863.4433 | 9375387.4976
4592 | 5952626.1883 | 0 | 0 | 5952626.1883
4593 | 7338772.5852 | 5386601.1337 | 534682.6756 | 13260056.3945
4594 | 5168648.4177 | 38380816.2506 | 0 | 43549464.6682
4595 | 12516067.3795 | 11646542.6646 | 0 | 24162610.0441
4596 | 24408054.2188 | 9873140.6746 | 70682.7819 | 34351877.6753
4597 | 5761615.8479 | 11127342.8311 | 1290577.9735 | 18179536.6526
4598 | 3796721.841 | 2068820.1392 | 249328.3125 | 6114870.2927
4599 | 5732173.9021 | 0 | 8115693.5753 | 13847867.4774
4600 | 7448180.374 | 11871169.6998 | 3835640.2315 | 23154990.3054
4601 | 3909496.6969 | 15107531.5564 | 5329544.2217 | 24346572.475
4602 | 13145790.2794 | 3686477.2341 | 396772.8301 | 17229040.3436
4603 | 14591730.6189 | 12957023.2532 | 12822286.8286 | 40371040.7007
4604 | 1817453.2788 | 5242716.5927 | 407189.1538 | 7467359.0254
4605 | 8130917.8488 | 8335490.7374 | 37286111.9728 | 53752520.559
4606 | 7817584.0749 | 0 | 0 | 7817584.0749
4607 | 4891285.3104 | 6814929.0112 | 0 | 11706214.3217
4608 | 3292002.8535 | 3185926.8272 | 43164.4572 | 6521094.1379
4609 | 386919.2106 | 0 | 5879220.6991 | 6266139.9096
4610 | 1946090.7053 | 12896925.2184 | 2583712.8443 | 17426728.768
4611 | 2463561.8971 | 9413665.8937 | 1365222.4394 | 13242450.2302
4612 | 9729396.572 | 3234879.5378 | 65265.5697 | 13029541.6795
4613 | 12208801.1299 | 10406966.0355 | 879029.7971 | 23494796.9625
4614 | 4290187.14 | 4181737.2679 | 3033750.2928 | 11505674.7006
4615 | 5715870.9403 | 0 | 2487012.3899 | 8202883.3302
4616 | 4103196.5102 | 3698153.2715 | 525309.3613 | 8326659.143
4617 | 6913476.8181 | 1897714.8226 | 3234056.6215 | 12045248.2622
4618 | 5310147.639 | 2784268.2105 | 10411855.9521 | 18506271.8015
4619 | 3133164.3562 | 11221027.8315 | 885280.2997 | 15239472.4874
4620 | 15829689.6061 | 2107736.0648 | 1178831.6307 | 19116257.3016
4621 | 12019161.8248 | 12612606.2789 | 2396111.9288 | 27027880.0325
4622 | 9683782.4503 | 6529200.0987 | 66746.6733 | 16279729.2223
4623 | 11780803.6976 | 5304843.1676 | 931522.6367 | 18017169.5019
4624 | 14402195.0877 | 19344211.0796 | 0 | 33746406.1673
4625 | 20653422.7435 | 6100862.3831 | 2155750.2669 | 28910035.3935
4626 | 10929569.9444 | 0 | 2412846.7168 | 13342416.6612
4627 | 7074329.5355 | 16345226.5295 | 2216620.1949 | 25636176.2598
4628 | 27454687.9418 | 3057844.6439 | 4196276.4449 | 34708809.0306
4629 | 30550175.663 | 4793154.6906 | 0 | 35343330.3536
4630 | 13033401.5424 | 10730834.6271 | 1665518.4104 | 25429754.5799
4631 | 617276.5397 | 4017558.0038 | 3149901.0483 | 7784735.5918
4632 | 11028645.7244 | 0 | 900234.2804 | 11928880.0048
4633 | 19855556.2886 | 6524356.7952 | 9259105.5822 | 35639018.666
4634 | 2558158.1404 | 4343477.8594 | 20024886.7584 | 26926522.7583
4635 | 28769662.6444 | 613518.5612 | 0 | 29383181.2056
4636 | 9569489.2546 | 3052659.8162 | 3789880.9818 | 16412030.0526
4637 | 13467918.1972 | 903197.422 | 0 | 14371115.6192
4638 | 3871815.3624 | 13080449.3696 | 226088.8137 | 17178353.5457
4639 | 2440746.0375 | 11332196.4977 | 0 | 13772942.5352
4640 | 11433320.3257 | 23672728.7731 | 868240.5117 | 35974289.6105
4641 | 9118293.5181 | 7843085.6672 | 4482995.6164 | 21444374.8017
4642 | 3143903.8086 | 4204474.0279 | 1931455.779 | 9279833.6155
4643 | 34254376.1967 | 0 | 388602.5178 | 34642978.7145
4644 | 7901823.6677 | 2007163.8801 | 3343768.7713 | 13252756.3191
4645 | 2232007.8607 | 4910545.6277 | 2966620.5311 | 10109174.0195
4646 | 10984043.462 | 1926427.987 | 1515041.3175 | 14425512.7666
4647 | 653370.0339 | 4963683.9946 | 297012.0783 | 5914066.1067
4648 | 4966291.9089 | 2882179.0086 | 0 | 7848470.9174
4649 | 8007819.8094 | 13490340.9058 | 1082013.8171 | 22580174.5323
4650 | 3326008.8471 | 3650045.2747 | 4510719.4276 | 11486773.5494
4651 | 2473025.1726 | 16436292.1635 | 147191.5886 | 19056508.9247
4652 | 2258834.557 | 2889027.6094 | 1341384.8544 | 6489247.0208
4653 | 14258972.773 | 7037959.2446 | 72152.3838 | 21369084.4014
4654 | 18237466.6758 | 7260699.0666 | 3114080.3798 | 28612246.1222
4655 | 7979764.9077 | 0 | 12802844.0302 | 20782608.9379
4656 | 9035308.0761 | 10424701.8313 | 1115850.3256 | 20575860.233
4657 | 8170557.6641 | 5536691.4268 | 3801677.5105 | 17508926.6014
4658 | 11525797.5729 | 8554609.372 | 5936990.2627 | 26017397.2076
4659 | 8107752.4396 | 4756661.2179 | 174480.5434 | 13038894.2009
4660 | 10699108.1245 | 11120695.1225 | 1828524.3722 | 23648327.6192
4661 | 8398359.5128 | 7225634.3068 | 550475.3735 | 16174469.1931
4662 | 9638290.0539 | 14017309.3074 | 0 | 23655599.3613
4663 | 17709387.6002 | 2931681.3075 | 0 | 20641068.9077
4664 | 1078984.6296 | 67569.1144 | 824512.2595 | 1971066.0034
4665 | 300904.045 | 15968546.9946 | 0 | 16269451.0396
4666 | 3197774.2245 | 0 | 3041718.8575 | 6239493.082
4667 | 4685026.3886 | 2936033.5183 | 697832.5973 | 8318892.5042
4668 | 28507014.7763 | 16048696.0298 | 1196529.9601 | 45752240.7662
4669 | 7911347.1556 | 7852866.2118 | 1913933.5014 | 17678146.8688
4670 | 9228919.0357 | 3782862.4941 | 2209120.0563 | 15220901.5862
4671 | 1980617.1445 | 0 | 839637.7437 | 2820254.8882
4672 | 11780176.6253 | 6156790.7774 | 477612.3388 | 18414579.7415
4673 | 7366220.9046 | 8141606.0133 | 2372107.6824 | 17879934.6003
4674 | 2947422.1181 | 10748069.5446 | 821673.0242 | 14517164.6869
4675 | 30834048.1286 | 1977212.2111 | 2409184.1859 | 35220444.5256
4676 | 8615664.0292 | 7427923.1114 | 542922.2056 | 16586509.3461
4677 | 4844330.543 | 32056912.6667 | 434744.3461 | 37335987.5558
4678 | 6671460.4035 | 23195061.9526 | 316017.447 | 30182539.8031
4679 | 1719540.7117 | 5912447.8658 | 1385700.5446 | 9017689.1221
4680 | 4383659.0013 | 3753606.5182 | 0 | 8137265.5195
4681 | 22680173.5334 | 9133434.696 | 48661.188 | 31862269.4174
4682 | 4127146.8465 | 15056263.4101 | 3460929.3697 | 22644339.6263
4683 | 17249832.7945 | 14406121.7056 | 1644092.9881 | 33300047.4882
4684 | 4261594.8527 | 3885941.1361 | 0 | 8147535.9888
4685 | 12850446.7339 | 4251325.1603 | 0 | 17101771.8942
4686 | 21150671.7408 | 0 | 59755.3047 | 21210427.0455
4687 | 17842284.5337 | 13676258.722 | 902767.9636 | 32421311.2192
4688 | 5508572.4346 | 4659425.1419 | 2842419.9948 | 13010417.5713
4689 | 1981557.9116 | 6643951.1818 | 264255.2354 | 8889764.3288
4690 | 5325105.7785 | 9748141.824 | 554419.7403 | 15627667.3428
4691 | 2383919.2574 | 1778601.9644 | 418415.2455 | 4580936.4672
4692 | 1592894.3641 | 23960486.3282 | 1359538.5689 | 26912919.2613
4693 | 5614445.883 | 16501991.3808 | 3733751.7859 | 25850189.0497
4694 | 2245189.1209 | 9648883.8322 | 1676703.8835 | 13570776.8366
4695 | 599779.8489 | 4069700.5452 | 86528.19 | 4756008.584
4696 | 4707851.9391 | 1557790.8936 | 0 | 6265642.8327
4697 | 2481000.188 | 9390761.0045 | 57294.9288 | 11929056.1213
4698 | 11040300.8765 | 4599338.6973 | 296149.2136 | 15935788.7874
4699 | 3922760.4485 | 7705765.1246 | 0 | 11628525.5731
4700 | 6295378.5324 | 6309304.9284 | 1304995.7847 | 13909679.2455
4701 | 3542498.7341 | 17129782.292 | 0 | 20672281.0261
4702 | 2087435.0437 | 16237202.8437 | 956756.0231 | 19281393.9104
4703 | 17867032.7737 | 12149103.5754 | 1091053.5265 | 31107189.8756
4704 | 9757551.1785 | 15166451.4367 | 118001.0936 | 25042003.7087
4705 | 34795131.5722 | 2209583.0288 | 1979897.0113 | 38984611.6123
4706 | 21353424.1226 | 0 | 146003.9743 | 21499428.097
4707 | 14448131.1667 | 20603981.8623 | 369767.8489 | 35421880.878
4708 | 6044142.2491 | 11949277.2245 | 2358214.8971 | 20351634.3707
4709 | 16486500.0521 | 538871.6221 | 1373371.2737 | 18398742.948
4710 | 16104826.0641 | 2795914.2885 | 570809.5761 | 19471549.9287
4711 | 15670588.3165 | 9000257.6722 | 1606889.1531 | 26277735.1419
4712 | 24762870.6426 | 0 | 17177175.4792 | 41940046.1218
4713 | 9110601.916 | 9891351.5086 | 764705.0821 | 19766658.5066
4714 | 4971494.5918 | 9683336.9224 | 442367.4169 | 15097198.9311
4715 | 8616756.6653 | 6691913.3484 | 3830462.7788 | 19139132.7925
4716 | 10510051.73 | 15309984.2073 | 2059502.1112 | 27879538.0484
4717 | 3526033.9428 | 9957776.1638 | 30207.8278 | 13514017.9343
4718 | 6902897.3519 | 7277465.1527 | 1464782.4465 | 15645144.9512
4719 | 6324606.9148 | 3926527.3399 | 0 | 10251134.2547
4720 | 28842316.2721 | 7343055.9812 | 819846.319 | 37005218.5723
4721 | 20250418.5413 | 5158833.7362 | 91699.3248 | 25500951.6023
4722 | 3782782.3674 | 3988051.4877 | 5242003.7869 | 13012837.642
4723 | 214394.536 | 12245401.5747 | 3394735.344 | 15854531.4547
4724 | 20208942.5757 | 6623735.8428 | 904130.2071 | 27736808.6256
4725 | 1608334.7454 | 0 | 3495158.4486 | 5103493.194
4726 | 5732250.1 | 0 | 0 | 5732250.1
4727 | 14956219.6728 | 12475470.5003 | 833802.1877 | 28265492.3608
4728 | 7979201.1358 | 5130899.8782 | 7536993.2653 | 20647094.2793
4729 | 4483215.0786 | 14277184.3635 | 2301977.7171 | 21062377.1592
4730 | 12410149.3361 | 9239227.5555 | 0 | 21649376.8916
4731 | 15548345.1362 | 9362926.9763 | 87930.2439 | 24999202.3564
4732 | 9166319.8261 | 4929853.2607 | 867880.3805 | 14964053.4674
4733 | 7991435.576 | 6528822.672 | 79617.7675 | 14599876.0154
4734 | 4000699.7844 | 0 | 7987266.5143 | 11987966.2987
4735 | 3604132.7807 | 10679696.4571 | 5786909.248 | 20070738.4858
4736 | 30443132.2201 | 4066039.2871 | 2465660.4978 | 36974832.005
4737 | 2209417.2827 | 8854938.5169 | 1325336.9107 | 12389692.7103
4738 | 7477672.9119 | 14323302.0931 | 1318124.7306 | 23119099.7356
4739 | 24725943.7293 | 0 | 456753.9298 | 25182697.6591
4740 | 1503266.6908 | 3748799.2622 | 7690418.41 | 12942484.3629
4741 | 4475141.6462 | 9162030.0343 | 2043439.0064 | 15680610.6869
4742 | 2547076.5283 | 4369825.4116 | 605154.2774 | 7522056.2173
4743 | 6876891.4025 | 9969268.383 | 1682552.55 | 18528712.3354
4744 | 2607389.1447 | 9967157.1098 | 2930785.106 | 15505331.3605
4745 | 9412831.83 | 21898989.7723 | 7800757.0941 | 39112578.6964
4746 | 4985157.8726 | 8110605.2673 | 15458606.384 | 28554369.5238
4747 | 3284530.6857 | 1521566.1767 | 3247603.1077 | 8053699.97
4748 | 1792746.6855 | 729812.189 | 2446895.2687 | 4969454.1433
4749 | 4338566.3475 | 8431679.7868 | 19235.4361 | 12789481.5704
4750 | 6757480.6784 | 0 | 384544.9378 | 7142025.6162
4751 | 5227578.747 | 11588878.7985 | 1075102.7169 | 17891560.2624
4752 | 5541557.393 | 0 | 807931.9567 | 6349489.3497
4753 | 23642071.4047 | 0 | 3281154.5495 | 26923225.9542
4754 | 4396845.4273 | 6439181.0707 | 0 | 10836026.498
4755 | 6370986.4533 | 5850564.5253 | 4119293.2335 | 16340844.2121
4756 | 11227983.6071 | 3582474.8873 | 1159037.2121 | 15969495.7065
4757 | 1172292.1289 | 6761272.3251 | 5581067.3862 | 13514631.8402
4758 | 2077969.6617 | 0 | 673082.3782 | 2751052.0399
4759 | 9150365.0568 | 19867500.8891 | 7889291.5612 | 36907157.5072
4760 | 13845318.2983 | 4432135.5002 | 474515.2457 | 18751969.0442
4761 | 4332651.4399 | 24999399.1343 | 239930.8244 | 29571981.3986
4762 | 11513893.4849 | 3992404.3003 | 1455299.6572 | 16961597.4424
4763 | 2993682.9103 | 0 | 3333162.0816 | 6326844.9919
4764 | 4407283.9472 | 4838003.9675 | 0 | 9245287.9147
4765 | 27535171.7218 | 19055552.4065 | 286849.9835 | 46877574.1118
4766 | 3721036.3028 | 6655549.6296 | 468720.3342 | 10845306.2666
4767 | 7069837.5467 | 11196243.548 | 2133459.5698 | 20399540.6644
4768 | 10006313.1623 | 13862708.2265 | 0 | 23869021.3889
4769 | 1085035.5816 | 6159821.3143 | 5911069.9078 | 13155926.8037
4770 | 7967229.7185 | 10113807.789 | 0 | 18081037.5075
4771 | 8763082.0751 | 0 | 2285048.5839 | 11048130.659
4772 | 4359988.3574 | 4355112.8487 | 90448.7657 | 8805549.9718
4773 | 26801917.6561 | 0 | 2701289.8966 | 29503207.5527
4774 | 4083376.3098 | 12748011.2759 | 1350817.529 | 18182205.1146
4775 | 3984551.2556 | 4533659.6304 | 914130.7907 | 9432341.6768
4776 | 15564667.4147 | 4043160.7527 | 0 | 19607828.1674
4777 | 5246037.901 | 3088077.1589 | 657648.8424 | 8991763.9022
4778 | 2850047.1292 | 7793951.2088 | 2564347.0822 | 13208345.4202
4779 | 6783510.5004 | 8357843.3735 | 193499.1263 | 15334853.0003
4780 | 7062185.6988 | 21990315.9772 | 339222.6608 | 29391724.3367
4781 | 8453954.63 | 595840.5101 | 1999160.9017 | 11048956.0418
4782 | 1090057.5968 | 2162117.0194 | 836350.199 | 4088524.8153
4783 | 2648042.2352 | 17703534.7933 | 121199.5757 | 20472776.6041
4784 | 2599849.3653 | 6520746.0131 | 1033327.2897 | 10153922.668
4785 | 23651609.2536 | 2014297.7712 | 2354284.592 | 28020191.6168
4786 | 2928536.0262 | 5548080.4091 | 1256843.7192 | 9733460.1544
4787 | 2531359.7212 | 4660118.8706 | 0 | 7191478.5918
4788 | 837886.6307 | 19362671.6694 | 72562.7435 | 20273121.0436
4789 | 3609196.8266 | 11996317.2438 | 146116.0071 | 15751630.0775
4790 | 11412594.1981 | 2950543.9576 | 0 | 14363138.1558
4791 | 2235656.9786 | 7383301.0125 | 11460144.665 | 21079102.6561
4792 | 4521017.0987 | 9045725.5574 | 3838479.6387 | 17405222.2948
4793 | 2266065.2552 | 5519912.743 | 713640.7009 | 8499618.6992
4794 | 15442530.8993 | 1563467.8862 | 331562.6182 | 17337561.4037
4795 | 3285357.1886 | 600896.1075 | 1454150.6885 | 5340403.9845
4796 | 13821350.8967 | 11626693.1659 | 0 | 25448044.0626
4797 | 969204.1103 | 0 | 7568587.9019 | 8537792.0122
4798 | 14689298.6789 | 8156023.2601 | 0 | 22845321.939
4799 | 4459392.9159 | 0 | 2110824.8682 | 6570217.7841
4800 | 15679373.8046 | 0 | 1438326.989 | 17117700.7935
4801 | 214112.2516 | 0 | 300577.9136 | 514690.1652
4802 | 13260008.038 | 16305642.3498 | 0 | 29565650.3878
4803 | 1031841.9427 | 5274065.2341 | 8030375.1148 | 14336282.2916
4804 | 1916889.1788 | 0 | 82607.3283 | 1999496.5072
4805 | 3197415.225 | 1933851.2253 | 710551.9785 | 5841818.4288
4806 | 17560979.2936 | 4528225.9156 | 1008048.1129 | 23097253.322
4807 | 1673117.6145 | 6878828.503 | 0 | 8551946.1175
4808 | 3282426.9885 | 1411271.3063 | 63844.5702 | 4757542.8651
4809 | 6545840.4994 | 2529060.3266 | 0 | 9074900.826
4810 | 2793891.0452 | 10148955.4401 | 0 | 12942846.4853
4811 | 1291790.1433 | 2707043.0193 | 2251754.5532 | 6250587.7158
4812 | 26201367.5699 | 11912202.6893 | 0 | 38113570.2592
4813 | 12875906.0631 | 11373997.4832 | 15296992.8907 | 39546896.437
4814 | 12144223.692 | 15914533.3976 | 384216.6455 | 28442973.7351
4815 | 7516784.5132 | 7039109.1191 | 2237591.4988 | 16793485.131
4816 | 2428277.1366 | 2414557.8283 | 0 | 4842834.965
4817 | 9791177.958 | 5893351.559 | 1579814.3211 | 17264343.8382
4818 | 1491979.4552 | 9454611.6549 | 5754621.3018 | 16701212.4119
4819 | 7987874.8359 | 0 | 1373542.3489 | 9361417.1849
4820 | 9545395.0639 | 13107951.8052 | 15241626.6378 | 37894973.5068
4821 | 1713945.7012 | 0 | 2616648.592 | 4330594.2932
4822 | 3885768.51 | 9273776.5836 | 1214347.5509 | 14373892.6445
4823 | 4733183.632 | 2207947.389 | 2136601.8761 | 9077732.897
4824 | 4492377.5144 | 15697813.564 | 0 | 20190191.0785
4825 | 1987529.2548 | 1937313.5576 | 2053852.4359 | 5978695.2483
4826 | 8718346.9826 | 0 | 0 | 8718346.9826
4827 | 959397.0474 | 13307223.2199 | 3155678.0544 | 17422298.3217
4828 | 3443234.2306 | 0 | 610979.365 | 4054213.5956
4829 | 18493439.1847 | 0 | 208149.2663 | 18701588.4511
4830 | 21109379.1452 | 11221347.6309 | 4077353.6636 | 36408080.4397
4831 | 13647232.7224 | 13179715.6428 | 4150079.1706 | 30977027.5359
4832 | 6268974.4386 | 9457294.2121 | 1188355.8384 | 16914624.4891
4833 | 7772658.1916 | 5195482.9406 | 5236338.4066 | 18204479.5387
4834 | 4867246.4325 | 3670962.0027 | 2716972.4328 | 11255180.868
4835 | 5081299.7016 | 11012639.9685 | 1755010.5507 | 17848950.2207
4836 | 12614044.169 | 6511298.8882 | 20344.6349 | 19145687.6921
4837 | 23091657.102 | 1467858.1831 | 225743.3589 | 24785258.644
4838 | 5762748.7083 | 8956417.9816 | 2906434.8157 | 17625601.5056
4839 | 26839541.808 | 12565179.056 | 4135944.4739 | 43540665.3379
4840 | 3433458.2709 | 990024.814 | 1030178.7948 | 5453661.8798
4841 | 24993206.5791 | 3475769.5219 | 46610.851 | 28515586.9519
4842 | 14240705.127 | 0 | 3088016.5737 | 17328721.7007
4843 | 11484011.2099 | 16426731.2701 | 8259019.163 | 36169761.643
4844 | 2931213.8274 | 3863117.0058 | 2518124.7202 | 9312455.5535
4845 | 16057568.182 | 9513328.3321 | 600692.6715 | 26171589.1856
4846 | 7994418.5732 | 14083844.4819 | 924414.8983 | 23002677.9534
4847 | 3663448.5874 | 4264863.847 | 17970653.3521 | 25898965.7865
4848 | 10136931.6747 | 33401132.0489 | 825639.9033 | 44363703.627
4849 | 4437348.4423 | 10060521.6048 | 0 | 14497870.0471
4850 | 2027029.1288 | 11325474.8485 | 0 | 13352503.9773
4851 | 2574654.4275 | 2188906.2495 | 1364496.893 | 6128057.57
4852 | 10182542.0836 | 3495738.6936 | 2150487.9993 | 15828768.7766
4853 | 4274768.3148 | 3298366.736 | 0 | 7573135.0508
4854 | 3706194.6664 | 8160379.6128 | 1002779.5908 | 12869353.8699
4855 | 3788000.0788 | 1809037.5326 | 2421865.7634 | 8018903.3748
4856 | 12466881.5453 | 8173129.4133 | 820802.4978 | 21460813.4563
4857 | 3958097.2961 | 6592430.566 | 241521.9411 | 10792049.8033
4858 | 7572729.505 | 2522648.9386 | 2778925.8827 | 12874304.3262
4859 | 3846546.8153 | 25737730.4686 | 13835622.0254 | 43419899.3093
4860 | 30198933.4078 | 4531183.2067 | 13859825.1595 | 48589941.774
4861 | 8712041.8602 | 6763732.9953 | 4566629.7613 | 20042404.6168
4862 | 1385912.011 | 0 | 3016850.8007 | 4402762.8117
4863 | 3801249.2276 | 12155358.4478 | 0 | 15956607.6754
4864 | 12476696.2102 | 0 | 69647.0455 | 12546343.2557
4865 | 2686625.3309 | 6659807.8282 | 1696301.2178 | 11042734.3768
4866 | 2559694.9954 | 5364461.6675 | 207542.0273 | 8131698.6902
4867 | 2685732.802 | 2508351.2193 | 1249461.5273 | 6443545.5485
4868 | 7019709.7931 | 4062166.7032 | 961906.1217 | 12043782.618
4869 | 4431169.6684 | 11859562.0998 | 2315813.2122 | 18606544.9803
4870 | 3702651.7151 | 6181280.041 | 3800141.2973 | 13684073.0534
4871 | 3949576.9351 | 3944539.4242 | 107837.0818 | 8001953.4411
4872 | 1909565.9622 | 14173235.1435 | 2860752.9665 | 18943554.0723
4873 | 6058016.2772 | 2458851.6222 | 6262674.1553 | 14779542.0548
4874 | 2356741.3952 | 0 | 5212521.5469 | 7569262.942
4875 | 13476210.8989 | 22357355.8102 | 1351444.3847 | 37185011.0938
4876 | 936670.7074 | 1833830.3776 | 64349.4505 | 2834850.5355
4877 | 2236214.4567 | 4898690.2719 | 2155660.7453 | 9290565.4738
4878 | 6614346.9527 | 143983.2314 | 895599.5725 | 7653929.7567
4879 | 7737132.8106 | 6742221.1943 | 0 | 14479354.0049
4880 | 4293653.693 | 848335.7298 | 1473180.5766 | 6615169.9994
4881 | 6532506.4277 | 17944095.6867 | 996836.4752 | 25473438.5896
4882 | 7124640.806 | 16233763.672 | 0 | 23358404.4779
4883 | 7178751.9725 | 3004000.7018 | 594077.135 | 10776829.8094
4884 | 16579285.2202 | 0 | 214427.8796 | 16793713.0997
4885 | 2589135.779 | 7866876.6744 | 2814397.838 | 13270410.2914
4886 | 5036262.4975 | 1900888.9592 | 295069.6253 | 7232221.082
4887 | 2831051.6375 | 2301256.2133 | 3883014.9875 | 9015322.8383
4888 | 20013048.4527 | 18830881.2707 | 8535350.9798 | 47379280.7032
4889 | 4526593.4841 | 0 | 363732.8762 | 4890326.3603
4890 | 5201191.3257 | 0 | 1824302.2851 | 7025493.6108
4891 | 6154394.6667 | 9734144.5206 | 0 | 15888539.1873
4892 | 5102555.667 | 4022966.2739 | 1311021.2848 | 10436543.2256
4893 | 6077651.1249 | 14288451.478 | 5870910.4621 | 26237013.0651
4894 | 3968966.6803 | 0 | 6371624.4254 | 10340591.1057
4895 | 836036.5453 | 17512704.8454 | 1631650.2897 | 19980391.6803
4896 | 6884364.5041 | 4066567.4985 | 1329107.1885 | 12280039.191
4897 | 3266076.2598 | 0 | 3394406.8958 | 6660483.1556
4898 | 4811978.3669 | 5447549.904 | 5273710.1979 | 15533238.4689
4899 | 5063322.2398 | 5868689.8746 | 71107.8546 | 11003119.969
4900 | 21009989.251 | 2041697.8562 | 870968.7907 | 23922655.8979
4901 | 8826761.1861 | 6205099.6774 | 527609.4382 | 15559470.3018
4902 | 14717027.8741 | 0 | 1651261.1228 | 16368288.9969
4903 | 4956761.4434 | 3646791.0486 | 336087.364 | 8939639.856
4904 | 1583256.3999 | 7551276.7215 | 868933.5436 | 10003466.6651
4905 | 9300057.4298 | 1686272.9626 | 279603.0741 | 11265933.4665
4906 | 7043883.625 | 0 | 1662100.2389 | 8705983.864
4907 | 3666081.6178 | 7769706.6081 | 3896395.7594 | 15332183.9853
4908 | 7667595.643 | 16161843.5098 | 16283844.3441 | 40113283.4969
4909 | 893682.9369 | 1048283.3245 | 1820133.1147 | 3762099.3761
4910 | 2394630.3728 | 4375747.5638 | 142976.9137 | 6913354.8504
4911 | 6704482.5566 | 2279932.1805 | 3364017.5574 | 12348432.2946
4912 | 4831147.0369 | 30381001.3308 | 0 | 35212148.3677
4913 | 810243.1702 | 5244280.5089 | 187290.1527 | 6241813.8318
4914 | 6348929.8574 | 4632018.8997 | 1724405.9203 | 12705354.6774
4915 | 34758895.255 | 7843740.8654 | 2438259.3838 | 45040895.5042
4916 | 9960724.3215 | 2254582.2536 | 1698673.6464 | 13913980.2215
4917 | 6635154.0276 | 0 | 4016361.5749 | 10651515.6024
4918 | 13338065.4764 | 4305491.8631 | 1735381.5688 | 19378938.9083
4919 | 19762728.0301 | 0 | 0 | 19762728.0301
4920 | 9210068.0995 | 17133118.9281 | 0 | 26343187.0276
4921 | 4190270.5912 | 1548716.7847 | 1387211.211 | 7126198.5869
4922 | 2181362.0714 | 8692868.4404 | 0 | 10874230.5118
4923 | 4689420.6088 | 5280881.2725 | 658832.3655 | 10629134.2468
4924 | 1739242.9685 | 14059338.5674 | 1267616.8844 | 17066198.4203
4925 | 3362772.8763 | 0 | 505840.9683 | 3868613.8446
4926 | 7761483.5385 | 14230815.9332 | 7773872.303 | 29766171.7746
4927 | 8750746.5421 | 17626652.2886 | 563700.8661 | 26941099.6968
4928 | 2298277.8262 | 7332986.8915 | 4421924.7176 | 14053189.4353
4929 | 9712725.9701 | 5651635.9395 | 0 | 15364361.9097
4930 | 3293042.0868 | 2244708.2423 | 2223569.2371 | 7761319.5662
4931 | 3419103.2051 | 0 | 1350706.1564 | 4769809.3614
4932 | 5617672.5589 | 10256639.0904 | 0 | 15874311.6493
4933 | 1285928.7626 | 9580423.8178 | 2666088.7817 | 13532441.3621
4934 | 13107747.7509 | 10780240.7346 | 0 | 23887988.4856
4935 | 6206235.7542 | 11067303.4965 | 1987021.8334 | 19260561.0842
4936 | 2889325.8409 | 2729932.3464 | 1015496.7111 | 6634754.8983
4937 | 14073018.3259 | 6170027.0526 | 0 | 20243045.3785
4938 | 2336679.8288 | 6640544.1515 | 17020334.5091 | 25997558.4894
4939 | 21140095.3348 | 4446223.8842 | 446907.8402 | 26033227.0591
4940 | 11099039.5163 | 0 | 754939.0454 | 11853978.5617
4941 | 445677.4957 | 0 | 2925400.5569 | 3371078.0527
4942 | 9619623.1282 | 7631775.4933 | 3064616.7834 | 20316015.405
4943 | 26426864.1172 | 0 | 960845.1383 | 27387709.2556
4944 | 8690662.9107 | 2187874.3354 | 0 | 10878537.246
4945 | 4272533.2984 | 10619653.6292 | 28958.415 | 14921145.3427
4946 | 9184916.9058 | 1754445.4013 | 15883912.1281 | 26823274.4352
4947 | 16083933.3271 | 4319475.6474 | 487356.2538 | 20890765.2283
4948 | 10868749.0075 | 28628658.2488 | 92075.6982 | 39589482.9546
4949 | 2700444.8131 | 11500546.1015 | 243890.2661 | 14444881.1807
4950 | 11619427.2119 | 2527244.3463 | 6097576.6367 | 20244248.1948
4951 | 4182433.254 | 5262002.3752 | 174815.6507 | 9619251.2798
4952 | 4475892.8394 | 13826277.3917 | 1945050.694 | 20247220.9251
4953 | 6231617.223 | 2407593.1532 | 53849.5569 | 8693059.9331
4954 | 7399631.0117 | 7495694.502 | 84019.6914 | 14979345.2051
4955 | 15824114.9597 | 3986581.5244 | 4531308.9896 | 24342005.4737
4956 | 16113574.171 | 8235579.1384 | 4019123.6364 | 28368276.9458
4957 | 17161072.9401 | 4029675.5965 | 1943911.5458 | 23134660.0824
4958 | 4819038.3275 | 3819566.0886 | 1868020.6407 | 10506625.0568
4959 | 2411581.1299 | 19461743.5887 | 0 | 21873324.7186
4960 | 8086396.706 | 17437430.087 | 1840693.9513 | 27364520.7443
4961 | 16575058.9268 | 2765185.0753 | 1801880.3305 | 21142124.3326
4962 | 9472971.9979 | 0 | 10714625.7569 | 20187597.7548
4963 | 2859742.1168 | 21170499.6803 | 176948.2794 | 24207190.0765
4964 | 1058981.3774 | 11531184.9519 | 240906.1673 | 12831072.4965
4965 | 2181137.132 | 2134748.3046 | 169476.837 | 4485362.2736
4966 | 3694397.3732 | 3965039.9208 | 94580.6697 | 7754017.9637
4967 | 9543012.6679 | 5754390.4599 | 3330890.6838 | 18628293.8115
4968 | 7856398.3137 | 3803714.8538 | 2277133.6543 | 13937246.8218
4969 | 7549166.845 | 16659365.886 | 4535586.4366 | 28744119.1676
4970 | 10691728.139 | 5465881.7745 | 734399.3215 | 16892009.235
4971 | 7583972.2289 | 13464955.8493 | 5498740.2449 | 26547668.3231
4972 | 9577337.9356 | 4586666.8837 | 288055.7583 | 14452060.5776
4973 | 7839133.2112 | 15611848.2094 | 3104289.3476 | 26555270.7682
4974 | 4216673.4823 | 25001723.5641 | 54119.1831 | 29272516.2295
4975 | 1848028.9833 | 1988178.6561 | 2027843.9505 | 5864051.5899
4976 | 23906040.926 | 14622924.1359 | 419732.5564 | 38948697.6182
4977 | 10696877.2014 | 0 | 262136.7191 | 10959013.9205
4978 | 7590375.3387 | 0 | 188558.9053 | 7778934.244
4979 | 5578154.4227 | 5725849.334 | 10926976.5214 | 22230980.278
4980 | 1369806.966 | 6264569.477 | 1059032.3855 | 8693408.8285
4981 | 2452043.2723 | 0 | 7420404.9006 | 9872448.1729
4982 | 2776891.6549 | 4714425.6256 | 172849.8475 | 7664167.128
4983 | 1112007.3697 | 4857662.9527 | 0 | 5969670.3224
4984 | 6311188.8783 | 29306969.2064 | 4356364.6762 | 39974522.7609
4985 | 7304055.293 | 28538327.6279 | 4547233.0807 | 40389616.0017
4986 | 2769457.5849 | 0 | 1273128.8703 | 4042586.4552
4987 | 3816941.2408 | 2360676.0598 | 78443.2496 | 6256060.5502
4988 | 7557375.5574 | 8474901.8246 | 1946524.2901 | 17978801.6721
4989 | 3043868.6236 | 5885197.6172 | 1503608.3038 | 10432674.5447
4990 | 4439364.3177 | 20416871.8859 | 0 | 24856236.2037
4991 | 5578069.2201 | 12074429.7664 | 2139524.3644 | 19792023.3509
4992 | 14161352.6113 | 3918870.6272 | 1137739.6699 | 19217962.9084
4993 | 5500635.887 | 170065.0347 | 1378571.9469 | 7049272.8687
4994 | 4035413.2068 | 0 | 1224195.2618 | 5259608.4686
4995 | 11622546.0862 | 1852356.9252 | 0 | 13474903.0114
4996 | 6435801.1264 | 11038815.1538 | 8089843.9597 | 25564460.2399
4997 | 17613539.92 | 6945116.8682 | 236323.5034 | 24794980.2916
4998 | 9521216.4143 | 2281518.7665 | 10526808.7158 | 22329543.8965
4999 | 11569269.7165 | 0 | 168205.5322 | 11737475.2486
5000 | 21070277.131 | 15034405.8269 | 32720481.3569 | 68825164.3148
5001 | 7855798.2228 | 11838928.0444 | 506995.2657 | 20201721.5329
5002 | 5619550.088 | 9386805.4269 | 13298034.8981 | 28304390.413
5003 | 1261212.0394 | 14635803.2876 | 2060283.1826 | 17957298.5096
5004 | 1762869.3186 | 23045777.4429 | 0 | 24808646.7615
5005 | 16745719.4493 | 7670492.3057 | 0 | 24416211.755
5006 | 11222692.4635 | 11067778.1584 | 0 | 22290470.622
5007 | 45176439.3326 | 846792.9173 | 288128.7934 | 46311361.0433
5008 | 1556800.5112 | 22678951.2452 | 1588230.1886 | 25823981.945
5009 | 4840406.0195 | 2883483.097 | 6677074.3144 | 14400963.4309
5010 | 4515322.0627 | 2318478.8007 | 270011.0016 | 7103811.865
5011 | 8692975.6837 | 18141758.9427 | 3201875.6549 | 30036610.2812
5012 | 6952990.082 | 5729203.9111 | 716927.9459 | 13399121.939
5013 | 2183953.2869 | 1647476.4146 | 304345.5445 | 4135775.2459
5014 | 2272404.4329 | 9839234.2762 | 97964.7115 | 12209603.4206
5015 | 19632870.7038 | 6733564.9503 | 0 | 26366435.654
5016 | 3724504.154 | 0 | 490515.1048 | 4215019.2589
5017 | 680352.6965 | 2853712.5588 | 1102406.3837 | 4636471.639
5018 | 10226661.4417 | 2318392.0127 | 0 | 12545053.4544
5019 | 18278371.31 | 1720019.2481 | 0 | 19998390.5581
5020 | 10359345.3988 | 12241024.5911 | 0 | 22600369.9899
5021 | 4677487.9717 | 6598449.1723 | 2458465.421 | 13734402.565
5022 | 7637846.7153 | 17402106.74 | 258103.1958 | 25298056.6511
5023 | 6469136.7284 | 9732774.5049 | 602719.5779 | 16804630.8112
5024 | 5063044.9116 | 2501269.6337 | 621370.8444 | 8185685.3897
5025 | 1743548.7449 | 0 | 58991.6381 | 1802540.383
5026 | 5743270.7732 | 0 | 3845189.362 | 9588460.1352
5027 | 3812962.679 | 24207273.9476 | 1808177.8378 | 29828414.4643
5028 | 8663152.6002 | 31554795.9297 | 333048.243 | 40550996.773
5029 | 5852333.4024 | 5947389.4796 | 49949.1314 | 11849672.0133
5030 | 4934837.9054 | 0 | 1417184.2313 | 6352022.1367
5031 | 8911684.8322 | 791261.5311 | 2199813.5511 | 11902759.9145
5032 | 34622286.5019 | 0 | 4541101.4529 | 39163387.9548
5033 | 2419832.7854 | 14928392.476 | 3881899.1004 | 21230124.3617
5034 | 11257204.716 | 5506784.5166 | 474762.5345 | 17238751.7671
5035 | 9949095.1906 | 9324501.3801 | 0 | 19273596.5707
5036 | 9902468.1486 | 9205400.2727 | 5581918.454 | 24689786.8753
5037 | 3379276.5234 | 11705988.5582 | 142737.705 | 15228002.7867
5038 | 12155210.4382 | 11090896.3576 | 7026303.7624 | 30272410.5582
5039 | 3181089.5385 | 1503157.3566 | 4034546.2638 | 8718793.1589
5040 | 11438597.0747 | 6320989.6198 | 2636253.9051 | 20395840.5996
5041 | 7642501.5829 | 6870941.5495 | 0 | 14513443.1324
5042 | 10990884.1273 | 17660677.6388 | 69019.4694 | 28720581.2355
5043 | 8486837.0294 | 0 | 0 | 8486837.0294
5044 | 13065152.6918 | 1731776.1012 | 281576.5741 | 15078505.3671
5045 | 68457.6658 | 7943307.9834 | 1001181.3042 | 9012946.9534
5046 | 6903758.1068 | 7853528.065 | 24858.8822 | 14782145.054
5047 | 2509476.7818 | 8484559.2542 | 2285520.2894 | 13279556.3253
5048 | 8383096.5543 | 2035979.9832 | 3542037.1132 | 13961113.6507
5049 | 15961336.9102 | 4395817.8882 | 2012838.7126 | 22369993.511
5050 | 12704173.5464 | 11224992.7236 | 3095806.758 | 27024973.0279
5051 | 16728400.7527 | 17465950.2213 | 7257162.0513 | 41451513.0253
5052 | 1708124.3449 | 7703558.7909 | 3213780.7966 | 12625463.9323
5053 | 7010807.4445 | 11100872.3395 | 0 | 18111679.784
5054 | 2360650.4546 | 5894085.865 | 3728718.6374 | 11983454.957
5055 | 14683174.8686 | 8028306.3912 | 0 | 22711481.2598
5056 | 1629385.0767 | 6390646.8468 | 7794942.2774 | 15814974.201
5057 | 2415862.5474 | 15700886.0651 | 0 | 18116748.6125
5058 | 8086158.456 | 0 | 1769791.1688 | 9855949.6249
5059 | 2945795.4922 | 1839822.5332 | 4254360.6678 | 9039978.6932
5060 | 615421.2054 | 11884697.6931 | 628164.2865 | 13128283.185
5061 | 10440072.4138 | 14409823.2136 | 1816959.9413 | 26666855.5687
5062 | 2950296.6141 | 13916315.4057 | 3183432.6909 | 20050044.7108
5063 | 4840637.1051 | 9897190.9499 | 11912842.5715 | 26650670.6265
5064 | 1230068.5093 | 7720988.0061 | 6842760.3114 | 15793816.8268
5065 | 12557010.023 | 3642956.3619 | 143747.2853 | 16343713.6702
5066 | 1464320.0324 | 26017411.6344 | 2294588.6609 | 29776320.3278
5067 | 2970844.8318 | 3541328.7318 | 232063.5789 | 6744237.1425
5068 | 11511916.6282 | 0 | 2902259.7543 | 14414176.3826
5069 | 5119069.2092 | 5203979.912 | 0 | 10323049.1213
5070 | 2838882.9757 | 4489148.8577 | 0 | 7328031.8334
5071 | 16918978.7603 | 0 | 33303.1311 | 16952281.8914
5072 | 11842299.4861 | 12097600.6095 | 3868622.7453 | 27808522.8409
5073 | 4321768.9413 | 4737096.1444 | 4112815.8575 | 13171680.9433
5074 | 14434924.8792 | 1579366.6076 | 3493048.8182 | 19507340.305
5075 | 9012086.3444 | 7612349.2997 | 0 | 16624435.6441
5076 | 10403558.6679 | 34986447.4824 | 1646038.6062 | 47036044.7565
5077 | 11529012.2415 | 0 | 7850159.4597 | 19379171.7012
5078 | 8708505.4702 | 556484.7126 | 305593.6707 | 9570583.8535
5079 | 8789197.4269 | 8968351.7676 | 1607683.0274 | 19365232.222
5080 | 2873520.0143 | 2506714.4893 | 1042866.2858 | 6423100.7894
5081 | 4504627.9969 | 1782786.945 | 852816.4872 | 7140231.4291
5082 | 7961998.698 | 3027764.1062 | 1741486.6257 | 12731249.4299
5083 | 6391337.8326 | 1684881.8132 | 83694.6561 | 8159914.3019
5084 | 19388184.9352 | 11513070.5694 | 0 | 30901255.5046
5085 | 438824.0015 | 354640.4902 | 25641935.3312 | 26435399.8229
5086 | 5685396.8001 | 2706863.1646 | 11452416.8524 | 19844676.8171
5087 | 16473387.1364 | 17693392.1266 | 2097838.6371 | 36264617.9001
5088 | 3181148.5374 | 7974233.1458 | 108123.2719 | 11263504.9551
5089 | 21441369.2005 | 7838349.7617 | 1490852.2165 | 30770571.1788
5090 | 2025217.5873 | 3785934.9115 | 2345638.7382 | 8156791.237
5091 | 6667433.0795 | 6741192.1796 | 2107677.7518 | 15516303.0109
5092 | 10405744.2766 | 6465190.2829 | 34928061.1681 | 51798995.7276
5093 | 17118099.4468 | 25857683.5833 | 7440706.9433 | 50416489.9734
5094 | 1888083.4585 | 569863.9175 | 2948583.4024 | 5406530.7784
5095 | 998622.5193 | 7035404.8434 | 136323.1684 | 8170350.5311
5096 | 4296665.8868 | 4334737.4987 | 174862.5796 | 8806265.9651
5097 | 1582799.3823 | 0 | 3067205.9544 | 4650005.3367
5098 | 2139873.9247 | 7827227.1802 | 1355278.3853 | 11322379.4902
5099 | 6994241.3558 | 5416113.0977 | 0 | 12410354.4535
5100 | 2895189.8617 | 0 | 2086200.497 | 4981390.3586
5101 | 770035.8438 | 11197991.6836 | 4947088.8037 | 16915116.3311
5102 | 11248186.7202 | 0 | 285171.7985 | 11533358.5187
5103 | 27763469.1415 | 5199614.7838 | 26531355.8989 | 59494439.8243
5104 | 15831830.0682 | 3869469.8241 | 1252473.6216 | 20953773.5139
5105 | 5890766.9529 | 11162146.7197 | 85992.5525 | 17138906.2251
5106 | 776100.3318 | 8361271.464 | 3773497.7498 | 12910869.5455
5107 | 17090421.7543 | 3173907.6152 | 687170.6953 | 20951500.0649
5108 | 3995105.6102 | 0 | 6009045.8141 | 10004151.4243
5109 | 1387178.3201 | 12950930.0551 | 1196555.3818 | 15534663.7569
5110 | 3326777.7427 | 4218859.5043 | 4916164.3214 | 12461801.5683
5111 | 3379011.0649 | 0 | 12806748.4863 | 16185759.5512
5112 | 9852194.4362 | 9875613.3452 | 1722757.103 | 21450564.8844
5113 | 2405959.0832 | 3800630.6107 | 1409874.0376 | 7616463.7315
5114 | 8138310.6165 | 8847671.172 | 71665.8397 | 17057647.6283
5115 | 17313426.1106 | 8413915.7598 | 7309942.2756 | 33037284.146
5116 | 10497927.4755 | 6027092.4748 | 405199.4571 | 16930219.4074
5117 | 12919614.6787 | 6643214.8736 | 2094544.622 | 21657374.1743
5118 | 7224367.604 | 3858405.5607 | 220575.8652 | 11303349.0298
5119 | 9850132.9641 | 4863954.4249 | 1449666.2923 | 16163753.6813
5120 | 5627105.5818 | 7886056.9977 | 769593.502 | 14282756.0814
5121 | 6407851.073 | 0 | 2714669.4268 | 9122520.4998
5122 | 6045676.9954 | 11289742.3536 | 2750219.6744 | 20085639.0234
5123 | 5740115.2807 | 1381804.2362 | 492867.3326 | 7614786.8495
5124 | 16515131.1817 | 13829058.8991 | 757720.317 | 31101910.3979
5125 | 3252410.3944 | 10229153.0437 | 23757256.2739 | 37238819.7121
5126 | 3165236.6063 | 17616827.5423 | 2786007.3264 | 23568071.475
5127 | 6754884.2259 | 0 | 767202.1768 | 7522086.4027
5128 | 8635896.7758 | 9092959.3786 | 4269735.8835 | 21998592.0378
5129 | 17397111.7772 | 0 | 8200879.6992 | 25597991.4764
5130 | 8156511.2095 | 9375518.9634 | 98409.1335 | 17630439.3063
5131 | 8300793.1358 | 31063285.7982 | 3966318.6024 | 43330397.5364
5132 | 5080752.8195 | 0 | 0 | 5080752.8195
5133 | 16194589.5308 | 0 | 1675857.0443 | 17870446.5751
5134 | 3633650.9297 | 4238798.2961 | 1196443.6017 | 9068892.8276
5135 | 7117623.6236 | 0 | 250761.295 | 7368384.9186
5136 | 9548381.1214 | 9335537.59 | 0 | 18883918.7114
5137 | 9910273.1319 | 3754516.1051 | 1168457.2007 | 14833246.4377
5138 | 3785953.5743 | 7934914.9727 | 1021814.8528 | 12742683.3999
5139 | 4509821.2412 | 9181575.138 | 1217845.1742 | 14909241.5533
5140 | 26455969.593 | 4058213.625 | 12243219.2874 | 42757402.5053
5141 | 12320276.5824 | 6136997.6489 | 1879309.0016 | 20336583.2328
5142 | 6384736.2378 | 13480276.8881 | 3333308.419 | 23198321.5449
5143 | 15601531.8349 | 3685953.0652 | 679933.2781 | 19967418.1782
5144 | 10323954.0125 | 2171460.3339 | 28595.7481 | 12524010.0946
5145 | 2995637.8921 | 9287689.5946 | 293278.765 | 12576606.2517
5146 | 6794245.4913 | 0 | 6364216.4016 | 13158461.8929
5147 | 6855909.8612 | 2174539.2552 | 4503935.4458 | 13534384.5622
5148 | 6417208.231 | 0 | 0 | 6417208.231
5149 | 2090004.1159 | 11472961.5862 | 322128.7169 | 13885094.419
5150 | 10202775.6232 | 5326906.5199 | 1243313.8291 | 16772995.9722
5151 | 13031053.5012 | 5504553.608 | 870967.675 | 19406574.7842
5152 | 2964162.5549 | 0 | 4733669.7071 | 7697832.262
5153 | 9447900.9029 | 2270792.6386 | 1373374.0872 | 13092067.6287
5154 | 13458598.0924 | 3544537.821 | 348435.8541 | 17351571.7675
5155 | 5272654.9636 | 11010597.677 | 442854.7135 | 16726107.3541
5156 | 376793.2072 | 494085.1317 | 64848.0143 | 935726.3532
5157 | 7911010.3602 | 4787235.8345 | 0 | 12698246.1947
5158 | 2583050.4216 | 0 | 288511.1961 | 2871561.6177
5159 | 4658446.5706 | 6671238.121 | 1707086.7665 | 13036771.4581
5160 | 4698037.8124 | 44020605.6618 | 29330.0427 | 48747973.5169
5161 | 10324072.0782 | 11089163.6958 | 593885.7246 | 22007121.4986
5162 | 9768772.7954 | 9463857.7695 | 1568778.4842 | 20801409.0491
5163 | 7060817.3535 | 8668350.0291 | 120248.6666 | 15849416.0492
5164 | 3816548.0533 | 33087157.3412 | 2491748.0754 | 39395453.4699
5165 | 18584915.8421 | 2557213.0494 | 0 | 21142128.8915
5166 | 13098393.3961 | 7284539.8167 | 877637.4722 | 21260570.6849
5167 | 12477966.3664 | 5821992.5713 | 0 | 18299958.9377
5168 | 16650471.3626 | 5073969.1424 | 110707.6864 | 21835148.1914
5169 | 15785230.088 | 19556161.9892 | 8615638.8198 | 43957030.8971
5170 | 10631284.1617 | 2839374.9858 | 13702761.2309 | 27173420.3783
5171 | 3542383.3811 | 3160509.3391 | 97448.7643 | 6800341.4845
5172 | 3650079.4247 | 0 | 5095439.9864 | 8745519.4111
5173 | 5788583.2193 | 22271240.0683 | 3704242.4585 | 31764065.746
5174 | 5781977.2568 | 7929240.7032 | 0 | 13711217.9601
5175 | 16570817.144 | 5329638.0441 | 760821.3714 | 22661276.5595
5176 | 6078389.8147 | 4399809.8329 | 419383.0578 | 10897582.7054
5177 | 15571663.2444 | 12161671.4227 | 6192424.7418 | 33925759.4089
5178 | 13039178.8159 | 6439524.7917 | 60795.0251 | 19539498.6327
5179 | 1157998.0532 | 5059917.9115 | 5906586.7556 | 12124502.7203
5180 | 12333104.5113 | 3931742.7888 | 0 | 16264847.3002
5181 | 3998889.266 | 13157626.4561 | 741557.0199 | 17898072.7421
5182 | 16040359.4728 | 0 | 2526458.2041 | 18566817.6769
5183 | 282005.781 | 7622849.2626 | 348476.976 | 8253332.0196
5184 | 4038573.2274 | 11227332.3607 | 5451364.2418 | 20717269.8298
5185 | 14960882.2732 | 4625751.1241 | 385855.2478 | 19972488.6452
5186 | 4599260.9256 | 4659761.7284 | 3017094.3921 | 12276117.0461
5187 | 4211471.4041 | 20003972.214 | 2732652.2892 | 26948095.9072
5188 | 8510773.6516 | 3657745.8597 | 1833366.8502 | 14001886.3614
5189 | 5730557.1477 | 5831272.2528 | 111661.0434 | 11673490.4439
5190 | 3738589.0362 | 0 | 1992695.0432 | 5731284.0794
5191 | 514792.7724 | 1859082.3023 | 4210339.9849 | 6584215.0596
5192 | 14986706.4086 | 2561874.7003 | 3290720.3328 | 20839301.4417
5193 | 9923361.2802 | 13891297.1296 | 650715.2663 | 24465373.6761
5194 | 7721861.3458 | 1436456.455 | 0 | 9158317.8008
5195 | 8326231.0634 | 3490193.7659 | 239729.3368 | 12056154.1662
5196 | 7500831.8881 | 0 | 0 | 7500831.8881
5197 | 9336026.5542 | 3454956.0224 | 2482237.7371 | 15273220.3137
5198 | 3101882.3911 | 35288464.7807 | 281067.6869 | 38671414.8587
5199 | 7737626.8667 | 7321931.8688 | 378801.1715 | 15438359.907
5200 | 4979538.8993 | 12082082.2417 | 3084712.1773 | 20146333.3184
5201 | 3888287.039 | 5670800.146 | 1682231.0241 | 11241318.2091
5202 | 707972.4802 | 7663949.8879 | 298719.9317 | 8670642.2998
5203 | 12927145.5709 | 4542292.6573 | 1332699.9223 | 18802138.1504
5204 | 17198475.2064 | 2501793.3857 | 0 | 19700268.592
5205 | 3844396.5453 | 7621473.7519 | 56659.648 | 11522529.9452
5206 | 3392378.544 | 4255445.5481 | 181537.3987 | 7829361.4908
5207 | 12374078.7121 | 0 | 3680598.0182 | 16054676.7303
5208 | 8357352.3589 | 0 | 8204258.9206 | 16561611.2795
5209 | 6396011.3534 | 0 | 4734912.4705 | 11130923.8239
5210 | 2896959.2 | 7639005.7353 | 88902.9374 | 10624867.8727
5211 | 6899936.3863 | 9635462.4586 | 28172107.1597 | 44707506.0046
5212 | 2486084.6276 | 6754765.5138 | 186637.9414 | 9427488.0828
5213 | 4286484.4741 | 1203934.6152 | 535671.0974 | 6026090.1867
5214 | 10386520.2948 | 2975784.4444 | 891678.8768 | 14253983.6159
5215 | 4777142.6873 | 2042652.8917 | 141254.6179 | 6961050.1969
5216 | 8960123.0465 | 14959294.6763 | 3588199.3221 | 27507617.0449
5217 | 7304121.2874 | 2560750.2449 | 1367224.6397 | 11232096.1721
5218 | 9127304.2471 | 11260857.6073 | 109941.6005 | 20498103.4549
5219 | 19541998.51 | 2425359.4823 | 1260830.8459 | 23228188.8383
5220 | 18748763.7688 | 0 | 2357258.6451 | 21106022.4139
5221 | 6746680.0851 | 6096388.9028 | 129643.631 | 12972712.6189
5222 | 3445131.8895 | 840395.9873 | 1294238.8481 | 5579766.7249
5223 | 5726861.0389 | 11620516.4522 | 758698.7812 | 18106076.2724
5224 | 6963084.6491 | 5487814.034 | 2257420.3363 | 14708319.0194
5225 | 4676285.0998 | 5616736.0109 | 2183885.421 | 12476906.5317
5226 | 10337699.9225 | 5561614.5853 | 0 | 15899314.5078
5227 | 20926900.6963 | 3044982.8841 | 0 | 23971883.5804
5228 | 19203881.8597 | 11838850.512 | 3843014.1207 | 34885746.4923
5229 | 5486325.4465 | 7192847.1692 | 1998865.3724 | 14678037.9881
5230 | 10955952.2565 | 0 | 6162269.7328 | 17118221.9893
5231 | 4050924.0895 | 0 | 386047.8172 | 4436971.9067
5232 | 11356246.0493 | 6298486.4713 | 12877260.6769 | 30531993.1974
5233 | 8356026.4938 | 2846176.6999 | 551917.1312 | 11754120.3249
5234 | 10591493.392 | 5691060.3218 | 260668.035 | 16543221.7488
5235 | 9814098.7753 | 0 | 2259902.0693 | 12074000.8445
5236 | 10679313.815 | 9392206.9494 | 0 | 20071520.7644
5237 | 3414151.6588 | 5038681.4023 | 10102922.7296 | 18555755.7907
5238 | 10605707.4346 | 0 | 897751.4164 | 11503458.851
5239 | 3715050.1483 | 4382976.0244 | 0 | 8098026.1727
5240 | 3439739.1825 | 0 | 460415.2141 | 3900154.3966
5241 | 14970651.2883 | 0 | 85875.4278 | 15056526.7161
5242 | 13139597.4573 | 11496351.5922 | 2780746.2965 | 27416695.346
5243 | 3577224.8957 | 0 | 1786602.8379 | 5363827.7336
5244 | 1651767.3025 | 12674515.2754 | 874277.0773 | 15200559.6552
5245 | 1681321.1935 | 10062202.0111 | 56844.2045 | 11800367.4091
5246 | 9438943.9424 | 952067.9524 | 532129.5295 | 10923141.4242
5247 | 10448662.1019 | 7241778.5984 | 4002545.1154 | 21692985.8157
5248 | 13748529.1696 | 14688363.7974 | 1771619.53 | 30208512.497
5249 | 6906256.9961 | 5491425.7908 | 4509059.5033 | 16906742.2902
5250 | 7741907.7109 | 11709276.3381 | 123430.838 | 19574614.8871
5251 | 26544164.1825 | 0 | 2289912.0708 | 28834076.2533
5252 | 5340524.4116 | 3191857.5559 | 23838747.0823 | 32371129.0498
5253 | 7906529.1216 | 14649826.0651 | 0 | 22556355.1866
5254 | 2194967.3214 | 8963757.3637 | 0 | 11158724.6851
5255 | 6750885.6557 | 2525440.3513 | 163054.4878 | 9439380.4948
5256 | 5697959.5066 | 4971291.7181 | 1054174.3069 | 11723425.5316
5257 | 1989560.9539 | 16336355.0836 | 4049628.8337 | 22375544.8711
5258 | 9678944.2297 | 11310700.1286 | 814660.2981 | 21804304.6564
5259 | 1397028.7046 | 20338540.5084 | 0 | 21735569.2131
5260 | 4490142.2447 | 13495514.3238 | 0 | 17985656.5685
5261 | 4526720.7002 | 1813205.6908 | 2875594.0577 | 9215520.4487
5262 | 10555118.4365 | 3203586.1598 | 2571615.5619 | 16330320.1582
5263 | 1199270.6223 | 13272061.9039 | 150851.6535 | 14622184.1798
5264 | 2176761.0171 | 6331497.2372 | 6232417.986 | 14740676.2403
5265 | 1711259.7191 | 6615159.0367 | 511851.7353 | 8838270.4912
5266 | 8365968.7935 | 32115468.2551 | 0 | 40481437.0486
5267 | 4837468.9383 | 4179209.2142 | 2201685.9645 | 11218364.117
5268 | 13360387.4714 | 0 | 1075346.9196 | 14435734.391
5269 | 11615354.9437 | 7714306.0814 | 1298844.9147 | 20628505.9398
5270 | 5456812.4363 | 8600679.8421 | 7780991.1149 | 21838483.3933
5271 | 1893832.6395 | 5041647.7505 | 4020478.2429 | 10955958.633
5272 | 4298654.5965 | 12853285.7606 | 391974.1064 | 17543914.4635
5273 | 10705565.0812 | 4095989.6983 | 0 | 14801554.7795
5274 | 6998399.4658 | 20297082.4783 | 62383.9004 | 27357865.8444
5275 | 8650025.8393 | 15339827.8425 | 371607.153 | 24361460.8349
5276 | 5079888.9815 | 1354537.5941 | 0 | 6434426.5756
5277 | 11957508.8049 | 2860838.9537 | 295482.9854 | 15113830.744
5278 | 1997763.361 | 0 | 33788.3318 | 2031551.6928
5279 | 8509729.0777 | 5458957.9361 | 1514274.9077 | 15482961.9216
5280 | 17056310.2042 | 8005226.472 | 986921.9069 | 26048458.5831
5281 | 13596970.1176 | 13912504.5416 | 398045.2633 | 27907519.9225
5282 | 3856808.6027 | 4141114.0027 | 3571897.8369 | 11569820.4423
5283 | 12887042.6607 | 3167956.3121 | 0 | 16054998.9728
5284 | 1686859.599 | 42901495.9721 | 6291148.1873 | 50879503.7584
5285 | 7288407.4332 | 5103512.906 | 19996766.9993 | 32388687.3384
5286 | 908707.3287 | 30537614.7072 | 17419.9611 | 31463741.9971
5287 | 14187571.2673 | 8508629.9804 | 49184.7759 | 22745386.0236
5288 | 278032.452 | 510394.6329 | 4333297.1554 | 5121724.2403
5289 | 5058360.5616 | 0 | 961504.8259 | 6019865.3875
5290 | 17829793.9849 | 19048989.1265 | 5121771.0527 | 42000554.1641
5291 | 948511.4558 | 12045743.409 | 8491881.5597 | 21486136.4245
5292 | 11009227.8514 | 14805711.0692 | 810182.2347 | 26625121.1553
5293 | 7883911.7191 | 1485711.2099 | 496921.7573 | 9866544.6862
5294 | 13628244.2021 | 0 | 1705090.1366 | 15333334.3387
5295 | 3364342.5524 | 3193285.7072 | 6075951.9921 | 12633580.2517
5296 | 6128744.4705 | 12596075.1789 | 0 | 18724819.6494
5297 | 12646250.2438 | 20321651.7861 | 10455185.1672 | 43423087.197
5298 | 3328301.2956 | 0 | 3082218.1027 | 6410519.3983
5299 | 6760542.6025 | 4115475.3871 | 1002226.6956 | 11878244.6853
5300 | 2775113.4746 | 8855930.6785 | 0 | 11631044.1531
5301 | 5691513.6739 | 16190194.5417 | 466724.484 | 22348432.6997
5302 | 1841600.4166 | 11644229.1031 | 1774280.0739 | 15260109.5936
5303 | 6175558.8217 | 0 | 1186762.3146 | 7362321.1363
5304 | 3379613.7239 | 5894453.3104 | 664469.6093 | 9938536.6436
5305 | 23981665.6257 | 12342706.18 | 2647778.5234 | 38972150.329
5306 | 9573951.835 | 18159967.58 | 3194032.6701 | 30927952.0851
5307 | 1905244.9659 | 0 | 0 | 1905244.9659
5308 | 16451146.1327 | 4903079.3881 | 5974426.9016 | 27328652.4224
5309 | 9801799.8466 | 0 | 8769969.3557 | 18571769.2023
5310 | 4439825.1261 | 2263872.1669 | 0 | 6703697.293
5311 | 4716689.1314 | 1203632.8436 | 1468249.8355 | 7388571.8105
5312 | 13467631.6115 | 0 | 354163.0769 | 13821794.6884
5313 | 8277564.511 | 8906965.829 | 191818.2467 | 17376348.5867
5314 | 7157827.2829 | 13128479.9051 | 5059980.4117 | 25346287.5996
5315 | 3838228.9273 | 9479247.692 | 2239924.5714 | 15557401.1908
5316 | 3325254.8317 | 13370690.9871 | 0 | 16695945.8189
5317 | 3019868.5274 | 5551504.2953 | 3070263.2395 | 11641636.0623
5318 | 8131459.6303 | 2499880.6272 | 0 | 10631340.2575
5319 | 3773351.8312 | 0 | 484341.2324 | 4257693.0636
5320 | 3672139.8574 | 1805681.0546 | 417645.2814 | 5895466.1934
5321 | 6051364.2179 | 9100743.5921 | 462387.7374 | 15614495.5473
5322 | 8192293.5545 | 6806251.5688 | 18466371.0164 | 33464916.1397
5323 | 792645.9597 | 4896281.8927 | 0 | 5688927.8524
5324 | 4106435.6522 | 0 | 1568376.4293 | 5674812.0815
5325 | 4449384.2397 | 0 | 8303751.1362 | 12753135.3759
5326 | 12808438.3981 | 6153711.5046 | 42492.8149 | 19004642.7177
5327 | 2304415.7831 | 0 | 1642970.8508 | 3947386.6339
5328 | 9600706.1375 | 12229199.0422 | 216502.5639 | 22046407.7437
5329 | 11299716.2643 | 7272017.7512 | 1602628.1074 | 20174362.1228
5330 | 3631554.7291 | 3620997.2143 | 2977865.5106 | 10230417.454
5331 | 3776316.6006 | 7728896.5084 | 287682.6155 | 11792895.7245
5332 | 4898436.4693 | 9153186.8531 | 272652.4503 | 14324275.7726
5333 | 3023977.2282 | 7477957.4401 | 4093248.8395 | 14595183.5077
5334 | 1614575.9882 | 3290321.6329 | 2784164.919 | 7689062.5401
5335 | 11412550.1931 | 0 | 326043.5747 | 11738593.7678
5336 | 9437270.9285 | 0 | 1142474.8594 | 10579745.7879
5337 | 4279204.4479 | 16704403.9813 | 6126148.9438 | 27109757.3731
5338 | 5337583.9511 | 8857547.0868 | 1608069.6766 | 15803200.7145
5339 | 3516506.4057 | 9047589.4096 | 419394.162 | 12983489.9773
5340 | 16165971.8229 | 0 | 1256844.466 | 17422816.289
5341 | 756895.5311 | 9493383.331 | 0 | 10250278.8621
5342 | 5760060.4391 | 2252924.6441 | 5289639.2009 | 13302624.2841
5343 | 1875460.752 | 2083418.7805 | 463843.4784 | 4422723.0109
5344 | 10906555.6674 | 0 | 311289.4794 | 11217845.1468
5345 | 4211865.4665 | 1582665.5789 | 308252.4342 | 6102783.4796
5346 | 21725757.1441 | 2862846.0312 | 0 | 24588603.1753
5347 | 9687189.2222 | 755284.5158 | 855660.4469 | 11298134.1849
5348 | 866090.9194 | 6101377.1673 | 12030879.4343 | 18998347.5211
5349 | 9431504.8236 | 5482546.4638 | 457841.7645 | 15371893.0519
5350 | 3062300.8362 | 2089062.5666 | 10502095.4394 | 15653458.8421
5351 | 1113131.3878 | 8554227.8276 | 826318.4606 | 10493677.6759
5352 | 15021803.8298 | 0 | 322481.2694 | 15344285.0992
5353 | 12146155.809 | 24162062.6004 | 998519.6198 | 37306738.0291
5354 | 4938768.8965 | 21603499.4143 | 1474140.1198 | 28016408.4306
5355 | 3763306.9132 | 4942987.8313 | 1345339.4519 | 10051634.1964
5356 | 1453233.9057 | 7966934.1016 | 1955060.6088 | 11375228.6161
5357 | 11386649.3608 | 0 | 4171459.145 | 15558108.5057
5358 | 10805691.5844 | 818038.4037 | 234403.8265 | 11858133.8145
5359 | 1821819.6777 | 7012494.2743 | 0 | 8834313.952
5360 | 3202387.8681 | 2377844.2786 | 301017.252 | 5881249.3986
5361 | 23440853.9776 | 4803542.1394 | 1427304.4845 | 29671700.6015
5362 | 11159523.509 | 684948.9904 | 1389437.8375 | 13233910.3369
5363 | 10849915.7418 | 6655525.0738 | 1323835.6618 | 18829276.4774
5364 | 1587390.2211 | 11894019.6013 | 803723.232 | 14285133.0544
5365 | 4704138.7756 | 0 | 248224.8951 | 4952363.6706
5366 | 9323796.9454 | 4019702.2105 | 8490902.2536 | 21834401.4095
5367 | 5996422.9943 | 8546137.061 | 16954965.3894 | 31497525.4446
5368 | 2257236.7383 | 2416210.1331 | 15618.1532 | 4689065.0246
5369 | 11929097.0905 | 0 | 1180140.5848 | 13109237.6754
5370 | 16131582.3114 | 0 | 1219306.5974 | 17350888.9088
5371 | 534229.6963 | 12937004.6902 | 498343.0155 | 13969577.402
5372 | 6707544.0721 | 18083262.5917 | 2715168.5857 | 27505975.2495
5373 | 20130239.9828 | 35725079.0626 | 220822.0989 | 56076141.1444
5374 | 15411250.1161 | 0 | 60941.6023 | 15472191.7185
5375 | 5794448.4112 | 7080819.1204 | 0 | 12875267.5315
5376 | 14291284.4986 | 7715828.6186 | 2226092.4213 | 24233205.5384
5377 | 3076769.5746 | 1971084.9764 | 1202418.3303 | 6250272.8813
5378 | 6779598.3769 | 1036762.0529 | 349627.398 | 8165987.8277
5379 | 4379052.3492 | 10004446.4075 | 183659.9408 | 14567158.6974
5380 | 15271141.4019 | 14316529.9341 | 2023705.5695 | 31611376.9055
5381 | 4989104.3004 | 0 | 3284078.9099 | 8273183.2102
5382 | 41903889.2077 | 6252265.4518 | 582129.7343 | 48738284.3937
5383 | 1831319.9105 | 20286800.0035 | 9454939.7931 | 31573059.7071
5384 | 4557674.5724 | 10394583.4297 | 1097303.7178 | 16049561.7199
5385 | 19487969.9977 | 8208304.4304 | 0 | 27696274.428
5386 | 20834789.1841 | 16011365.6254 | 0 | 36846154.8095
5387 | 5772618.0886 | 2680135.1365 | 2472967.6606 | 10925720.8857
5388 | 10818921.9134 | 21358942.9682 | 8571898.3454 | 40749763.2271
5389 | 18722608.8174 | 4973741.2311 | 1294529.4252 | 24990879.4737
5390 | 3152704.7766 | 6171827.9849 | 1083988.2229 | 10408520.9845
5391 | 3710082.7517 | 20991514.5286 | 664911.7168 | 25366508.9971
5392 | 4142007.0917 | 9139913.5081 | 2592261.9448 | 15874182.5446
5393 | 1069533.1456 | 4996961.8262 | 225793.5945 | 6292288.5663
5394 | 9582870.969 | 6551814.6405 | 0 | 16134685.6095
5395 | 4503955.0575 | 38161293.9164 | 5539338.7295 | 48204587.7034
5396 | 4640631.701 | 9701229.7797 | 10983232.7325 | 25325094.2133
5397 | 9680648.1706 | 746832.6676 | 82008.253 | 10509489.0912
5398 | 9084270.9252 | 10308312.6279 | 0 | 19392583.5531
5399 | 245849.7888 | 2783031.283 | 3219679.4589 | 6248560.5307
5400 | 9042585.969 | 0 | 2183202.9284 | 11225788.8974
5401 | 3974149.3903 | 5994735.4173 | 2358564.7809 | 12327449.5885
5402 | 6307259.2243 | 0 | 169808.9589 | 6477068.1832
5403 | 7186029.9434 | 7856054.9722 | 0 | 15042084.9156
5404 | 8407612.5315 | 0 | 1216019.9004 | 9623632.4319
5405 | 7833719.2193 | 3904854.6569 | 914417.1584 | 12652991.0345
5406 | 9330145.846 | 3490468.2396 | 197865.6186 | 13018479.7042
5407 | 8004135.5519 | 3412819.8377 | 699835.1765 | 12116790.5661
5408 | 2453200.762 | 3516822.5836 | 903476.3644 | 6873499.71
5409 | 6902919.9024 | 4671664.0807 | 219359.3656 | 11793943.3486
5410 | 5532901.7639 | 4869280.2637 | 720842.8075 | 11123024.8351
5411 | 9046645.2451 | 0 | 3439208.6787 | 12485853.9239
5412 | 8314833.4084 | 25466548.7487 | 2634033.4876 | 36415415.6446
5413 | 23442259.0576 | 6916920.7656 | 2689178.5041 | 33048358.3273
5414 | 2750090.5362 | 6712375.3516 | 230350.1997 | 9692816.0875
5415 | 4180604.1176 | 10673965.3409 | 431446.9906 | 15286016.449
5416 | 3813500.8775 | 5208436.9973 | 473366.4708 | 9495304.3456
5417 | 4122352.1629 | 2612487.8704 | 3596934.5432 | 10331774.5766
5418 | 4151187.0755 | 4732808.5739 | 5166858.2237 | 14050853.8731
5419 | 1695892.2795 | 743341.4486 | 1861274.6639 | 4300508.392
5420 | 3603303.0742 | 10799330.7411 | 10979987.998 | 25382621.8132
5421 | 16466585.4285 | 6882587.6984 | 495398.167 | 23844571.2939
5422 | 5105179.1673 | 11098683.4317 | 63181.9376 | 16267044.5366
5423 | 4563532.3183 | 5056993.3338 | 247368.9305 | 9867894.5825
5424 | 9504500.2796 | 4048091.9368 | 308725.8608 | 13861318.0773
5425 | 1822461.6267 | 11662015.0682 | 137429.9398 | 13621906.6347
5426 | 5458239.6124 | 7081747.8872 | 4876637.9543 | 17416625.4539
5427 | 4123898.1158 | 5643646.5162 | 229420.6062 | 9996965.2382
5428 | 19676382.6635 | 9990969.7521 | 1423411.8691 | 31090764.2847
5429 | 4870017.8944 | 0 | 216000.272 | 5086018.1664
5430 | 6295145.1304 | 0 | 0 | 6295145.1304
5431 | 601054.2106 | 11769172.5048 | 509455.5409 | 12879682.2563
5432 | 224642.2065 | 13018711.1444 | 1211364.6736 | 14454718.0245
5433 | 13628866.0564 | 11813839.0282 | 7004816.8964 | 32447521.981
5434 | 8240720.6512 | 0 | 604522.4215 | 8845243.0728
5435 | 1018666.8385 | 8755952.5376 | 446057.2983 | 10220676.6743
5436 | 4371819.1905 | 0 | 1805757.3113 | 6177576.5018
5437 | 18735149.538 | 5952044.8913 | 423243.1515 | 25110437.5808
5438 | 3089343.0601 | 3521415.7352 | 99693.7461 | 6710452.5414
5439 | 2003630.5572 | 4121750.0757 | 1546910.8249 | 7672291.4579
5440 | 3739809.1913 | 5887915.4949 | 2355706.3424 | 11983431.0286
5441 | 13584158.8731 | 904361.1555 | 36647023.2585 | 51135543.2871
5442 | 10500022.9748 | 12551969.9606 | 1606790.1936 | 24658783.1291
5443 | 3497907.3862 | 0 | 671340.9727 | 4169248.3588
5444 | 11402952.5116 | 17150539.2112 | 9763767.9925 | 38317259.7153
5445 | 3040846.5533 | 0 | 279376.3925 | 3320222.9458
5446 | 4081083.9443 | 8113264.2573 | 916202.8683 | 13110551.0699
5447 | 4930078.649 | 652000.9303 | 29417.069 | 5611496.6483
5448 | 7594964.582 | 8107292.5323 | 3048529.1939 | 18750786.3082
5449 | 5269699.71 | 2913082.7572 | 0 | 8182782.4672
5450 | 3905133.2672 | 3679725.783 | 112317.2444 | 7697176.2945
5451 | 7366373.8936 | 5708596.2267 | 21033255.8092 | 34108225.9295
5452 | 2061104.6188 | 7828973.1285 | 17864.3578 | 9907942.1052
5453 | 9551445.7551 | 9318205.2232 | 1781617.672 | 20651268.6503
5454 | 7929653.4869 | 3327579.0863 | 169935.8278 | 11427168.401
5455 | 2946802.9175 | 2397799.8704 | 23052.6908 | 5367655.4787
5456 | 15074643.7743 | 1241903.0141 | 322745.7177 | 16639292.5062
5457 | 2728999.5992 | 6826355.9923 | 411966.2267 | 9967321.8181
5458 | 4080981.5539 | 19873628.9968 | 2903837.8738 | 26858448.4245
5459 | 5430719.011 | 9773998.4582 | 1608699.3312 | 16813416.8004
5460 | 4764134.1552 | 0 | 272935.4947 | 5037069.6499
5461 | 6784244.9172 | 12280746.9796 | 1533023.1086 | 20598015.0054
5462 | 4417940.8355 | 16088731.6233 | 44610.1274 | 20551282.5862
5463 | 5634160.4252 | 10403393.6292 | 75184.9058 | 16112738.9601
5464 | 8128077.6527 | 10599160.0783 | 2198192.6519 | 20925430.3829
5465 | 18118268.6928 | 3026201.8624 | 839812.8884 | 21984283.4436
5466 | 6607864.4455 | 15323257.1485 | 0 | 21931121.594
5467 | 11794413.1506 | 3343111.6717 | 0 | 15137524.8223
5468 | 5359361.4619 | 2382452.5446 | 2906794.4525 | 10648608.459
5469 | 9003325.9723 | 0 | 0 | 9003325.9723
5470 | 4339166.2223 | 0 | 582255.7197 | 4921421.942
5471 | 11448970.3632 | 8546180.5372 | 1961878.8775 | 21957029.7779
5472 | 5496981.1386 | 586462.1553 | 125572.9354 | 6209016.2293
5473 | 3405646.0515 | 1267860.3361 | 400717.0333 | 5074223.421
5474 | 20981858.009 | 6347100.2214 | 0 | 27328958.2304
5475 | 9453968.6921 | 15769691.3833 | 447198.8739 | 25670858.9494
5476 | 0 | 2903785.0711 | 9615164.8919 | 12518949.963
5477 | 18421612.0526 | 6363143.4172 | 0 | 24784755.4698
5478 | 3176769.1286 | 0 | 204343.2755 | 3381112.4041
5479 | 4452312.1288 | 4204640.6887 | 0 | 8656952.8175
5480 | 2944363.4876 | 5681083.1414 | 0 | 8625446.629
5481 | 5711952.7525 | 7694914.2772 | 504006.8815 | 13910873.9111
5482 | 1030587.0686 | 5621939.8078 | 3014844.0475 | 9667370.924
5483 | 8132193.5027 | 4057676.3192 | 14722487.3269 | 26912357.1489
5484 | 9584730.1799 | 7214921.3633 | 1569369.165 | 18369020.7081
5485 | 1778103.8186 | 4160594.1075 | 4782186.8625 | 10720884.7885
5486 | 11345384.7027 | 10070536.7919 | 0 | 21415921.4945
5487 | 5049246.2578 | 288060.632 | 1004848.7469 | 6342155.6367
5488 | 12838250.0572 | 6987030.1463 | 844982.5797 | 20670262.7831
5489 | 457994.212 | 2349245.9612 | 0 | 2807240.1732
5490 | 14399619.3171 | 2740333.6602 | 538237.4319 | 17678190.4093
5491 | 6489936.1096 | 5609992.2862 | 84567.8966 | 12184496.2924
5492 | 3204154.7077 | 3752444.5015 | 797038.7613 | 7753637.9705
5493 | 10592270.1351 | 5613717.9329 | 1652009.587 | 17857997.655
5494 | 13371371.8984 | 8524730.3881 | 702087.9499 | 22598190.2363
5495 | 2578384.7908 | 7250348.2003 | 3810199.7351 | 13638932.7262
5496 | 8605627.1325 | 4596044.427 | 119848.5849 | 13321520.1444
5497 | 4595296.9873 | 5509736.075 | 257609.5791 | 10362642.6415
5498 | 21149446.15 | 3922597.2269 | 15690792.8165 | 40762836.1934
5499 | 10456149.9045 | 20185924.4298 | 1069677.3058 | 31711751.6401
5500 | 2862559.4421 | 515888.1605 | 209239.5321 | 3587687.1346
5501 | 6191000.0153 | 4441385.7636 | 2245137.9592 | 12877523.7381
5502 | 5100559.341 | 7905147.928 | 211841.2194 | 13217548.4883
5503 | 6892802.0156 | 3594953.5062 | 3629202.2698 | 14116957.7916
5504 | 19456424.2996 | 2385079.8275 | 1199050.8866 | 23040555.0137
5505 | 493142.5067 | 8795572.2697 | 0 | 9288714.7764
5506 | 9383319.0394 | 0 | 1076990.259 | 10460309.2984
5507 | 9824094.9283 | 2201554.5046 | 584782.6591 | 12610432.0919
5508 | 3576232.4713 | 26028014.2476 | 0 | 29604246.7189
5509 | 2728447.5306 | 2777766.5735 | 848523.4867 | 6354737.5908
5510 | 2052117.2971 | 6673328.8138 | 1843464.3046 | 10568910.4155
5511 | 3024544.107 | 2933379.4856 | 1578598.0621 | 7536521.6547
5512 | 1891933.5129 | 1737953.5265 | 712796.8887 | 4342683.928
5513 | 7972586.7251 | 0 | 7310772.3341 | 15283359.0592
5514 | 26210000.5825 | 5045429.1464 | 1784460.9011 | 33039890.6299
5515 | 4922045.9141 | 0 | 9111906.5409 | 14033952.455
5516 | 3658957.3962 | 9679248.8844 | 16007504.3265 | 29345710.6071
5517 | 8877189.9222 | 14727526.9255 | 0 | 23604716.8477
5518 | 19440021.5441 | 6525328.702 | 1399997.9661 | 27365348.2122
5519 | 6474503.564 | 13468489.1795 | 291639.1552 | 20234631.8986
5520 | 5075238.8453 | 0 | 2199162.3385 | 7274401.1838
5521 | 5242590.8514 | 26355902.2493 | 6448887.8167 | 38047380.9175
5522 | 2526131.6106 | 2256768.8709 | 1318220.3704 | 6101120.8518
5523 | 10002212.8957 | 0 | 4573076.2753 | 14575289.171
5524 | 19811879.2066 | 6664053.3971 | 949138.3568 | 27425070.9606
5525 | 3072922.5385 | 7062887.9927 | 210986.2451 | 10346796.7763
5526 | 3133424.7506 | 6012247.9947 | 666604.6289 | 9812277.3742
5527 | 15205401.7616 | 5357608.1624 | 0 | 20563009.9241
5528 | 16340620.1096 | 2501551.6919 | 4325498.3378 | 23167670.1393
5529 | 19103999.4587 | 9663471.07 | 929412.504 | 29696883.0328
5530 | 6988805.6455 | 4124577.4507 | 3806766.3065 | 14920149.4027
5531 | 9968901.7719 | 1861268.5574 | 102055.0373 | 11932225.3666
5532 | 6015426.3078 | 2840784.8127 | 2396864.7705 | 11253075.891
5533 | 4173815.2644 | 2977043.1267 | 1312584.785 | 8463443.1762
5534 | 6344115.7594 | 9635685.6228 | 183300.3383 | 16163101.7204
5535 | 27706265.6532 | 6310812.1196 | 0 | 34017077.7728
5536 | 1246637.343 | 8115085.0324 | 1037063.361 | 10398785.7364
5537 | 897769.5695 | 17388966.4839 | 192510.093 | 18479246.1464
5538 | 2522123.4245 | 7861587.4097 | 631017.2402 | 11014728.0744
5539 | 11090883.6726 | 3935682.6621 | 0 | 15026566.3347
5540 | 17686201.1731 | 9018314.4096 | 325461.1759 | 27029976.7585
5541 | 1965386.4983 | 0 | 0 | 1965386.4983
5542 | 5054395.9522 | 11351884.6028 | 59934.9958 | 16466215.5508
5543 | 19421665.2245 | 167115.6999 | 3348749.9855 | 22937530.91
5544 | 8095279.9456 | 7987258.9934 | 6672866.1119 | 22755405.0509
5545 | 8645942.1467 | 3174915.2121 | 1709499.9964 | 13530357.3552
5546 | 30061145.377 | 12630034.9205 | 19337347.3038 | 62028527.6013
5547 | 996766.9689 | 25113812.7019 | 1034382.2102 | 27144961.881
5548 | 7471436.702 | 0 | 18854.5444 | 7490291.2464
5549 | 7200736.6223 | 32691848.4805 | 72522.9702 | 39965108.0729
5550 | 13762660.8457 | 2977131.5211 | 2039731.6954 | 18779524.0621
5551 | 9763139.2272 | 18037392.2255 | 751493.3487 | 28552024.8013
5552 | 2423120.7389 | 4892743.9934 | 52365.7386 | 7368230.4709
5553 | 2706606.9292 | 7676061.6653 | 171989.3489 | 10554657.9434
5554 | 9640412.6441 | 13725781.4739 | 0 | 23366194.1179
5555 | 4048484.0124 | 8962890.5517 | 36339442.3002 | 49350816.8643
5556 | 4151857.6675 | 17478086.0152 | 24318992.7063 | 45948936.3891
5557 | 18937343.9701 | 13325101.7055 | 187093.6278 | 32449539.3034
5558 | 7009568.124 | 7419747.5393 | 2320619.8492 | 16749935.5125
5559 | 3937448.0185 | 20310504.6363 | 305869.1481 | 24553821.803
5560 | 4977677.674 | 0 | 1917161.6354 | 6894839.3094
5561 | 17140863.7298 | 2084691.0903 | 7265844.4289 | 26491399.249
5562 | 10782028.4762 | 4251321.9693 | 10422827.3701 | 25456177.8155
5563 | 29496295.8985 | 4931907.1287 | 578943.9631 | 35007146.9903
5564 | 20249343.9206 | 18618346.0096 | 72897.9256 | 38940587.8558
5565 | 4763063.3479 | 0 | 4507173.9224 | 9270237.2703
5566 | 8067520.5668 | 2841113.0466 | 999310.7232 | 11907944.3365
5567 | 20783360.1037 | 7323753.2135 | 608800.5727 | 28715913.8899
5568 | 8566551.8005 | 18532958.9416 | 514427.0157 | 27613937.7579
5569 | 723306.6608 | 4956665.5682 | 1082826.6952 | 6762798.9242
5570 | 7916923.2733 | 18312988.8578 | 0 | 26229912.1312
5571 | 1348565.3205 | 3328391.5321 | 5822429.7094 | 10499386.5619
5572 | 12103464.4602 | 7717734.0298 | 300411.891 | 20121610.381
5573 | 3547370.8594 | 4577070.3196 | 2026331.2511 | 10150772.4302
5574 | 19178026.4902 | 15704114.9152 | 983937.6668 | 35866079.0722
5575 | 6891383.0656 | 10073364.1815 | 1637923.2872 | 18602670.5342
5576 | 2837950.1895 | 4488354.5395 | 732938.8832 | 8059243.6121
5577 | 858193.449 | 0 | 587630.5613 | 1445824.0103
5578 | 8905827.1817 | 22647914.6225 | 5188554.5329 | 36742296.3371
5579 | 2142196.3034 | 3481214.8583 | 38542.3587 | 5661953.5204
5580 | 28270810.9136 | 9143735.6787 | 247596.6885 | 37662143.2808
5581 | 4884627.2664 | 185512.301 | 5377761.6487 | 10447901.2161
5582 | 4087888.4284 | 10340767.1223 | 756399.5452 | 15185055.0959
5583 | 3079577.6949 | 5792464.399 | 627186.2294 | 9499228.3234
5584 | 15127760.6756 | 3550692.6992 | 0 | 18678453.3748
5585 | 10941740.7447 | 10564880.1217 | 877676.6574 | 22384297.5238
5586 | 11316488.1173 | 4100103.2027 | 0 | 15416591.32
5587 | 1061360.5377 | 5366121.876 | 0 | 6427482.4136
5588 | 33861260.4718 | 16612376.4103 | 72648.6505 | 50546285.5326
5589 | 5917729.7155 | 742489.2754 | 1420954.3543 | 8081173.3452
5590 | 7001485.9151 | 0 | 401783.4726 | 7403269.3877
5591 | 10032033.5947 | 6190724.8136 | 1433921.3384 | 17656679.7467
5592 | 8126514.3272 | 0 | 11078247.4791 | 19204761.8063
5593 | 1482054.5301 | 1971977.4583 | 662935.3501 | 4116967.3385
5594 | 1968393.6534 | 8173418.017 | 904967.2126 | 11046778.8829
5595 | 11797421.9884 | 2848458.9034 | 13249368.5826 | 27895249.4743
5596 | 3353948.6522 | 21804443.0792 | 3842708.6139 | 29001100.3453
5597 | 873861.3341 | 0 | 870593.2485 | 1744454.5826
5598 | 4353848.957 | 5077816.7589 | 0 | 9431665.7159
5599 | 16437630.2232 | 5322463.9591 | 9317431.7951 | 31077525.9774
5600 | 5209894.806 | 1435018.2698 | 14347.7672 | 6659260.8429
5601 | 2669725.8862 | 2521108.6486 | 503635.4532 | 5694469.988
5602 | 11401258.6002 | 18955225.807 | 0 | 30356484.4071
5603 | 10464923.1434 | 6903434.352 | 15108161.3864 | 32476518.8819
5604 | 3462077.4198 | 0 | 1555534.9884 | 5017612.4082
5605 | 1517698.7647 | 6100013.8423 | 3107132.1973 | 10724844.8043
5606 | 7775694.8692 | 3627907.4151 | 191729.5809 | 11595331.8653
5607 | 6854433.4733 | 7580227.4504 | 234364.594 | 14669025.5177
5608 | 17588906.4655 | 6425381.4535 | 0 | 24014287.9191
5609 | 18767990.2698 | 7751919.176 | 1815317.1855 | 28335226.6314
5610 | 9167451.5363 | 0 | 2188703.163 | 11356154.6993
5611 | 3968643.4812 | 8459719.1839 | 0 | 12428362.6651
5612 | 8297106.2326 | 7229402.7104 | 1808368.1593 | 17334877.1023
5613 | 4331266.2171 | 7075324.0245 | 2497344.874 | 13903935.1155
5614 | 12688051.1422 | 601443.4803 | 0 | 13289494.6225
5615 | 9949594.7836 | 0 | 7023042.6961 | 16972637.4798
5616 | 3815989.7846 | 4174857.2015 | 5040716.8901 | 13031563.8762
5617 | 18983838.9711 | 0 | 1299248.2189 | 20283087.19
5618 | 8140243.1121 | 11265414.3775 | 1133249.3334 | 20538906.823
5619 | 1524358.9246 | 11978326.4598 | 991394.0751 | 14494079.4595
5620 | 28482643.9524 | 8415201.2262 | 1824162.385 | 38722007.5637
5621 | 8429277.3011 | 0 | 13654080.5109 | 22083357.812
5622 | 10443249.8289 | 2392950.9503 | 0 | 12836200.7792
5623 | 14276394.726 | 0 | 1373795.9497 | 15650190.6757
5624 | 12778501.8806 | 4859352.7669 | 497825.2548 | 18135679.9023
5625 | 4700177.7365 | 11544906.5728 | 332025.7366 | 16577110.0459
5626 | 13145956.8646 | 6210345.2464 | 0 | 19356302.111
5627 | 655034.2362 | 8441295.0424 | 3166425.914 | 12262755.1926
5628 | 31295683.9812 | 9550957.0361 | 2146173.3141 | 42992814.3314
5629 | 4525388.7701 | 5270560.1755 | 1329823.6467 | 11125772.5923
5630 | 44784020.2068 | 3865563.5185 | 2986122.5956 | 51635706.3209
5631 | 2098856.5977 | 1271727.3433 | 576192.5538 | 3946776.4948
5632 | 28166847.7703 | 19210012.3738 | 1468388.0171 | 48845248.1611
5633 | 1915417.4536 | 4733582.4866 | 2384026.6632 | 9033026.6034
5634 | 12355174.6066 | 4094138.1686 | 744180.5377 | 17193493.3129
5635 | 597693.6067 | 4406496.019 | 81557.3541 | 5085746.9798
5636 | 8233182.2419 | 26175428.2001 | 2032327.1104 | 36440937.5524
5637 | 10440027.7912 | 5702718.8343 | 323329.0899 | 16466075.7155
5638 | 3044542.7204 | 934211.4029 | 1747961.1965 | 5726715.3197
5639 | 1720884.5983 | 4791832.8075 | 0 | 6512717.4058
5640 | 8763639.6686 | 20451216.6653 | 597101.1657 | 29811957.4997
5641 | 2490381.1607 | 16335458.67 | 3784946.4143 | 22610786.245
5642 | 28268280.0633 | 6786527.0823 | 721079.697 | 35775886.8426
5643 | 10300457.1981 | 6311561.1387 | 5883016.2915 | 22495034.6283
5644 | 15957083.2765 | 16082252.969 | 3902785.0132 | 35942121.2586
5645 | 8577703.21 | 14319556.6687 | 566176.7219 | 23463436.6006
5646 | 5506586.8818 | 7943523.2849 | 543198.5078 | 13993308.6745
5647 | 5686092.5363 | 23120066.2547 | 747521.6669 | 29553680.4579
5648 | 16457806.1567 | 0 | 243244.588 | 16701050.7447
5649 | 27455931.3885 | 1461147.4129 | 17049407.4191 | 45966486.2204
5650 | 4258223.0823 | 22806463.6828 | 3270173.628 | 30334860.3931
5651 | 16865587.6542 | 9158373.5906 | 0 | 26023961.2448
5652 | 8168286.2728 | 4776855.136 | 1399605.9879 | 14344747.3968
5653 | 26371152.3188 | 14748647.7172 | 0 | 41119800.036
5654 | 13771752.5845 | 2176085.6639 | 173714.6822 | 16121552.9306
5655 | 25053888.149 | 6581320.0455 | 1474150.6013 | 33109358.7958
5656 | 11276816.8506 | 4341607.1306 | 12311583.6036 | 27930007.5847
5657 | 3651362.703 | 4721702.912 | 1458198.0288 | 9831263.6438
5658 | 11548629.6799 | 1640507.7346 | 9455139.4576 | 22644276.8721
5659 | 5528891.5893 | 2924622.6084 | 0 | 8453514.1977
5660 | 16292336.1479 | 3113068.8899 | 6953567.3706 | 26358972.4085
5661 | 10853630.1244 | 4236353.4866 | 0 | 15089983.611
5662 | 27804739.9573 | 4025295.3548 | 23933977.2599 | 55764012.572
5663 | 5243969.7708 | 0 | 108869.1012 | 5352838.8719
5664 | 5611327.3409 | 0 | 95741.3594 | 5707068.7003
5665 | 6963900.4734 | 8725264.9818 | 2343683.0496 | 18032848.5048
5666 | 4533394.6552 | 0 | 1035552.9805 | 5568947.6356
5667 | 15822158.3582 | 10478564.5672 | 4456722.496 | 30757445.4214
5668 | 31897543.9084 | 11199820.0383 | 311050.7869 | 43408414.7336
5669 | 8143034.3355 | 5160027.6876 | 17167.4378 | 13320229.4609
5670 | 11063881.5036 | 1959287.7507 | 76270.5847 | 13099439.8389
5671 | 13352644.9097 | 1725946.1073 | 10279986.9369 | 25358577.954
5672 | 6715196.127 | 5087197.4915 | 8989.0199 | 11811382.6385
5673 | 1348941.5239 | 0 | 829319.8764 | 2178261.4002
5674 | 7947318.5004 | 2621956.8497 | 45788.5845 | 10615063.9345
5675 | 16888977.3643 | 0 | 0 | 16888977.3643
5676 | 2056054.6302 | 4264907.9761 | 70035.1167 | 6390997.723
5677 | 5146733.522 | 0 | 2778393.6818 | 7925127.2038
5678 | 1215563.2425 | 5741888.5559 | 0 | 6957451.7984
5679 | 4931974.3857 | 4165906.477 | 0 | 9097880.8627
5680 | 9251483.5547 | 3538986.5732 | 4424495.5768 | 17214965.7047
5681 | 1938483.5887 | 805038.8532 | 2997376.6119 | 5740899.0538
5682 | 5405791.6622 | 4758066.588 | 33695.0169 | 10197553.267
5683 | 463762.9796 | 0 | 0 | 463762.9796
5684 | 19533449.0289 | 21079594.9443 | 1765731.6522 | 42378775.6254
5685 | 8966502.9181 | 13450372.2918 | 338697.1729 | 22755572.3828
5686 | 1068245.2442 | 2924958.1941 | 959451.485 | 4952654.9234
5687 | 3950229.2979 | 2764408.5988 | 0 | 6714637.8967
5688 | 4708859.7412 | 9894439.8811 | 0 | 14603299.6223
5689 | 15793210.2737 | 13848272.3302 | 2173723.9847 | 31815206.5886
5690 | 2665257.5373 | 15729542.7044 | 0 | 18394800.2417
5691 | 21981600.3086 | 14488789.1462 | 2778143.5795 | 39248533.0343
5692 | 2688515.6301 | 0 | 6064022.0519 | 8752537.682
5693 | 9246998.396 | 9329869.7194 | 7184318.1961 | 25761186.3114
5694 | 26904204.2179 | 2210567.2337 | 10037643.6657 | 39152415.1173
5695 | 45821857.7674 | 13726134.1284 | 669830.279 | 60217822.1748
5696 | 9389288.8442 | 6030471.7078 | 1737061.0762 | 17156821.6283
5697 | 23544050.3279 | 9406250.0673 | 2741561.603 | 35691861.9982
5698 | 3328536.1945 | 1941914.0925 | 890647.6626 | 6161097.9495
5699 | 3878283.0868 | 0 | 0 | 3878283.0868
5700 | 37787069.2308 | 8152426.354 | 1887391.2182 | 47826886.8031
5701 | 7227130.8443 | 5925560.135 | 1317364.0426 | 14470055.0219
5702 | 10594790.8984 | 0 | 0 | 10594790.8984
5703 | 2437622.0606 | 1910605.0644 | 2808303.5891 | 7156530.7141
5704 | 119559.5177 | 3959524.09 | 106799.6903 | 4185883.298
5705 | 10395902.1465 | 6244809.7368 | 869720.2285 | 17510432.1119
5706 | 9094380.5222 | 0 | 0 | 9094380.5222
5707 | 6365754.8779 | 0 | 0 | 6365754.8779
5708 | 5661220.2983 | 0 | 1229806.6637 | 6891026.962
5709 | 634384.5727 | 7345522.7407 | 0 | 7979907.3134
5710 | 5387429.5961 | 0 | 6667477.7648 | 12054907.3609
5711 | 9085622.3812 | 853471.8565 | 76533.9678 | 10015628.2054
5712 | 5160997.8539 | 2233071.7231 | 1332493.2018 | 8726562.7788
5713 | 10691472.8023 | 1098836.1446 | 0 | 11790308.9469
5714 | 2538747.783 | 3832317.1947 | 1343112.5234 | 7714177.5011
5715 | 5405897.9483 | 2357539.2574 | 206596.5679 | 7970033.7736
5716 | 42527431.7645 | 24797241.2403 | 1485534.8345 | 68810207.8393
5717 | 4695183.9515 | 13811882.0949 | 373420.4985 | 18880486.5449
5718 | 5169607.1073 | 0 | 1185661.0606 | 6355268.1678
5719 | 751349.4355 | 3318958.8176 | 3373452.1256 | 7443760.3787
5720 | 1537619.7921 | 6785207.6438 | 1499701.5168 | 9822528.9528
5721 | 4174240.9061 | 0 | 609631.7307 | 4783872.6369
5722 | 16791095.6531 | 22756467.8726 | 504207.6273 | 40051771.1531
5723 | 6656898.1125 | 2041497.8289 | 0 | 8698395.9415
5724 | 2951792.023 | 2008233.7723 | 0 | 4960025.7953
5725 | 24056430.5622 | 28352646.9228 | 0 | 52409077.485
5726 | 10757957.4298 | 2207657.6471 | 1987570.459 | 14953185.5359
5727 | 3446581.0359 | 30530967.3184 | 103902.1669 | 34081450.5212
5728 | 49388.4444 | 14512382.8281 | 1162419.3949 | 15724190.6675
5729 | 169296.2213 | 0 | 3829125.0065 | 3998421.2278
5730 | 6219011.6295 | 5181051.9802 | 492633.4979 | 11892697.1076
5731 | 4438886.5078 | 5047163.936 | 3020003.55 | 12506053.9938
5732 | 6979847.0148 | 5598089.5514 | 165840.5952 | 12743777.1614
5733 | 24900553.9925 | 8961674.3311 | 9809038.4758 | 43671266.7994
5734 | 5186858.905 | 0 | 284574.0317 | 5471432.9367
5735 | 13704428.2464 | 7249679.3717 | 13439692.1982 | 34393799.8163
5736 | 13438661.3842 | 8673383.8931 | 1945881.1989 | 24057926.4762
5737 | 4345544.2326 | 0 | 3829136.8232 | 8174681.0558
5738 | 9449968.3756 | 4166733.8612 | 339795.7503 | 13956497.9871
5739 | 418367.174 | 7956905.2926 | 771886.9724 | 9147159.439
5740 | 16179820.1507 | 5586640.932 | 130349.0314 | 21896810.1141
5741 | 3760681.0974 | 14345856.3411 | 5507051.4343 | 23613588.8728
5742 | 4172787.9775 | 5883593.7333 | 828023.4258 | 10884405.1366
5743 | 8504309.3975 | 2348356.8081 | 4825793.2619 | 15678459.4674
5744 | 6849248.9919 | 3106799.045 | 32793.5965 | 9988841.6335
5745 | 3777275.844 | 0 | 591960.1886 | 4369236.0327
5746 | 1485141.2446 | 19800046.6762 | 1600989.6326 | 22886177.5534
5747 | 973425.4942 | 7004446.8074 | 713408.1151 | 8691280.4167
5748 | 5286849.4656 | 3368536.0092 | 4241812.3179 | 12897197.7926
5749 | 1611185.6752 | 4329559.911 | 28780.6909 | 5969526.2771
5750 | 18906774.3063 | 7256017.3887 | 652893.7158 | 26815685.4108
5751 | 4821008.1435 | 7350159.8236 | 2123607.1593 | 14294775.1265
5752 | 14602268.2448 | 11646848.2581 | 893135.8168 | 27142252.3196
5753 | 7443840.7639 | 0 | 421988.1206 | 7865828.8845
5754 | 16043134.8788 | 2775394.8989 | 11335534.2366 | 30154064.0143
5755 | 2050886.8014 | 5562962.0083 | 1660885.6375 | 9274734.4472
5756 | 6126846.6005 | 929680.323 | 243578.1889 | 7300105.1124
5757 | 2475646.8884 | 2100408.015 | 47194.7756 | 4623249.679
5758 | 980352.9896 | 13794167.8295 | 913351.5096 | 15687872.3287
5759 | 17534537.4367 | 2217552.4222 | 1197429.5584 | 20949519.4172
5760 | 15897164.2427 | 14793612.3166 | 507720.5128 | 31198497.0722
5761 | 2322765.2607 | 3710703.8362 | 6390382.8781 | 12423851.975
5762 | 4193895.9328 | 2823652.4872 | 213889.7521 | 7231438.1721
5763 | 11559243.0173 | 4419854.103 | 0 | 15979097.1202
5764 | 10749958.0132 | 5261371.5012 | 10849196.1624 | 26860525.6768
5765 | 33753281.7527 | 10221370.7301 | 9830743.0426 | 53805395.5254
5766 | 8433087.8622 | 3888981.5857 | 18521039.0494 | 30843108.4973
5767 | 4233667.334 | 11621312.6427 | 2531528.6543 | 18386508.6309
5768 | 23023012.0469 | 6594104.4368 | 4089478.0721 | 33706594.5558
5769 | 17039503.6913 | 4904030.9334 | 597328.3175 | 22540862.9422
5770 | 29043412.1046 | 6676124.1202 | 217763.7673 | 35937299.9922
5771 | 0 | 10768176.2372 | 570197.0099 | 11338373.2471
5772 | 4727515.0755 | 12252341.498 | 2143604.8762 | 19123461.4496
5773 | 6182462.0718 | 1292728.4311 | 7644976.3458 | 15120166.8488
5774 | 6369627.6344 | 0 | 1389237.2561 | 7758864.8905
5775 | 6069427.0294 | 4908867.9963 | 2060888.7322 | 13039183.7578
5776 | 7155130.3607 | 0 | 0 | 7155130.3607
5777 | 8658581.6647 | 18444530.2944 | 8127635.9441 | 35230747.9032
5778 | 14505320.7812 | 2290834.6796 | 1272715.9686 | 18068871.4295
5779 | 13272181.7055 | 0 | 4652452.0285 | 17924633.734
5780 | 6683835.8249 | 5017365.0394 | 3248089.7767 | 14949290.6409
5781 | 3557533.3518 | 2773785.1255 | 536695.1488 | 6868013.626
5782 | 16421344.6852 | 6745988.2913 | 0 | 23167332.9765
5783 | 3052153.0292 | 396469.4987 | 2723737.4084 | 6172359.9363
5784 | 15391126.3732 | 7879502.8441 | 160692.6697 | 23431321.887
5785 | 10363943.9592 | 5820235.018 | 20777303.2624 | 36961482.2395
5786 | 18237729.33 | 0 | 3168295.6889 | 21406025.0189
5787 | 9620564.0364 | 11151665.4303 | 5270611.435 | 26042840.9018
5788 | 1177295.3527 | 5575338.4681 | 876399.7351 | 7629033.556
5789 | 6127677.855 | 10144077.3631 | 0 | 16271755.2181
5790 | 4025548.0811 | 6837982.4199 | 324945.7595 | 11188476.2606
5791 | 21013888.8567 | 11377055.5042 | 5408268.6598 | 37799213.0207
5792 | 10041537.9249 | 4689821.1891 | 652208.2123 | 15383567.3263
5793 | 16414900.6438 | 2744351.6747 | 0 | 19159252.3184
5794 | 2888621.0533 | 10637924.5519 | 1324827.6926 | 14851373.2978
5795 | 10581413.9636 | 6545383.5607 | 0 | 17126797.5243
5796 | 2121329.3575 | 9357064.3421 | 9723988.7652 | 21202382.4647
5797 | 4033812.1016 | 2265548.6674 | 0 | 6299360.769
5798 | 5454066.9291 | 5896668.3006 | 325715.6254 | 11676450.8551
5799 | 4249654.8687 | 2109784.8236 | 118791.7749 | 6478231.4672
5800 | 6053546.9854 | 5578313.5706 | 409326.6501 | 12041187.2061
5801 | 6827476.6805 | 9497349.0133 | 349648.2336 | 16674473.9274
5802 | 4057108.7913 | 5737360.9727 | 686341.3334 | 10480811.0974
5803 | 6324228.9468 | 6984171.2663 | 57119.8018 | 13365520.0149
5804 | 12759689.1112 | 5327606.9925 | 0 | 18087296.1038
5805 | 2878304.9442 | 5889613.1561 | 32870.2037 | 8800788.3039
5806 | 3462152.9267 | 0 | 11564551.5335 | 15026704.4601
5807 | 7145559.5045 | 12290139.6952 | 957208.5534 | 20392907.7531
5808 | 4942414.1311 | 3950723.4628 | 8118207.5659 | 17011345.1598
5809 | 3178223.3268 | 26774437.9333 | 2326024.2315 | 32278685.4916
5810 | 10312619.4332 | 0 | 26407.7126 | 10339027.1458
5811 | 10840134.8037 | 0 | 0 | 10840134.8037
5812 | 2818868.1198 | 0 | 248455.7008 | 3067323.8206
5813 | 3662629.5048 | 15440229.2399 | 2784387.7461 | 21887246.4908
5814 | 11603239.2804 | 0 | 471451.9746 | 12074691.2551
5815 | 5388659.3262 | 4222320.6071 | 2608310.0952 | 12219290.0286
5816 | 1355505.4088 | 11627020.2747 | 344626.5222 | 13327152.2057
5817 | 7062044.3013 | 2733956.1373 | 5089316.7269 | 14885317.1655
5818 | 848069.7385 | 6478113.6786 | 534346.2112 | 7860529.6283
5819 | 1861049.8246 | 5495283.2193 | 3219496.522 | 10575829.566
5820 | 1721412.2216 | 18083971.7234 | 17785959.3911 | 37591343.3361
5821 | 4943617.2435 | 8241535.0303 | 6134834.923 | 19319987.1968
5822 | 11704087.7688 | 2807529.0491 | 4444448.8498 | 18956065.6677
5823 | 3574939.9613 | 3139580.5977 | 2890516.6441 | 9605037.203
5824 | 25408460.147 | 2925752.7852 | 2059776.6787 | 30393989.611
5825 | 4748060.9753 | 22040500.3798 | 10527466.5866 | 37316027.9418
5826 | 5958402.0574 | 25942055.7759 | 60490.1484 | 31960947.9817
5827 | 13097817.4638 | 2550473.6191 | 372135.6617 | 16020426.7446
5828 | 9074312.3189 | 5280879.872 | 45074.4234 | 14400266.6143
5829 | 8061780.8039 | 11954871.2704 | 2145425.2829 | 22162077.3573
5830 | 7604121.1351 | 6653808.2701 | 5241412.2354 | 19499341.6406
5831 | 1559156.4816 | 22500774.3363 | 135212.9794 | 24195143.7973
5832 | 4085406.1351 | 4034394.65 | 1875514.2709 | 9995315.0561
5833 | 23301091.2174 | 4654349.5279 | 0 | 27955440.7453
5834 | 1341524.7459 | 5969902.7248 | 109936.2627 | 7421363.7334
5835 | 13412941.3817 | 0 | 1154864.0227 | 14567805.4043
5836 | 12191393.8378 | 11132383.9648 | 0 | 23323777.8026
5837 | 5180286.526 | 8359515.0384 | 1870656.0217 | 15410457.5861
5838 | 3946069.611 | 12547283.6778 | 43644.0017 | 16536997.2905
5839 | 2975573.011 | 10053099.888 | 86594.182 | 13115267.081
5840 | 8179367.5491 | 6275596.5777 | 166609.1863 | 14621573.3131
5841 | 5568029.8873 | 11541342.7021 | 8465242.9185 | 25574615.508
5842 | 6240491.8824 | 9825648.6935 | 3341633.8894 | 19407774.4653
5843 | 17913224.3831 | 10260082.1484 | 1887931.9548 | 30061238.4863
5844 | 3382741.5691 | 7666476.6012 | 0 | 11049218.1703
5845 | 5660484.7203 | 215694.242 | 40489.3611 | 5916668.3233
5846 | 5690245.1036 | 14012497.3759 | 0 | 19702742.4794
5847 | 7929891.4294 | 10974142.7485 | 3268607.2176 | 22172641.3954
5848 | 4192668.1412 | 3001263.0205 | 950452.8543 | 8144384.016
5849 | 5122347.2174 | 2370326.3559 | 5100842.0975 | 12593515.6708
5850 | 6859920.0364 | 4248936.2294 | 135792.7843 | 11244649.0501
5851 | 19088957.8842 | 0 | 444396.7172 | 19533354.6015
5852 | 9333525.0203 | 0 | 35539.3188 | 9369064.3391
5853 | 7300347.5689 | 6886347.3524 | 2175052.0332 | 16361746.9544
5854 | 2045068.9034 | 8590644.4634 | 0 | 10635713.3668
5855 | 219708.6564 | 0 | 44367.4242 | 264076.0807
5856 | 22331778.0263 | 5143519.7503 | 1115245.1534 | 28590542.93
5857 | 9227104.4386 | 5761344.6579 | 6100615.533 | 21089064.6295
5858 | 3022898.6554 | 0 | 1179792.5881 | 4202691.2435
5859 | 12495182.8279 | 2559641.0365 | 2086051.7143 | 17140875.5787
5860 | 4402283.1617 | 932923.5133 | 1497324.0651 | 6832530.7401
5861 | 5480337.0154 | 0 | 3677935.6396 | 9158272.655
5862 | 9555456.054 | 8038388.4494 | 143878.9502 | 17737723.4535
5863 | 1067240.6766 | 0 | 547430.448 | 1614671.1246
5864 | 6837434.1138 | 6649632.5248 | 3229094.0412 | 16716160.6798
5865 | 19389090.3963 | 2672495.1315 | 0 | 22061585.5278
5866 | 12400004.1051 | 4186508.1981 | 10474895.4732 | 27061407.7764
5867 | 14157991.2154 | 14218322.7724 | 679075.0031 | 29055388.9909
5868 | 3802274.2777 | 7574525.3687 | 6412885.5068 | 17789685.1532
5869 | 5677638.2442 | 9675428.279 | 1892466.8468 | 17245533.37
5870 | 18845438.071 | 0 | 0 | 18845438.071
5871 | 7345367.0595 | 13299210.8388 | 786210.3107 | 21430788.209
5872 | 6092211.0366 | 6672587.2326 | 0 | 12764798.2692
5873 | 8606306.3354 | 7200907.6708 | 0 | 15807214.0062
5874 | 2836967.5321 | 1288538.9044 | 0 | 4125506.4365
5875 | 2940945.54 | 0 | 0 | 2940945.54
5876 | 6860660.7328 | 6202279.8998 | 2395390.5587 | 15458331.1913
5877 | 30799912.6112 | 16907976.438 | 0 | 47707889.0492
5878 | 2372529.4396 | 39561634.0777 | 951361.895 | 42885525.4123
5879 | 3462668.0655 | 1636295.0724 | 1848256.8527 | 6947219.9906
5880 | 4626989.878 | 4261724.8067 | 4818745.7614 | 13707460.4461
5881 | 15310900.8227 | 0 | 2050435.3547 | 17361336.1775
5882 | 11836857.0917 | 4935439.3639 | 2783356.9144 | 19555653.3699
5883 | 9450489.9345 | 7025616.3742 | 2417494.5812 | 18893600.8899
5884 | 3379532.8921 | 6212533.3658 | 413978.2148 | 10006044.4727
5885 | 2758743.9703 | 3659590.0804 | 262449.68 | 6680783.7307
5886 | 8454349.7468 | 8305577.7419 | 42875.3696 | 16802802.8583
5887 | 4485418.0283 | 12245871.2573 | 5746556.2099 | 22477845.4954
5888 | 1197351.9025 | 18207091.5362 | 854770.4635 | 20259213.9023
5889 | 10754187.4666 | 17656903.1097 | 0 | 28411090.5763
5890 | 33930186.9826 | 3852353.2449 | 0 | 37782540.2275
5891 | 2485371.0897 | 14197744.3272 | 1384302.7396 | 18067418.1565
5892 | 1725021.7006 | 13503151.1802 | 25809624.4537 | 41037797.3345
5893 | 2415495.4475 | 3027998.2277 | 8056163.0798 | 13499656.755
5894 | 7874660.2718 | 5177581.5766 | 62826.3334 | 13115068.1818
5895 | 8075674.9982 | 12717776.5943 | 3587640.0273 | 24381091.6198
5896 | 7502622.469 | 3732034.4578 | 1317310.3882 | 12551967.3149
5897 | 16553287.5926 | 0 | 0 | 16553287.5926
5898 | 2314759.5049 | 8160488.3523 | 1994908.1266 | 12470155.9837
5899 | 5606706.7 | 6180006.7564 | 0 | 11786713.4564
5900 | 3571503.1853 | 8868699.9435 | 12964725.3117 | 25404928.4405
5901 | 5543039.3361 | 1529598.2607 | 5390758.8015 | 12463396.3983
5902 | 5532418.7626 | 6112342.8507 | 117410.1405 | 11762171.7538
5903 | 5464005.1997 | 10437693.6818 | 0 | 15901698.8814
5904 | 12195435.957 | 429392.8565 | 10354864.874 | 22979693.6875
5905 | 2874321.5953 | 6227209.0605 | 273071.0378 | 9374601.6936
5906 | 4925907.4714 | 5218250.9566 | 92945.0632 | 10237103.4912
5907 | 4604180.9703 | 2632240.8238 | 55738.5601 | 7292160.3542
5908 | 7950603.9369 | 0 | 528640.4449 | 8479244.3818
5909 | 6319666.9729 | 8321406.6872 | 7281545.9676 | 21922619.6277
5910 | 4126746.5817 | 651704.6475 | 1033332.6679 | 5811783.897
5911 | 3548695.5938 | 29593632.8829 | 1637231.1668 | 34779559.6435
5912 | 6016944.7845 | 8086758.4908 | 0 | 14103703.2753
5913 | 16242041.9238 | 9843707.0236 | 1044442.2416 | 27130191.1891
5914 | 13406456.5534 | 1500359.7367 | 973251.8458 | 15880068.1359
5915 | 32170185.2671 | 8791405.7023 | 2570961.0687 | 43532552.0381
5916 | 5554736.3309 | 10903021.6601 | 3602672.2081 | 20060430.199
5917 | 5311313.115 | 862480.1971 | 853884.5514 | 7027677.8635
5918 | 16301229.1366 | 4278256.0761 | 239132.3262 | 20818617.5389
5919 | 6155862.0228 | 0 | 7837.1346 | 6163699.1575
5920 | 4303166.2603 | 4609633.0323 | 1710182.3768 | 10622981.6693
5921 | 19141215.5996 | 0 | 55395.4787 | 19196611.0783
5922 | 1524925.8503 | 0 | 6759456.0141 | 8284381.8645
5923 | 4984796.1232 | 5591790.0147 | 1861117.4894 | 12437703.6273
5924 | 17979435.2298 | 13347360.7244 | 722266.7837 | 32049062.7379
5925 | 9222896.976 | 0 | 0 | 9222896.976
5926 | 4773453.2661 | 6384626.8314 | 1269434.0783 | 12427514.1758
5927 | 826939.287 | 23218719.4763 | 1234641.6998 | 25280300.4632
5928 | 2165355.6377 | 13328732.3338 | 525442.9614 | 16019530.933
5929 | 6407846.7166 | 5177329.0513 | 5406136.5385 | 16991312.3063
5930 | 19672778.6934 | 3439675.5169 | 948643.1727 | 24061097.383
5931 | 18606824.3618 | 5552546.2346 | 227201.8365 | 24386572.4329
5932 | 20837787.3736 | 4160357.7821 | 2603314.4959 | 27601459.6516
5933 | 4805247.4802 | 1810505.8363 | 1293270.7622 | 7909024.0787
5934 | 4997717.1667 | 4027505.9908 | 0 | 9025223.1575
5935 | 126898.2201 | 18379054.6888 | 3323276.373 | 21829229.2818
5936 | 20156838.1756 | 7594195.9653 | 1203987.2358 | 28955021.3767
5937 | 10320719.8337 | 5040893.7947 | 1884538.9805 | 17246152.6089
5938 | 5581096.8019 | 1401657.2751 | 25406.4068 | 7008160.4838
5939 | 3439971.2959 | 8638219.9291 | 0 | 12078191.2251
5940 | 35857253.0822 | 4608388.179 | 2100626.6306 | 42566267.8918
5941 | 4387773.2084 | 0 | 0 | 4387773.2084
5942 | 8756077.6192 | 0 | 227933.0693 | 8984010.6884
5943 | 7726456.7312 | 1049272.079 | 1515395.6483 | 10291124.4584
5944 | 4596778.2989 | 3182450.8336 | 1156141.4201 | 8935370.5527
5945 | 2651356.1841 | 0 | 162155.8082 | 2813511.9924
5946 | 3976056.1922 | 5336148.5654 | 78441.634 | 9390646.3915
5947 | 4745967.2647 | 0 | 2726719.0548 | 7472686.3195
5948 | 3235259.5701 | 0 | 49020.9822 | 3284280.5522
5949 | 11399198.7834 | 0 | 49333.7325 | 11448532.5158
5950 | 4133839.7597 | 13463784.1416 | 17895103.2985 | 35492727.1998
5951 | 4439558.1086 | 0 | 88273.696 | 4527831.8046
5952 | 4024102.6816 | 7337382.8269 | 0 | 11361485.5085
5953 | 3697623.8936 | 4244184.1702 | 1519885.0911 | 9461693.1549
5954 | 20504900.3336 | 6840538.7819 | 5479203.9346 | 32824643.0501
5955 | 6573116.0873 | 16460239.2122 | 5686175.0814 | 28719530.3808
5956 | 24508618.1294 | 1881148.9951 | 1677326.5057 | 28067093.6302
5957 | 5278924.5302 | 0 | 13385846.2633 | 18664770.7935
5958 | 27305261.0193 | 3417424.8242 | 2622482.8881 | 33345168.7316
5959 | 4404096.5215 | 16934350.3802 | 263868.7485 | 21602315.6502
5960 | 3851931.6026 | 9886825.4153 | 9922989.1896 | 23661746.2076
5961 | 3088113.8045 | 3435585.0884 | 7477428.493 | 14001127.3859
5962 | 1730879.6706 | 0 | 4366793.4868 | 6097673.1574
5963 | 521978.3028 | 8934533.9752 | 4687563.5631 | 14144075.841
5964 | 8687798.0294 | 7558698.3033 | 4031399.9403 | 20277896.2729
5965 | 8565158.4118 | 3395672.7028 | 676658.6456 | 12637489.7602
5966 | 8599003.3941 | 7447477.9369 | 9102595.6492 | 25149076.9803
5967 | 22307853.4505 | 1679505.9084 | 859860.4472 | 24847219.8061
5968 | 5251711.2307 | 9831753.9909 | 984722.4468 | 16068187.6684
5969 | 5353467.1044 | 2536018.8207 | 576923.7878 | 8466409.7128
5970 | 12697659.8628 | 9483575.9773 | 1203776.0082 | 23385011.8483
5971 | 6674109.7052 | 1814667.933 | 22918739.4858 | 31407517.124
5972 | 22361490.342 | 0 | 5868933.5011 | 28230423.8431
5973 | 715386.8904 | 27244094.3728 | 927784.1774 | 28887265.4406
5974 | 24631854.6723 | 0 | 4624909.4833 | 29256764.1556
5975 | 7790370.1141 | 15817695.9746 | 531028.259 | 24139094.3478
5976 | 10646359.3847 | 264256.143 | 712023.8043 | 11622639.332
5977 | 44967677.9048 | 0 | 855812.9832 | 45823490.8879
5978 | 6269566.4146 | 4385728.6077 | 1647701.6718 | 12302996.6941
5979 | 6135238.0972 | 0 | 2334948.8496 | 8470186.9468
5980 | 8675616.4696 | 2115773.3882 | 2926559.6624 | 13717949.5201
5981 | 7513261.0699 | 8022501.692 | 287751.6667 | 15823514.4286
5982 | 3507119.149 | 0 | 0 | 3507119.149
5983 | 20048436.8236 | 7941696.4162 | 2226538.7807 | 30216672.0205
5984 | 16967520.7222 | 4813461.0571 | 0 | 21780981.7793
5985 | 6231001.6318 | 5796904.0239 | 1595425.4675 | 13623331.1233
5986 | 10353804.1643 | 3316596.3601 | 458770.7355 | 14129171.2598
5987 | 13223215.5937 | 12035417.6481 | 7537299.3983 | 32795932.64
5988 | 6451569.5439 | 2999009.7938 | 2645233.1808 | 12095812.5185
5989 | 5341943.1411 | 35378265.3404 | 0 | 40720208.4815
5990 | 10533471.7003 | 11932384.1435 | 0 | 22465855.8439
5991 | 5928539.292 | 1903501.5355 | 116762.7109 | 7948803.5384
5992 | 68803663.5134 | 6623372.5806 | 102367.5176 | 75529403.6115
5993 | 663041.2306 | 7137483.066 | 2573200.036 | 10373724.3326
5994 | 20020512.7542 | 12866565.0556 | 3560291.3757 | 36447369.1855
5995 | 2380599.6457 | 19481856.4341 | 4971511.3668 | 26833967.4466
5996 | 792696.1333 | 8202791.9991 | 854943.9913 | 9850432.1236
5997 | 3602714.2936 | 12459261.6118 | 19012545.4805 | 35074521.386
5998 | 2324292.4476 | 0 | 8993641.651 | 11317934.0986
5999 | 5112350.8468 | 0 | 88477.1 | 5200827.9469
6000 | 17315695.7446 | 6218550.5851 | 129301.1758 | 23663547.5056
6001 | 5699213.1336 | 2401943.529 | 0 | 8101156.6626
6002 | 8386161.7415 | 12624343.7994 | 2469933.8519 | 23480439.3928
6003 | 30214357.5404 | 0 | 258848.1545 | 30473205.6949
6004 | 7266343.1592 | 0 | 40600.3718 | 7306943.531
6005 | 3068026.4926 | 317131.8037 | 381653.5219 | 3766811.8182
6006 | 8357859.0199 | 5307801.2515 | 4255459.4156 | 17921119.687
6007 | 7854954.949 | 25137244.1475 | 3390751.7019 | 36382950.7984
6008 | 5351566.1401 | 9868123.0636 | 0 | 15219689.2037
6009 | 2085196.7524 | 8075524.0185 | 315377.0786 | 10476097.8495
6010 | 23800180.9961 | 8669033.7646 | 1195519.6388 | 33664734.3995
6011 | 7295412.5277 | 13698167.8168 | 639444.26 | 21633024.6044
6012 | 7202836.3223 | 33167598.411 | 1699616.621 | 42070051.3543
6013 | 2919330.9587 | 6617286.4725 | 2715868.8246 | 12252486.2558
6014 | 9605373.6373 | 7177130.3455 | 15141775.9705 | 31924279.9533
6015 | 12711839.3153 | 16927543.0671 | 4303031.9975 | 33942414.3799
6016 | 3704663.5827 | 1304280.4645 | 16948131.7037 | 21957075.7508
6017 | 6489021.1751 | 12930788.6779 | 2530227.3858 | 21950037.2388
6018 | 3428576.2198 | 5033034.7207 | 6613888.5999 | 15075499.5404
6019 | 3696666.9626 | 13136347.5344 | 1207556.1071 | 18040570.604
6020 | 5858070.4858 | 7991353.0521 | 2463374.0349 | 16312797.5729
6021 | 7959340.6019 | 10125047.2729 | 7465660.4313 | 25550048.3062
6022 | 15004212.4597 | 0 | 606180.2185 | 15610392.6782
6023 | 13200171.9692 | 8225756.3691 | 1712778.7121 | 23138707.0504
6024 | 7577055.1821 | 13972955.5895 | 526447.5394 | 22076458.311
6025 | 18772220.2728 | 14819380.2735 | 205163.3617 | 33796763.908
6026 | 2870959.4787 | 13941174.4365 | 6656627.905 | 23468761.8201
6027 | 11144045.1224 | 4315571.7771 | 12764935.9446 | 28224552.844
6028 | 18164413.2678 | 10685422.0725 | 0 | 28849835.3403
6029 | 14440385.9191 | 22054978.7085 | 10202307.0663 | 46697671.6939
6030 | 301410.4472 | 0 | 106022.1628 | 407432.61
6031 | 23543606.963 | 6633078.7464 | 666472.7687 | 30843158.4781
6032 | 5102770.9517 | 14376585.1421 | 2629658.5452 | 22109014.639
6033 | 4672249.6638 | 11548287.5613 | 0 | 16220537.2251
6034 | 9327052.9659 | 3434791.8908 | 1022960.6389 | 13784805.4955
6035 | 8929193.9495 | 3595386.5343 | 1227165.7635 | 13751746.2473
6036 | 2199690.2059 | 5360786.796 | 76629.1026 | 7637106.1045
6037 | 16410048.4586 | 12378407.8955 | 5797462.0544 | 34585918.4084
6038 | 891469.6448 | 18850869.0702 | 2471523.3544 | 22213862.0693
6039 | 46597947.6549 | 9309302.5934 | 0 | 55907250.2483
6040 | 24143400.3226 | 2069113.5006 | 4597417.7343 | 30809931.5575
6041 | 14066105.3065 | 3423288.9187 | 6460768.3433 | 23950162.5684
6042 | 727938.7245 | 2052207.5324 | 350274.5953 | 3130420.8522
6043 | 7691838.9972 | 4050218.1877 | 42968.3527 | 11785025.5377
6044 | 1637361.8872 | 2260671.834 | 288614.0511 | 4186647.7724
6045 | 6347817.8452 | 0 | 1618086.9722 | 7965904.8174
6046 | 477571.2509 | 6565012.8002 | 1312514.3218 | 8355098.373
6047 | 5966250.9066 | 0 | 4815522.9049 | 10781773.8114
6048 | 759971.3616 | 2992419.0187 | 1682337.8255 | 5434728.2058
6049 | 10482858.5831 | 34543451.7735 | 1845337.5865 | 46871647.9431
6050 | 7300123.2867 | 0 | 256053.0211 | 7556176.3078
6051 | 10794839.9033 | 19430880.0501 | 279282.5521 | 30505002.5056
6052 | 4863893.9693 | 6750373.9051 | 663148.1756 | 12277416.05
6053 | 1568193.462 | 5601097.953 | 5107713.7336 | 12277005.1486
6054 | 9561779.7868 | 13033208.2274 | 336886.0343 | 22931874.0485
6055 | 5562078.7607 | 12015213.267 | 2421819.5372 | 19999111.5649
6056 | 13567158.9307 | 7178940.8426 | 1150859.9357 | 21896959.7091
6057 | 16686470.1051 | 1420919.2633 | 20446119.7786 | 38553509.1471
6058 | 5565400.9945 | 10499759.8373 | 5677782.414 | 21742943.2458
6059 | 3002236.4361 | 6195488.2678 | 35006.4487 | 9232731.1526
6060 | 32033110.4286 | 3222291.3845 | 391686.1177 | 35647087.9308
6061 | 13184445.526 | 0 | 135455.6262 | 13319901.1522
6062 | 9995549.6621 | 12584843.5339 | 1760500.1677 | 24340893.3637
6063 | 6453174.8781 | 11060224.1314 | 267558.4809 | 17780957.4905
6064 | 2863227.8003 | 772242.0671 | 6453306.506 | 10088776.3734
6065 | 7867411.1848 | 2658945.0472 | 9429.1924 | 10535785.4244
6066 | 2794114.0553 | 5429781.0842 | 5742995.5087 | 13966890.6482
6067 | 1759716.1617 | 4225474.3498 | 2691412.7902 | 8676603.3018
6068 | 11614394.1867 | 4082049.4332 | 205129.067 | 15901572.6869
6069 | 10570211.5593 | 6238882.3027 | 1094306.7195 | 17903400.5815
6070 | 5310917.6087 | 4968096.5761 | 0 | 10279014.1848
6071 | 2550943.2187 | 0 | 607145.8028 | 3158089.0215
6072 | 5149806.2575 | 7886154.0462 | 2381782.5968 | 15417742.9005
6073 | 18935193.0132 | 19309772.3312 | 35383997.1134 | 73628962.4578
6074 | 5042645.8171 | 3413623.3176 | 612215.0092 | 9068484.1438
6075 | 6312634.7809 | 0 | 390224.6073 | 6702859.3881
6076 | 22014893.5833 | 7751618.4046 | 829058.8334 | 30595570.8212
6077 | 2087478.0319 | 10338159.9516 | 0 | 12425637.9836
6078 | 8674463.1732 | 26853350.204 | 242891.7035 | 35770705.0807
6079 | 15949684.7147 | 1782536.1457 | 2178037.3471 | 19910258.2074
6080 | 1704993.0158 | 16429919.0584 | 1717109.1555 | 19852021.2297
6081 | 1370038.8702 | 14321302.8253 | 178575.9037 | 15869917.5992
6082 | 6481905.3568 | 4486572.139 | 2835552.9929 | 13804030.4887
6083 | 13031403.0727 | 14127806.755 | 73311.8385 | 27232521.6662
6084 | 4464808.0658 | 351798.5845 | 4243504.7736 | 9060111.4239
6085 | 7064424.3461 | 5317471.0498 | 790952.3343 | 13172847.7303
6086 | 12071034.6471 | 10058845.7508 | 4523802.5943 | 26653682.9922
6087 | 17027743.3776 | 2290201.6541 | 2307659.8756 | 21625604.9073
6088 | 15974487.3175 | 1433672.5267 | 830092.8631 | 18238252.7073
6089 | 5077307.2534 | 2351888.961 | 8202358.6568 | 15631554.8712
6090 | 2741601.3281 | 4841460.2716 | 0 | 7583061.5997
6091 | 17999677.6725 | 4026673.6848 | 344976.9304 | 22371328.2877
6092 | 9901865.4755 | 2247925.1756 | 3600192.2996 | 15749982.9507
6093 | 6232524.8121 | 4591740.491 | 3433510.1443 | 14257775.4473
6094 | 13776543.3068 | 16768446.6297 | 118109.2688 | 30663099.2053
6095 | 5302981.1734 | 0 | 102192.2793 | 5405173.4527
6096 | 4275099.6648 | 0 | 222745.8711 | 4497845.5359
6097 | 6160216.3943 | 0 | 177006.7163 | 6337223.1106
6098 | 6405922.6874 | 4867042.5442 | 1924767.6377 | 13197732.8693
6099 | 18083783.1775 | 21908766.3614 | 3387011.8994 | 43379561.4383
6100 | 3295597.2584 | 0 | 0 | 3295597.2584
6101 | 3395797.8034 | 2498846.9693 | 6475318.3162 | 12369963.0889
6102 | 5904309.3537 | 18277109.8908 | 0 | 24181419.2446
6103 | 17945501.1707 | 14600171.2466 | 3416572.4183 | 35962244.8356
6104 | 5558970.8702 | 16963231.9833 | 377953.1298 | 22900155.9833
6105 | 2732281.8135 | 22948484.1521 | 0 | 25680765.9656
6106 | 1653349.2216 | 1175498.1901 | 3880046.4702 | 6708893.8819
6107 | 27564395.5627 | 1963207.3371 | 5375417.8039 | 34903020.7037
6108 | 15878265.9028 | 11681913.2572 | 0 | 27560179.16
6109 | 11234862.7227 | 0 | 1626139.6357 | 12861002.3584
6110 | 2771633.349 | 4706542.644 | 427822.3396 | 7905998.3327
6111 | 18197452.7425 | 2561542.9901 | 0 | 20758995.7326
6112 | 7125748.9105 | 0 | 51175.5746 | 7176924.4851
6113 | 6607304.0751 | 6702110.1566 | 85069.4379 | 13394483.6695
6114 | 12613072.1323 | 8629828.2724 | 1887259.9001 | 23130160.3048
6115 | 15359755.9944 | 21017306.9573 | 206090.2136 | 36583153.1652
6116 | 4669939.9747 | 14545892.9952 | 5252287.5398 | 24468120.5097
6117 | 6254567.6159 | 9810925.2058 | 1978987.7273 | 18044480.549
6118 | 7159576.7043 | 6841154.4964 | 10614543.7728 | 24615274.9734
6119 | 4795694.4868 | 1445522.2629 | 1300683.3267 | 7541900.0765
6120 | 17256392.4299 | 4660096.5225 | 752894.3202 | 22669383.2727
6121 | 4536139.3868 | 13774736.8021 | 713636.3968 | 19024512.5856
6122 | 10341564.0954 | 3177184.2445 | 0 | 13518748.3399
6123 | 5413221.6001 | 5437325.9284 | 0 | 10850547.5285
6124 | 8387041.3424 | 3452003.1066 | 2570221.7834 | 14409266.2324
6125 | 892885.2213 | 3792017.6395 | 0 | 4684902.8608
6126 | 9259666.9728 | 3398892.9381 | 2639183.5813 | 15297743.4923
6127 | 8962726.3065 | 6217173.1473 | 2120460.989 | 17300360.4428
6128 | 8853335.2198 | 7214584.1048 | 3677944.8686 | 19745864.1933
6129 | 2791698.1208 | 3235198.5683 | 356445.9806 | 6383342.6698
6130 | 19416994.496 | 5039755.1404 | 642865.1353 | 25099614.7717
6131 | 9694280.6094 | 2171085.681 | 1109254.5187 | 12974620.8092
6132 | 1311960.9472 | 15859467.0218 | 3089507.7125 | 20260935.6816
6133 | 6341345.4993 | 0 | 321394.4554 | 6662739.9547
6134 | 11491304.7594 | 0 | 0 | 11491304.7594
6135 | 12382636.7823 | 12626142.7461 | 0 | 25008779.5284
6136 | 1340938.0054 | 6686266.1757 | 329243.0036 | 8356447.1847
6137 | 6353726.3213 | 6292468.1914 | 532790.736 | 13178985.2486
6138 | 5349890.9925 | 10486066.3754 | 513350.3223 | 16349307.6901
6139 | 4205291.154 | 36647323.1859 | 9444048.4441 | 50296662.7841
6140 | 16800120.7283 | 5223871.8535 | 264764.4064 | 22288756.9882
6141 | 4583384.8548 | 0 | 165341.7027 | 4748726.5575
6142 | 12298221.2231 | 6827876.9424 | 1356962.4245 | 20483060.59
6143 | 3270031.5438 | 0 | 11005097.8431 | 14275129.3869
6144 | 17183604.1036 | 4562692.7731 | 238631.88 | 21984928.7568
6145 | 18534793.5919 | 8129550.8155 | 1241609.8567 | 27905954.2642
6146 | 4625498.3829 | 13904745.5733 | 126681.5384 | 18656925.4946
6147 | 10528444.6065 | 14887852.4739 | 0 | 25416297.0805
6148 | 4708811.6505 | 0 | 0 | 4708811.6505
6149 | 4286720.0186 | 5055725.9335 | 12756849.4656 | 22099295.4177
6150 | 6907264.2181 | 5746439.0961 | 30972028.4767 | 43625731.7909
6151 | 5784218.9112 | 24529459.4629 | 0 | 30313678.3741
6152 | 1604178.1306 | 11722327.4076 | 1221806.3382 | 14548311.8764
6153 | 11353609.2328 | 4380355.0446 | 3501331.1571 | 19235295.4345
6154 | 24429044.7149 | 9746931.7635 | 5065673.9529 | 39241650.4313
6155 | 114360.4584 | 5502425.39 | 2039636.4134 | 7656422.2617
6156 | 7553161.2384 | 0 | 4338440.5024 | 11891601.7408
6157 | 8697219.9214 | 7939553.6349 | 1635605.5665 | 18272379.1229
6158 | 6461727.4345 | 0 | 2475250.5146 | 8936977.9492
6159 | 10204192.2603 | 19110976.0865 | 18247707.0443 | 47562875.3911
6160 | 11779878.9445 | 6558157.0883 | 724901.4569 | 19062937.4897
6161 | 3136547.7235 | 25810766.6039 | 281595.4404 | 29228909.7679
6162 | 1155935.1468 | 0 | 0 | 1155935.1468
6163 | 6686575.269 | 643797.3317 | 11062494.2041 | 18392866.8048
6164 | 3862670.8222 | 16003933.7736 | 1353136.062 | 21219740.6578
6165 | 16349852.1431 | 5329825.7344 | 433750.0304 | 22113427.9079
6166 | 12682351.7688 | 16420693.236 | 440330.4883 | 29543375.4932
6167 | 4661321.217 | 9274599.3672 | 273947.7009 | 14209868.2851
6168 | 3044139.3202 | 2660767.9608 | 2470400.6913 | 8175307.9723
6169 | 2055007.2598 | 5440094.6052 | 710116.4526 | 8205218.3176
6170 | 1806311.1346 | 2836118.35 | 4904577.7108 | 9547007.1954
6171 | 2679574.5148 | 3776808.384 | 1052560.0717 | 7508942.9705
6172 | 8238178.2818 | 8625222.3959 | 0 | 16863400.6777
6173 | 1991166.7453 | 6376486.3673 | 1285716.8261 | 9653369.9388
6174 | 6547169.6698 | 1976285.3903 | 0 | 8523455.0601
6175 | 5836937.5249 | 1833584.676 | 2599740.1117 | 10270262.3126
6176 | 15220733.8312 | 5230598.356 | 402114.9398 | 20853447.127
6177 | 5276725.8178 | 0 | 350675.1499 | 5627400.9677
6178 | 5261307.5403 | 25509067.462 | 929219.6014 | 31699594.6037
6179 | 15266731.2084 | 2869494.537 | 1327341.3774 | 19463567.1227
6180 | 31532884.5039 | 8458918.943 | 0 | 39991803.4469
6181 | 7150247.8594 | 2852246.6704 | 207976.5637 | 10210471.0935
6182 | 14356472.311 | 3978000.0028 | 1181567.4757 | 19516039.7895
6183 | 5612996.0591 | 2028841.683 | 329495.1228 | 7971332.8649
6184 | 11804957.7221 | 3712234.9714 | 9596357.8033 | 25113550.4968
6185 | 9616340.1332 | 0 | 0 | 9616340.1332
6186 | 2168720.1892 | 2059302.5281 | 0 | 4228022.7173
6187 | 2706943.5251 | 5570002.3438 | 3566121.162 | 11843067.0309
6188 | 14553117.1004 | 3460689.136 | 5453315.2431 | 23467121.4796
6189 | 3879802.5101 | 6339079.3709 | 5011845.3964 | 15230727.2774
6190 | 5543576.1521 | 16322373.9598 | 0 | 21865950.1119
6191 | 2836927.0005 | 21835630.411 | 0 | 24672557.4115
6192 | 11771346.428 | 2914936.6206 | 0 | 14686283.0485
6193 | 23724714.7556 | 0 | 1832780.5271 | 25557495.2827
6194 | 1715786.7806 | 1239756.34 | 343179.0689 | 3298722.1894
6195 | 6026005.7984 | 496762.6533 | 10640863.4651 | 17163631.9168
6196 | 8350883.4176 | 10523390.4005 | 2312926.7086 | 21187200.5268
6197 | 9443889.7496 | 16744633.4795 | 599916.4772 | 26788439.7063
6198 | 7317887.7399 | 0 | 2150309.5638 | 9468197.3036
6199 | 1263800.0898 | 11337790.4181 | 1666122.5468 | 14267713.0546
6200 | 4604967.2904 | 2668336.0235 | 0 | 7273303.3139
6201 | 12704221.9991 | 14284525.6012 | 1177803.0182 | 28166550.6185
6202 | 5072235.3446 | 2950685.1057 | 2265824.2965 | 10288744.7468
6203 | 18423690.8615 | 3077450.0235 | 2167977.4124 | 23669118.2974
6204 | 10524155.8631 | 0 | 5713924.8864 | 16238080.7496
6205 | 1231313.7223 | 5159586.4982 | 793926.4378 | 7184826.6583
6206 | 3474431.1489 | 0 | 12511526.0793 | 15985957.2283
6207 | 9966844.3843 | 8509651.3307 | 3818148.8718 | 22294644.5868
6208 | 7433302.6119 | 31570385.7167 | 86763.4988 | 39090451.8275
6209 | 32747885.8718 | 4349857.9168 | 0 | 37097743.7886
6210 | 9557143.2771 | 10967843.136 | 5074722.0069 | 25599708.4201
6211 | 4906481.8 | 273855.3931 | 7701859.3404 | 12882196.5334
6212 | 2684712.8501 | 7177970.4211 | 2674410.6859 | 12537093.9571
6213 | 11475814.5439 | 5045811.4533 | 2115928.283 | 18637554.2801
6214 | 5217107.6692 | 0 | 1462345.6133 | 6679453.2825
6215 | 5122260.6771 | 0 | 22808.2506 | 5145068.9278
6216 | 38507383.1847 | 3389502.4326 | 827356.6866 | 42724242.3039
6217 | 6046028.7586 | 4686469.0212 | 659542.6323 | 11392040.4122
6218 | 11667169.5151 | 3430400.3046 | 42173.3298 | 15139743.1495
6219 | 3000593.2347 | 5933563.0764 | 3161549.9065 | 12095706.2176
6220 | 2095973.2031 | 6416908.4445 | 721368.3755 | 9234250.0231
6221 | 5785901.2942 | 19864571.0311 | 0 | 25650472.3253
6222 | 15104403.9141 | 2768662.7012 | 0 | 17873066.6153
6223 | 3142337.3474 | 4363226.4785 | 1070514.4456 | 8576078.2714
6224 | 2635314.828 | 0 | 472052.8736 | 3107367.7016
6225 | 8573419.8162 | 12410599.39 | 2068693.8209 | 23052713.027
6226 | 4397202.0959 | 6614392.6226 | 0 | 11011594.7185
6227 | 9380454.2388 | 3239885.6587 | 0 | 12620339.8975
6228 | 6306981.5975 | 3823029.3508 | 0 | 10130010.9483
6229 | 9234695.6864 | 1915172.6592 | 1961099.1344 | 13110967.48
6230 | 16677887.7999 | 0 | 173185.7216 | 16851073.5215
6231 | 393702.9244 | 6572385.5875 | 0 | 6966088.5119
6232 | 5933932.0613 | 12508027.849 | 2846760.1043 | 21288720.0147
6233 | 10463741.9148 | 20319647.1622 | 394421.1784 | 31177810.2554
6234 | 3067505.0828 | 17554508.6323 | 4359918.1136 | 24981931.8287
6235 | 1717306.5079 | 6871302.7518 | 1621709.9568 | 10210319.2166
6236 | 3687832.246 | 4601036.0382 | 0 | 8288868.2842
6237 | 85879417.3736 | 11334721.2316 | 130841.9449 | 97344980.55
6238 | 2962915.4455 | 332062.7671 | 2228172.2746 | 5523150.4873
6239 | 4256151.5528 | 696781.1925 | 0 | 4952932.7453
6240 | 13324618.4022 | 3491379.0243 | 3207221.3287 | 20023218.7553
6241 | 4363907.9329 | 7316779.123 | 9492942.567 | 21173629.623
6242 | 978040.2754 | 0 | 387720.3321 | 1365760.6074
6243 | 6305917.4463 | 6240870.9938 | 6094764.3738 | 18641552.814
6244 | 592116.204 | 14411811.8493 | 5391338.6935 | 20395266.7468
6245 | 11062154.0444 | 5359171.3164 | 600949.8564 | 17022275.2173
6246 | 859562.7906 | 4006886.5139 | 385570.8041 | 5252020.1086
6247 | 13314003.3271 | 2930695.9298 | 12230.9714 | 16256930.2283
6248 | 7305054.4864 | 5819067.8639 | 0 | 13124122.3503
6249 | 9567213.2936 | 16502274.4207 | 11773765.6648 | 37843253.3792
6250 | 9907986.7333 | 0 | 844030.7785 | 10752017.5118
6251 | 8309594.2265 | 2983348.2524 | 189718.2053 | 11482660.6841
6252 | 15112411.6676 | 3958082.8943 | 6000988.8233 | 25071483.3852
6253 | 6298797.0196 | 7268203.1318 | 4190877.5163 | 17757877.6677
6254 | 3880299.5485 | 2652046.0582 | 997498.7082 | 7529844.3149
6255 | 22298042.9578 | 2811927.3573 | 785609.1129 | 25895579.4279
6256 | 4446349.6576 | 21477208.803 | 728297.755 | 26651856.2156
6257 | 4772884.9752 | 10101226.3838 | 140013.4994 | 15014124.8583
6258 | 12987504.0818 | 5456167.9907 | 126791.838 | 18570463.9104
6259 | 2681044.1429 | 11658419.1223 | 1772587.3219 | 16112050.5871
6260 | 17010327.1659 | 15856499.1481 | 0 | 32866826.314
6261 | 1769549.4568 | 7500483.6298 | 429350.423 | 9699383.5097
6262 | 5192153.9863 | 4348849.7564 | 1949164.2887 | 11490168.0314
6263 | 6938483.6726 | 5132124.6796 | 0 | 12070608.3522
6264 | 8156344.8057 | 7110739.1612 | 0 | 15267083.9668
6265 | 13749743.2049 | 40623682.1771 | 0 | 54373425.382
6266 | 1109870.687 | 8614185.8754 | 429800.8451 | 10153857.4076
6267 | 1816981.1934 | 1243131.0255 | 0 | 3060112.2189
6268 | 7314828.3299 | 6868629.9419 | 2790906.5001 | 16974364.7719
6269 | 3668781.7335 | 0 | 701664.2838 | 4370446.0172
6270 | 9047969.5755 | 5695351.9787 | 2974471.0112 | 17717792.5654
6271 | 2379954.1843 | 1755463.5312 | 782174.0255 | 4917591.741
6272 | 31492140.6898 | 5519099.5554 | 1606714.2886 | 38617954.5339
6273 | 14685579.6524 | 13330567.627 | 0 | 28016147.2794
6274 | 1871272.2395 | 0 | 2230339.5547 | 4101611.7942
6275 | 3951011.4871 | 0 | 1339545.8446 | 5290557.3317
6276 | 8991925.3164 | 11709461.7487 | 5753569.605 | 26454956.6701
6277 | 4239749.3266 | 4106417.5647 | 75787.9718 | 8421954.863
6278 | 15651082.1804 | 15343450.8071 | 0 | 30994532.9875
6279 | 3942961.4446 | 6740521.6132 | 2772141.2326 | 13455624.2904
6280 | 7316822.19 | 19278669.0283 | 284275.4496 | 26879766.6679
6281 | 17428019.0865 | 22268553.1255 | 568783.3942 | 40265355.6062
6282 | 4496456.1985 | 4024561.4935 | 2161893.579 | 10682911.2709
6283 | 10418539.2718 | 28508217.308 | 0 | 38926756.5798
6284 | 3333571.38 | 4063316.7861 | 78036.154 | 7474924.3201
6285 | 2457574.037 | 10580278.2132 | 2905447.8916 | 15943300.1419
6286 | 27865926.066 | 8355777.8154 | 580521.3594 | 36802225.2408
6287 | 3270177.2665 | 20180927.2172 | 447361.1187 | 23898465.6023
6288 | 24424076.4702 | 12370822.4533 | 0 | 36794898.9235
6289 | 2825195.9777 | 7791367.1212 | 119237.1562 | 10735800.2551
6290 | 5770278.8183 | 6783126.9678 | 0 | 12553405.7861
6291 | 6201601.2896 | 0 | 3113931.6373 | 9315532.9269
6292 | 12934301.8774 | 1770251.0227 | 0 | 14704552.9001
6293 | 8446144.7471 | 0 | 338178.9398 | 8784323.6869
6294 | 7345470.7719 | 8004869.1315 | 5418623.9224 | 20768963.8259
6295 | 2211333.1791 | 4770365.7732 | 9453820.2233 | 16435519.1756
6296 | 687075.6466 | 6398754.2716 | 4301268.3643 | 11387098.2826
6297 | 14703488.3493 | 8195142.7526 | 87298.159 | 22985929.2609
6298 | 3282460.461 | 3221870.3132 | 12898057.073 | 19402387.8472
6299 | 173108.6437 | 18294027.3812 | 5386843.0675 | 23853979.0924
6300 | 10817646.942 | 4436598.7992 | 918373.0959 | 16172618.8371
6301 | 2777180.5703 | 6638215.9015 | 161590.7274 | 9576987.1992
6302 | 11112095.7317 | 5262660.2467 | 2935643.2482 | 19310399.2267
6303 | 1340589.5997 | 429488.638 | 3248890.9461 | 5018969.1838
6304 | 10026897.5504 | 0 | 2518948.5116 | 12545846.062
6305 | 6508314.4798 | 0 | 0 | 6508314.4798
6306 | 12379987.8439 | 1527559.9449 | 2312183.0014 | 16219730.7902
6307 | 4089501.6897 | 3711685.1329 | 779133.2857 | 8580320.1083
6308 | 3019612.1247 | 11046346.4931 | 2438702.4244 | 16504661.0422
6309 | 5914164.024 | 2189912.1612 | 809932.2095 | 8914008.3947
6310 | 4170881.3028 | 0 | 12008888.5723 | 16179769.8751
6311 | 4361507.0213 | 3397687 | 3163901.8897 | 10923095.911
6312 | 1943782.5192 | 14509695.3426 | 2130445.7086 | 18583923.5704
6313 | 11552773.0811 | 2751387.3979 | 0 | 14304160.479
6314 | 5838274.5101 | 4751267.5854 | 1010895.1898 | 11600437.2853
6315 | 4218163.0188 | 0 | 0 | 4218163.0188
6316 | 6213396.9299 | 0 | 4635326.2788 | 10848723.2087
6317 | 16061137.2421 | 966098.5201 | 2462720.1349 | 19489955.897
6318 | 7287337.5577 | 590142.9918 | 213877.2697 | 8091357.8192
6319 | 2197655.7055 | 24464191.4291 | 2126453.6687 | 28788300.8033
6320 | 6473040.1499 | 1947941.799 | 8514217.5565 | 16935199.5054
6321 | 1667879.7617 | 16917972.0081 | 348978.3673 | 18934830.1371
6322 | 12379876.8377 | 9044973.9999 | 851048.1995 | 22275899.037
6323 | 4392555.4883 | 8861137.1121 | 631409.2375 | 13885101.8379
6324 | 3690716.2221 | 2237221.9057 | 0 | 5927938.1277
6325 | 3817236.3359 | 2595738.1796 | 1849164.2218 | 8262138.7374
6326 | 7425040.2832 | 8099788.9232 | 843916.454 | 16368745.6604
6327 | 3996451.8867 | 3764051.2715 | 2787561.6565 | 10548064.8146
6328 | 1445042.1211 | 12185777.4428 | 2101972.4316 | 15732791.9955
6329 | 4881698.7705 | 11985871.8338 | 854920.8195 | 17722491.4237
6330 | 23300362.4674 | 0 | 1978684.6677 | 25279047.1351
6331 | 21072507.3049 | 5158821.2391 | 2390086.969 | 28621415.513
6332 | 3374286.1042 | 0 | 0 | 3374286.1042
6333 | 2102765.7537 | 12295905.8927 | 1795238.2033 | 16193909.8497
6334 | 279769.3122 | 4472439.5483 | 775935.4694 | 5528144.3299
6335 | 17600147.699 | 0 | 1570775.1886 | 19170922.8875
6336 | 17863849.7157 | 1615500.7562 | 1207419.0839 | 20686769.5558
6337 | 6123051.2721 | 13819339.2035 | 2736300.8165 | 22678691.292
6338 | 3093903.5604 | 4098313.6244 | 389631.127 | 7581848.3117
6339 | 7851072.2553 | 5536742.1178 | 263784.8024 | 13651599.1754
6340 | 14445783.1364 | 0 | 751964.8812 | 15197748.0176
6341 | 6343431.4727 | 3090627.2939 | 2254820.0313 | 11688878.7979
6342 | 23903268.9129 | 0 | 3867277.3809 | 27770546.2939
6343 | 2413929.0138 | 7707172.2679 | 803254.321 | 10924355.6027
6344 | 2208275.73 | 11935998.5005 | 496085.1562 | 14640359.3868
6345 | 4128534.3637 | 5939849.719 | 2245644.2134 | 12314028.296
6346 | 2749705.3711 | 28092179.0848 | 1349484.4632 | 32191368.919
6347 | 15487446.3358 | 0 | 0 | 15487446.3358
6348 | 2044125.8253 | 7175599.9663 | 0 | 9219725.7916
6349 | 23844053.5975 | 5997949.0342 | 857968.6764 | 30699971.3081
6350 | 6869890.2715 | 3063952.6326 | 0 | 9933842.9042
6351 | 21695750.3902 | 16817421.6132 | 1655547.0139 | 40168719.0173
6352 | 11294218.2218 | 16401792.7227 | 1472633.5858 | 29168644.5302
6353 | 7839268.9875 | 10003394.7318 | 444008.1879 | 18286671.9072
6354 | 3683098.3334 | 5512273.6748 | 3398686.7183 | 12594058.7265
6355 | 3429496.0808 | 11910472.1365 | 2266543.116 | 17606511.3333
6356 | 9636581.9317 | 22823840.5291 | 3464726.4692 | 35925148.93
6357 | 8795095.1913 | 25387811.2801 | 0 | 34182906.4714
6358 | 4516099.8926 | 4297604.8412 | 2029790.2842 | 10843495.018
6359 | 6132471.8956 | 5362291.0061 | 76824.248 | 11571587.1497
6360 | 28768237.5318 | 5853901.5263 | 2994335.4054 | 37616474.4634
6361 | 4861792.2006 | 14490782.8555 | 3292262.1779 | 22644837.234
6362 | 0 | 3585211.5456 | 4646827.8688 | 8232039.4144
6363 | 4836104.2618 | 4412292.6663 | 4177958.8688 | 13426355.7969
6364 | 6891447.9412 | 3492249.6687 | 2044673.1453 | 12428370.7553
6365 | 3964801.1226 | 6969130.6883 | 39617.6572 | 10973549.468
6366 | 7352873.5791 | 24676867.0401 | 83427.5605 | 32113168.1796
6367 | 6640144.424 | 0 | 0 | 6640144.424
6368 | 1784861.9468 | 0 | 868056.5793 | 2652918.5261
6369 | 1596377.4672 | 12038640.1345 | 11195669.607 | 24830687.2087
6370 | 4855504.3749 | 6843213.697 | 34588.945 | 11733307.017
6371 | 10216734.1476 | 3535821.0461 | 7457724.7738 | 21210279.9675
6372 | 9162051.4654 | 0 | 0 | 9162051.4654
6373 | 2874675.5626 | 3241719.1252 | 42559.3109 | 6158953.9987
6374 | 22169211.0017 | 2145987.4987 | 4093723.6815 | 28408922.1818
6375 | 4927679.8927 | 9786103.8729 | 72077.4012 | 14785861.1669
6376 | 12395730.0459 | 3941130.7407 | 673426.4212 | 17010287.2078
6377 | 2340714.7215 | 5760366.023 | 775858.6599 | 8876939.4044
6378 | 4641066.886 | 3695120.8685 | 1985029.0721 | 10321216.8266
6379 | 17767176.284 | 18265102.9114 | 497716.0601 | 36529995.2556
6380 | 15206329.8871 | 4486146.5082 | 0 | 19692476.3953
6381 | 18471732.2409 | 8831837.3631 | 4929119.9128 | 32232689.5169
6382 | 22367319.4545 | 5839011.6965 | 666751.031 | 28873082.182
6383 | 8432875.0226 | 9454216.5716 | 3361784.4002 | 21248875.9944
6384 | 7361916.2781 | 0 | 0 | 7361916.2781
6385 | 4874127.7731 | 0 | 11350954.5277 | 16225082.3008
6386 | 22145410.9973 | 0 | 57303.1983 | 22202714.1956
6387 | 26703877.779 | 7559128.0802 | 4450313.0647 | 38713318.9239
6388 | 7244639.9674 | 20017590.7497 | 1739238.7401 | 29001469.4572
6389 | 23123515.8664 | 7086861.8499 | 5335328.4496 | 35545706.166
6390 | 11359468.5351 | 2972810.3558 | 2482300.9491 | 16814579.84
6391 | 11680976.7638 | 15824429.3934 | 5386255.4503 | 32891661.6074
6392 | 6392930.5168 | 9141494.2281 | 53955.6286 | 15588380.3735
6393 | 18172120.86 | 11941416.8471 | 854049.9449 | 30967587.652
6394 | 8487087.0751 | 20202290.196 | 10552114.3402 | 39241491.6114
6395 | 26004770.3409 | 0 | 0 | 26004770.3409
6396 | 21573521.1928 | 5651078.7422 | 174165.7669 | 27398765.7019
6397 | 11507055.8228 | 6158019.1332 | 1927162.8182 | 19592237.7742
6398 | 1484527.4663 | 19797593.7932 | 4661921.1017 | 25944042.3612
6399 | 4662049.4444 | 1561828.8896 | 1475261.8764 | 7699140.2104
6400 | 874548.1947 | 25018270.6444 | 702343.1167 | 26595161.9559
6401 | 8969685.9117 | 0 | 1970327.4062 | 10940013.318
6402 | 180655.1077 | 5428074.7681 | 649353.0811 | 6258082.9569
6403 | 8957033.2382 | 1439195.6521 | 476369.6026 | 10872598.493
6404 | 2883158.58 | 0 | 0 | 2883158.58
6405 | 19686973.0074 | 0 | 0 | 19686973.0074
6406 | 6096042.7025 | 9149446.4887 | 1408221.5107 | 16653710.7018
6407 | 15306394.0027 | 9064395.4078 | 35766.2341 | 24406555.6446
6408 | 19098121.6721 | 11970849.38 | 2830164.3176 | 33899135.3697
6409 | 10869932.9678 | 2032629.0456 | 1856397.6412 | 14758959.6546
6410 | 18425541.5477 | 5875328.5956 | 4577546.7774 | 28878416.9208
6411 | 11790851.7793 | 7731167.5377 | 415862.8738 | 19937882.1909
6412 | 7756104.7314 | 5895512.8403 | 756604.2979 | 14408221.8696
6413 | 9410069.264 | 20608256.7917 | 483150.232 | 30501476.2877
6414 | 10629817.7908 | 2316487.9124 | 2339120.2943 | 15285425.9974
6415 | 4678097.6092 | 6424916.1439 | 2135604.8547 | 13238618.6078
6416 | 5212011.7155 | 2200431.8395 | 1933444.8908 | 9345888.4458
6417 | 7461346.2798 | 5616591.9091 | 1133673.7641 | 14211611.953
6418 | 8799139.9846 | 10841671.4865 | 1477840.6993 | 21118652.1704
6419 | 1162574.2312 | 5858564.0032 | 0 | 7021138.2345
6420 | 7719858.1337 | 6457530.4383 | 3713034.9996 | 17890423.5716
6421 | 2335053.3664 | 34525534.0223 | 3798573.0267 | 40659160.4153
6422 | 18149930.0944 | 2092222.7824 | 0 | 20242152.8768
6423 | 17021825.7495 | 7873785.5148 | 4714847.7563 | 29610459.0207
6424 | 6566532.8829 | 13564461.2573 | 3595436.6405 | 23726430.7808
6425 | 21378764.7764 | 4412886.805 | 23659212.0958 | 49450863.6772
6426 | 10458618.6059 | 472398.1414 | 281632.4876 | 11212649.2348
6427 | 14427431.3271 | 4351942.7155 | 908005.5885 | 19687379.6311
6428 | 6161943.2564 | 0 | 4898218.888 | 11060162.1445
6429 | 2898742.4752 | 7175135.9135 | 1233823.3055 | 11307701.6942
6430 | 1990525.6721 | 9180805.3705 | 68343.0575 | 11239674.1001
6431 | 12870634.0491 | 4902036.5877 | 2821141.7177 | 20593812.3544
6432 | 13450183.8476 | 3798403.6913 | 0 | 17248587.5389
6433 | 4716765.2351 | 2405364.3957 | 4386248.4415 | 11508378.0722
6434 | 9503369.5736 | 8800802.437 | 1360312.3649 | 19664484.3754
6435 | 3258328.3006 | 12682616.805 | 687030.9964 | 16627976.102
6436 | 6816519.0705 | 0 | 238791.3349 | 7055310.4054
6437 | 6771766.3557 | 9908330.8805 | 824048.8038 | 17504146.0401
6438 | 4432328.2332 | 3795483.9678 | 2929234.2646 | 11157046.4657
6439 | 12162305.1992 | 1417956.0107 | 0 | 13580261.2099
6440 | 25808169.6925 | 9124030.7181 | 228058.9906 | 35160259.4012
6441 | 13873852.0518 | 5024895.9568 | 192940.4806 | 19091688.4892
6442 | 8346208.0798 | 3538832.999 | 1181035.2868 | 13066076.3656
6443 | 8729213.2501 | 11975371.3685 | 0 | 20704584.6186
6444 | 22089684.365 | 0 | 78389.9395 | 22168074.3045
6445 | 3173495.3529 | 19957079.0703 | 1115355.0097 | 24245929.4329
6446 | 4924280.9185 | 4275164.5619 | 2957437.5154 | 12156882.9958
6447 | 8662973.3186 | 5031932.5042 | 3213125.5469 | 16908031.3697
6448 | 2705413.677 | 11653422.7155 | 661245.3168 | 15020081.7093
6449 | 4036133.0758 | 14122740.6772 | 1244560.2632 | 19403434.0162
6450 | 22561279.3989 | 16274659.6713 | 0 | 38835939.0702
6451 | 4584671.3717 | 0 | 220697.2305 | 4805368.6021
6452 | 7930372.6606 | 17699156.3996 | 0 | 25629529.0601
6453 | 3729638.3021 | 8242212.0389 | 134649.2133 | 12106499.5543
6454 | 11974345.4247 | 10219338.492 | 1463366.4416 | 23657050.3583
6455 | 2407343.7908 | 3809073.0508 | 15940.4964 | 6232357.338
6456 | 8073654.381 | 7587908.9081 | 2474576.9947 | 18136140.2838
6457 | 13999848.4695 | 11803899.0357 | 0 | 25803747.5052
6458 | 17786903.3885 | 9350057.267 | 1497606.8321 | 28634567.4877
6459 | 27316807.0913 | 29080739.1346 | 2401972.3065 | 58799518.5324
6460 | 10030767.3554 | 22715752.2359 | 633177.9525 | 33379697.5439
6461 | 15727642.7129 | 5627332.3079 | 126194.2099 | 21481169.2307
6462 | 4275975.8741 | 7106083.8838 | 2154116.6202 | 13536176.3782
6463 | 12419836.972 | 8054026.2504 | 0 | 20473863.2223
6464 | 2405843.8546 | 9854297.9469 | 16454000.9169 | 28714142.7185
6465 | 5737862.0836 | 14756126.1563 | 2205436.3383 | 22699424.5781
6466 | 22856385.0005 | 2715751.2346 | 474234.0608 | 26046370.2959
6467 | 37542600.1182 | 7949024.8114 | 6096314.8076 | 51587939.7372
6468 | 4018742.9897 | 21233155.3687 | 675002.6977 | 25926901.056
6469 | 3920483.9651 | 2593393.9928 | 627732.7605 | 7141610.7184
6470 | 2085602.7146 | 4142765.4469 | 3794119.6193 | 10022487.7808
6471 | 2309886.9599 | 5452050.3747 | 7416456.3656 | 15178393.7002
6472 | 7750813.2666 | 15150508.8984 | 2401512.5334 | 25302834.6984
6473 | 17230220.8945 | 10130218.3282 | 1533795.9574 | 28894235.1801
6474 | 9895055.7661 | 4608414.7071 | 67569.0181 | 14571039.4914
6475 | 7016285.6672 | 9163491.7829 | 12967680.8675 | 29147458.3176
6476 | 14240005.1282 | 13153270.7706 | 0 | 27393275.8987
6477 | 4436949.7919 | 1959826.6786 | 0 | 6396776.4705
6478 | 11233418.8096 | 5374077.0008 | 264165.4927 | 16871661.3031
6479 | 8714098.1867 | 9449109.3869 | 0 | 18163207.5736
6480 | 5528486.5542 | 5603226.3145 | 1938716.3983 | 13070429.267
6481 | 16839502.222 | 0 | 903669.5527 | 17743171.7747
6482 | 2829460.5884 | 4685843.4524 | 0 | 7515304.0408
6483 | 1353589.4092 | 3549467.6312 | 349019.916 | 5252076.9564
6484 | 9199271.4776 | 3546331.8864 | 0 | 12745603.364
6485 | 10005078.2161 | 7847095.0679 | 955117.9223 | 18807291.2062
6486 | 15394681.1185 | 6491015.0404 | 0 | 21885696.1589
6487 | 6836357.1945 | 5785173.2727 | 709003.3816 | 13330533.8487
6488 | 6887537.7677 | 10259400.7944 | 1739696.6861 | 18886635.2482
6489 | 2512568.9348 | 8615866.6924 | 10778064.0923 | 21906499.7195
6490 | 5617015.7736 | 8075989.5151 | 101407.2581 | 13794412.5469
6491 | 6479179.1038 | 20523263.9625 | 410628.8978 | 27413071.9641
6492 | 10607289.6677 | 1030192.8318 | 2384789.8426 | 14022272.3421
6493 | 10348158.6067 | 12817333.4982 | 0 | 23165492.1049
6494 | 5015840.5851 | 19125685.3069 | 1692758.8687 | 25834284.7608
6495 | 36532086.2599 | 0 | 1914577.1864 | 38446663.4463
6496 | 8981434.5846 | 7044906.825 | 0 | 16026341.4096
6497 | 21049670.781 | 0 | 0 | 21049670.781
6498 | 7393665.6026 | 0 | 4037273.5907 | 11430939.1933
6499 | 4579166.3333 | 8985905.9726 | 2698419.1814 | 16263491.4872
6500 | 25359361.4634 | 845511.3105 | 17720.542 | 26222593.3159
6501 | 8276680.5405 | 2307609.9078 | 0 | 10584290.4484
6502 | 12978939.5222 | 10293143.2685 | 605055.8859 | 23877138.6765
6503 | 8451881.0777 | 0 | 0 | 8451881.0777
6504 | 5585201.7531 | 39710820.8142 | 146547.66 | 45442570.2273
6505 | 6364661.443 | 5527098.511 | 0 | 11891759.954
6506 | 19924322.2328 | 8312060.2926 | 55129.0179 | 28291511.5433
6507 | 6811438.8728 | 0 | 625632.8623 | 7437071.735
6508 | 3100955.1939 | 0 | 8195992.0726 | 11296947.2665
6509 | 1017626.4685 | 1002786.5949 | 699304.4549 | 2719717.5184
6510 | 14106441.3005 | 4271645.2615 | 2135272.4376 | 20513358.9996
6511 | 4309428.0484 | 0 | 0 | 4309428.0484
6512 | 3777741.107 | 3388373.4227 | 2241654.9515 | 9407769.4812
6513 | 7322400.6844 | 1264145.2549 | 1594337.1292 | 10180883.0685
6514 | 1441472.3269 | 16562354.2328 | 556652.2845 | 18560478.8443
6515 | 6266434.7349 | 2461272.7386 | 0 | 8727707.4735
6516 | 4986124.7227 | 3779339.2693 | 3225621.307 | 11991085.299
6517 | 3046934.8855 | 15204237.4183 | 409893.9022 | 18661066.2059
6518 | 11069384.1171 | 5837647.978 | 47052.6989 | 16954084.794
6519 | 7327646.8938 | 1626755.2708 | 10969102.2153 | 19923504.3799
6520 | 11679214.4767 | 1590192.906 | 8216322.1898 | 21485729.5724
6521 | 1210292.5647 | 6693304.53 | 8317842.8864 | 16221439.981
6522 | 204363.1034 | 0 | 1100199.5635 | 1304562.667
6523 | 11889468.0299 | 14037682.7795 | 879197.1392 | 26806347.9486
6524 | 5698434.7928 | 3163772.2075 | 1003805.2229 | 9866012.2232
6525 | 17194607.0635 | 4026862.5698 | 15547722.8262 | 36769192.4595
6526 | 6969140.2054 | 0 | 1706049.909 | 8675190.1144
6527 | 3936212.8889 | 5454480.7687 | 3747059.5955 | 13137753.253
6528 | 10872000.5724 | 4534556.6801 | 311397.6013 | 15717954.8537
6529 | 17745736.9016 | 7527622.2527 | 498371.5689 | 25771730.7232
6530 | 44422967.2012 | 40987829.0817 | 8003771.2596 | 93414567.5425
6531 | 1800536.4269 | 6403553.9846 | 804725.0295 | 9008815.441
6532 | 4869193.7938 | 9313413.8404 | 0 | 14182607.6343
6533 | 9472085.8454 | 3028863.1893 | 1176351.4648 | 13677300.4995
6534 | 12792298.9177 | 12629324.0376 | 762839.5557 | 26184462.511
6535 | 2893866.0774 | 249160.8304 | 1947389.1368 | 5090416.0446
6536 | 2547934.0264 | 2534926.0225 | 434712.0526 | 5517572.1014
6537 | 2600003.697 | 0 | 2369941.3509 | 4969945.048
6538 | 1413546.3591 | 702085.8502 | 1104104.4275 | 3219736.6369
6539 | 2329597.1852 | 3751557.3313 | 148640.6339 | 6229795.1505
6540 | 11330593.1291 | 1036449.4067 | 13183294.6881 | 25550337.2239
6541 | 6912459.5686 | 24809929.6699 | 13102208.9125 | 44824598.151
6542 | 3262841.5018 | 8224226.4898 | 1631263.7771 | 13118331.7686
6543 | 28834016.8986 | 5104118.1989 | 2389939.1325 | 36328074.23
6544 | 24010774.8213 | 3606235.7392 | 10299736.0952 | 37916746.6557
6545 | 22841172.863 | 11018739.8892 | 326356.3577 | 34186269.1099
6546 | 8085044.7224 | 15402582.9842 | 10717155.9591 | 34204783.6657
6547 | 15591477.5196 | 16779246.7342 | 334109.0133 | 32704833.2671
6548 | 10562219.3112 | 7812227.2321 | 0 | 18374446.5433
6549 | 3774508.553 | 2628566.1894 | 2986212.2517 | 9389286.9942
6550 | 5821484.5574 | 6166502.1241 | 6967991.6683 | 18955978.3498
6551 | 1639917.2737 | 6537328.5513 | 575656.8237 | 8752902.6487
6552 | 18786642.8016 | 504611.573 | 732794.9959 | 20024049.3705
6553 | 9857684.6407 | 14305846.4238 | 653215.5615 | 24816746.626
6554 | 7769271.981 | 1464105.9117 | 412320.3491 | 9645698.2418
6555 | 6523554.8602 | 0 | 1371633.7209 | 7895188.5811
6556 | 5141026.3009 | 15939522.3443 | 844626.2565 | 21925174.9017
6557 | 11254141.48 | 6754285.9529 | 0 | 18008427.4329
6558 | 5199184.5261 | 0 | 1140008.0477 | 6339192.5737
6559 | 5167098.2136 | 0 | 2244606.096 | 7411704.3097
6560 | 2274585.8575 | 4455443.8557 | 0 | 6730029.7132
6561 | 2770642.6438 | 29151082.3781 | 16219799.7528 | 48141524.7747
6562 | 22920888.742 | 0 | 440205.888 | 23361094.63
6563 | 5870284.9334 | 12371207.788 | 419505.1377 | 18660997.8591
6564 | 8013595.5561 | 0 | 1306181.4833 | 9319777.0395
6565 | 9475375.5771 | 0 | 565223.393 | 10040598.97
6566 | 21419336.1629 | 10599760.9814 | 3836156.2009 | 35855253.3452
6567 | 19069536.4323 | 0 | 0 | 19069536.4323
6568 | 12247893.3754 | 0 | 210793.0593 | 12458686.4348
6569 | 2137855.5759 | 2670038.6246 | 0 | 4807894.2005
6570 | 1408407.7878 | 5461606.9063 | 230395.6553 | 7100410.3494
6571 | 9775308.1999 | 13690568.9932 | 1814980.5987 | 25280857.7918
6572 | 12563954.6132 | 13672867.0995 | 861480.5816 | 27098302.2943
6573 | 8939349.6073 | 0 | 1106891.888 | 10046241.4953
6574 | 4133949.703 | 20526599.2941 | 5166098.214 | 29826647.2111
6575 | 10211506.993 | 18104611.9779 | 1182012.2416 | 29498131.2125
6576 | 5770562.6085 | 14573038.454 | 1659472.7919 | 22003073.8544
6577 | 1942816.6161 | 0 | 283675.6811 | 2226492.2973
6578 | 3836161.5937 | 11697360.2845 | 2335166.1191 | 17868687.9973
6579 | 1612233.372 | 6603915.5677 | 1826641.1423 | 10042790.082
6580 | 25180465.0458 | 17854444.8069 | 1971833.2932 | 45006743.146
6581 | 2167844.8547 | 2312698.7904 | 0 | 4480543.6451
6582 | 33018630.3072 | 10744206.0713 | 235155.7458 | 43997992.1244
6583 | 29702419.7367 | 22162098.2357 | 2265696.1919 | 54130214.1643
6584 | 10359.1019 | 5619300.3027 | 871300.8057 | 6500960.2103
6585 | 11939676.9777 | 7265103.2067 | 1697251.4976 | 20902031.6819
6586 | 1016230.9932 | 1770788.1554 | 11379945.385 | 14166964.5336
6587 | 15823329.4622 | 4456820.1563 | 704591.4053 | 20984741.0238
6588 | 2702003.5504 | 7260046.2448 | 1905366.831 | 11867416.6261
6589 | 17098713.9655 | 3455853.4014 | 569471.2776 | 21124038.6445
6590 | 2746161.6826 | 15914122.205 | 24127443.4725 | 42787727.3601
6591 | 10518527.1887 | 13613754.5452 | 0 | 24132281.7339
6592 | 26999676.0628 | 12714546.0643 | 949793.7272 | 40664015.8543
6593 | 8214982.5789 | 6202517.459 | 3714365.8348 | 18131865.8726
6594 | 12801472.8366 | 6567728.7322 | 2718249.3589 | 22087450.9277
6595 | 4820737.8715 | 6773784.9156 | 1521929.6809 | 13116452.4679
6596 | 29853755.4147 | 10289027.3912 | 23762575.0169 | 63905357.8228
6597 | 15162621.5658 | 9404341.9206 | 469260.3965 | 25036223.8828
6598 | 9893846.3208 | 17080676.2262 | 1310179.2428 | 28284701.7898
6599 | 5567186.4633 | 1381430.3693 | 400203.9207 | 7348820.7533
6600 | 1204030.2609 | 12367554.6106 | 2959532.8511 | 16531117.7227
6601 | 4054621.8448 | 5475106.7872 | 3002536.5907 | 12532265.2227
6602 | 1066544.4826 | 10361727.642 | 740315.2277 | 12168587.3523
6603 | 2224652.0716 | 16285622.2764 | 3636686.8406 | 22146961.1886
6604 | 13350068.933 | 7462361.4147 | 0 | 20812430.3477
6605 | 10062094.2916 | 2175204.1057 | 1738834.5182 | 13976132.9154
6606 | 13656621.2633 | 2992085.7438 | 0 | 16648707.0072
6607 | 12205215.0744 | 0 | 1574060.1245 | 13779275.1989
6608 | 4508000.5189 | 6764721.6491 | 79923.0051 | 11352645.1732
6609 | 6004271.1166 | 5178432.8877 | 992468.8793 | 12175172.8836
6610 | 12394628.787 | 1305061.0943 | 9468161.38 | 23167851.2613
6611 | 6528879.5019 | 10788367.8899 | 127530.6236 | 17444778.0154
6612 | 1084792.5585 | 6946420.8488 | 319336.1839 | 8350549.5913
6613 | 5776799.0909 | 16454418.3562 | 11383224.263 | 33614441.7101
6614 | 11021588.095 | 3345243.9821 | 35094.8109 | 14401926.8879
6615 | 10323387.8393 | 0 | 3294654.4959 | 13618042.3351
6616 | 9242956.326 | 3742446.8077 | 143350.9132 | 13128754.0469
6617 | 4871537.3653 | 4716845.2402 | 674952.7263 | 10263335.3319
6618 | 5988260.7271 | 2863904.3927 | 157562.4285 | 9009727.5483
6619 | 12401052.0548 | 16241059.5094 | 849984.9828 | 29492096.5471
6620 | 3321323.8948 | 13060007.2949 | 1162265.9887 | 17543597.1784
6621 | 3002771.3591 | 9427915.5027 | 563082.2894 | 12993769.1512
6622 | 12000481.9804 | 28031692.0046 | 184322.9192 | 40216496.9043
6623 | 17810616.9664 | 0 | 261145.64 | 18071762.6064
6624 | 6856519.8467 | 0 | 1452993.0776 | 8309512.9243
6625 | 8783100.8132 | 2788715.3865 | 1029683.1368 | 12601499.3366
6626 | 3224328.4714 | 3698901.5219 | 2010717.9985 | 8933947.9918
6627 | 6753506.3676 | 0 | 3311528.6704 | 10065035.038
6628 | 4105440.5839 | 27659869.8953 | 14537616.8411 | 46302927.3202
6629 | 864329.9677 | 5741589.0993 | 532144.0072 | 7138063.0742
6630 | 930704.5594 | 3827318.0233 | 11267122.5157 | 16025145.0984
6631 | 21843250.5311 | 26725370.7768 | 0 | 48568621.308
6632 | 6133381.34 | 7472291.9955 | 2908104.7795 | 16513778.115
6633 | 18243442.7614 | 5085813.7267 | 357206.5092 | 23686462.9973
6634 | 29769749.9054 | 7056973.2862 | 82129.3951 | 36908852.5867
6635 | 200889.2758 | 4146539.9281 | 15961905.2491 | 20309334.453
6636 | 27025665.9227 | 1309820.3211 | 482829.8847 | 28818316.1285
6637 | 4467281.3609 | 2846668.7714 | 311554.0556 | 7625504.1879
6638 | 9828144.461 | 4508813.566 | 0 | 14336958.0269
6639 | 2128766.957 | 10280129.5861 | 582062.9544 | 12990959.4975
6640 | 4211490.2498 | 2722378.1512 | 1586099.4564 | 8519967.8575
6641 | 5445053.1503 | 3564546.0336 | 1469007.5614 | 10478606.7453
6642 | 11507169.7562 | 17505346.3196 | 1630775.0398 | 30643291.1155
6643 | 16873745.7398 | 2747428.0756 | 693704.1449 | 20314877.9603
6644 | 6843388.6084 | 1384159.5208 | 551311.5375 | 8778859.6668
6645 | 18531027.0367 | 2171668.1344 | 310616.1387 | 21013311.3099
6646 | 6126831.8817 | 10662323.717 | 5957918.2913 | 22747073.89
6647 | 3294824.8999 | 872737.913 | 215792.5189 | 4383355.3318
6648 | 4897883.3305 | 9020500.2277 | 1888101.7414 | 15806485.2995
6649 | 3975910.9859 | 17870143.4159 | 0 | 21846054.4018
6650 | 16053856.4893 | 0 | 121841.8377 | 16175698.327
6651 | 2159403.9343 | 3573385.4858 | 878491.5818 | 6611281.002
6652 | 5344292.6699 | 11169056.4422 | 2274442.3904 | 18787791.5024
6653 | 897149.9897 | 3944886.059 | 5107971.4157 | 9950007.4644
6654 | 12847612.6605 | 15833681.9184 | 2508008.6557 | 31189303.2346
6655 | 4862706.7763 | 2423850.3678 | 1867130.1702 | 9153687.3143
6656 | 4758300.9316 | 0 | 1515896.922 | 6274197.8537
6657 | 1977505.1786 | 2811528.3297 | 3900798.3252 | 8689831.8335
6658 | 9269815.6858 | 3546581.3586 | 3639148.0897 | 16455545.1341
6659 | 3759425.0457 | 0 | 46159.291 | 3805584.3368
6660 | 971239.1647 | 0 | 3635711.8759 | 4606951.0406
6661 | 1995956.9719 | 2637992.7828 | 218987.4304 | 4852937.1851
6662 | 5185813.6699 | 14531915.0008 | 3099669.1153 | 22817397.786
6663 | 2488612.9082 | 8233810.0101 | 557521.2594 | 11279944.1777
6664 | 1408033.8419 | 1658651.3073 | 3996182.3263 | 7062867.4756
6665 | 16463750.8268 | 0 | 77614.8369 | 16541365.6637
6666 | 14441059.4821 | 3064013.4632 | 856622.9103 | 18361695.8557
6667 | 2719424.4035 | 9288823.2012 | 2642063.7843 | 14650311.389
6668 | 8387339.1488 | 0 | 3597465.5613 | 11984804.7101
6669 | 5975762.0461 | 7582707.1657 | 22620.2406 | 13581089.4524
6670 | 13814654.5279 | 0 | 0 | 13814654.5279
6671 | 5875769.3167 | 4312166.4675 | 1186471.6446 | 11374407.4288
6672 | 10442637.0312 | 3223588.23 | 0 | 13666225.2613
6673 | 2371345.1296 | 2017779.6558 | 434324.1518 | 4823448.9372
6674 | 4868339.6226 | 6391544.5097 | 1424777.2324 | 12684661.3647
6675 | 7566502.6068 | 16174894.6789 | 3980770.8651 | 27722168.1509
6676 | 4233788.0024 | 5624458.1716 | 423726.1469 | 10281972.3208
6677 | 26216221.0849 | 10285553.7209 | 1890625.8471 | 38392400.6529
6678 | 15992982.4697 | 3548934.75 | 901822.7477 | 20443739.9674
6679 | 4727747.3234 | 0 | 216863.9774 | 4944611.3008
6680 | 7835293.167 | 8852197.0418 | 109610.2004 | 16797100.4091
6681 | 19739957.8304 | 0 | 671714.1721 | 20411672.0025
6682 | 4166161.7055 | 9252190.5964 | 111277.7227 | 13529630.0245
6683 | 1291783.3638 | 0 | 5470878.7656 | 6762662.1294
6684 | 4406958.6754 | 0 | 784613.5564 | 5191572.2318
6685 | 17729038.454 | 7345800.6341 | 362064.2803 | 25436903.3683
6686 | 7281584.4598 | 12892884.8567 | 71444.7807 | 20245914.0971
6687 | 3713662.4219 | 4673537.3459 | 579248.1572 | 8966447.925
6688 | 7621947.3152 | 0 | 3428062.4104 | 11050009.7255
6689 | 5183907.3571 | 0 | 2042518.6918 | 7226426.0489
6690 | 21004585.6457 | 0 | 0 | 21004585.6457
6691 | 1952775.4624 | 2967320.6828 | 85404.3483 | 5005500.4935
6692 | 4975485.3103 | 5515710.861 | 10157311.6266 | 20648507.798
6693 | 6975056.7348 | 20805147.1429 | 6355816.0496 | 34136019.9273
6694 | 20534298.5048 | 15245908.7145 | 198915.7494 | 35979122.9687
6695 | 3961718.1512 | 31345977.9 | 1358554.9446 | 36666250.9958
6696 | 13283686.4813 | 3403637.3505 | 0 | 16687323.8317
6697 | 30305137.371 | 10412251.7065 | 912259.2084 | 41629648.2859
6698 | 4392990.8422 | 2842382.8772 | 713937.7615 | 7949311.4809
6699 | 9137565.5046 | 4907252.3815 | 2782024.2949 | 16826842.181
6700 | 6892818.5123 | 8957981.3577 | 482185.1519 | 16332985.0219
6701 | 1878475.2883 | 0 | 0 | 1878475.2883
6702 | 7591931.336 | 16340873.2747 | 0 | 23932804.6107
6703 | 15175782.431 | 4374488.0812 | 258711.2897 | 19808981.8019
6704 | 1957419.8483 | 4042804.285 | 0 | 6000224.1332
6705 | 14503111.6628 | 17930091.8817 | 1336612.6851 | 33769816.2296
6706 | 5437864.472 | 7247433.23 | 1457383.0997 | 14142680.8018
6707 | 3320684.9102 | 3043609.6204 | 1537464.0956 | 7901758.6262
6708 | 14015982.617 | 10733487.2497 | 7309451.2577 | 32058921.1243
6709 | 2877676.762 | 12740300.0591 | 90799.464 | 15708776.2851
6710 | 3096261.4462 | 524675.4869 | 54177.3731 | 3675114.3062
6711 | 7464836.3554 | 5703106.7284 | 1618376.0208 | 14786319.1046
6712 | 7441771.6806 | 8635882.3716 | 120789.9452 | 16198443.9975
6713 | 3785958.4931 | 0 | 899281.8469 | 4685240.34
6714 | 3890386.26 | 14679649.4115 | 1777985.6002 | 20348021.2717
6715 | 5980801.4891 | 2017432.0331 | 78210.4661 | 8076443.9883
6716 | 4587195.019 | 9561672.4888 | 971216.2884 | 15120083.7962
6717 | 1988929.1106 | 2703187.222 | 2697709.0243 | 7389825.3569
6718 | 19832049.0885 | 3710622.3696 | 82315.932 | 23624987.3901
6719 | 12155728.7697 | 0 | 0 | 12155728.7697
6720 | 7861345.0123 | 6233042.7687 | 0 | 14094387.781
6721 | 11331283.9822 | 3230606.5551 | 135027.7132 | 14696918.2505
6722 | 8172239.539 | 1052778.8057 | 2153321.505 | 11378339.8496
6723 | 8464781.3033 | 8445400.1552 | 0 | 16910181.4584
6724 | 28634454.8973 | 18267107.8974 | 45959763.4161 | 92861326.2108
6725 | 12796384.0532 | 2235718.9461 | 335200.8329 | 15367303.8322
6726 | 14183913.5859 | 7185390.0474 | 334575.3082 | 21703878.9415
6727 | 6624200.3488 | 7997750.2369 | 0 | 14621950.5857
6728 | 14951945.5652 | 246663.7768 | 1427906.5782 | 16626515.9202
6729 | 14829441.8555 | 0 | 973134.7343 | 15802576.5898
6730 | 8388156.9328 | 13965615.4314 | 0 | 22353772.3642
6731 | 4222896.2074 | 8822601.0612 | 8268933.0262 | 21314430.2948
6732 | 12865264.0251 | 3360251.7808 | 3547048.5424 | 19772564.3483
6733 | 4636326.8105 | 12422813.9517 | 657492.7806 | 17716633.5428
6734 | 16833446.7058 | 0 | 21261104.0805 | 38094550.7863
6735 | 6167913.8804 | 2209399.5352 | 9607033.162 | 17984346.5775
6736 | 12713644.1951 | 3290229.8269 | 9357000.1497 | 25360874.1717
6737 | 6464624.2199 | 987017.2972 | 20977118.0899 | 28428759.6069
6738 | 6131674.9005 | 3252948.0784 | 5060881.4356 | 14445504.4144
6739 | 11858868.9622 | 12728510.864 | 3775014.1039 | 28362393.9301
6740 | 10269126.0681 | 0 | 443016.2999 | 10712142.368
6741 | 7229021.2513 | 16867473.1587 | 2863450.923 | 26959945.333
6742 | 3393092.7134 | 5492698.9239 | 2254270.8796 | 11140062.5169
6743 | 5877708.8832 | 12260.2265 | 4581211.8754 | 10471180.9851
6744 | 7422726.1247 | 5955889.7125 | 1142410.5428 | 14521026.3801
6745 | 7468682.1911 | 0 | 1747681.4372 | 9216363.6283
6746 | 2887151.6879 | 6677128.0394 | 0 | 9564279.7273
6747 | 6110729.0264 | 12491292.3975 | 11770274.0212 | 30372295.4451
6748 | 3019327.3053 | 3362275.4589 | 4694941.1233 | 11076543.8875
6749 | 4390108.9876 | 11435387.9319 | 80439.0459 | 15905935.9654
6750 | 6878711.0001 | 12574607.7271 | 8874684.2414 | 28328002.9686
6751 | 9196657.5111 | 8910207.752 | 0 | 18106865.263
6752 | 4993133.7485 | 1730164.5759 | 14869095.9465 | 21592394.2709
6753 | 13688360.0423 | 0 | 1500614.2466 | 15188974.2889
6754 | 3770697.0695 | 4806274.8866 | 210076.8782 | 8787048.8342
6755 | 10929718.7778 | 0 | 8228.8729 | 10937947.6506
6756 | 7500310.763 | 1343209.9498 | 2469300.0312 | 11312820.744
6757 | 7504919.0158 | 13000725.5064 | 5470369.6099 | 25976014.1321
6758 | 4540697.0695 | 1530277.9981 | 0 | 6070975.0676
6759 | 2942287.2073 | 18363372.3117 | 18937.2036 | 21324596.7226
6760 | 418846.7559 | 13132868.1871 | 94761.4055 | 13646476.3485
6761 | 11470258.3358 | 0 | 1770281.3125 | 13240539.6483
6762 | 18421561.8474 | 12388072.305 | 395562.2399 | 31205196.3923
6763 | 6070110.2771 | 17272651.9327 | 624586.3354 | 23967348.5452
6764 | 2334846.4791 | 20086358.0953 | 3512458.8649 | 25933663.4393
6765 | 10436500.4773 | 11177805.7854 | 4459539.1441 | 26073845.4068
6766 | 10075649.3047 | 13938747.2422 | 957066.7821 | 24971463.329
6767 | 19012410.8085 | 5151015.3949 | 491850.3643 | 24655276.5677
6768 | 11258811.849 | 6521285.5223 | 1897548.0538 | 19677645.4251
6769 | 3530648.6793 | 10439530.096 | 382466.3136 | 14352645.0889
6770 | 13061023.9564 | 233618.8776 | 29600.8283 | 13324243.6623
6771 | 5440990.758 | 5656770.0038 | 1913080.4874 | 13010841.2492
6772 | 20280600.0336 | 2709033.711 | 698387.6709 | 23688021.4156
6773 | 2460780.915 | 8986980.6568 | 0 | 11447761.5719
6774 | 8585695.8484 | 1658514.3284 | 10360328.1656 | 20604538.3424
6775 | 4414670.7025 | 21494700.4638 | 0 | 25909371.1664
6776 | 4974729.6272 | 2164142.867 | 22319829.3662 | 29458701.8604
6777 | 3325458.7362 | 2062253.6106 | 154720.5909 | 5542432.9377
6778 | 28114201.3658 | 24755574.0841 | 688082.4023 | 53557857.8522
6779 | 655723.4173 | 11043691.2722 | 0 | 11699414.6894
6780 | 6192193.9718 | 6421676.6837 | 0 | 12613870.6555
6781 | 2949029.6512 | 5155884.8855 | 1468011.3324 | 9572925.8691
6782 | 14039122.455 | 0 | 2456253.7169 | 16495376.1719
6783 | 4673949.975 | 3231473.051 | 84978.5914 | 7990401.6174
6784 | 16870449.4095 | 7809342.0971 | 76889.986 | 24756681.4926
6785 | 1618945.0187 | 5955280.7654 | 482914.6918 | 8057140.476
6786 | 6883843.1273 | 9117607.0343 | 1723490.4915 | 17724940.6531
6787 | 26603821.6077 | 6789461.3304 | 5128681.4991 | 38521964.4373
6788 | 4867845.5379 | 17332014.7158 | 117972.9506 | 22317833.2044
6789 | 6124975.4191 | 5231917.8274 | 5421032.8686 | 16777926.1151
6790 | 2111293.9977 | 0 | 45923.7587 | 2157217.7564
6791 | 3212269.6619 | 5184488.8973 | 1418740.8693 | 9815499.4285
6792 | 23703642.0291 | 17073284.9373 | 0 | 40776926.9664
6793 | 9745881.4998 | 3662141.3244 | 119874.5711 | 13527897.3953
6794 | 4056511.4626 | 0 | 5647043.9256 | 9703555.3883
6795 | 5975746.2625 | 17137079.5229 | 443278.9009 | 23556104.6863
6796 | 5941408.4754 | 3430290.872 | 473789.1653 | 9845488.5127
6797 | 2569795.514 | 19456030.1203 | 1542919.4141 | 23568745.0484
6798 | 21723235.4447 | 6463569.4236 | 311515.859 | 28498320.7273
6799 | 8494161.3372 | 14543747.3867 | 4335663.2457 | 27373571.9696
6800 | 1626279.2993 | 10170468.0804 | 20011882.1303 | 31808629.51
6801 | 10754475.7444 | 4883129.4698 | 32314.0049 | 15669919.2191
6802 | 13579558.1664 | 9904006.9567 | 300598.4724 | 23784163.5954
6803 | 11598966.8911 | 10417791.5962 | 126744.1293 | 22143502.6167
6804 | 33601.4033 | 4632646.6396 | 1382571.0882 | 6048819.1311
6805 | 2352108.3297 | 5349508.7055 | 1148161.243 | 8849778.2782
6806 | 5652066.6683 | 8006406.7489 | 0 | 13658473.4173
6807 | 4261548.8416 | 15246351.1703 | 4270701.8265 | 23778601.8384
6808 | 5090233.0999 | 15284965.4097 | 2196819.2395 | 22572017.7491
6809 | 6278520.4558 | 7901113.1705 | 31200006.8108 | 45379640.437
6810 | 4285668.3154 | 0 | 3022675.4197 | 7308343.7351
6811 | 2666827.2648 | 25956771.0423 | 0 | 28623598.307
6812 | 15173805.4502 | 13176648.4339 | 2100713.4799 | 30451167.364
6813 | 3579966.7374 | 2591338.1385 | 4448896.9317 | 10620201.8076
6814 | 1644232.8652 | 2375304.1717 | 70609.3417 | 4090146.3786
6815 | 11441431.5796 | 8663473.7603 | 300994.6546 | 20405899.9946
6816 | 8276776.7704 | 7198734.5225 | 2962994.5533 | 18438505.8462
6817 | 13481143.1156 | 2312279.5393 | 1461028.1125 | 17254450.7675
6818 | 8514708.3603 | 13427941.3782 | 6883891.8844 | 28826541.6228
6819 | 3880013.8553 | 7345540.6373 | 1495327.0236 | 12720881.5162
6820 | 9768013.8596 | 0 | 579104.9495 | 10347118.8091
6821 | 10394939.6662 | 4342124.9028 | 3669071.8864 | 18406136.4555
6822 | 4965166.6014 | 9706168.6932 | 3483744.8164 | 18155080.111
6823 | 5719901.0327 | 17941206.3058 | 189374.9308 | 23850482.2692
6824 | 4706966.3845 | 9567127.3923 | 955856.6657 | 15229950.4425
6825 | 9253747.389 | 0 | 0 | 9253747.389
6826 | 12310639.5784 | 8414467.8745 | 4297929.822 | 25023037.2749
6827 | 5840456.6213 | 2327423.8232 | 848133.4108 | 9016013.8552
6828 | 7904317.1518 | 8777817.3306 | 1046382.7328 | 17728517.2153
6829 | 7567604.1036 | 2872916.6618 | 438726.0957 | 10879246.8611
6830 | 8892447.1453 | 1327670.8925 | 16283839.4491 | 26503957.4869
6831 | 11692609.012 | 1586516.7655 | 115860.2142 | 13394985.9918
6832 | 11898592.8145 | 12528906.2394 | 15494.5934 | 24442993.6473
6833 | 2845701.859 | 0 | 3868108.0164 | 6713809.8754
6834 | 4404249.0494 | 0 | 1344072.5322 | 5748321.5816
6835 | 4944291.1597 | 8829843.8997 | 254325.766 | 14028460.8254
6836 | 15113458.3722 | 13082160.3218 | 4460004.1953 | 32655622.8892
6837 | 28895744.7667 | 0 | 166707.2408 | 29062452.0075
6838 | 5438897.7168 | 8577507.4987 | 2893421.6816 | 16909826.8972
6839 | 399198.0273 | 6608716.1481 | 2495637.626 | 9503551.8014
6840 | 12059779.1071 | 3672373.852 | 3600437.4488 | 19332590.4079
6841 | 3311149.3648 | 6124025.9236 | 2368521.4405 | 11803696.7289
6842 | 16842989.9633 | 0 | 1294725.0333 | 18137714.9966
6843 | 4568417.2768 | 0 | 481829.6616 | 5050246.9385
6844 | 13312609.4472 | 30961609.8665 | 2829758.192 | 47103977.5058
6845 | 9788706.5173 | 18721435.6743 | 2654563.2036 | 31164705.3952
6846 | 7655708.7444 | 7125857.0417 | 5621601.6892 | 20403167.4754
6847 | 7796334.5564 | 25572188.571 | 790826.0802 | 34159349.2075
6848 | 5999182.2812 | 4082542.6122 | 1861864.6057 | 11943589.4991
6849 | 3073111.0044 | 0 | 270971.5162 | 3344082.5206
6850 | 4835445.8842 | 7815237.9938 | 0 | 12650683.878
6851 | 8883855.3 | 11897767.3351 | 261926.6178 | 21043549.2529
6852 | 4247331.949 | 5457960.6519 | 3070375.1281 | 12775667.729
6853 | 768174.1108 | 3892877.4785 | 127477.7645 | 4788529.3539
6854 | 641711.7575 | 6776864.8167 | 0 | 7418576.5742
6855 | 4102753.405 | 6628565.2896 | 0 | 10731318.6946
6856 | 7109345.6055 | 25191103.7077 | 0 | 32300449.3132
6857 | 10403824.8654 | 0 | 316493.3489 | 10720318.2144
6858 | 10635361.3493 | 7191081.5831 | 1430838.7921 | 19257281.7246
6859 | 25572264.0696 | 1990894.0226 | 21203247.2322 | 48766405.3245
6860 | 4128325.4164 | 3125401.8938 | 194631.2016 | 7448358.5118
6861 | 7098860.3874 | 1527088.8802 | 5463291.2744 | 14089240.542
6862 | 2426802.2438 | 2226885.2592 | 321183.0731 | 4974870.5761
6863 | 1907271.4969 | 0 | 1591781.8427 | 3499053.3396
6864 | 2710408.5597 | 3084220.8929 | 0 | 5794629.4526
6865 | 2101807.0396 | 3265257.9384 | 436642.1729 | 5803707.1509
6866 | 20439836.756 | 692663.4306 | 0 | 21132500.1866
6867 | 7821584.9134 | 3750292.984 | 0 | 11571877.8975
6868 | 10036278.3792 | 26393368.3912 | 0 | 36429646.7703
6869 | 3456788.8421 | 4081677.0899 | 233368.4508 | 7771834.3828
6870 | 10072873.0168 | 666750.6279 | 4593876.5844 | 15333500.2291
6871 | 15887116.6205 | 4168435.4498 | 0 | 20055552.0703
6872 | 2603489.6817 | 5116070.557 | 1578022.2052 | 9297582.4439
6873 | 17671604.8058 | 1421835.5488 | 159601.7585 | 19253042.1131
6874 | 10096073.6364 | 4848544.952 | 7201000.7969 | 22145619.3853
6875 | 444409.6135 | 0 | 1694676.145 | 2139085.7585
6876 | 2428926.6022 | 2372650.2217 | 0 | 4801576.8239
6877 | 79551233.8904 | 7030068.5652 | 5093113.0907 | 91674415.5463
6878 | 19351163.6317 | 7497455.7417 | 5595709.5444 | 32444328.9178
6879 | 5808536.751 | 902618.7344 | 667736.2877 | 7378891.7731
6880 | 9020325.5772 | 5289227.5906 | 0 | 14309553.1679
6881 | 7511482.8685 | 0 | 35371.816 | 7546854.6845
6882 | 6686786.6737 | 548267.6603 | 4204177.3864 | 11439231.7205
6883 | 12017023.7422 | 5216656.3673 | 866561.8031 | 18100241.9126
6884 | 19424464.6325 | 3814760.4566 | 0 | 23239225.0892
6885 | 5861161.1677 | 16503230.1084 | 255494.7053 | 22619885.9814
6886 | 7657529.6459 | 9942240.473 | 6818115.4691 | 24417885.588
6887 | 6905794.4278 | 19602453.5196 | 26041.1522 | 26534289.0995
6888 | 15487137.511 | 4392078.8725 | 3001670.5468 | 22880886.9303
6889 | 7204101.2759 | 23241733.3923 | 510264.9877 | 30956099.6559
6890 | 23026448.9439 | 11194375.9055 | 102505.6242 | 34323330.4736
6891 | 4059842.7063 | 18716338.1563 | 1590313.0476 | 24366493.9102
6892 | 4410397.6915 | 4008986.5857 | 829666.0115 | 9249050.2887
6893 | 6267529.3546 | 0 | 0 | 6267529.3546
6894 | 12889493.4572 | 15660710.2141 | 4552262.5151 | 33102466.1864
6895 | 14996647.5395 | 39710485.3795 | 71252.8031 | 54778385.722
6896 | 2810166.1213 | 5720052.224 | 13265112.1454 | 21795330.4908
6897 | 3333504.9532 | 7574558.5367 | 5050304.2446 | 15958367.7345
6898 | 4822909.8736 | 809818.9078 | 0 | 5632728.7813
6899 | 3351951.596 | 5828622.5834 | 0 | 9180574.1795
6900 | 19448173.0282 | 1395386.18 | 4585563.0136 | 25429122.2217
6901 | 4083304.9415 | 2270392.0868 | 8592648.0675 | 14946345.0959
6902 | 7680903.2696 | 1684032.2282 | 108548.9262 | 9473484.4239
6903 | 8886119.4761 | 7920241.42 | 526141.3227 | 17332502.2189
6904 | 8524971.8105 | 10448986.6831 | 0 | 18973958.4936
6905 | 4022816.1307 | 0 | 1930211.6422 | 5953027.7729
6906 | 15941156.5286 | 32324981.7763 | 7925546.1873 | 56191684.4921
6907 | 3454168.5507 | 5048300.0482 | 159376.8108 | 8661845.4097
6908 | 8751230.6502 | 5592285.0888 | 1352559.822 | 15696075.5611
6909 | 8261009.5803 | 16792761.5915 | 2604388.8843 | 27658160.056
6910 | 12377963.2299 | 31206156.4638 | 2362566.7545 | 45946686.4482
6911 | 6679953.1085 | 23151892.5223 | 2668856.9094 | 32500702.5402
6912 | 7712659.9983 | 7241495.8285 | 6827224.3081 | 21781380.1349
6913 | 2305363.741 | 1166693.0807 | 1897245.21 | 5369302.0317
6914 | 3313826.1892 | 3548526.2952 | 490387.6828 | 7352740.1671
6915 | 5076291.5381 | 6336162.7945 | 195422.2428 | 11607876.5754
6916 | 12162009.1849 | 5580369.9875 | 0 | 17742379.1724
6917 | 3861461.4332 | 7337785.8134 | 59074.7246 | 11258321.9712
6918 | 6615471.25 | 5627044.2144 | 0 | 12242515.4644
6919 | 28876291.6169 | 11513858.2737 | 320514.1229 | 40710664.0135
6920 | 5811669.8139 | 14072166.4442 | 1281972.199 | 21165808.4571
6921 | 13389463.813 | 4589123.914 | 0 | 17978587.727
6922 | 12823453.5937 | 10132022.2323 | 303298.0148 | 23258773.8407
6923 | 10847877.2512 | 8123481.0935 | 3206448.8959 | 22177807.2405
6924 | 11559367.3734 | 3325079.4184 | 1547169.5445 | 16431616.3363
6925 | 2133095.6139 | 12704973.0991 | 487971.9809 | 15326040.6939
6926 | 7879890.272 | 1428361.4566 | 1174744.3312 | 10482996.0598
6927 | 3426660.4349 | 8230049.1862 | 6966339.0842 | 18623048.7053
6928 | 11118183.7653 | 16770059.1582 | 1031261.0744 | 28919503.9978
6929 | 9610543.5382 | 6346260.8724 | 0 | 15956804.4106
6930 | 9291293.0626 | 7765598.2753 | 634013.4589 | 17690904.7968
6931 | 1073585.9288 | 8093445.6428 | 0 | 9167031.5716
6932 | 8210865.1414 | 4708734.1576 | 0 | 12919599.2991
6933 | 13047673.8502 | 2053241.1611 | 2309042.3014 | 17409957.3126
6934 | 7328485.655 | 14253632.4765 | 315418.7838 | 21897536.9152
6935 | 5792806.5655 | 0 | 4236355.6574 | 10029162.2229
6936 | 4949890.8498 | 15051421.2268 | 23168614.467 | 43169926.5436
6937 | 22868903.2408 | 4011079.2398 | 661545.6849 | 27541528.1655
6938 | 4902013.5626 | 18145366.7012 | 0 | 23047380.2638
6939 | 1467556.5443 | 9606641.1251 | 8005083.88 | 19079281.5494
6940 | 6483934.89 | 7101581.558 | 0 | 13585516.448
6941 | 1582032.1557 | 15064302.9385 | 312374.3135 | 16958709.4077
6942 | 5569152.5638 | 7007450.2948 | 0 | 12576602.8586
6943 | 13039764.1668 | 5729656.588 | 0 | 18769420.7548
6944 | 2265767.3222 | 2770278.3399 | 2892664.8304 | 7928710.4926
6945 | 11334322.021 | 6839900.7864 | 0 | 18174222.8074
6946 | 2598031.3605 | 9730561.5047 | 109491.0582 | 12438083.9235
6947 | 16587615.7656 | 7688103.7294 | 1423230.891 | 25698950.386
6948 | 5657763.4226 | 1058256.6786 | 0 | 6716020.1011
6949 | 6252183.9917 | 0 | 25291.9678 | 6277475.9595
6950 | 10919201.7616 | 1896421.1896 | 2958175.5722 | 15773798.5234
6951 | 5299548.7839 | 17575223.6076 | 3176124.6222 | 26050897.0136
6952 | 11839381.4635 | 6138240.4672 | 5580759.5757 | 23558381.5064
6953 | 12505083.3526 | 1904326.8357 | 45842.5712 | 14455252.7596
6954 | 8220168.4765 | 7369737.7479 | 280097.3781 | 15870003.6025
6955 | 861301.8138 | 6992213.975 | 949131.5713 | 8802647.36
6956 | 19852294.5744 | 7766409.3566 | 1540907.2126 | 29159611.1436
6957 | 36079656.5482 | 4719542.5884 | 10255607.662 | 51054806.7987
6958 | 21290747.4719 | 7464697.7253 | 2475299.0012 | 31230744.1984
6959 | 615909.7763 | 2780969.1802 | 568644.6194 | 3965523.576
6960 | 1772088.27 | 0 | 7647057.7729 | 9419146.0429
6961 | 2355233.4927 | 15175923.8001 | 971848.7701 | 18503006.0628
6962 | 10242388.1882 | 20471475.3898 | 3069798.1242 | 33783661.7022
6963 | 12272366.5489 | 20862483.3344 | 0 | 33134849.8833
6964 | 2177110.3923 | 4849029.9056 | 0 | 7026140.2979
6965 | 8046953.4781 | 12894034.3411 | 263293.4645 | 21204281.2837
6966 | 7171402.7246 | 5378352.8827 | 3014992.7556 | 15564748.3628
6967 | 1585121.1054 | 864243.1899 | 4988670.5381 | 7438034.8334
6968 | 4711268.3883 | 2605162.739 | 1684053.1227 | 9000484.25
6969 | 14528410.5419 | 12936703.0389 | 483214.3578 | 27948327.9386
6970 | 4358886.3353 | 10080786.7833 | 3216951.9232 | 17656625.0417
6971 | 9334870.9962 | 3963624.9265 | 574565.0839 | 13873061.0066
6972 | 849094.0688 | 7162370.1424 | 476281.3256 | 8487745.5368
6973 | 15732485.8902 | 11368152.2471 | 129332.0675 | 27229970.2048
6974 | 10540557.2989 | 3897918.1092 | 918437.9242 | 15356913.3324
6975 | 5853561.6035 | 5321323.6819 | 1627905.9731 | 12802791.2585
6976 | 5774442.5232 | 6288288.9407 | 22100298.1781 | 34163029.642
6977 | 6401954.4271 | 0 | 9797317.8325 | 16199272.2595
6978 | 3385796.3787 | 11570111.8001 | 37263.6939 | 14993171.8727
6979 | 16680700.1634 | 4980733.5379 | 10049338.0084 | 31710771.7097
6980 | 10985983.6111 | 9395520.6914 | 2848232.5633 | 23229736.8658
6981 | 11145279.2896 | 3135376.909 | 0 | 14280656.1986
6982 | 6489392.3047 | 6245724.1851 | 2543277.2136 | 15278393.7034
6983 | 13598927.5976 | 0 | 120857.5608 | 13719785.1584
6984 | 7632767.8511 | 3168010.9484 | 18197701.7366 | 28998480.5361
6985 | 2502020.975 | 482218.4001 | 1922094.1868 | 4906333.5619
6986 | 10310979.2503 | 0 | 1529228.2472 | 11840207.4974
6987 | 9965071.3736 | 13643593.8233 | 9379692.2709 | 32988357.4678
6988 | 4603683.2788 | 1694011.8088 | 11089756.209 | 17387451.2966
6989 | 2378126.4291 | 6303387.7252 | 258816.567 | 8940330.7213
6990 | 4240870.7122 | 4488716.5393 | 0 | 8729587.2514
6991 | 25161122.8589 | 2141263.3395 | 0 | 27302386.1984
6992 | 16619484.39 | 1918300.5894 | 256335.6583 | 18794120.6376
6993 | 2961569.0255 | 4665638.8785 | 0 | 7627207.9039
6994 | 1546603.7892 | 10289450.1498 | 2732326.3402 | 14568380.2792
6995 | 20316003.0973 | 3782445.0812 | 6319826.1693 | 30418274.3478
6996 | 6226090.7131 | 15131169.0495 | 5571616.8993 | 26928876.6619
6997 | 19372907.2043 | 8313715.9338 | 2221983.1675 | 29908606.3056
6998 | 21923247.4223 | 2108770.4417 | 803628.6142 | 24835646.4782
6999 | 2846398.0118 | 6693363.0409 | 0 | 9539761.0528
7000 | 7016075.5886 | 0 | 3295457.8087 | 10311533.3973
7001 | 7617741.82 | 2453941.7439 | 3149011.8599 | 13220695.4237
7002 | 9189175.9267 | 36879623.5246 | 0 | 46068799.4513
7003 | 4066765.633 | 6898739.4063 | 536386.7803 | 11501891.8196
7004 | 224338.574 | 2388200.094 | 968729.1745 | 3581267.8425
7005 | 12574534.5511 | 10040032.265 | 0 | 22614566.8161
7006 | 24817906.8705 | 9091767.9689 | 0 | 33909674.8394
7007 | 3134642.6382 | 1088510.9576 | 19665843.4994 | 23888997.0952
7008 | 14158812.108 | 13648603.3329 | 341971.6778 | 28149387.1186
7009 | 34383556.4065 | 10827798.6485 | 13796202.6583 | 59007557.7133
7010 | 11177918.0027 | 6229361.2901 | 0 | 17407279.2927
7011 | 4923197.247 | 8834073.2324 | 2798322.6598 | 16555593.1391
7012 | 9189329.9569 | 5208930.5623 | 258335.3739 | 14656595.8931
7013 | 6837056.3766 | 8593421.27 | 1648546.7011 | 17079024.3477
7014 | 10620733.7529 | 6414373.4796 | 9770229.3286 | 26805336.561
7015 | 7348077.4166 | 5673587.4929 | 5347049.0742 | 18368713.9837
7016 | 2274265.5975 | 3594754.3424 | 2692061.4572 | 8561081.3972
7017 | 7578079.8859 | 4883315.7843 | 2505549.5308 | 14966945.201
7018 | 3993342.7253 | 0 | 0 | 3993342.7253
7019 | 11801731.7271 | 1881738.6146 | 3447070.2999 | 17130540.6416
7020 | 2763263.1278 | 10160928.85 | 215041.8455 | 13139233.8233
7021 | 6498874.8674 | 2353428.2739 | 3293286.9502 | 12145590.0915
7022 | 5084696.6878 | 2605364.0364 | 0 | 7690060.7242
7023 | 18436507.565 | 4334278.3445 | 73948.8979 | 22844734.8074
7024 | 2832216.5853 | 7719322.0596 | 1721007.5099 | 12272546.1548
7025 | 4828021.4146 | 2141154.7896 | 0 | 6969176.2042
7026 | 13602255.4052 | 5625843.7186 | 1485788.4416 | 20713887.5653
7027 | 2065862.2244 | 0 | 66503.1796 | 2132365.404
7028 | 8200501.0829 | 13688960.3209 | 1264573.3054 | 23154034.7091
7029 | 6372573.2503 | 0 | 1464327.9174 | 7836901.1677
7030 | 8410131.0948 | 1442721.2444 | 13570015.2705 | 23422867.6097
7031 | 11334317.4697 | 11326545.3285 | 7499144.7217 | 30160007.52
7032 | 3042308.4725 | 13197896.5284 | 4165218.1526 | 20405423.1535
7033 | 2245339.9433 | 10968409.8273 | 103953.3543 | 13317703.1249
7034 | 6708336.1303 | 7528566.8646 | 0 | 14236902.9949
7035 | 4316832.4011 | 7811960.0953 | 127892.6274 | 12256685.1238
7036 | 10511996.0387 | 6598355.1658 | 0 | 17110351.2045
7037 | 5097658.058 | 0 | 1063916.6159 | 6161574.6739
7038 | 4740816.1538 | 2861855.4806 | 2496266.8826 | 10098938.517
7039 | 1526954.5029 | 0 | 186633.6428 | 1713588.1457
7040 | 2516575.1167 | 5038535.9392 | 148346.0352 | 7703457.0911
7041 | 10625628.6422 | 12520424.1387 | 2210424.8842 | 25356477.6652
7042 | 4006596.1598 | 7153308.2811 | 75498.8032 | 11235403.2441
7043 | 958389.6897 | 0 | 311466.9497 | 1269856.6393
7044 | 20574335.6135 | 16627169.6348 | 2099291.8472 | 39300797.0955
7045 | 4583999.854 | 10014160.7574 | 354514.6922 | 14952675.3036
7046 | 23726865.989 | 765306.3727 | 5482194.9833 | 29974367.345
7047 | 2321015.7776 | 2506700.4304 | 9050091.9222 | 13877808.1302
7048 | 9947124.2685 | 2803464.5917 | 660423.1912 | 13411012.0514
7049 | 16306918.1395 | 7037793.5526 | 15097319.4303 | 38442031.1223
7050 | 7516538.8815 | 1932317.2952 | 0 | 9448856.1768
7051 | 6329195.1553 | 4048724.4337 | 2860844.959 | 13238764.548
7052 | 20668007.081 | 13027878.7379 | 3226963.7118 | 36922849.5308
7053 | 2663121.5882 | 6331868.6858 | 1824662.0888 | 10819652.3627
7054 | 4072345.7625 | 9465815.3525 | 609123.7196 | 14147284.8346
7055 | 12586919.065 | 6722335.49 | 837550.2529 | 20146804.808
7056 | 317784.8752 | 4081287.9062 | 408722.8493 | 4807795.6307
7057 | 2835300.4123 | 10879037.7274 | 0 | 13714338.1397
7058 | 4622090.2855 | 20486330.5115 | 0 | 25108420.797
7059 | 12017171.5072 | 11091249.3926 | 139313.7313 | 23247734.6311
7060 | 8258625.0367 | 4109499.6034 | 1374146.7129 | 13742271.353
7061 | 5193345.1238 | 5320405.013 | 110073.9958 | 10623824.1326
7062 | 8366742.1102 | 12191694.4803 | 1065928.3891 | 21624364.9796
7063 | 11355100.8504 | 4716674.3676 | 1341763.0476 | 17413538.2656
7064 | 3528657.0238 | 9601513.2858 | 126175.362 | 13256345.6715
7065 | 1311484.2804 | 5952050.7595 | 2297561.7927 | 9561096.8325
7066 | 9360037.6143 | 11909244.0173 | 4203908.4314 | 25473190.0629
7067 | 6970741.5545 | 8740300.9166 | 2638775.3539 | 18349817.825
7068 | 19924309.4685 | 9317870.5564 | 1431558.728 | 30673738.7529
7069 | 11982977.908 | 12425453.5965 | 1806016.1978 | 26214447.7023
7070 | 14234105.2859 | 0 | 2794494.1479 | 17028599.4339
7071 | 1822480.1847 | 5263829.9081 | 1238695.2896 | 8325005.3824
7072 | 1595820.5684 | 18881570.827 | 0 | 20477391.3954
7073 | 2566714.5824 | 4921388.1732 | 8970743.7327 | 16458846.4883
7074 | 11019999.1785 | 8134351.7818 | 4044163.5183 | 23198514.4786
7075 | 8342118.483 | 6379134.601 | 5241189.9726 | 19962443.0566
7076 | 6285953.0655 | 3105038.3787 | 760286.6149 | 10151278.0591
7077 | 11088014.5555 | 21243825.6449 | 541981.2397 | 32873821.44
7078 | 5566682.9681 | 12949854.7025 | 818368.1833 | 19334905.8538
7079 | 3826567.4646 | 2974510.4325 | 2316342.6202 | 9117420.5172
7080 | 6843311.4088 | 27403102.8737 | 198145.6419 | 34444559.9245
7081 | 15952711.1794 | 4451352.2514 | 3247679.7062 | 23651743.1369
7082 | 1441483.447 | 14388684.3078 | 139775.1172 | 15969942.872
7083 | 1506123.0253 | 5199170.5617 | 787041.0929 | 7492334.6799
7084 | 9434662.8093 | 6566997.4854 | 828023.4501 | 16829683.7447
7085 | 1877757.5974 | 2178536.3787 | 7082835.3066 | 11139129.2827
7086 | 22245755.6433 | 5289449.0779 | 1581285.4338 | 29116490.155
7087 | 5109727.1405 | 10777476.5395 | 3667779.4762 | 19554983.1563
7088 | 7362011.382 | 6372551.9065 | 1009199.6267 | 14743762.9153
7089 | 5285327.9225 | 5897327.7686 | 2011203.938 | 13193859.6292
7090 | 22864203.3828 | 2193952.4049 | 2670263.2247 | 27728419.0124
7091 | 12672527.5861 | 26182589.6091 | 2435452.8391 | 41290570.0343
7092 | 22066223.6267 | 10259358.8506 | 8702009.5959 | 41027592.0731
7093 | 4547348.8606 | 9290248.958 | 3322258.042 | 17159855.8606
7094 | 4812211.9504 | 14108673.2632 | 111203.647 | 19032088.8606
7095 | 2937168.1551 | 2244235.1134 | 3859371.4975 | 9040774.7659
7096 | 796203.1036 | 2790009.2998 | 9650539.7633 | 13236752.1667
7097 | 884651.9737 | 10837601.2709 | 4858590.6831 | 16580843.9276
7098 | 2467515.8251 | 52170484.2571 | 1174494.6437 | 55812494.7259
7099 | 6706407.8553 | 5090897.1392 | 634483.4505 | 12431788.445
7100 | 9254116.9203 | 19963559.3493 | 164867.4022 | 29382543.6718
7101 | 7017853.1805 | 12034842.1469 | 864367.4629 | 19917062.7903
7102 | 21571409.9385 | 4047263.5428 | 593804.2726 | 26212477.7539
7103 | 2365834.3661 | 3025618.7094 | 5263326.6347 | 10654779.7102
7104 | 11380971.4923 | 7309177.0447 | 1381753.7293 | 20071902.2662
7105 | 6853593.0336 | 1932055.3245 | 2672188.261 | 11457836.6191
7106 | 3717129.9713 | 13796545.9137 | 1070782.3353 | 18584458.2203
7107 | 2715149.5847 | 4806805.342 | 7482359.5465 | 15004314.4732
7108 | 41860371.4801 | 4801698.119 | 9130754.5191 | 55792824.1181
7109 | 26658021.8336 | 1239702.527 | 4107877.4435 | 32005601.804
7110 | 4770834.3975 | 12444920.0064 | 1840254.9981 | 19056009.402
7111 | 10153603.8964 | 3290148.0243 | 12839478.163 | 26283230.0837
7112 | 6188915.1246 | 9973805.6659 | 907666.2819 | 17070387.0724
7113 | 5492590.7561 | 5040755.4558 | 0 | 10533346.2119
7114 | 19929316.5025 | 15064161.3879 | 0 | 34993477.8904
7115 | 15650469.1146 | 29525714.1356 | 0 | 45176183.2501
7116 | 3443534.5838 | 5140077.5562 | 7421269.2618 | 16004881.4019
7117 | 3177851.3714 | 12486350.6086 | 4253011.9796 | 19917213.9595
7118 | 6383108.3343 | 7621356.7734 | 2917902.1797 | 16922367.2874
7119 | 1746467.9559 | 14097358.2243 | 1438661.8537 | 17282488.0339
7120 | 1959271.3655 | 1462351.5122 | 0 | 3421622.8777
7121 | 5221097.9832 | 8563274.5041 | 5386277.2602 | 19170649.7474
7122 | 7361694.0652 | 14543578.094 | 0 | 21905272.1592
7123 | 9114004.7884 | 11146568.6699 | 271961.1347 | 20532534.593
7124 | 2560619.4534 | 6409319.822 | 47178.2808 | 9017117.5563
7125 | 2141260.5543 | 9403441.573 | 2484615.7739 | 14029317.9012
7126 | 7912653.7854 | 9693129.1158 | 157524.9896 | 17763307.8907
7127 | 3243305.8338 | 9671965.2783 | 3437345.6892 | 16352616.8013
7128 | 4619357.1321 | 2399741.2782 | 662603.7749 | 7681702.1852
7129 | 9066946.0003 | 6249992.3345 | 6675822.4997 | 21992760.8344
7130 | 7064308.0107 | 3000329.0989 | 3312998.9458 | 13377636.0554
7131 | 6905728.3793 | 4824044.8105 | 709764.4401 | 12439537.6298
7132 | 14685191.9897 | 7973853.2886 | 0 | 22659045.2784
7133 | 2862889.0928 | 20829373.3546 | 8463293.9301 | 32155556.3775
7134 | 11898804.4375 | 23869217.9774 | 3066488.4819 | 38834510.8968
7135 | 5994089.929 | 12615746.4608 | 12854179.2378 | 31464015.6276
7136 | 30024907.3096 | 2301711.7931 | 48135.1478 | 32374754.2506
7137 | 15898538.0489 | 2021331.7467 | 276425.1698 | 18196294.9654
7138 | 13718022.8637 | 3757691.4042 | 0 | 17475714.268
7139 | 3331827.1384 | 28246397.6007 | 0 | 31578224.7391
7140 | 1095413.0569 | 0 | 1188474.8334 | 2283887.8903
7141 | 11687911.9671 | 6684738.3266 | 4812740.3696 | 23185390.6634
7142 | 10271076.8466 | 25912911.1675 | 271239.0735 | 36455227.0876
7143 | 5286236.2965 | 4336549.6941 | 956798.8993 | 10579584.8899
7144 | 21978151.4232 | 6195448.2247 | 886252.1695 | 29059851.8174
7145 | 20597410.2156 | 5467780.1881 | 15521.1701 | 26080711.5738
7146 | 3310832.02 | 6215958.259 | 4117703.9729 | 13644494.2519
7147 | 3549459.7379 | 12645168.2644 | 10480719.943 | 26675347.9452
7148 | 16532977.4154 | 7594747.3378 | 1619149.4403 | 25746874.1935
7149 | 3154205.519 | 4595078.4494 | 141942.9929 | 7891226.9612
7150 | 7120839.1386 | 23569470.3663 | 253229.7267 | 30943539.2316
7151 | 7613452.5015 | 17899801.4351 | 1752900.3379 | 27266154.2746
7152 | 3079895.3223 | 5151564.1167 | 5574334.1183 | 13805793.5573
7153 | 17277459.7038 | 7200392.2831 | 4661671.7844 | 29139523.7713
7154 | 7961682.7474 | 10734082.8998 | 9952109.7234 | 28647875.3707
7155 | 3865865.6952 | 3590653.6262 | 466787.4957 | 7923306.817
7156 | 10055537.6181 | 14525084.8356 | 121380.3542 | 24702002.8079
7157 | 426325.8466 | 5488318.8961 | 2554301.4467 | 8468946.1894
7158 | 2381995.4496 | 1646882.0779 | 1684861.7509 | 5713739.2784
7159 | 11412330.128 | 10831305.9214 | 636458.8623 | 22880094.9117
7160 | 21772295.7482 | 750352.7584 | 0 | 22522648.5066
7161 | 6680081.0142 | 2465758.7971 | 1759294.3077 | 10905134.1191
7162 | 7942251.5282 | 25227760.9426 | 2992128.4817 | 36162140.9525
7163 | 141251.2761 | 0 | 0 | 141251.2761
7164 | 11853044.8971 | 10102718.0624 | 563297.3955 | 22519060.3551
7165 | 4169886.2379 | 0 | 11347933.8785 | 15517820.1164
7166 | 13198701.944 | 0 | 1706508.8254 | 14905210.7694
7167 | 9216858.9845 | 5315935.8085 | 2072626.0313 | 16605420.8243
7168 | 6173492.5401 | 0 | 2663684.9982 | 8837177.5383
7169 | 19273135.6445 | 7147772.8314 | 7058457.4452 | 33479365.9212
7170 | 2126612.8288 | 3316182.601 | 11475870.0201 | 16918665.45
7171 | 6831234.0275 | 0 | 2865016.9619 | 9696250.9894
7172 | 11930318.4909 | 9154804.2423 | 2490353.0387 | 23575475.7719
7173 | 5902474.8044 | 25058539.572 | 431900.4425 | 31392914.8189
7174 | 34120278.3976 | 532391.9945 | 1399898.0679 | 36052568.46
7175 | 1857853.6487 | 14829510.8485 | 392003.4372 | 17079367.9344
7176 | 1303925.9552 | 10846794.7599 | 0 | 12150720.715
7177 | 871355.823 | 8986615.6889 | 0 | 9857971.5119
7178 | 4067033.8641 | 8897438.2213 | 5826503.6825 | 18790975.7678
7179 | 20328220.5319 | 483095.8602 | 57993.6814 | 20869310.0735
7180 | 11040299.5378 | 4106113.6958 | 0 | 15146413.2336
7181 | 8635309.633 | 0 | 305436.2697 | 8940745.9027
7182 | 16962025.364 | 0 | 7312011.3082 | 24274036.6722
7183 | 10851295.454 | 0 | 157897.3712 | 11009192.8252
7184 | 13408249.6266 | 8490042.8016 | 258296.9416 | 22156589.3698
7185 | 10722797.9802 | 5356330.8709 | 17498444.2903 | 33577573.1413
7186 | 21829073.6924 | 4794108.1302 | 1808319.0753 | 28431500.8979
7187 | 4340842.0069 | 3470343.3068 | 0 | 7811185.3136
7188 | 11686364.8919 | 19016956.649 | 92451.7778 | 30795773.3187
7189 | 3749404.5554 | 1868313.8938 | 132509.0762 | 5750227.5255
7190 | 5057327.7235 | 6756366.6753 | 4519794.2859 | 16333488.6847
7191 | 12824561.3956 | 21405585.2832 | 422345.7869 | 34652492.4657
7192 | 9564804.6484 | 16402120.1952 | 1274648.908 | 27241573.7516
7193 | 20430730.2864 | 7290682.2841 | 777567.0415 | 28498979.612
7194 | 11205589.7899 | 2278033.4368 | 1024221.6552 | 14507844.8819
7195 | 3791809.2822 | 18078742.0233 | 98599.1799 | 21969150.4854
7196 | 4922177.1939 | 6362066.6552 | 490120.917 | 11774364.7661
7197 | 3497292.4272 | 9563750.208 | 2326829.2953 | 15387871.9304
7198 | 8595621.5521 | 4152891.6758 | 3352331.3187 | 16100844.5466
7199 | 3236206.0208 | 9363290.3385 | 77477.1156 | 12676973.475
7200 | 8571797.6406 | 2227965.1002 | 814265.3147 | 11614028.0555
7201 | 5178144.5851 | 2167775.9607 | 3958079.2904 | 11303999.8363
7202 | 3575283.6944 | 8856523.0834 | 3435654.5083 | 15867461.286
7203 | 17518208.7305 | 8612413.2221 | 424946.2284 | 26555568.181
7204 | 9993070.8311 | 7356089.7294 | 2066060.6374 | 19415221.198
7205 | 4183776.6248 | 6425451.0275 | 0 | 10609227.6523
7206 | 3742908.0466 | 14728661.2851 | 57911.3044 | 18529480.6361
7207 | 14499339.7871 | 0 | 2684246.9734 | 17183586.7605
7208 | 3081806.8448 | 6189274.8898 | 1271843.524 | 10542925.2585
7209 | 9172401.9701 | 7029570.2983 | 1179313.1666 | 17381285.435
7210 | 9644442.3896 | 20034170.7129 | 13591702.1651 | 43270315.2676
7211 | 9242749.9645 | 0 | 1195425.049 | 10438175.0135
7212 | 6790382.3299 | 11074927.2455 | 0 | 17865309.5754
7213 | 4758937.5381 | 8269376.181 | 20468.6658 | 13048782.385
7214 | 26093951.359 | 7485523.5754 | 0 | 33579474.9344
7215 | 2633972.7231 | 17549675.9236 | 976327.9267 | 21159976.5735
7216 | 6891599.6708 | 0 | 596474.2065 | 7488073.8773
7217 | 2385991.3827 | 13057240.8415 | 446268.903 | 15889501.1273
7218 | 5140450.2479 | 1859452.8102 | 19028628.014 | 26028531.0722
7219 | 4605074.0082 | 6953387.4101 | 1800316.3438 | 13358777.7621
7220 | 15266533.2192 | 11614287.9444 | 1575979.2634 | 28456800.4271
7221 | 7461255.9347 | 5012705.5408 | 0 | 12473961.4755
7222 | 2262967.7781 | 1852135.0638 | 545979.4345 | 4661082.2764
7223 | 3327518.8851 | 4112409.8934 | 770444.7915 | 8210373.5701
7224 | 19344115.2694 | 8054567.8123 | 3551857.1666 | 30950540.2482
7225 | 5285223.5721 | 3811309.795 | 1833981.8849 | 10930515.252
7226 | 6327126.5911 | 0 | 1660721.5558 | 7987848.1468
7227 | 22598360.044 | 22522171.2854 | 1547828.5115 | 46668359.8409
7228 | 5449113.9297 | 2034556.3219 | 1747522.3193 | 9231192.5708
7229 | 23642754.0429 | 12098106.7798 | 0 | 35740860.8227
7230 | 4547651.1341 | 2640946.9464 | 1350186.1987 | 8538784.2793
7231 | 14849399.4492 | 16756831.687 | 6616065.7964 | 38222296.9325
7232 | 3722631.3526 | 19439763.9501 | 3139234.9789 | 26301630.2816
7233 | 5026513.6562 | 26732916.6718 | 7062607.2862 | 38822037.6141
7234 | 4433161.5384 | 8182883.4877 | 598253.3535 | 13214298.3796
7235 | 4440110.4763 | 4782256.3443 | 0 | 9222366.8206
7236 | 2916762.2669 | 1729181.9903 | 0 | 4645944.2572
7237 | 19741977.4893 | 2061017.4783 | 244980.752 | 22047975.7195
7238 | 4897137.2668 | 0 | 2610214.2602 | 7507351.527
7239 | 22719333.5502 | 6304021.7434 | 2363485.1066 | 31386840.4002
7240 | 1907279.7268 | 0 | 8016712.9685 | 9923992.6952
7241 | 16125434.0677 | 4590212.1237 | 30132.4736 | 20745778.665
7242 | 5355176.7757 | 22477466.6827 | 608374.8376 | 28441018.2961
7243 | 9199566.4228 | 840404.6211 | 2268214.7041 | 12308185.748
7244 | 14491239.3339 | 6849122.5811 | 7380647.2294 | 28721009.1444
7245 | 4090585.5466 | 25726345.6366 | 3931096.2656 | 33748027.4487
7246 | 5850907.8232 | 2530375.4985 | 2749225.5567 | 11130508.8783
7247 | 662693.3603 | 13852729.3509 | 3817325.1483 | 18332747.8594
7248 | 9190314.6935 | 4633439.9048 | 903708.895 | 14727463.4933
7249 | 7484677.4104 | 900938.0159 | 8912764.9532 | 17298380.3795
7250 | 6991573.7739 | 11649964.4786 | 473059.5627 | 19114597.8152
7251 | 3862374.7976 | 15026970.6773 | 1124860.3872 | 20014205.8621
7252 | 11029397.4638 | 4923235.2065 | 1728925.5093 | 17681558.1797
7253 | 16121464.7318 | 18246143.218 | 0 | 34367607.9498
7254 | 18280329.0884 | 12789597.4106 | 496794.7427 | 31566721.2416
7255 | 2704200.8569 | 0 | 6517354.7488 | 9221555.6058
7256 | 13193256.378 | 4342112.432 | 1533581.6058 | 19068950.4158
7257 | 24387981.4977 | 5085565.5586 | 2238824.428 | 31712371.4843
7258 | 4366692.5731 | 6475197.7386 | 3059943.86 | 13901834.1716
7259 | 6436510.2418 | 15880012.4721 | 2264270.7828 | 24580793.4967
7260 | 16735080.3365 | 0 | 1127394.1092 | 17862474.4457
7261 | 15913489.5998 | 7484694.0001 | 130325.7891 | 23528509.389
7262 | 6820466.3135 | 5895200.1501 | 517184.6834 | 13232851.147
7263 | 6496221.2259 | 21359402.9624 | 3849228.2217 | 31704852.41
7264 | 4394598.9479 | 29202879.2909 | 5549594.4103 | 39147072.6491
7265 | 6603349.7769 | 12850828.6709 | 0 | 19454178.4478
7266 | 15180792.232 | 17767172.8875 | 2122592.5761 | 35070557.6955
7267 | 3212177.9856 | 12609213.1604 | 15024317.047 | 30845708.1931
7268 | 2817893.6876 | 0 | 1070384.1678 | 3888277.8555
7269 | 6334073.4332 | 8451003.4954 | 69134.0745 | 14854211.003
7270 | 24519096.97 | 6541977.3386 | 30784.3107 | 31091858.6194
7271 | 9440689.7993 | 10347617.1344 | 318799.7602 | 20107106.6939
7272 | 7260301.6864 | 4264770.7847 | 4356698.8154 | 15881771.2866
7273 | 11807598.6253 | 4904396.4876 | 500201.8517 | 17212196.9646
7274 | 2960117.3781 | 0 | 28288288.6086 | 31248405.9867
7275 | 3257611.4218 | 2884099.5139 | 3440660.3865 | 9582371.3223
7276 | 3905194.821 | 41232878.7825 | 1265949.1484 | 46404022.7519
7277 | 16631132.3548 | 6039509.6385 | 2535663.6297 | 25206305.623
7278 | 2483212.8638 | 2308272.9633 | 132585.9183 | 4924071.7454
7279 | 6677650.3318 | 7568533.351 | 275570.3735 | 14521754.0562
7280 | 3433149.099 | 21097697.9341 | 239211.384 | 24770058.4171
7281 | 6408889.9456 | 4755277.7987 | 1781580.5737 | 12945748.318
7282 | 2712417.9893 | 19161855.8226 | 1303277.6014 | 23177551.4132
7283 | 1523494.3798 | 9198359.037 | 0 | 10721853.4168
7284 | 8579457.7263 | 10085034.8343 | 0 | 18664492.5606
7285 | 10947308.5286 | 0 | 357487.7678 | 11304796.2964
7286 | 15418329.5497 | 6548321.1612 | 6556810.2096 | 28523460.9205
7287 | 2024112.3331 | 3717541.5102 | 1309693.7028 | 7051347.5461
7288 | 11214110.2944 | 36814372.9163 | 633546.3641 | 48662029.5748
7289 | 4085372.1642 | 4960372.3485 | 1374702.2745 | 10420446.7872
7290 | 11706860.8926 | 3146095.578 | 148897.0804 | 15001853.551
7291 | 8890316.3647 | 9356823.7406 | 0 | 18247140.1053
7292 | 5979828.6999 | 5075132.5267 | 12359115.0047 | 23414076.2313
7293 | 2494379.1361 | 5467972.517 | 258587.2489 | 8220938.902
7294 | 9604988.9284 | 16666558.2473 | 124121.8557 | 26395669.0314
7295 | 3011989.5624 | 0 | 3454891.678 | 6466881.2404
7296 | 2190367.1022 | 11909950.8267 | 2869540.0436 | 16969857.9725
7297 | 4869309.9618 | 16934933.6087 | 3784364.8913 | 25588608.4617
7298 | 3893648.3408 | 18632973.7396 | 882061.5847 | 23408683.6651
7299 | 17126712.5659 | 13310660.7558 | 1840737.7126 | 32278111.0342
7300 | 5079723.4572 | 3412220.0092 | 0 | 8491943.4664
7301 | 22197806.9212 | 2495353.4123 | 1400870.0733 | 26094030.4068
7302 | 9050360.8812 | 4508388.4503 | 175098.3001 | 13733847.6316
7303 | 7739596.8626 | 8078711.0953 | 2865675.3296 | 18683983.2875
7304 | 22230198.7128 | 3888762.1393 | 550110.47 | 26669071.3221
7305 | 11470223.0503 | 4658162.3806 | 574832.1431 | 16703217.574
7306 | 3523285.3088 | 1536488.2223 | 0 | 5059773.5311
7307 | 4956370.4505 | 0 | 1424441.7571 | 6380812.2076
7308 | 5685056.676 | 15572196.4019 | 353702.5703 | 21610955.6482
7309 | 4982407.1073 | 0 | 162720.6975 | 5145127.8048
7310 | 11990005.2078 | 9734565.937 | 1038219.8864 | 22762791.0312
7311 | 7099905.7413 | 17704772.9597 | 29566.1954 | 24834244.8963
7312 | 989638.6219 | 1459729.4301 | 3576882.3348 | 6026250.3868
7313 | 1971878.1171 | 0 | 1094712.2386 | 3066590.3557
7314 | 8787200.5843 | 2776195.3518 | 0 | 11563395.9361
7315 | 8829437.2764 | 11969468.1433 | 11395016.5367 | 32193921.9565
7316 | 2124893.0273 | 960061.9879 | 3498703.1667 | 6583658.1818
7317 | 24637981.1075 | 4096510.4803 | 0 | 28734491.5878
7318 | 6990775.4298 | 137255.0071 | 7477165.7003 | 14605196.1372
7319 | 7168457.0796 | 2050211.4363 | 154431.649 | 9373100.1649
7320 | 10430178.0756 | 11954646.8006 | 553006.6238 | 22937831.5
7321 | 1902527.7414 | 5828114.3224 | 0 | 7730642.0638
7322 | 9872871.6598 | 0 | 254051.9191 | 10126923.5789
7323 | 4823589.6496 | 7370757.3284 | 65238.1077 | 12259585.0856
7324 | 2277035.5326 | 2003774.6151 | 9780.0617 | 4290590.2094
7325 | 13163416.6322 | 4519573.4808 | 141598.7271 | 17824588.8401
7326 | 4483775.5848 | 11171667.805 | 9754188.8378 | 25409632.2276
7327 | 26577244.0872 | 7986682.3296 | 100090.0623 | 34664016.4791
7328 | 3850225.7643 | 23770863.3827 | 1202000.2307 | 28823089.3777
7329 | 11040998.9843 | 4865800.7849 | 139320.8213 | 16046120.5905
7330 | 8426032.1734 | 2795911.7135 | 1101208.3154 | 12323152.2022
7331 | 3400053.3576 | 9656080.5981 | 9736087.2081 | 22792221.1638
7332 | 3347549.1535 | 15481830.0149 | 16048862.8169 | 34878241.9853
7333 | 4642640.1947 | 9568347.2728 | 9204814.3139 | 23415801.7813
7334 | 3768533.2037 | 3878062.8 | 905784.2433 | 8552380.247
7335 | 5703699.1927 | 11444791.0852 | 15261130.0199 | 32409620.2978
7336 | 1883401.2746 | 8119252.8246 | 0 | 10002654.0992
7337 | 1856694.4963 | 12094879.5009 | 157382.4056 | 14108956.4028
7338 | 10702700.6061 | 0 | 26112822.8202 | 36815523.4263
7339 | 13946143.538 | 6396154.7455 | 2285432.2961 | 22627730.5797
7340 | 5715966.8341 | 17875052.0964 | 440026.4801 | 24031045.4106
7341 | 4876069.0697 | 7476322.8056 | 544511.2497 | 12896903.125
7342 | 4701058.9112 | 5455744.8093 | 75298.3441 | 10232102.0646
7343 | 3313880.4572 | 6847099.374 | 5219536.2889 | 15380516.1201
7344 | 680755.5588 | 11168288.2913 | 1260537.6643 | 13109581.5144
7345 | 3776546.3058 | 0 | 14134235.064 | 17910781.3698
7346 | 12348347.8862 | 0 | 1477026.3476 | 13825374.2338
7347 | 4517818.276 | 4543429.004 | 1533949.8572 | 10595197.1372
7348 | 4003777.547 | 0 | 0 | 4003777.547
7349 | 28415766.1672 | 0 | 1794282.0656 | 30210048.2328
7350 | 11024745.5421 | 0 | 2092803.1369 | 13117548.679
7351 | 2344530.0699 | 7834208.6089 | 118553.0404 | 10297291.7191
7352 | 4965109.3169 | 0 | 3237956.0157 | 8203065.3326
7353 | 4716673.1789 | 320076.1145 | 424806.3448 | 5461555.6382
7354 | 4753669.3803 | 6937438.6388 | 3266426.6064 | 14957534.6254
7355 | 12193275.8962 | 4978308.6242 | 627340.9081 | 17798925.4284
7356 | 4834765.2181 | 4980244.5879 | 2046843.5389 | 11861853.3449
7357 | 4544000.2307 | 1473031.4687 | 184250.0764 | 6201281.7758
7358 | 9392188.5481 | 6923513.0043 | 0 | 16315701.5524
7359 | 22490203.0825 | 21852130.0162 | 84874.0587 | 44427207.1573
7360 | 7383252.984 | 8873164.8862 | 1777573.4017 | 18033991.2719
7361 | 7439619.724 | 2793555.8249 | 1820168.0682 | 12053343.6172
7362 | 14283249.0184 | 0 | 9576693.0323 | 23859942.0507
7363 | 10636714.7404 | 5502651.3267 | 3661417.7247 | 19800783.7919
7364 | 6708711.6333 | 14220740.302 | 1419142.693 | 22348594.6282
7365 | 8753962.8219 | 9945878.6792 | 2823831.2625 | 21523672.7636
7366 | 4259150.9588 | 3700209.9274 | 2809569.9034 | 10768930.7896
7367 | 10976543.1042 | 0 | 0 | 10976543.1042
7368 | 18262340.9989 | 4119414.3904 | 0 | 22381755.3893
7369 | 2237444.1587 | 5561521.4995 | 5574090.7536 | 13373056.4117
7370 | 13925186.4562 | 0 | 1465598.5092 | 15390784.9654
7371 | 30013949.9035 | 12542689.7725 | 130966.1037 | 42687605.7796
7372 | 28943605.2671 | 12829188.7899 | 0 | 41772794.057
7373 | 5471230.7306 | 3664355.7411 | 145044.6408 | 9280631.1125
7374 | 1474046.5643 | 5301555.2981 | 0 | 6775601.8624
7375 | 4353546.2083 | 5281838.7465 | 0 | 9635384.9548
7376 | 12682563.0503 | 0 | 5959571.4614 | 18642134.5117
7377 | 466578.5728 | 6699063.4242 | 5704849.0527 | 12870491.0498
7378 | 4739398.3892 | 2793484.4389 | 429062.5665 | 7961945.3946
7379 | 3213134.9806 | 3846385.4101 | 1338148.6723 | 8397669.0629
7380 | 9058055.4202 | 0 | 898078.7372 | 9956134.1574
7381 | 9439235.1046 | 2772162.583 | 1220056.947 | 13431454.6346
7382 | 19953821.5063 | 16599396.3895 | 11655873.6728 | 48209091.5685
7383 | 1436166.9812 | 5785459.3821 | 3234892.956 | 10456519.3193
7384 | 13439675.7415 | 5228690.2927 | 73041.3312 | 18741407.3655
7385 | 3784619.2586 | 5953411.1878 | 10549370.4999 | 20287400.9463
7386 | 11094362.8261 | 5969076.0867 | 5693533.917 | 22756972.8299
7387 | 390652.8266 | 9044378.4691 | 5494628.162 | 14929659.4578
7388 | 31382821.6122 | 5670186.433 | 381945.2096 | 37434953.2548
7389 | 5491941.5072 | 6541759.2179 | 2721650.1543 | 14755350.8795
7390 | 15691653.7834 | 103594.2704 | 38768.6307 | 15834016.6845
7391 | 30859603.4368 | 15333923.8424 | 2848795.8156 | 49042323.0948
7392 | 5114155.7432 | 5333665.0452 | 10318334.7679 | 20766155.5564
7393 | 5923301.2249 | 7725532.1021 | 8580248.9956 | 22229082.3226
7394 | 2503067.3522 | 20856731.7967 | 219311.8478 | 23579110.9967
7395 | 8107848.7811 | 18954630.308 | 0 | 27062479.0891
7396 | 16535055.4907 | 20033396.2561 | 0 | 36568451.7468
7397 | 6938873.312 | 7014482.1141 | 3527752.1611 | 17481107.5873
7398 | 4451214.5593 | 37909408.9939 | 325010.5087 | 42685634.062
7399 | 10806638.8389 | 4609091.7407 | 94431.8809 | 15510162.4605
7400 | 9368373.4505 | 0 | 0 | 9368373.4505
7401 | 8330280.7866 | 12490612.7072 | 1518632.382 | 22339525.8757
7402 | 1255616.5546 | 14930169.1841 | 6868280.5846 | 23054066.3232
7403 | 6427855.2295 | 7411137.1424 | 3018919.6641 | 16857912.036
7404 | 7703630.3032 | 15194437.3478 | 582100.3122 | 23480167.9631
7405 | 15687201.4442 | 4425258.4583 | 3210402.0308 | 23322861.9332
7406 | 1908509.6391 | 7304672.9476 | 0 | 9213182.5867
7407 | 4871056.8893 | 11353448.5816 | 1330927.5438 | 17555433.0147
7408 | 14316815.8743 | 7476559.1067 | 3590203.8461 | 25383578.8271
7409 | 355913.7929 | 4513811.3035 | 2894019.8319 | 7763744.9283
7410 | 7257295.6115 | 0 | 2024986.4182 | 9282282.0297
7411 | 19050737.0523 | 5708152.2405 | 1217270.9676 | 25976160.2604
7412 | 1544497.391 | 0 | 1179671.4554 | 2724168.8464
7413 | 5744719.6002 | 866696.3637 | 5848316.7205 | 12459732.6844
7414 | 5750805.4036 | 15170068.3984 | 0 | 20920873.802
7415 | 5478525.1363 | 0 | 82180.5628 | 5560705.6991
7416 | 11439590.9865 | 1946718.0438 | 2068259.641 | 15454568.6714
7417 | 4632444.6792 | 7706332.82 | 661176.6752 | 12999954.1745
7418 | 3414079.2996 | 4517849.295 | 16736994.5967 | 24668923.1913
7419 | 9020574.9951 | 3147136.3803 | 176505.7203 | 12344217.0957
7420 | 4781991.9885 | 99323.4755 | 4200109.5807 | 9081425.0446
7421 | 6590309.8956 | 15060660.964 | 1296258.0841 | 22947228.9438
7422 | 5790915.3291 | 11361035.3445 | 97379.2039 | 17249329.8776
7423 | 15718499.1828 | 0 | 1967333.2123 | 17685832.3951
7424 | 19404955.0947 | 2836096.9063 | 0 | 22241052.001
7425 | 9066997.315 | 7771962.0942 | 743884.8669 | 17582844.2762
7426 | 13569966.9606 | 4710027.6317 | 1403196.8873 | 19683191.4795
7427 | 9395605.5234 | 5202761.1629 | 5067306.1954 | 19665672.8818
7428 | 3396874.3693 | 0 | 1080457.8268 | 4477332.196
7429 | 6631668.4439 | 2685161.7388 | 0 | 9316830.1827
7430 | 14537887.3084 | 4917166.716 | 0 | 19455054.0244
7431 | 4857832.3223 | 0 | 506491.9322 | 5364324.2545
7432 | 1719318.4252 | 0 | 0 | 1719318.4252
7433 | 8143071.848 | 6103102.8558 | 4722834.8408 | 18969009.5446
7434 | 5898768.0248 | 52989953.0352 | 1100142.4298 | 59988863.4898
7435 | 8652797.3781 | 0 | 2042461.2116 | 10695258.5897
7436 | 9205110.225 | 7968373.959 | 862968.4481 | 18036452.632
7437 | 5023109.8991 | 3964611.0609 | 6894438.0283 | 15882158.9883
7438 | 7327860.6362 | 7079273.9327 | 321096.9579 | 14728231.5267
7439 | 3570224.4824 | 1108314.3921 | 29071107.7006 | 33749646.5752
7440 | 8156353.4523 | 2895766.5404 | 4926970.7368 | 15979090.7296
7441 | 5945038.3418 | 5671467.4685 | 1778454.7172 | 13394960.5275
7442 | 653824.4631 | 981113.8445 | 1220009.5493 | 2854947.8569
7443 | 2435442.2447 | 5214814.8581 | 1438745.9372 | 9089003.0399
7444 | 15675356.1616 | 22458527.1367 | 4008622.8639 | 42142506.1621
7445 | 4232667.9496 | 3475340.9931 | 0 | 7708008.9427
7446 | 11962680.3487 | 12992679.6756 | 17421.76 | 24972781.7843
7447 | 2713997.7667 | 483851.1442 | 1828504.9399 | 5026353.8508
7448 | 432051.5376 | 10574715.8372 | 3283427.9211 | 14290195.2959
7449 | 9379191.7209 | 0 | 0 | 9379191.7209
7450 | 8240841.4288 | 9996981.0378 | 271476.6615 | 18509299.1281
7451 | 15184055.042 | 0 | 444985.5384 | 15629040.5804
7452 | 6532463.7024 | 18837601.4379 | 0 | 25370065.1403
7453 | 16087148.1084 | 4727764.93 | 2090377.0997 | 22905290.1382
7454 | 3171403.7657 | 5990210.6429 | 0 | 9161614.4086
7455 | 29367922.5447 | 17353539.6346 | 3400887.6008 | 50122349.7801
7456 | 8266089.2074 | 1802980.7249 | 324718.0998 | 10393788.0321
7457 | 3021966.8678 | 14978940.4652 | 334105.729 | 18335013.062
7458 | 3453707.8082 | 1243613.7491 | 158262.5875 | 4855584.1448
7459 | 23762105.0455 | 1981346.3004 | 2349572.8683 | 28093024.2142
7460 | 10357497.63 | 30429885.6427 | 0 | 40787383.2727
7461 | 5977310.1367 | 2867498.9385 | 0 | 8844809.0752
7462 | 3676344.2428 | 5952254.6566 | 3796477.0572 | 13425075.9566
7463 | 5057043.815 | 6867280.6404 | 2665546.4196 | 14589870.8751
7464 | 7258348.5517 | 2058418.0676 | 392194.1383 | 9708960.7576
7465 | 10240013.8347 | 10776914.1743 | 2577885.7353 | 23594813.7442
7466 | 1952518.6666 | 1094158.3376 | 18352705.223 | 21399382.2272
7467 | 4822793.3748 | 4838787.7609 | 1543158.0412 | 11204739.1768
7468 | 9181036.5051 | 2531107.0586 | 11530478.0113 | 23242621.575
7469 | 5509755.7013 | 3228260.8603 | 1751171.1634 | 10489187.725
7470 | 7146630.6996 | 0 | 1859100.0106 | 9005730.7102
7471 | 13237821.9423 | 14405655.0679 | 1440573.4819 | 29084050.4921
7472 | 6556464.5403 | 2725717.5892 | 1856977.24 | 11139159.3695
7473 | 3082402.3498 | 16151611.5911 | 24993.4557 | 19259007.3965
7474 | 19657405.5433 | 0 | 63675.6879 | 19721081.2312
7475 | 1762360.1059 | 18694505.6171 | 5308258.9334 | 25765124.6564
7476 | 33620756.3374 | 9469397.7916 | 4684792.8464 | 47774946.9753
7477 | 1340956.8654 | 5328016.9088 | 1644682.8186 | 8313656.5928
7478 | 4457195.4957 | 5528440.4301 | 67854.1905 | 10053490.1163
7479 | 15862221.6045 | 5577619.5616 | 0 | 21439841.1661
7480 | 4019163.0655 | 513978.7732 | 8389475.1346 | 12922616.9733
7481 | 35066468.6569 | 870902.4234 | 1814683.6809 | 37752054.7612
7482 | 8434369.0657 | 0 | 433652.7666 | 8868021.8323
7483 | 4409459.0419 | 7776834.5812 | 3646570.1727 | 15832863.7957
7484 | 11127603.97 | 13361713.2536 | 0 | 24489317.2237
7485 | 1664006.178 | 7031469.1854 | 730117.1748 | 9425592.5381
7486 | 4250467.3618 | 2103881.1643 | 8341272.933 | 14695621.4591
7487 | 11592187.9274 | 4526335.7521 | 1285484.0932 | 17404007.7726
7488 | 11827013.709 | 2246894.0929 | 896377.5786 | 14970285.3805
7489 | 3346597.384 | 4697363.7685 | 0 | 8043961.1525
7490 | 27217938.6725 | 9055143.7308 | 0 | 36273082.4032
7491 | 1766402.4468 | 10068602.0153 | 103778.9396 | 11938783.4016
7492 | 5781482.654 | 13589353.1086 | 1831348.4979 | 21202184.2606
7493 | 4810291.3393 | 1841872.8649 | 2434688.8098 | 9086853.014
7494 | 5284182.2716 | 6203808.5125 | 4030104.5834 | 15518095.3674
7495 | 7763364.2817 | 0 | 3094931.7221 | 10858296.0038
7496 | 14828581.1616 | 1750087.8259 | 784840.1216 | 17363509.1091
7497 | 5431052.4878 | 16169420.9207 | 2666803.3221 | 24267276.7307
7498 | 2610994.8399 | 7595180.7941 | 4496540.5843 | 14702716.2183
7499 | 6786052.8442 | 0 | 597569.5694 | 7383622.4136
7500 | 19368975.1089 | 4290713.7889 | 637162.9701 | 24296851.868
7501 | 7361353.7453 | 10847159.8258 | 29053.6709 | 18237567.242
7502 | 17827647.4372 | 7911553.8954 | 6077962.4267 | 31817163.7592
7503 | 1033434.4434 | 25714121.3209 | 0 | 26747555.7644
7504 | 3216194.8112 | 8296520.8579 | 81421.8676 | 11594137.5368
7505 | 571588.0226 | 16311850.7618 | 1573362.8352 | 18456801.6197
7506 | 20279286.4373 | 8726244.4452 | 4284546.3726 | 33290077.2551
7507 | 5539404.1553 | 12089047.2773 | 223395.91 | 17851847.3425
7508 | 10547633.6262 | 37419124.2451 | 52692.7068 | 48019450.5781
7509 | 6584823.8874 | 6039370.2065 | 5954662.3259 | 18578856.4199
7510 | 41988734.3683 | 13712250.9335 | 4022906.3676 | 59723891.6694
7511 | 8669725.8351 | 0 | 38628.1845 | 8708354.0196
7512 | 5830071.1288 | 7960802.3339 | 1866507.4368 | 15657380.8994
7513 | 1315868.9362 | 8233570.8389 | 2439241.841 | 11988681.6162
7514 | 4056138.3727 | 4509467.469 | 2342901.0036 | 10908506.8452
7515 | 655747.2714 | 13168218.7544 | 17082.5522 | 13841048.578
7516 | 5087842.4524 | 8252906.0641 | 0 | 13340748.5166
7517 | 3998310.503 | 7740911.2501 | 8399915.7863 | 20139137.5394
7518 | 1594070.4414 | 6036748.8063 | 1058778.8514 | 8689598.0991
7519 | 12640169.6767 | 4316487.5858 | 0 | 16956657.2625
7520 | 8033560.6622 | 7168781.1937 | 882331.9784 | 16084673.8343
7521 | 8324865.8761 | 3114591.2222 | 3285931.001 | 14725388.0993
7522 | 2138007.2561 | 7928779.6476 | 12587957.7334 | 22654744.6371
7523 | 4781636.3925 | 1581209.5764 | 5637461.7161 | 12000307.685
7524 | 11408919.4194 | 0 | 0 | 11408919.4194
7525 | 24515767.7314 | 4158224.5889 | 141541.2844 | 28815533.6046
7526 | 7139308.3954 | 13818963.9488 | 1941533.7358 | 22899806.08
7527 | 9785506.5441 | 9879459.0328 | 544458.1027 | 20209423.6797
7528 | 5687370.5592 | 7665297.2622 | 432946.8611 | 13785614.6824
7529 | 19077699.893 | 3718256.7088 | 1385019.1416 | 24180975.7434
7530 | 4426458.4061 | 15813691.6335 | 1886696.8785 | 22126846.9182
7531 | 5858296.3341 | 2656023.3715 | 28754090.3729 | 37268410.0784
7532 | 11506962.1704 | 5536017.8972 | 0 | 17042980.0676
7533 | 19773958.3506 | 10505164.2934 | 1523575.6484 | 31802698.2925
7534 | 2957490.317 | 0 | 83709.9857 | 3041200.3027
7535 | 10538549.4305 | 6638590.908 | 1924037.5605 | 19101177.899
7536 | 3931927.0055 | 1752194.7816 | 4365950.2479 | 10050072.035
7537 | 2860081.4083 | 4031319.6493 | 5988051.503 | 12879452.5607
7538 | 8482935.6349 | 3488095.0098 | 563354.5512 | 12534385.1959
7539 | 4098693.4872 | 3294018.2926 | 9329802.1147 | 16722513.8945
7540 | 1372606.8015 | 2818037.8501 | 0 | 4190644.6517
7541 | 8059677.6639 | 28690282.8717 | 3218844.5743 | 39968805.1099
7542 | 13073561.5744 | 6430800.4046 | 0 | 19504361.979
7543 | 2368710.7464 | 3516147.4146 | 0 | 5884858.161
7544 | 7936989.9377 | 5553641.2804 | 2044096.232 | 15534727.4501
7545 | 9104095.7361 | 6106981.3678 | 185619.8494 | 15396696.9533
7546 | 5141410.8214 | 2003502.7132 | 17079556.404 | 24224469.9386
7547 | 1630680.7168 | 20308557.4466 | 6962619.7777 | 28901857.9411
7548 | 14121318.7504 | 7879198.5165 | 7232811.8162 | 29233329.0831
7549 | 6444125.4312 | 17769014.0688 | 25426402.2588 | 49639541.7588
7550 | 576756.823 | 2769886.38 | 702468.1659 | 4049111.369
7551 | 5592467.0938 | 6631870.4664 | 1946347.2085 | 14170684.7687
7552 | 3604336.2457 | 5348944.8611 | 791035.2046 | 9744316.3115
7553 | 12983774.4867 | 6770379.0469 | 3608554.2571 | 23362707.7907
7554 | 2621189.1062 | 4059473.9707 | 83420.489 | 6764083.566
7555 | 8541454.7703 | 4113481.1617 | 3119104.64 | 15774040.572
7556 | 15040366.7541 | 3172752.4146 | 340750.4097 | 18553869.5784
7557 | 7545727.4191 | 0 | 0 | 7545727.4191
7558 | 6144979.9603 | 6522230.5448 | 153280.3647 | 12820490.8699
7559 | 23248420.1654 | 2325642.4755 | 63267696.9528 | 88841759.5937
7560 | 12803100.2193 | 12947092.7779 | 915022.2502 | 26665215.2475
7561 | 5528397.9644 | 11506014.068 | 365853.1528 | 17400265.1852
7562 | 8348183.3463 | 6624332.1554 | 4984203.1975 | 19956718.6993
7563 | 18728856.5292 | 36141199.029 | 15828197.5044 | 70698253.0625
7564 | 15039886.3185 | 3307543.9256 | 5989688.327 | 24337118.5711
7565 | 5029331.6959 | 15493361.7684 | 505387.3232 | 21028080.7875
7566 | 9357228.0711 | 3576531.0304 | 3026386.3791 | 15960145.4807
7567 | 3689590.41 | 15141020.6178 | 1788467.7766 | 20619078.8045
7568 | 7677144.9452 | 2728867.0248 | 3155406.9869 | 13561418.9568
7569 | 2265360.941 | 0 | 280995.4322 | 2546356.3732
7570 | 4171598.0539 | 7328688.4496 | 1136496.9999 | 12636783.5034
7571 | 8035848.8738 | 0 | 137038.2932 | 8172887.167
7572 | 2404613.4421 | 6494164.5577 | 1772471.5737 | 10671249.5735
7573 | 6857635.4644 | 0 | 11600096.0152 | 18457731.4796
7574 | 7946013.0823 | 2877035.772 | 13177110.8913 | 24000159.7455
7575 | 6897925.3663 | 3072385.5372 | 0 | 9970310.9034
7576 | 1974362.5544 | 6017808.3567 | 4575853.4737 | 12568024.3848
7577 | 4099102.8405 | 2394020.5979 | 758343.8228 | 7251467.2613
7578 | 27258028.7618 | 5761128.7125 | 0 | 33019157.4743
7579 | 23096858.5051 | 6693809.539 | 0 | 29790668.0441
7580 | 3270818.3633 | 6413269.8658 | 0 | 9684088.2291
7581 | 10912136.3056 | 11473888.6791 | 1339892.9213 | 23725917.9061
7582 | 39888493.0148 | 0 | 87279.7103 | 39975772.7251
7583 | 1727985.143 | 11695706.2457 | 1607736.8426 | 15031428.2313
7584 | 2504316.336 | 5216557.3524 | 1167349.1714 | 8888222.8598
7585 | 6751215.1855 | 41387364.9321 | 0 | 48138580.1177
7586 | 283105.5778 | 6412426.5238 | 675971.4278 | 7371503.5294
7587 | 6357408.8296 | 6426286.4879 | 891126.7032 | 13674822.0207
7588 | 9566639.6149 | 10153921.0594 | 0 | 19720560.6743
7589 | 4782036.062 | 10884899.6723 | 2899190.8422 | 18566126.5766
7590 | 10968707.4136 | 0 | 2907950.0247 | 13876657.4383
7591 | 8721593.6303 | 3637204.4486 | 2232211.6969 | 14591009.7758
7592 | 5605046.8766 | 2669269.9785 | 0 | 8274316.8551
7593 | 3037331.9028 | 8590171.2329 | 543194.5152 | 12170697.6509
7594 | 2896737.2082 | 8903578.2469 | 4085668.6043 | 15885984.0593
7595 | 20996163.0404 | 16905674.7513 | 48240.8611 | 37950078.6528
7596 | 5638913.4567 | 4352852.7653 | 0 | 9991766.222
7597 | 13687092.0923 | 8177346.0835 | 933678.9748 | 22798117.1506
7598 | 9193084.4185 | 8897648.4186 | 313394.492 | 18404127.3291
7599 | 9322951.6142 | 312187.5777 | 3888039.1589 | 13523178.3508
7600 | 21229877.8482 | 1322779.8324 | 0 | 22552657.6805
7601 | 4543348.1214 | 0 | 387614.1573 | 4930962.2787
7602 | 5248678.0583 | 15860717.3193 | 630562.8678 | 21739958.2454
7603 | 5398656.0398 | 1278131.7096 | 20499415.5997 | 27176203.349
7604 | 5317382.6425 | 7505108.3397 | 4003900.4909 | 16826391.4732
7605 | 8648298.1271 | 17374498.534 | 103800.178 | 26126596.8392
7606 | 3087302.7567 | 2378973.0424 | 188407.9785 | 5654683.7776
7607 | 21104189.31 | 10894539.5644 | 16084715.4979 | 48083444.3724
7608 | 4055749.9179 | 5320762.5535 | 0 | 9376512.4715
7609 | 4420491.8808 | 850625.3497 | 7745617.6978 | 13016734.9283
7610 | 2935822.8716 | 12470884.6751 | 9432404.1421 | 24839111.6887
7611 | 5593519.4779 | 10581183.6832 | 517894.6046 | 16692597.7657
7612 | 696429.765 | 7796359.095 | 14860553.4084 | 23353342.2684
7613 | 11076836.7927 | 33935302.6389 | 72315.7961 | 45084455.2278
7614 | 2946916.6278 | 20425278.7703 | 649766.1089 | 24021961.5071
7615 | 8422154.0471 | 21507649.8886 | 9035372.5836 | 38965176.5193
7616 | 3538666.7648 | 5020317.7244 | 70609.2192 | 8629593.7084
7617 | 14243734.751 | 3895617.486 | 559855.7825 | 18699208.0194
7618 | 1860346.6267 | 12815061.4525 | 445585.4389 | 15120993.5181
7619 | 6595079.8021 | 5368895.6113 | 0 | 11963975.4134
7620 | 12875378.8523 | 4886247.4449 | 2118492.3897 | 19880118.6868
7621 | 12256572.5679 | 2970499.6203 | 6471110.9422 | 21698183.1304
7622 | 8271727.7476 | 2092303.7285 | 517922.8146 | 10881954.2908
7623 | 8847404.0812 | 0 | 5625205.5444 | 14472609.6256
7624 | 4953825.6984 | 7774401.7144 | 187977.7301 | 12916205.1429
7625 | 22662211.2175 | 5325291.7062 | 1195682.533 | 29183185.4567
7626 | 11643219.3226 | 11829141.6836 | 1730293.9493 | 25202654.9555
7627 | 3112164.2135 | 7560494.8061 | 1195453.366 | 11868112.3856
7628 | 6342988.585 | 11078707.4234 | 3068503.5042 | 20490199.5125
7629 | 6455020.6463 | 12816510.7485 | 612345.4123 | 19883876.8071
7630 | 13453732.6144 | 25035552.5582 | 7143204.7023 | 45632489.8748
7631 | 2742019.5869 | 4889346.1122 | 4247484.7692 | 11878850.4684
7632 | 22510865.2627 | 0 | 0 | 22510865.2627
7633 | 2236593.7059 | 5608417.3948 | 0 | 7845011.1008
7634 | 2953768.4916 | 2503536.2209 | 103783.5442 | 5561088.2566
7635 | 6066737.8994 | 0 | 0 | 6066737.8994
7636 | 7320093.942 | 2469430.5712 | 62296.4426 | 9851820.9558
7637 | 13452508.8216 | 5789283.0562 | 3560731.4855 | 22802523.3633
7638 | 6810685.7792 | 13204960.8644 | 360044.4406 | 20375691.0842
7639 | 15284681.497 | 0 | 2139461.9279 | 17424143.425
7640 | 5968183.8392 | 16134670.8901 | 682462.9824 | 22785317.7118
7641 | 2690028.6711 | 5319187.8874 | 24308.8834 | 8033525.4419
7642 | 11665640.557 | 8414793.1886 | 89015.0082 | 20169448.7537
7643 | 6709919.837 | 2076238.6869 | 1666319.1605 | 10452477.6843
7644 | 13011378.0822 | 0 | 10305271.0883 | 23316649.1705
7645 | 30854738.9726 | 4775256.9394 | 9024294.468 | 44654290.3801
7646 | 19088927.3242 | 0 | 11590094.4724 | 30679021.7966
7647 | 2526439.4161 | 19359858.6583 | 173078.3933 | 22059376.4677
7648 | 8311641.6364 | 897271.4333 | 317921.8874 | 9526834.957
7649 | 6272273.8094 | 11616076.4914 | 403752.1572 | 18292102.458
7650 | 10518326.7937 | 6995812.3114 | 1936494.1594 | 19450633.2645
7651 | 9988377.0815 | 16338803.9326 | 254634.7635 | 26581815.7776
7652 | 3583802.4108 | 13198370.6158 | 974207.0505 | 17756380.0771
7653 | 9578523.8436 | 1265744.4145 | 3265648.1533 | 14109916.4115
7654 | 13675521.2324 | 7500680.1967 | 4999109.0186 | 26175310.4477
7655 | 2790221.2475 | 7692541.8134 | 43251.4425 | 10526014.5033
7656 | 3060124.7618 | 5495009.2738 | 1832319.0597 | 10387453.0954
7657 | 21407857.3636 | 0 | 26228991.9976 | 47636849.3612
7658 | 4033727.4792 | 3514939.387 | 140110.0066 | 7688776.8729
7659 | 6597148.0789 | 3798182.9933 | 400019.0688 | 10795350.141
7660 | 299071.946 | 0 | 0 | 299071.946
7661 | 13132053.44 | 7249430.7349 | 0 | 20381484.175
7662 | 28412790.1994 | 2977529.1625 | 633884.3109 | 32024203.6727
7663 | 22642867.3473 | 32238156.3257 | 1862337.8895 | 56743361.5625
7664 | 4557687.3361 | 8959635.6072 | 113276.1382 | 13630599.0815
7665 | 2465904.3513 | 12955234.3213 | 0 | 15421138.6726
7666 | 2115525.9597 | 7915311.9755 | 172411.9563 | 10203249.8915
7667 | 1524960.1656 | 19745027.5205 | 1116207.0575 | 22386194.7436
7668 | 3668595.6441 | 0 | 321104.0223 | 3989699.6663
7669 | 12513003.4402 | 934858.5103 | 0 | 13447861.9505
7670 | 7958854.355 | 2367241.115 | 25921990.0128 | 36248085.4828
7671 | 8945896.228 | 2042237.9412 | 1221382.0651 | 12209516.2343
7672 | 3564417.3966 | 0 | 3101367.9085 | 6665785.3051
7673 | 4338608.7595 | 0 | 4776829.4443 | 9115438.2038
7674 | 3757726.4122 | 5641327.9013 | 5839911.4106 | 15238965.7241
7675 | 7597486.1194 | 2866268.0861 | 3273375.31 | 13737129.5155
7676 | 1234134.7977 | 3276387.397 | 4249761.4417 | 8760283.6364
7677 | 7244600.7515 | 26070407.0571 | 2806042.768 | 36121050.5765
7678 | 12980137.3855 | 4495839.8408 | 1345576.0445 | 18821553.2708
7679 | 4735069.562 | 2782904.1442 | 1141238.4399 | 8659212.1461
7680 | 3013745.7834 | 12597078.0011 | 0 | 15610823.7845
7681 | 12324169.0276 | 9245907.4673 | 2961535.9004 | 24531612.3953
7682 | 6417486.1805 | 9076614.9851 | 1504033.8174 | 16998134.9831
7683 | 2217432.7647 | 7393044.7163 | 0 | 9610477.481
7684 | 6497649.2944 | 6168100.5123 | 967420.4047 | 13633170.2113
7685 | 41191296.7263 | 9198647.4567 | 1634435.355 | 52024379.538
7686 | 7717014.3167 | 22550240.1413 | 920284.9079 | 31187539.366
7687 | 3024250.2655 | 5980559.1493 | 985880.7902 | 9990690.205
7688 | 16529965.9117 | 0 | 432953.7782 | 16962919.6899
7689 | 2836932.831 | 5938874.6835 | 0 | 8775807.5145
7690 | 3550135.6248 | 4873846.608 | 8002968.3192 | 16426950.552
7691 | 27657211.5914 | 9852383.169 | 793827.3262 | 38303422.0866
7692 | 1626456.3999 | 11630622.928 | 0 | 13257079.3278
7693 | 5438560.454 | 5736321.9752 | 892328.6621 | 12067211.0913
7694 | 9138530.5979 | 5251504.5858 | 401081.6752 | 14791116.859
7695 | 5314631.5232 | 10287217.5925 | 86071.0041 | 15687920.1198
7696 | 19419601.7617 | 0 | 11157784.9149 | 30577386.6766
7697 | 17915765.4337 | 6331798.7455 | 4957524.3692 | 29205088.5484
7698 | 7961661.8674 | 20305610.2308 | 1004279.6307 | 29271551.7289
7699 | 10315813.9324 | 3986932.2253 | 3444815.7091 | 17747561.8667
7700 | 5694730.5176 | 0 | 0 | 5694730.5176
7701 | 5580323.2277 | 6045054.0233 | 1090474.5708 | 12715851.8218
7702 | 9771589.5081 | 11076044.6874 | 0 | 20847634.1955
7703 | 3282261.6552 | 1741930.5573 | 398127.2487 | 5422319.4613
7704 | 16766392.9786 | 3839653.02 | 562173.5552 | 21168219.5538
7705 | 28684295.7795 | 8013740.0024 | 8735488.6503 | 45433524.4322
7706 | 8074412.1106 | 11107840.8473 | 281930.6451 | 19464183.603
7707 | 4234445.8184 | 2907921.9206 | 4689650.7762 | 11832018.5152
7708 | 1755742.8485 | 2735889.4444 | 10683514.889 | 15175147.182
7709 | 2099886.7517 | 7388669.5373 | 1774585.2953 | 11263141.5842
7710 | 4817165.6633 | 293563.3996 | 18450869.2108 | 23561598.2738
7711 | 2045919.6117 | 2832619.6535 | 1143586.3621 | 6022125.6273
7712 | 5694239.1434 | 1864203.6918 | 141208.1647 | 7699651
7713 | 3910552.1836 | 10935213.3254 | 0 | 14845765.509
7714 | 1121387.4678 | 1538953.139 | 721522.9479 | 3381863.5547
7715 | 5522183.0041 | 1882113.67 | 440196.0844 | 7844492.7585
7716 | 8487935.7561 | 6669462.1404 | 115233.112 | 15272631.0084
7717 | 11538814.8707 | 5373351.1019 | 2995798.0939 | 19907964.0665
7718 | 7847421.1853 | 2183550.4632 | 0 | 10030971.6485
7719 | 5878750.2418 | 3819274.7447 | 428546.2289 | 10126571.2154
7720 | 5840334.1696 | 0 | 2195042.8194 | 8035376.989
7721 | 9998150.8642 | 3199492.6534 | 512590.2841 | 13710233.8017
7722 | 5373182.6509 | 0 | 139147.1066 | 5512329.7575
7723 | 2839687.3773 | 2113562.0797 | 14541.6209 | 4967791.078
7724 | 6568960.2908 | 28305561.8134 | 941486.7032 | 35816008.8075
7725 | 3200621.0575 | 17934768.8436 | 0 | 21135389.9011
7726 | 16519227.3748 | 2821212.9821 | 138483.047 | 19478923.4039
7727 | 11398562.9777 | 13771829.9439 | 12347550.9186 | 37517943.8402
7728 | 6970528.0526 | 3595967.4323 | 79536.7856 | 10646032.2705
7729 | 11293399.5205 | 4993851.2781 | 10365452.2098 | 26652703.0084
7730 | 11047997.8606 | 25042281.7957 | 386785.8088 | 36477065.4652
7731 | 4863613.6337 | 16095135.412 | 10134040.6106 | 31092789.6562
7732 | 21517322.8935 | 2828156.4436 | 193883.8196 | 24539363.1567
7733 | 27595231.546 | 0 | 297104.2509 | 27892335.7969
7734 | 14778740.3203 | 13478153.3536 | 3850618.3836 | 32107512.0575
7735 | 9636608.4177 | 10086064.7638 | 0 | 19722673.1814
7736 | 5918188.7198 | 1438693.6978 | 15020540.435 | 22377422.8526
7737 | 1784489.5769 | 3191322.4253 | 1790626.5732 | 6766438.5754
7738 | 7467244.0124 | 1668580.7158 | 16351780.1621 | 25487604.8903
7739 | 4589806.6312 | 4229278.5185 | 712397.1768 | 9531482.3265
7740 | 5483038.6031 | 8851738.865 | 2980519.2451 | 17315296.7131
7741 | 14160026.7947 | 0 | 2602277.0276 | 16762303.8223
7742 | 3530155.5618 | 6879046.1803 | 1619160.7657 | 12028362.5077
7743 | 25815053.1368 | 6787321.0464 | 58232.0943 | 32660606.2775
7744 | 26796854.1206 | 10298579.4938 | 2377187.6451 | 39472621.2595
7745 | 8978126.4303 | 25729383.5307 | 224231.3332 | 34931741.2943
7746 | 6021353.1435 | 3162090.6344 | 0 | 9183443.7779
7747 | 2587679.7202 | 9825778.1961 | 698523.5849 | 13111981.5012
7748 | 22746420.4283 | 11999852.8034 | 224496.8581 | 34970770.0898
7749 | 8854751.6445 | 7223874.4806 | 272105.9978 | 16350732.123
7750 | 20389123.4391 | 0 | 0 | 20389123.4391
7751 | 20864059.9529 | 10626977.9686 | 6145997.0745 | 37637034.9961
7752 | 2436511.2871 | 11635615.7678 | 607720.8387 | 14679847.8935
7753 | 1793235.6018 | 9062666.0794 | 0 | 10855901.6812
7754 | 1484928.1914 | 7432770.0884 | 16092935.1355 | 25010633.4153
7755 | 9500350.6571 | 651979.361 | 6584324.389 | 16736654.4071
7756 | 6603103.0008 | 4149354.2954 | 4318108.1794 | 15070565.4756
7757 | 8819192.8969 | 5752089.4246 | 594213.4877 | 15165495.8092
7758 | 14566341.8788 | 12883112.7541 | 128077.6768 | 27577532.3097
7759 | 4563557.9717 | 0 | 682461.5771 | 5246019.5488
7760 | 2170020.4917 | 43184517.6736 | 1006934.1391 | 46361472.3044
7761 | 3187682.1435 | 8488921.4755 | 1877024.6492 | 13553628.2682
7762 | 9354223.2219 | 0 | 202513.1892 | 9556736.4111
7763 | 11744342.7413 | 5309888.6457 | 1147897.136 | 18202128.523
7764 | 25247046.5451 | 0 | 3335977.6607 | 28583024.2058
7765 | 3266365.6941 | 4237176.1466 | 3284977.7599 | 10788519.6007
7766 | 7540049.7447 | 7267173.6625 | 668515.5198 | 15475738.927
7767 | 2696839.716 | 4687989.5404 | 1250789.1896 | 8635618.446
7768 | 245016.829 | 2524189.7709 | 282859.1945 | 3052065.7944
7769 | 20702865.4065 | 3021114.176 | 102732.5352 | 23826712.1177
7770 | 17053294.6847 | 0 | 14227242.1286 | 31280536.8133
7771 | 2471980.8364 | 1826046.0802 | 3000053.7944 | 7298080.711
7772 | 22408031.4658 | 4765704.6806 | 0 | 27173736.1464
7773 | 45030567.2232 | 4877366.3457 | 4743643.9367 | 54651577.5056
7774 | 2107814.4142 | 0 | 1656324.3495 | 3764138.7637
7775 | 15226985.6243 | 0 | 15247516.9311 | 30474502.5554
7776 | 13485280.2405 | 38635089.0023 | 0 | 52120369.2427
7777 | 12259832.4854 | 15477369.7471 | 2864760.2787 | 30601962.5112
7778 | 7541398.2703 | 8059609.5539 | 9872364.349 | 25473372.1733
7779 | 3634132.523 | 12463236.6176 | 26119294.7915 | 42216663.9322
7780 | 7187453.0557 | 5320605.3446 | 33560.8622 | 12541619.2625
7781 | 18721950.1819 | 10575424.1041 | 0 | 29297374.286
7782 | 11662260.8682 | 8716635.9311 | 2327858.6933 | 22706755.4925
7783 | 264097.2585 | 4275984.9818 | 207616.9895 | 4747699.2297
7784 | 3231381.3759 | 7676894.4213 | 1406975.3947 | 12315251.1919
7785 | 12453761.3239 | 6199690.4137 | 2537643.4077 | 21191095.1454
7786 | 839386.1416 | 6765170.5242 | 9265450.4741 | 16870007.1399
7787 | 11273545.3465 | 8910460.383 | 2723530.0803 | 22907535.8098
7788 | 22415603.7823 | 3866259.9443 | 591566.0084 | 26873429.735
7789 | 4535502.9543 | 3200983.2718 | 685610.0933 | 8422096.3193
7790 | 10760970.0668 | 9691166.2684 | 115097.9033 | 20567234.2384
7791 | 7018802.3968 | 8328240.4272 | 4760926.9948 | 20107969.8188
7792 | 9218851.231 | 0 | 11786090.7535 | 21004941.9846
7793 | 19776258.846 | 15485245.2538 | 1353707.0979 | 36615211.1976
7794 | 2894207.8245 | 2829225.3499 | 30243.5777 | 5753676.7521
7795 | 2833627.7274 | 8321540.9927 | 142576.2904 | 11297745.0105
7796 | 8228483.2744 | 35901828.976 | 1852941.9804 | 45983254.2308
7797 | 7243885.6721 | 12536675.5314 | 136808.3873 | 19917369.5908
7798 | 4217418.7224 | 10181044.9114 | 1520895.9288 | 15919359.5626
7799 | 2453893.9065 | 12298339.5179 | 2239711.3544 | 16991944.7788
7800 | 22826069.8056 | 7753504.1967 | 1316483.859 | 31896057.8614
7801 | 8991216.2966 | 6939997.2942 | 2251022.344 | 18182235.9348
7802 | 7454249.3496 | 33947289.7953 | 0 | 41401539.1449
7803 | 4931943.1133 | 1383423.0617 | 3341208.1268 | 9656574.3018
7804 | 21351194.1679 | 0 | 13987105.7463 | 35338299.9142
7805 | 7455679.9276 | 1619833.3836 | 1226805.2127 | 10302318.5238
7806 | 5592691.5989 | 5855296.7148 | 320251.6732 | 11768239.9869
7807 | 2669846.4121 | 3507612.5649 | 3714785.1411 | 9892244.1181
7808 | 5959556.2243 | 3885697.5597 | 1348758.1217 | 11194011.9058
7809 | 8188605.7006 | 0 | 201859.084 | 8390464.7846
7810 | 14887029.9963 | 6466841.7436 | 18532578.123 | 39886449.8629
7811 | 11064005.3157 | 11922572.6117 | 102548.4853 | 23089126.4127
7812 | 10536722.4446 | 19456966.996 | 0 | 29993689.4405
7813 | 11787687.0643 | 0 | 535269.667 | 12322956.7314
7814 | 6702530.9759 | 6379286.6994 | 580979.962 | 13662797.6374
7815 | 3096175.602 | 2377709.3688 | 1090056.1482 | 6563941.119
7816 | 12999815.6118 | 4127487.3945 | 1350679.0293 | 18477982.0356
7817 | 3377834.2663 | 7512482.1938 | 1563793.3894 | 12454109.8495
7818 | 3083591.6059 | 0 | 9653359.3868 | 12736950.9927
7819 | 9294417.5528 | 7603767.1263 | 0 | 16898184.6791
7820 | 4452715.3712 | 4312454.6853 | 2158138.7177 | 10923308.7741
7821 | 5481363.7513 | 1701313.2167 | 101601.1765 | 7284278.1446
7822 | 7903422.5777 | 3556607.2287 | 0 | 11460029.8064
7823 | 6908521.9918 | 25361674.4145 | 6383844.8493 | 38654041.2557
7824 | 1996545.6445 | 4402962.8338 | 8880985.4173 | 15280493.8956
7825 | 50744841.82 | 9495613.3684 | 0 | 60240455.1884
7826 | 3836188.8751 | 2878090.4153 | 0 | 6714279.2905
7827 | 707053.4645 | 16095044.4287 | 166910.1647 | 16969008.0579
7828 | 5594318.6975 | 9686527.9984 | 3789004.4719 | 19069851.1678
7829 | 3987961.659 | 6605482.8611 | 695126.5893 | 11288571.1095
7830 | 7811287.072 | 8436556.7344 | 6238391.9147 | 22486235.721
7831 | 2805678.737 | 5730269.6274 | 1664627.6068 | 10200575.9712
7832 | 7302797.8445 | 4744800.9952 | 508663.4797 | 12556262.3194
7833 | 24545685.8092 | 331006.6242 | 409267.048 | 25285959.4814
7834 | 2291241.1116 | 0 | 1784791.425 | 4076032.5366
7835 | 3496983.5696 | 3020220.3348 | 0 | 6517203.9044
7836 | 7768401.599 | 6293246.381 | 1783540.1345 | 15845188.1145
7837 | 5800886.6163 | 0 | 444320.3088 | 6245206.9251
7838 | 17321389.5199 | 0 | 11535580.3492 | 28856969.8691
7839 | 1829066.8059 | 4165447.1089 | 3547294.5551 | 9541808.4699
7840 | 5102004.9114 | 4164910.8175 | 307283.8108 | 9574199.5397
7841 | 16819180.5608 | 31945514.6775 | 943615.1436 | 49708310.3819
7842 | 9129707.1226 | 11114297.9458 | 0 | 20244005.0684
7843 | 6985393.6753 | 0 | 10037345.7333 | 17022739.4086
7844 | 11290648.7905 | 11367872.3749 | 0 | 22658521.1654
7845 | 9076760.6233 | 12842334.6342 | 1278554.2565 | 23197649.514
7846 | 8169729.1548 | 7861349.8664 | 65764.2609 | 16096843.282
7847 | 11569383.492 | 6985764.7355 | 1039992.7269 | 19595140.9545
7848 | 1573712.2621 | 23040182.4324 | 103955.4154 | 24717850.11
7849 | 10062079.8302 | 4132971.713 | 3001307.8797 | 17196359.4229
7850 | 3936459.0901 | 2779163.891 | 0 | 6715622.9811
7851 | 15936307.0936 | 3764102.5167 | 589746.058 | 20290155.6684
7852 | 7974700.6545 | 5416608.0245 | 107060.0233 | 13498368.7023
7853 | 9116363.6766 | 12093733.2788 | 145943.93 | 21356040.8854
7854 | 19201935.5154 | 0 | 9611114.2099 | 28813049.7252
7855 | 3244236.8524 | 0 | 5396213.751 | 8640450.6034
7856 | 11250900.1888 | 0 | 667472.9805 | 11918373.1693
7857 | 6595831.7199 | 0 | 1453596.5277 | 8049428.2476
7858 | 1302031.7988 | 12136987.2231 | 265799.477 | 13704818.4989
7859 | 3203791.248 | 9875250.538 | 0 | 13079041.7861
7860 | 4744899.4265 | 23874345.5032 | 3688329.0396 | 32307573.9693
7861 | 17363820.4184 | 8475946.7128 | 3081763.18 | 28921530.3112
7862 | 18921654.3546 | 2951652.2608 | 716733.3097 | 22590039.9251
7863 | 37630669.4982 | 7957559.0774 | 0 | 45588228.5756
7864 | 5072898.2828 | 5546211.396 | 24130.322 | 10643240.0008
7865 | 3965340.7258 | 32651380.1542 | 494883.6937 | 37111604.5737
7866 | 11714935.1536 | 12800826.7711 | 283040.3867 | 24798802.3115
7867 | 21623850.2416 | 1392057.6834 | 0 | 23015907.925
7868 | 9036761.0188 | 6043760.7636 | 3361835.0574 | 18442356.8397
7869 | 3947682.7317 | 5816023.7439 | 0 | 9763706.4756
7870 | 8042340.9171 | 10908809.8046 | 2121273.5022 | 21072424.2238
7871 | 19186058.1543 | 6281330.8559 | 3622810.0151 | 29090199.0254
7872 | 2078888.6556 | 0 | 450522.9804 | 2529411.636
7873 | 3288191.4441 | 4825303.3578 | 21620099.23 | 29733594.0319
7874 | 25209564.5221 | 0 | 3005134.189 | 28214698.7111
7875 | 7291431.0906 | 7659326.1667 | 1833260.1521 | 16784017.4094
7876 | 4384581.0219 | 4942749.2262 | 3170690.1419 | 12498020.39
7877 | 3638891.8384 | 0 | 3111774.4015 | 6750666.24
7878 | 6047561.752 | 0 | 1040955.5411 | 7088517.2932
7879 | 13522612.516 | 4543417.5853 | 446509.28 | 18512539.3813
7880 | 6103730.061 | 3087977.4345 | 4349458.471 | 13541165.9666
7881 | 2364902.6729 | 0 | 1624350.2755 | 3989252.9484
7882 | 13834287.9244 | 0 | 0 | 13834287.9244
7883 | 6629782.9148 | 12745897.2007 | 0 | 19375680.1155
7884 | 19785281.0307 | 2552722.6261 | 48438.1002 | 22386441.7569
7885 | 11511041.0108 | 7279253.9655 | 234346.9298 | 19024641.9061
7886 | 1079758.7234 | 7069378.0351 | 3061368.8662 | 11210505.6247
7887 | 18121821.3315 | 0 | 4718084.6948 | 22839906.0263
7888 | 50401158.9437 | 265301.0537 | 1836981.2784 | 52503441.2758
7889 | 4701451.7182 | 3429702.7088 | 3714062.6625 | 11845217.0894
7890 | 2515424.4862 | 660734.5137 | 22203109.8223 | 25379268.8222
7891 | 10874766.5943 | 10702683.6284 | 1425631.6454 | 23003081.8681
7892 | 4030926.5938 | 6218785.5536 | 2252336.3021 | 12502048.4495
7893 | 3506246.8692 | 5119045.5416 | 876750.6011 | 9502043.0119
7894 | 5983769.4599 | 43258582.216 | 1008004.1293 | 50250355.8052
7895 | 10909672.5059 | 2258889.8381 | 1168723.2023 | 14337285.5463
7896 | 168833.0866 | 3961270.8814 | 720191.3117 | 4850295.2797
7897 | 7906397.7727 | 2703727.7666 | 33595.5238 | 10643721.0631
7898 | 1727543.8629 | 4141079.7781 | 751171.5676 | 6619795.2087
7899 | 14558089.0056 | 769882.9909 | 3300381.8121 | 18628353.8086
7900 | 9985962.2482 | 7016172.0013 | 1358085.1875 | 18360219.4371
7901 | 9912241.0121 | 1628970.4776 | 0 | 11541211.4897
7902 | 21359066.4441 | 23071671.5191 | 0 | 44430737.9632
7903 | 2964638.2808 | 0 | 1720487.6248 | 4685125.9056
7904 | 2466133.2027 | 10892786.7215 | 0 | 13358919.9242
7905 | 3412220.4233 | 1063554.9121 | 124980.7315 | 4600756.0669
7906 | 8908422.4031 | 2551665.8943 | 10433689.653 | 21893777.9503
7907 | 6816659.6304 | 12908545.4317 | 113722.6733 | 19838927.7353
7908 | 42552603.7834 | 12513414.4818 | 376042.9161 | 55442061.1812
7909 | 18433116.5317 | 8342546.8639 | 3128935.6842 | 29904599.0798
7910 | 22933515.7075 | 7981903.009 | 399445.0447 | 31314863.7612
7911 | 1848222.4145 | 4292318.6852 | 0 | 6140541.0997
7912 | 6048227.7881 | 1979738.2654 | 0 | 8027966.0535
7913 | 6359910.5065 | 15793990.3263 | 416484.3574 | 22570385.1902
7914 | 10102566.3401 | 16238311.9582 | 369586.142 | 26710464.4403
7915 | 2854732.8886 | 8138790.7554 | 0 | 10993523.6439
7916 | 4257710.336 | 11146992.4205 | 1709374.0474 | 17114076.8039
7917 | 5434533.7867 | 0 | 0 | 5434533.7867
7918 | 5797458.533 | 0 | 630945.016 | 6428403.549
7919 | 12409805.1165 | 2559030.6262 | 1115694.7164 | 16084530.4591
7920 | 4335282.8468 | 20466425.5874 | 5457347.9148 | 30259056.349
7921 | 6089567.7526 | 0 | 0 | 6089567.7526
7922 | 11584668.7684 | 5203026.7477 | 0 | 16787695.5161
7923 | 24536384.9143 | 13344350.818 | 4195527.2268 | 42076262.9591
7924 | 3788080.4304 | 3919137.1459 | 0 | 7707217.5763
7925 | 7521065.0413 | 7540761.9777 | 0 | 15061827.019
7926 | 8323772.7455 | 5720301.393 | 194201.8756 | 14238276.014
7927 | 3597992.5572 | 8331303.8413 | 929830.3456 | 12859126.7441
7928 | 23225979.12 | 4988309.2079 | 1822456.0382 | 30036744.3661
7929 | 10877808.9898 | 11500614.1858 | 8892541.6954 | 31270964.8709
7930 | 3243377.1678 | 23050146.1231 | 8362.9305 | 26301886.2215
7931 | 5930332.4217 | 15979247.1868 | 1570432.9056 | 23480012.514
7932 | 1873084.6402 | 2978450.5043 | 84003.5606 | 4935538.7051
7933 | 9082522.0897 | 0 | 1302764.6493 | 10385286.7389
7934 | 10175233.0118 | 0 | 0 | 10175233.0118
7935 | 8330900.4439 | 11821014.0266 | 1159143.5089 | 21311057.9795
7936 | 12994442.6742 | 4634636.7662 | 1366677.368 | 18995756.8083
7937 | 25730136.0392 | 0 | 2445195.4728 | 28175331.512
7938 | 10928255.1857 | 17383984.7421 | 428706.0598 | 28740945.9876
7939 | 2167536.3678 | 3249051.5861 | 0 | 5416587.9539
7940 | 3104179.5962 | 3162729.5891 | 993253.1077 | 7260162.2931
7941 | 14240180.3514 | 11877906.5751 | 0 | 26118086.9265
7942 | 2555408.3913 | 916892.0273 | 876630.2816 | 4348930.7001
7943 | 5584787.4187 | 13175419.4731 | 825055.8689 | 19585262.7607
7944 | 19828270.5863 | 6482292.0236 | 1088532.0609 | 27399094.6707
7945 | 2132435.0057 | 5098185.105 | 2121728.6506 | 9352348.7612
7946 | 11488378.142 | 2941794.4986 | 970701.9467 | 15400874.5873
7947 | 12253546.9363 | 23263488.2961 | 2244405.9118 | 37761441.1442
7948 | 6292764.598 | 6505882.8686 | 638454.4701 | 13437101.9366
7949 | 3860931.3526 | 8476054.0643 | 666168.9898 | 13003154.4067
7950 | 5541158.2532 | 0 | 11912254.1387 | 17453412.392
7951 | 3447265.3952 | 4635371.563 | 9832368.025 | 17915004.9832
7952 | 7540864.2106 | 2226224.3905 | 18103071.6306 | 27870160.2317
7953 | 7075606.3114 | 22921763.6226 | 53113.3016 | 30050483.2357
7954 | 1265683.0261 | 395843.9174 | 7779606.7594 | 9441133.7028
7955 | 5228124.8336 | 20951358.4709 | 2187912.5291 | 28367395.8336
7956 | 6349127.4152 | 0 | 1451976.0484 | 7801103.4637
7957 | 30058642.1078 | 0 | 1009001.6799 | 31067643.7877
7958 | 4287729.4785 | 7388448.5198 | 1142374.723 | 12818552.7213
7959 | 4082782.104 | 2137077.3592 | 13855.2739 | 6233714.7371
7960 | 2517410.4894 | 11339056.7482 | 6941852.4472 | 20798319.6847
7961 | 1710619.5652 | 4634040.9381 | 82158.4825 | 6426818.9857
7962 | 10135858.1823 | 2211780.2091 | 180294.4424 | 12527932.8338
7963 | 1870462.3232 | 0 | 7319291.2379 | 9189753.5611
7964 | 3610194.3508 | 6603559.051 | 3692468.2189 | 13906221.6207
7965 | 12620807.7779 | 0 | 5203137.5284 | 17823945.3063
7966 | 5114826.6261 | 9822965.6714 | 175088.404 | 15112880.7015
7967 | 16432551.8139 | 2411734.0505 | 1719196.2765 | 20563482.1409
7968 | 6594436.9159 | 10608246.0866 | 1376763.9576 | 18579446.9601
7969 | 8034946.5732 | 0 | 3263418.0928 | 11298364.666
7970 | 2955340.9921 | 2736632.1824 | 0 | 5691973.1744
7971 | 3206703.4236 | 2734273.227 | 0 | 5940976.6506
7972 | 26856151.6399 | 3024384.7765 | 1813462.4077 | 31693998.8241
7973 | 1498697.8887 | 3793448.0818 | 0 | 5292145.9706
7974 | 1328132.4513 | 580356.9025 | 1699811.2979 | 3608300.6517
7975 | 3013422.9611 | 4724653.6721 | 4260449.2542 | 11998525.8873
7976 | 11007551.7833 | 7080588.0168 | 0 | 18088139.8001
7977 | 13614587.368 | 15051865.9903 | 3579891.3862 | 32246344.7446
7978 | 15197278.4719 | 8768249.649 | 116764.5056 | 24082292.6265
7979 | 1517291.5459 | 1424320.5241 | 2117595.9367 | 5059208.0068
7980 | 6075244.1868 | 12509600.9862 | 17845813.1675 | 36430658.3405
7981 | 5117010.6996 | 8617792.0959 | 13695924.1337 | 27430726.9292
7982 | 1069998.2876 | 4830429.979 | 2739060.3053 | 8639488.5719
7983 | 6383717.8786 | 14901790.6266 | 1283962.8138 | 22569471.319
7984 | 8936534.1223 | 7370358.0466 | 0 | 16306892.169
7985 | 5177003.1245 | 14093108.3782 | 47625.5748 | 19317737.0775
7986 | 1974099.5301 | 5756224.9814 | 1201062.7275 | 8931387.239
7987 | 11236969.8452 | 2535259.4649 | 4172441.3838 | 17944670.6939
7988 | 10485765.0179 | 2343283.8987 | 0 | 12829048.9166
7989 | 2302944.6132 | 7961807.2511 | 2082641.4875 | 12347393.3518
7990 | 4831415.1432 | 8917040.8524 | 6102598.4002 | 19851054.3959
7991 | 4887470.5862 | 5044508.3428 | 0 | 9931978.929
7992 | 4781434.9647 | 24631690.0599 | 4347205.3468 | 33760330.3714
7993 | 5684505.6059 | 3361561.9519 | 0 | 9046067.5578
7994 | 14823638.3452 | 0 | 3411511.766 | 18235150.1112
7995 | 7119833.8538 | 4081058.0263 | 14387.7185 | 11215279.5986
7996 | 2187941.7408 | 4055163.642 | 0 | 6243105.3828
7997 | 3582940.6357 | 10543713.8164 | 1082702.6865 | 15209357.1386
7998 | 6646412.9255 | 0 | 421695.0958 | 7068108.0213
7999 | 11313729.7753 | 29198828.5384 | 0 | 40512558.3137
8000 | 7661344.3351 | 3071618.7957 | 145738.8756 | 10878702.0064
8001 | 5171636.0898 | 0 | 311440.5709 | 5483076.6607
8002 | 2147294.1819 | 5534651.8281 | 624378.2466 | 8306324.2566
8003 | 576957.139 | 1817118.1477 | 6579904.8528 | 8973980.1395
8004 | 8059463.0379 | 2050096.7368 | 1534831.1989 | 11644390.9736
8005 | 30433832.5297 | 26076860.4247 | 430857.4812 | 56941550.4356
8006 | 5775485.3363 | 0 | 2840596.1126 | 8616081.449
8007 | 12291547.8254 | 10479329.6496 | 8112548.5902 | 30883426.0652
8008 | 6120198.4471 | 20394179.4607 | 7361563.9032 | 33875941.811
8009 | 3585835.9814 | 0 | 151531.0239 | 3737367.0054
8010 | 7305778.8288 | 17772629.9979 | 8962669.7962 | 34041078.6228
8011 | 17521753.3058 | 1942064.3923 | 606952.7989 | 20070770.4971
8012 | 4162951.2477 | 12257334.0959 | 2363101.2396 | 18783386.5831
8013 | 5792505.29 | 10904445.6736 | 739354.4154 | 17436305.379
8014 | 11017369.581 | 6677603.1252 | 1839789.0487 | 19534761.755
8015 | 5043524.3398 | 3266718.854 | 13458455.3145 | 21768698.5083
8016 | 1597078.4477 | 11799939.4846 | 321072.9737 | 13718090.906
8017 | 4185666.1428 | 16146733.0432 | 744968.787 | 21077367.9729
8018 | 6954438.8119 | 26313859.2529 | 5298482.0911 | 38566780.1559
8019 | 6007380.2079 | 0 | 2062060.3933 | 8069440.6013
8020 | 7686953.5819 | 6156244.2688 | 1213390.2376 | 15056588.0883
8021 | 44425923.1943 | 9561802.7284 | 132013.4394 | 54119739.3621
8022 | 11593292.7027 | 14883206.7678 | 2205213.682 | 28681713.1524
8023 | 4412912.1577 | 5908246.4093 | 3738230.2474 | 14059388.8144
8024 | 5338310.4355 | 6301233.7374 | 2065493.3666 | 13705037.5395
8025 | 4613103.9455 | 21590964.8349 | 0 | 26204068.7804
8026 | 37192863.5201 | 0 | 1398482.9114 | 38591346.4315
8027 | 12020597.2624 | 4609065.4654 | 265238.8278 | 16894901.5556
8028 | 1348312.8315 | 19852254.9497 | 1823065.7085 | 23023633.4897
8029 | 20549108.5907 | 12672121.4253 | 2371491.4993 | 35592721.5153
8030 | 14125913.7301 | 6176357.1376 | 1479663.5053 | 21781934.373
8031 | 3649952.2393 | 0 | 5942736.2869 | 9592688.5262
8032 | 6594457.5676 | 2677943.3115 | 2598783.4725 | 11871184.3517
8033 | 4651774.9802 | 11083456.1792 | 0 | 15735231.1594
8034 | 2302054.3573 | 16009236.1574 | 375890.5686 | 18687181.0834
8035 | 4352014.056 | 10943968.7198 | 430967.1689 | 15726949.9447
8036 | 1440393.7392 | 6889856.6686 | 757850.8824 | 9088101.2902
8037 | 3212882.5527 | 0 | 7153818.0981 | 10366700.6508
8038 | 9584089.3909 | 2580509.1298 | 95883.7912 | 12260482.3119
8039 | 3412122.9847 | 0 | 2543017.6198 | 5955140.6045
8040 | 26247544.6543 | 5337273.1084 | 106450.1801 | 31691267.9428
8041 | 12571485.3721 | 7628557.6617 | 225162.0336 | 20425205.0674
8042 | 5957169.9629 | 2831310.2168 | 6104126.292 | 14892606.4717
8043 | 7900654.4577 | 883993.6266 | 0 | 8784648.0843
8044 | 2543216.3889 | 7907019.8234 | 679336.6253 | 11129572.8376
8045 | 8878041.8933 | 0 | 8043300.7216 | 16921342.6149
8046 | 2184667.816 | 0 | 1993932.6359 | 4178600.4519
8047 | 19219404.582 | 17783496.5893 | 0 | 37002901.1713
8048 | 5881548.4829 | 4153534.1264 | 12959658.5993 | 22994741.2086
8049 | 1972981.1247 | 8540317.9814 | 7554186.545 | 18067485.6511
8050 | 11910710.1612 | 3540647.2825 | 845646.2183 | 16297003.662
8051 | 4647010.3917 | 0 | 0 | 4647010.3917
8052 | 11723370.291 | 2979714.478 | 5654119.0703 | 20357203.8393
8053 | 41529633.4338 | 0 | 3019033.0337 | 44548666.4676
8054 | 3138073.3849 | 19445583.5151 | 134043.5835 | 22717700.4835
8055 | 6175864.8498 | 4852921.7456 | 4508907.7543 | 15537694.3496
8056 | 2916958.7862 | 10953810.6044 | 793844.1288 | 14664613.5195
8057 | 7345889.1415 | 3404786.6889 | 4286648.2468 | 15037324.0772
8058 | 6822823.1206 | 6191146.8516 | 364073.8247 | 13378043.797
8059 | 7423753.2577 | 0 | 0 | 7423753.2577
8060 | 4204195.0771 | 15657561.2006 | 1138529.7341 | 21000286.0118
8061 | 12266059.9423 | 5265210.3816 | 1276983.8805 | 18808254.2044
8062 | 20585335.5995 | 7343834.6453 | 1975889.0977 | 29905059.3425
8063 | 7079084.5204 | 8893131.8233 | 2957617.3903 | 18929833.734
8064 | 6118136.5346 | 2643866.3114 | 0 | 8762002.846
8065 | 12503966.4082 | 18314351.1579 | 1102864.5421 | 31921182.1082
8066 | 9584790.2958 | 7924431.9591 | 0 | 17509222.2549
8067 | 3311432.4404 | 0 | 0 | 3311432.4404
8068 | 915716.1145 | 9463693.2031 | 2200551.2107 | 12579960.5283
8069 | 7524084.9104 | 4075066.6737 | 11278618.2102 | 22877769.7943
8070 | 21401460.482 | 3091638.7228 | 0 | 24493099.2048
8071 | 9374243.6773 | 10852747.1759 | 15091332.4898 | 35318323.343
8072 | 17080356.1085 | 0 | 208484.1467 | 17288840.2552
8073 | 10234282.9522 | 8319546.2605 | 2036662.3027 | 20590491.5154
8074 | 2319832.1691 | 17951793.1221 | 2157697.0346 | 22429322.3258
8075 | 7235900.0246 | 1236136.7256 | 0 | 8472036.7502
8076 | 1321139.1018 | 4912735.5616 | 6650487.7723 | 12884362.4357
8077 | 6344790.2847 | 872502.4163 | 5682703.4391 | 12899996.1401
8078 | 2271044.5277 | 3503355.3542 | 1913471.9364 | 7687871.8183
8079 | 8325961.5812 | 3818092.4488 | 3570033.5331 | 15714087.563
8080 | 5073884.2695 | 23251940.7767 | 2657023.5418 | 30982848.588
8081 | 4575558.5866 | 4055236.9847 | 6884505.2182 | 15515300.7895
8082 | 3424545.5668 | 4573337.8734 | 4215658.8333 | 12213542.2735
8083 | 9977486.3797 | 7109573.2517 | 0 | 17087059.6314
8084 | 1770250.1406 | 16071155.8514 | 1331118.0745 | 19172524.0666
8085 | 6600488.6925 | 0 | 648308.27 | 7248796.9625
8086 | 2373387.11 | 3474975.9876 | 4290396.0995 | 10138759.1971
8087 | 26731741.361 | 0 | 1446026.4093 | 28177767.7703
8088 | 18598879.2891 | 3078660.1809 | 11758962.4636 | 33436501.9336
8089 | 7308286.6474 | 7346385.7102 | 0 | 14654672.3576
8090 | 13705229.6277 | 3965439.9279 | 1410141.2428 | 19080810.7984
8091 | 6778172.6494 | 4288626.7588 | 0 | 11066799.4082
8092 | 15578478.4425 | 0 | 0 | 15578478.4425
8093 | 2125554.4423 | 4190061.3453 | 375086.859 | 6690702.6466
8094 | 1349547.2213 | 4139603.0161 | 0 | 5489150.2374
8095 | 4243927.8999 | 62379965.4445 | 1369965.9269 | 67993859.2712
8096 | 5817685.2805 | 7009393.8146 | 0 | 12827079.0951
8097 | 19080339.8588 | 5595943.0024 | 3485092.4247 | 28161375.2859
8098 | 663806.619 | 0 | 2901890.3071 | 3565696.9261
8099 | 10069121.0783 | 17631925.2024 | 1487973.2938 | 29189019.5746
8100 | 5574809.2982 | 12427778.7844 | 1287223.4303 | 19289811.5129
8101 | 1105378.79 | 0 | 990750.9275 | 2096129.7175
8102 | 7200103.3435 | 10589531.5616 | 1157799.1332 | 18947434.0384
8103 | 2906429.704 | 5863427.9172 | 0 | 8769857.6212
8104 | 5080506.266 | 8621725.4682 | 1757357.8497 | 15459589.5839
8105 | 2390098.1497 | 0 | 573859.9087 | 2963958.0583
8106 | 1653791.6756 | 6055043.4895 | 2136368.4423 | 9845203.6075
8107 | 5358333.8449 | 3466698.2016 | 939115.1875 | 9764147.234
8108 | 3265772.023 | 21979366.3465 | 0 | 25245138.3696
8109 | 5234752.9659 | 0 | 0 | 5234752.9659
8110 | 4932268.0742 | 15624674.9676 | 3654948.4764 | 24211891.5183
8111 | 9673664.1862 | 3512877.147 | 4396747.7999 | 17583289.1331
8112 | 6472014.9349 | 6788566.4527 | 4909177.9313 | 18169759.3189
8113 | 9252656.1303 | 8840475.8291 | 0 | 18093131.9594
8114 | 1554481.7925 | 12735265.3632 | 1783712.3718 | 16073459.5275
8115 | 17301055.7808 | 0 | 1939361.2216 | 19240417.0023
8116 | 5694110.3202 | 4693254.1616 | 0 | 10387364.4818
8117 | 5172650.6005 | 16792492.8321 | 159585.3655 | 22124728.798
8118 | 4697929.6464 | 10158718.3478 | 608669.2276 | 15465317.2218
8119 | 15887021.6476 | 647016.9052 | 1068471.7088 | 17602510.2616
8120 | 3640942.5783 | 15872655.1459 | 454974.4469 | 19968572.171
8121 | 34711793.5454 | 12311631.8395 | 0 | 47023425.3849
8122 | 12213124.4176 | 0 | 1864740.7141 | 14077865.1317
8123 | 7736323.5634 | 10095102.2555 | 151660.9188 | 17983086.7377
8124 | 12200637.647 | 4263738.6072 | 0 | 16464376.2542
8125 | 2328117.3241 | 0 | 12362674.3866 | 14690791.7106
8126 | 3672890.4219 | 8384919.1155 | 0 | 12057809.5374
8127 | 3296459.5635 | 10016044.1046 | 1417494.566 | 14729998.2341
8128 | 9102149.613 | 4695051.7513 | 310629.1207 | 14107830.4851
8129 | 7006923.4718 | 32757966.9982 | 1696805.2282 | 41461695.6982
8130 | 9293154.843 | 805620.4528 | 1353456.9419 | 11452232.2377
8131 | 1042179.5001 | 17804240.6379 | 3046031.6935 | 21892451.8315
8132 | 5438451.5096 | 1009102.6532 | 288590.2616 | 6736144.4244
8133 | 5032344.4042 | 0 | 395124.2134 | 5427468.6176
8134 | 13299117.3668 | 8831389.1959 | 0 | 22130506.5627
8135 | 2572946.3029 | 6421706.5815 | 3875979.6296 | 12870632.5139
8136 | 4962193.2572 | 0 | 879889.9544 | 5842083.2116
8137 | 6377505.065 | 4120050.6765 | 0 | 10497555.7415
8138 | 7769283.7341 | 15692615.1432 | 965154.5628 | 24427053.4401
8139 | 3351480.8379 | 0 | 40132.7329 | 3391613.5707
8140 | 2863295.7175 | 8407930.9594 | 555118.0629 | 11826344.7399
8141 | 5241422.6797 | 0 | 3519261.6146 | 8760684.2943
8142 | 6424743.9728 | 11400857.8014 | 605355.6384 | 18430957.4125
8143 | 7423121.2932 | 22722762.4336 | 1323707.7214 | 31469591.4481
8144 | 19822639.2017 | 1967572.3052 | 0 | 21790211.5069
8145 | 4890710.1085 | 5691197.1364 | 4952426.7537 | 15534333.9986
8146 | 9894514.8214 | 25195868.8509 | 1665186.7742 | 36755570.4464
8147 | 7796654.5774 | 0 | 115187.2281 | 7911841.8055
8148 | 4766678.4386 | 2595298.1663 | 0 | 7361976.605
8149 | 6189812.4869 | 0 | 31992576.1416 | 38182388.6285
8150 | 12070430.8679 | 669452.7646 | 0 | 12739883.6325
8151 | 8975629.1866 | 7220679.0056 | 0 | 16196308.1922
8152 | 4653336.3894 | 11912332.8951 | 1277599.4029 | 17843268.6874
8153 | 1852753.4306 | 10598309.715 | 1567256.481 | 14018319.6266
8154 | 6918597.9106 | 0 | 644322.4409 | 7562920.3516
8155 | 34912312.047 | 3622649.8449 | 3042548.4575 | 41577510.3494
8156 | 6392413.9533 | 7746458.2533 | 2965159.2837 | 17104031.4903
8157 | 1360544.0145 | 37900698.8574 | 2096016.8697 | 41357259.7416
8158 | 5653995.8637 | 6150140.1095 | 2592518.3498 | 14396654.323
8159 | 2217561.637 | 19999723.6743 | 1771584.3968 | 23988869.7081
8160 | 2092613.2197 | 6219493.4571 | 0 | 8312106.6768
8161 | 13495076.7144 | 0 | 250897.9392 | 13745974.6536
8162 | 1707359.6089 | 20376794.6862 | 1336922.4401 | 23421076.7351
8163 | 12950967.3727 | 8430821.7494 | 2961737.6487 | 24343526.7708
8164 | 23448681.3263 | 0 | 6326556.2536 | 29775237.5798
8165 | 5543003.9942 | 20305838.5398 | 2617912.9058 | 28466755.4398
8166 | 664384.1606 | 7756417.0928 | 0 | 8420801.2534
8167 | 8968320.1711 | 2130010.4638 | 79146.2545 | 11177476.8894
8168 | 4464735.9284 | 22357040.8131 | 1428097.5778 | 28249874.3192
8169 | 4615896.0058 | 35190207.8926 | 358823.6805 | 40164927.5788
8170 | 21197982.5337 | 14289557.3164 | 977914.9041 | 36465454.7542
8171 | 3758213.1422 | 2570201.704 | 2148672.7192 | 8477087.5655
8172 | 1909000.8967 | 15401764.004 | 1245144.3738 | 18555909.2745
8173 | 875997.9906 | 9174408.898 | 2984641.8983 | 13035048.7869
8174 | 3958644.852 | 5029813.5933 | 1156259.6015 | 10144718.0468
8175 | 22840710.1602 | 3395161.5319 | 2883401.5165 | 29119273.2085
8176 | 3136418.5811 | 10732208.4724 | 0 | 13868627.0536
8177 | 4053221.0826 | 21572161.2056 | 2448659.679 | 28074041.9672
8178 | 20543201.1691 | 170140.4082 | 914987.9952 | 21628329.5725
8179 | 11307550.0794 | 5992975.2662 | 521323.3895 | 17821848.7351
8180 | 5473549.4962 | 11430174.0205 | 158589.6132 | 17062313.1299
8181 | 4915634.4134 | 21943910.4767 | 2573628.8976 | 29433173.7877
8182 | 8191444.0225 | 6929834.5587 | 2881839.4003 | 18003117.9815
8183 | 7972720.8218 | 1745676.0173 | 14208189.3496 | 23926586.1887
8184 | 22667059.6897 | 4500401.4331 | 9951130.0226 | 37118591.1455
8185 | 13421514.1768 | 2919240.8228 | 30559.1776 | 16371314.1772
8186 | 5924244.3639 | 2339891.9966 | 2618111.116 | 10882247.4765
8187 | 5064099.8287 | 0 | 1308887.7203 | 6372987.549
8188 | 12703955.6582 | 9116984.6356 | 2222789.9009 | 24043730.1946
8189 | 10043911.7676 | 26909303.4554 | 148162.0029 | 37101377.2259
8190 | 10683701.6234 | 6123404.7824 | 84281.1666 | 16891387.5724
8191 | 21223049.9747 | 2304669.3792 | 7114.7555 | 23534834.1094
8192 | 1645726.3632 | 4326689.1849 | 0 | 5972415.5481
8193 | 3204004.3616 | 4502985.7253 | 1875357.1074 | 9582347.1942
8194 | 14184873.1068 | 5488044.2314 | 3120405.3691 | 22793322.7072
8195 | 5494636.2464 | 11993495.9068 | 286581.3119 | 17774713.4651
8196 | 12421337.8845 | 7315702.2514 | 9398020.7471 | 29135060.883
8197 | 34937469.9131 | 1361830.3234 | 345938.3682 | 36645238.6048
8198 | 6619603.3088 | 17043178.6492 | 4269052.3704 | 27931834.3283
8199 | 4540525.298 | 7131128.7584 | 495588.1427 | 12167242.1992
8200 | 5106367.0468 | 15986861.0407 | 1264471.3504 | 22357699.4379
8201 | 39329582.5718 | 4927604.8857 | 84540.4188 | 44341727.8763
8202 | 24763064.9298 | 18912524.4956 | 1623062.7083 | 45298652.1337
8203 | 9906464.8219 | 12464680.5198 | 63600.835 | 22434746.1766
8204 | 12803490.6213 | 7367416.1047 | 1704887.7883 | 21875794.5142
8205 | 7682640.4977 | 8476036.1108 | 0 | 16158676.6085
8206 | 16527491.688 | 7841544.6994 | 0 | 24369036.3874
8207 | 4863976.0562 | 16542374.392 | 2553020.3485 | 23959370.7968
8208 | 6330559.1562 | 0 | 302031.1694 | 6632590.3255
8209 | 7669558.6253 | 472212.7713 | 1594879.8339 | 9736651.2305
8210 | 201959.9162 | 3065294.3742 | 1000404.1898 | 4267658.4801
8211 | 4078489.1851 | 3685385.5141 | 447400.0554 | 8211274.7546
8212 | 5524277.0716 | 5128650.0016 | 760594.4817 | 11413521.5548
8213 | 13350990.6188 | 5270594.5955 | 4566998.876 | 23188584.0903
8214 | 3376547.0305 | 0 | 811415.842 | 4187962.8725
8215 | 5753775.1264 | 3058539.3194 | 176806.6417 | 8989121.0875
8216 | 9056494.3536 | 5479752.0779 | 2753843.0447 | 17290089.4762
8217 | 1509329.3654 | 1818884.3629 | 14064343.1482 | 17392556.8765
8218 | 13133501.1175 | 7647499.2308 | 1147307.2859 | 21928307.6343
8219 | 5547214.5761 | 12504523.9084 | 1899142.2497 | 19950880.7343
8220 | 5397407.1373 | 9040917.1038 | 433076.3393 | 14871400.5804
8221 | 5145875.5749 | 4147298.3753 | 957628.6439 | 10250802.5941
8222 | 10429321.0897 | 3321723.7943 | 71579.5896 | 13822624.4736
8223 | 7865170.0254 | 0 | 0 | 7865170.0254
8224 | 6100127.9281 | 6245114.9164 | 1794035.2037 | 14139278.0482
8225 | 6356436.6656 | 9044694.6481 | 0 | 15401131.3137
8226 | 8955696.9851 | 1858791.6339 | 11502505.2542 | 22316993.8731
8227 | 936262.8414 | 13900565.4892 | 19417598.7801 | 34254427.1108
8228 | 7763452.9506 | 0 | 225295.5068 | 7988748.4574
8229 | 6463217.4553 | 12668676.9923 | 0 | 19131894.4475
8230 | 8442705.0602 | 4061475.3759 | 2022968.8701 | 14527149.3063
8231 | 6766585.1179 | 2444385.4001 | 578080.7131 | 9789051.231
8232 | 7347219.7899 | 19119034.2798 | 2303384.4043 | 28769638.474
8233 | 11749307.4217 | 1777379.4469 | 6571042.5773 | 20097729.446
8234 | 11218250.7353 | 17219499.6254 | 0 | 28437750.3607
8235 | 4400924.548 | 16129970.442 | 8473565.5593 | 29004460.5494
8236 | 23608832.7263 | 0 | 0 | 23608832.7263
8237 | 2656955.1718 | 5039030.5226 | 3508089.2524 | 11204074.9469
8238 | 14579869.0787 | 10697333.3614 | 1411635.1297 | 26688837.5697
8239 | 25978780.6401 | 15289890.3981 | 119064.3794 | 41387735.4176
8240 | 21594503.4023 | 4505243.2471 | 208847.203 | 26308593.8523
8241 | 10016822.9169 | 9717479.2668 | 2290002.4102 | 22024304.5939
8242 | 13872226.6084 | 16486844.2988 | 954371.051 | 31313441.9583
8243 | 13512261.7208 | 2060518.9098 | 9241786.9997 | 24814567.6303
8244 | 2453561.2203 | 9444846.8222 | 49052.4275 | 11947460.47
8245 | 13299821.527 | 11406080.5799 | 1143761.2462 | 25849663.3531
8246 | 7339024.7277 | 15471337.1305 | 6054230.6877 | 28864592.5458
8247 | 4273154.8542 | 5278546.0112 | 412632.6744 | 9964333.5398
8248 | 3544850.509 | 4254823.3528 | 3763940.239 | 11563614.1009
8249 | 16374909.1724 | 373635.5693 | 232571.3473 | 16981116.089
8250 | 6998182.0346 | 0 | 679770.6089 | 7677952.6435
8251 | 713899.8353 | 0 | 15114938.7617 | 15828838.597
8252 | 1653518.3542 | 1821229.3183 | 9484657.0395 | 12959404.7119
8253 | 14925712.0915 | 0 | 2970947.2317 | 17896659.3232
8254 | 3504552.5566 | 5706432.9539 | 6026529.5223 | 15237515.0328
8255 | 4359984.3222 | 21951835.1529 | 5629704.4485 | 31941523.9236
8256 | 9595984.6055 | 5013635.5911 | 3194565.6124 | 17804185.809
8257 | 575257.8256 | 0 | 1753923.0564 | 2329180.882
8258 | 27982435.4951 | 9797128.9927 | 0 | 37779564.4878
8259 | 6980835.6396 | 10421570.6999 | 12049614.2857 | 29452020.6252
8260 | 22175300.8411 | 10315106.2121 | 329671.9885 | 32820079.0416
8261 | 2723174.3572 | 0 | 141913.8174 | 2865088.1746
8262 | 4124847.1399 | 4781476.8445 | 0 | 8906323.9844
8263 | 11612771.4732 | 15579028.3849 | 1510029.5449 | 28701829.403
8264 | 7370958.4827 | 3520577.2193 | 171433.5032 | 11062969.2053
8265 | 14473003.2923 | 4125047.1601 | 18232460.7947 | 36830511.2471
8266 | 11163907.6552 | 2495332.5791 | 48015.4453 | 13707255.6796
8267 | 4787045.5023 | 0 | 289465.7116 | 5076511.2139
8268 | 13880385.149 | 3010388.1215 | 1580775.5262 | 18471548.7967
8269 | 6719802.1044 | 3370324.0924 | 179504.5406 | 10269630.7373
8270 | 1575430.1346 | 4082023.1988 | 3734246.9309 | 9391700.2643
8271 | 3561443.1992 | 3620809.2267 | 167957.7115 | 7350210.1373
8272 | 11760317.3051 | 10805181.4731 | 1290788.8645 | 23856287.6427
8273 | 13637204.2348 | 8065640.1637 | 491671.7876 | 22194516.1861
8274 | 5153115.5693 | 0 | 609416.5411 | 5762532.1104
8275 | 13171711.7512 | 10627105.0714 | 66330.2583 | 23865147.0809
8276 | 3377153.371 | 5431301.9634 | 10609858.0617 | 19418313.3961
8277 | 3162076.1308 | 3828485.1756 | 1635545.3442 | 8626106.6506
8278 | 35093299.2117 | 854407.9414 | 571440.6346 | 36519147.7877
8279 | 4736315.344 | 8676490.7903 | 4569517.8763 | 17982324.0106
8280 | 15995674.929 | 16285219.8556 | 2947056.4245 | 35227951.2091
8281 | 5408443.3062 | 10781888.9621 | 607675.7785 | 16798008.0469
8282 | 6974201.2157 | 2925311.8409 | 87692.8057 | 9987205.8624
8283 | 4013580.2201 | 8394013.5159 | 1187918.4902 | 13595512.2261
8284 | 6307385.8349 | 2586134.4813 | 121407.9627 | 9014928.2789
8285 | 5956421.1067 | 14347081.6244 | 2584174.892 | 22887677.6231
8286 | 48880546.2083 | 4763540.9886 | 3336904.0724 | 56980991.2693
8287 | 6300744.126 | 7864773.9057 | 3136519.9187 | 17302037.9503
8288 | 5533002.7804 | 2525525.5111 | 7935840.1141 | 15994368.4057
8289 | 17220426.9099 | 4212071.9163 | 0 | 21432498.8262
8290 | 4172739.5534 | 4804471.9954 | 0 | 8977211.5487
8291 | 11159608.9291 | 7641887.6975 | 9282944.3197 | 28084440.9463
8292 | 12682317.5919 | 11494840.0328 | 566933.5775 | 24744091.2022
8293 | 3341136.4789 | 4034725.2862 | 1895838.7337 | 9271700.4987
8294 | 5719462.5747 | 21065330.878 | 3411470.2845 | 30196263.7372
8295 | 4710362.1127 | 10819782.9775 | 19765516.4112 | 35295661.5015
8296 | 6513709.5565 | 15122371.6748 | 287562.8254 | 21923644.0567
8297 | 8102145.595 | 5864875.2375 | 18676636.5637 | 32643657.3962
8298 | 7775455.368 | 25791123.4723 | 0 | 33566578.8403
8299 | 6882497.1776 | 0 | 981030.2861 | 7863527.4637
8300 | 9012316.1068 | 0 | 4197529.8211 | 13209845.9279
8301 | 14654678.7305 | 27796975.9136 | 12007579.0635 | 54459233.7076
8302 | 4311403.7932 | 0 | 1314572.1955 | 5625975.9886
8303 | 2408869.6359 | 21748172.8324 | 4189010.8093 | 28346053.2776
8304 | 12087051.9842 | 12018713.666 | 4578048.2947 | 28683813.9449
8305 | 12204709.8222 | 4429376.4219 | 0 | 16634086.2441
8306 | 6077526.3666 | 17079851.2755 | 28079546.2914 | 51236923.9335
8307 | 17093323.8404 | 991125.4751 | 598938.6958 | 18683388.0113
8308 | 2862802.9372 | 3479327.5384 | 375541.5296 | 6717672.0052
8309 | 9304282.3246 | 2806536.3706 | 2005774.5968 | 14116593.292
8310 | 4971853.6914 | 3334917.0667 | 307321.124 | 8614091.8821
8311 | 3991090.6888 | 27376509.7931 | 3564768.2975 | 34932368.7795
8312 | 11053208.7528 | 6622055.9239 | 1039102.3365 | 18714367.0131
8313 | 13187980.0115 | 22384409.9046 | 3472671.385 | 39045061.3012
8314 | 8838904.8259 | 4238113.3742 | 1441111.1087 | 14518129.3088
8315 | 7614908.7305 | 1140349.3701 | 306289.2029 | 9061547.3035
8316 | 13378084.73 | 6033249.0934 | 0 | 19411333.8234
8317 | 6778967.3699 | 8433764.2026 | 7256032.6992 | 22468764.2717
8318 | 22748628.1133 | 6888617.2508 | 936655.2414 | 30573900.6056
8319 | 4882438.546 | 4648929.7183 | 1307683.6718 | 10839051.9361
8320 | 12535251.224 | 1469506.2239 | 63777.0096 | 14068534.4576
8321 | 26674353.0417 | 5342060.9828 | 64120.9389 | 32080534.9634
8322 | 2158319.1279 | 0 | 193481.9332 | 2351801.0611
8323 | 7268805.3484 | 2500002.6395 | 1339845.1987 | 11108653.1865
8324 | 11912330.6873 | 5951158.1912 | 400844.7413 | 18264333.6198
8325 | 9915218.2618 | 8435932.6894 | 0 | 18351150.9512
8326 | 6360968.5867 | 34704562.8131 | 23109.8728 | 41088641.2726
8327 | 1967392.3392 | 2106537.0162 | 632501.3104 | 4706430.6659
8328 | 2639222.1148 | 14444294.3433 | 0 | 17083516.4581
8329 | 3982322.5151 | 12435122.0342 | 921815.4822 | 17339260.0315
8330 | 11678967.0039 | 0 | 1233187.0493 | 12912154.0532
8331 | 737579.8751 | 6382674.6345 | 122019.3643 | 7242273.874
8332 | 10927562.3742 | 2256748.4873 | 6837637.5749 | 20021948.4364
8333 | 7548602.1624 | 858624.3806 | 54370.9156 | 8461597.4586
8334 | 13756135.3465 | 16647836.9614 | 1401632.1693 | 31805604.4771
8335 | 9783140.6891 | 0 | 747331.6532 | 10530472.3423
8336 | 10687829.3328 | 22946148.4306 | 48782.8709 | 33682760.6343
8337 | 6581724.8243 | 3268516.3898 | 370554.5422 | 10220795.7563
8338 | 1695842.3505 | 5429081.6861 | 9800234.5565 | 16925158.5931
8339 | 1716492.0946 | 7037034.7308 | 0 | 8753526.8254
8340 | 9460963.8943 | 8481953.5229 | 279480.348 | 18222397.7653
8341 | 5814902.3521 | 0 | 115842.1627 | 5930744.5148
8342 | 5511955.7187 | 15232116.2607 | 180165.7403 | 20924237.7198
8343 | 7274065.9763 | 7068984.9347 | 1160215.9192 | 15503266.8302
8344 | 3077170.3249 | 8719815.2681 | 1381927.4226 | 13178913.0156
8345 | 11282572.821 | 22106000.3751 | 1618704.3389 | 35007277.5349
8346 | 4353368.7797 | 2893394.4248 | 0 | 7246763.2045
8347 | 8160505.6955 | 0 | 227598.4924 | 8388104.1878
8348 | 19097034.0074 | 9789285.126 | 389650.4268 | 29275969.5603
8349 | 14397885.747 | 7440134.7572 | 3772685.1273 | 25610705.6315
8350 | 7666952.2216 | 9475322.009 | 1381817.473 | 18524091.7036
8351 | 1451721.1048 | 0 | 1073259.8583 | 2524980.9631
8352 | 1232263.3244 | 3104012.3103 | 2065848.7108 | 6402124.3454
8353 | 13995108.8255 | 0 | 476421.4481 | 14471530.2736
8354 | 460342.6334 | 0 | 112536.5766 | 572879.21
8355 | 4132149.7849 | 5581903.2188 | 449623.5845 | 10163676.5883
8356 | 33946264.4626 | 6587803.9045 | 727082.008 | 41261150.3751
8357 | 7432634.7422 | 0 | 6741893.9188 | 14174528.661
8358 | 15548452.382 | 5211118.4296 | 1112034.4358 | 21871605.2475
8359 | 7270212.905 | 24450736.8876 | 0 | 31720949.7926
8360 | 14812159.1876 | 0 | 5633133.711 | 20445292.8985
8361 | 23872788.8651 | 7237396.4952 | 497657.442 | 31607842.8023
8362 | 1506014.6752 | 15931871.2208 | 2302951.7813 | 19740837.6774
8363 | 2949655.8113 | 384178.8075 | 705380.1835 | 4039214.8023
8364 | 10864548.4666 | 6296984.9272 | 1122929.1475 | 18284462.5412
8365 | 27739771.0469 | 5345921.5761 | 1185390.4161 | 34271083.0391
8366 | 3996478.6977 | 12857720.2193 | 4225614.4194 | 21079813.3365
8367 | 2704671.7085 | 6776104.0248 | 202287.4233 | 9683063.1567
8368 | 6186735.8584 | 0 | 0 | 6186735.8584
8369 | 11718706.0467 | 14305547.8515 | 728430.8335 | 26752684.7318
8370 | 2281630.5567 | 1397117.4302 | 6343516.426 | 10022264.4129
8371 | 3764769.5945 | 0 | 1007527.3819 | 4772296.9765
8372 | 21133604.0928 | 3759867.5867 | 1631944.0521 | 26525415.7315
8373 | 4475128.1086 | 4957071.255 | 1170071.453 | 10602270.8167
8374 | 1490197.1932 | 4989658.1684 | 0 | 6479855.3615
8375 | 1827316.8438 | 0 | 1219395.5965 | 3046712.4403
8376 | 11972832.8809 | 2408981.5129 | 314009.0389 | 14695823.4326
8377 | 1154889.9535 | 8112417.0564 | 5769583.4319 | 15036890.4419
8378 | 14487853.0957 | 0 | 3740512.278 | 18228365.3737
8379 | 9300011.4001 | 20788292.2283 | 0 | 30088303.6285
8380 | 6262867.5026 | 8033827.9893 | 5473524.3719 | 19770219.8639
8381 | 8082133.7094 | 11082114.5034 | 1224414.7923 | 20388663.0051
8382 | 9077618.71 | 8540240.7579 | 2792107.903 | 20409967.3708
8383 | 15233376.2753 | 6557133.2439 | 2597879.6099 | 24388389.1291
8384 | 14680010.9669 | 32566253.9816 | 2010980.9964 | 49257245.9449
8385 | 21604850.5196 | 2892363.6814 | 146126.7468 | 24643340.9478
8386 | 20370871.1005 | 8251451.0019 | 8979092.8684 | 37601414.9708
8387 | 4221792.3048 | 14598217.3173 | 0 | 18820009.6221
8388 | 2043027.5812 | 8042432.7706 | 272126.7333 | 10357587.085
8389 | 10190354.2294 | 1925975.9768 | 165066.8142 | 12281397.0204
8390 | 18087431.9056 | 3856257.804 | 0 | 21943689.7096
8391 | 4384244.9858 | 1004696.7516 | 2824934.4388 | 8213876.1761
8392 | 2394357.1873 | 9532201.6958 | 1393715.7574 | 13320274.6406
8393 | 3283841.4646 | 3143461.6156 | 380469.8031 | 6807772.8833
8394 | 2930587.0487 | 11261833.4486 | 0 | 14192420.4973
8395 | 11430171.0965 | 11257794.4279 | 7915470.414 | 30603435.9384
8396 | 12059118.4183 | 1885903.9681 | 1768921.6573 | 15713944.0436
8397 | 9663688.8781 | 9476107.5988 | 2597788.8751 | 21737585.352
8398 | 15087483.729 | 12052781.5562 | 2207295.6292 | 29347560.9144
8399 | 6341451.6006 | 6146916.0362 | 17544922.0782 | 30033289.715
8400 | 5334050.2648 | 0 | 147202.445 | 5481252.7098
8401 | 1924105.9844 | 0 | 1241721.0096 | 3165826.994
8402 | 18610215.3416 | 3828659.1823 | 448531.9774 | 22887406.5012
8403 | 84556.8823 | 10405522.8595 | 0 | 10490079.7418
8404 | 15637507.3709 | 171740.8887 | 0 | 15809248.2596
8405 | 4675518.9999 | 13108226.1111 | 14789272.1868 | 32573017.2978
8406 | 4033983.7331 | 5405938.0686 | 3841565.0664 | 13281486.8681
8407 | 10733182.1612 | 13549544.1069 | 353999.8031 | 24636726.0711
8408 | 2857333.3851 | 0 | 2920399.445 | 5777732.83
8409 | 3025126.9884 | 5279235.802 | 50599.5447 | 8354962.3351
8410 | 8191267.0181 | 2904810.5045 | 8484465.8996 | 19580543.4222
8411 | 4556137.9166 | 16370730.8044 | 8016957.9575 | 28943826.6785
8412 | 3244019.8358 | 730647.1993 | 76605.5439 | 4051272.579
8413 | 14454000.9921 | 4597227.195 | 3295425.1233 | 22346653.3104
8414 | 8640837.3209 | 11238817.2052 | 3743797.2791 | 23623451.8052
8415 | 3620798.8918 | 4800227.6296 | 481427.54 | 8902454.0614
8416 | 19746220.0512 | 24328834.2296 | 4585884.0813 | 48660938.3621
8417 | 12526018.8358 | 0 | 11540304.0652 | 24066322.901
8418 | 6039268.6586 | 0 | 7462033.6365 | 13501302.2951
8419 | 9314547.2144 | 4790518.0979 | 2389218.4732 | 16494283.7855
8420 | 8925953.8506 | 6807875.8068 | 95663.5613 | 15829493.2187
8421 | 4012470.7985 | 2789391.8218 | 170979.5015 | 6972842.1217
8422 | 10631900.6728 | 6208835.3743 | 2817118.1014 | 19657854.1485
8423 | 3589873.2432 | 0 | 517887.0405 | 4107760.2837
8424 | 2160672.5921 | 12973818.5765 | 124341.3965 | 15258832.5651
8425 | 2219155.0538 | 7264145.0264 | 0 | 9483300.0802
8426 | 15823281.5111 | 1927621.0056 | 412524.5383 | 18163427.0549
8427 | 1613255.5866 | 12555787.4028 | 10239232.1706 | 24408275.16
8428 | 4438677.738 | 5126628.0535 | 4674744.2665 | 14240050.058
8429 | 14974803.8829 | 4533933.4189 | 289892.9307 | 19798630.2324
8430 | 9433716.1002 | 16551528.395 | 1129380.373 | 27114624.8682
8431 | 3612817.0462 | 3307499.9202 | 5236891.0827 | 12157208.0491
8432 | 831568.9229 | 17979367.9285 | 532387.147 | 19343323.9984
8433 | 1887954.3774 | 3069028.6023 | 17427.2084 | 4974410.1881
8434 | 11564774.1275 | 10823781.0731 | 2018793.3198 | 24407348.5204
8435 | 5324657.4769 | 14962323.5181 | 133677.2978 | 20420658.2927
8436 | 1445930.0023 | 9241672.0804 | 883247.762 | 11570849.8448
8437 | 2938679.3986 | 4809417.3195 | 0 | 7748096.7181
8438 | 6121300.1284 | 3914817.6765 | 647345.1397 | 10683462.9446
8439 | 3324292.0127 | 9143220.6697 | 2252874.7561 | 14720387.4385
8440 | 17104773.9467 | 3475340.2165 | 0 | 20580114.1632
8441 | 3534409.0541 | 3732237.704 | 2574304.9518 | 9840951.7099
8442 | 3488194.8475 | 7006896.2159 | 3957127.0975 | 14452218.1609
8443 | 3396017.2086 | 667207.9692 | 0 | 4063225.1779
8444 | 3043170.6905 | 4060734.082 | 1227485.3476 | 8331390.12
8445 | 8086714.8223 | 9661793.5886 | 0 | 17748508.4109
8446 | 5893817.0014 | 4348073.7694 | 6789785.6623 | 17031676.433
8447 | 19620361.8977 | 6066624.8335 | 131508.2818 | 25818495.0129
8448 | 10939390.9688 | 10746556.4944 | 9345631.2034 | 31031578.6666
8449 | 14200795.3288 | 7260720.0519 | 0 | 21461515.3807
8450 | 12546213.7764 | 4768891.7704 | 1809125.2275 | 19124230.7743
8451 | 16213511.3921 | 2701435.9624 | 0 | 18914947.3545
8452 | 2393986.7142 | 1633741.1163 | 370845.0434 | 4398572.8739
8453 | 4480047.1866 | 5957775.7086 | 558660.8593 | 10996483.7545
8454 | 11396762.6328 | 7362819.2994 | 60411.6741 | 18819993.6063
8455 | 16667936.2417 | 0 | 1905929.7945 | 18573866.0362
8456 | 26713764.0775 | 13985654.3038 | 150906.24 | 40850324.6213
8457 | 4419518.8322 | 4539547.5759 | 3510398.0003 | 12469464.4084
8458 | 28680809.1267 | 1155178.6281 | 177223.8844 | 30013211.6393
8459 | 2236061.8251 | 6716885.806 | 209577.902 | 9162525.5331
8460 | 10581348.9701 | 4928593.9362 | 485077.3682 | 15995020.2745
8461 | 2456136.2978 | 0 | 3596186.9294 | 6052323.2272
8462 | 1086184.209 | 1213411.8394 | 172302.9557 | 2471899.0041
8463 | 5063187.7158 | 0 | 0 | 5063187.7158
8464 | 10625153.8318 | 3403044.0032 | 524735.8715 | 14552933.7065
8465 | 5024941.2038 | 111783.8762 | 138290.0524 | 5275015.1324
8466 | 8263555.8204 | 23246398.306 | 166659.1573 | 31676613.2837
8467 | 12925916.4394 | 9396264.9813 | 0 | 22322181.4207
8468 | 17702803.6196 | 0 | 315137.2733 | 18017940.8929
8469 | 4057319.7244 | 3548233.4611 | 2774836.8019 | 10380389.9874
8470 | 9804866.6515 | 5517926.5449 | 1036614.7991 | 16359407.9955
8471 | 4913723.6741 | 3020916.9725 | 0 | 7934640.6467
8472 | 9732388.4853 | 0 | 1668668.7078 | 11401057.1931
8473 | 3903829.6396 | 12283139.2607 | 69235.6313 | 16256204.5317
8474 | 3882728.4882 | 12070231.271 | 19748.6756 | 15972708.4348
8475 | 31089527.5703 | 1928679.6301 | 0 | 33018207.2003
8476 | 366291.5155 | 11230593.3471 | 3391936.9215 | 14988821.784
8477 | 1597594.833 | 10178885.0942 | 1000255.2982 | 12776735.2254
8478 | 9902022.8849 | 0 | 0 | 9902022.8849
8479 | 124313.9735 | 8441280.9027 | 988330.5841 | 9553925.4603
8480 | 4074319.7662 | 7125685.3894 | 7764339.3964 | 18964344.552
8481 | 6662769.7055 | 4889794.9678 | 2283817.5247 | 13836382.198
8482 | 12056494.5893 | 20206913.585 | 9977462.8776 | 42240871.052
8483 | 3454781.8779 | 0 | 5741309.0873 | 9196090.9652
8484 | 17805067.2643 | 10408919.7702 | 559944.6837 | 28773931.7183
8485 | 17987208.0159 | 6110472.0115 | 41211.5742 | 24138891.6016
8486 | 5937851.8032 | 1739203.9109 | 1786510.4456 | 9463566.1597
8487 | 4387210.4548 | 5408359.7007 | 6053477.1023 | 15849047.2578
8488 | 890321.5041 | 0 | 317284.3259 | 1207605.83
8489 | 8448590.6593 | 7098754.7108 | 2855090.4913 | 18402435.8614
8490 | 1182222.2641 | 322366.0991 | 2754165.7785 | 4258754.1417
8491 | 2341224.5027 | 50342328.3838 | 364459.395 | 53048012.2814
8492 | 2536313.8423 | 9775674.753 | 0 | 12311988.5953
8493 | 18450867.9451 | 4155384.8391 | 0 | 22606252.7842
8494 | 10827856.8706 | 8355593.8643 | 3314330.6882 | 22497781.4232
8495 | 6136529.0532 | 5125932.3203 | 68734.599 | 11331195.9725
8496 | 9772659.5656 | 969447.0301 | 22823826.5521 | 33565933.1478
8497 | 4725966.276 | 2087268.3459 | 0 | 6813234.6219
8498 | 328931.5087 | 2430921.3078 | 3154956.2449 | 5914809.0614
8499 | 2796630.4347 | 0 | 97835.7738 | 2894466.2085
8500 | 1837154.4765 | 8194956.5726 | 104472.4185 | 10136583.4676
8501 | 4775793.0257 | 1167131.3647 | 5200631.5656 | 11143555.956
8502 | 4317787.1895 | 405528.2926 | 253456.1164 | 4976771.5985
8503 | 14049732.5281 | 1806533.1565 | 4611747.3089 | 20468012.9936
8504 | 29009053.5655 | 5311833.1759 | 0 | 34320886.7414
8505 | 6132095.1419 | 4862219.2885 | 1612847.9844 | 12607162.4147
8506 | 6283731.8376 | 0 | 0 | 6283731.8376
8507 | 7254102.4932 | 30700.0173 | 66659.4264 | 7351461.9369
8508 | 2579048.0836 | 1383377.5654 | 1164394.3267 | 5126819.9757
8509 | 5766956.3862 | 9277636.0059 | 646074.7465 | 15690667.1385
8510 | 8812283.571 | 21313834.9728 | 1950789.7837 | 32076908.3275
8511 | 8498067.7779 | 7031187.9926 | 3687063.4875 | 19216319.258
8512 | 27547815.2707 | 0 | 0 | 27547815.2707
8513 | 1098272.8866 | 5387876.2896 | 10029739.471 | 16515888.6473
8514 | 10041499.959 | 5225140.5781 | 363943.749 | 15630584.2862
8515 | 752897.3722 | 4819511.6185 | 0 | 5572408.9907
8516 | 7184256.3151 | 3557673.32 | 1097193.6352 | 11839123.2703
8517 | 14570336.2917 | 4497528.0946 | 2725667.6896 | 21793532.0759
8518 | 2056916.136 | 1721341.2982 | 1256006.839 | 5034264.2732
8519 | 4622297.2944 | 7686460.6613 | 80313.4861 | 12389071.4418
8520 | 4950941.582 | 1881398.4467 | 24762764.2227 | 31595104.2515
8521 | 18668542.0254 | 10749868.3587 | 0 | 29418410.3842
8522 | 5063431.8747 | 0 | 0 | 5063431.8747
8523 | 5659473.7098 | 12289064.4277 | 4358286.9025 | 22306825.04
8524 | 8497506.5238 | 943014.2545 | 0 | 9440520.7783
8525 | 5625752.7421 | 266955.1744 | 13533693.0476 | 19426400.9642
8526 | 6229633.8216 | 4740778.0518 | 250919.8147 | 11221331.6881
8527 | 1982679.9984 | 13838527.2343 | 816016.5841 | 16637223.8168
8528 | 7665271.9388 | 3967492.8036 | 2904068.7381 | 14536833.4805
8529 | 4080966.8709 | 14247545.8964 | 4167194.7331 | 22495707.5004
8530 | 13213107.5847 | 3995366.7638 | 509306.2964 | 17717780.645
8531 | 16304652.1098 | 4799462.9264 | 337382.5095 | 21441497.5457
8532 | 20337859.0168 | 10599963.9322 | 0 | 30937822.949
8533 | 8561775.1542 | 0 | 9114005.9515 | 17675781.1057
8534 | 1964301.2369 | 0 | 239557.8255 | 2203859.0624
8535 | 910531.8578 | 12368141.7084 | 4166677.0832 | 17445350.6494
8536 | 5586279.2291 | 3106561.5812 | 2307672.7287 | 11000513.539
8537 | 5358266.1571 | 5477726.2281 | 0 | 10835992.3853
8538 | 2714415.0277 | 4935516.7173 | 3421443.0476 | 11071374.7927
8539 | 16186758.8425 | 2096102.5699 | 3206444.3403 | 21489305.7527
8540 | 10315698.3057 | 3561634.2956 | 1561229.1917 | 15438561.7929
8541 | 1579512.0955 | 0 | 0 | 1579512.0955
8542 | 3702101.6753 | 12249316.0135 | 3273971.5741 | 19225389.2629
8543 | 1898226.6078 | 5291156.1818 | 10460665.7983 | 17650048.5878
8544 | 3699761.717 | 2855994.9664 | 4711803.887 | 11267560.5704
8545 | 5321622.5962 | 0 | 0 | 5321622.5962
8546 | 17539188.6397 | 26546598.9692 | 50226.5803 | 44136014.1892
8547 | 7210491.6053 | 11015796.0653 | 2269699.047 | 20495986.7176
8548 | 1174600.1504 | 13535841.2533 | 987501.7325 | 15697943.1362
8549 | 471038.0503 | 0 | 71400.3524 | 542438.4027
8550 | 1646459.0159 | 4346230.7582 | 34655.2907 | 6027345.0649
8551 | 2812840.3673 | 0 | 4800924.6596 | 7613765.0269
8552 | 238349.7025 | 22385432.9168 | 10132347.3655 | 32756129.9847
8553 | 3337812.7095 | 5262092.2094 | 0 | 8599904.9189
8554 | 1539841.56 | 5771034.4424 | 945273.0756 | 8256149.078
8555 | 13155555.2981 | 5858423.4663 | 171351.0458 | 19185329.8103
8556 | 4055646.7528 | 0 | 988878.1046 | 5044524.8574
8557 | 11434998.8996 | 14563056.0157 | 3845522.9682 | 29843577.8834
8558 | 863897.9584 | 9883389.1997 | 4739604.4416 | 15486891.5998
8559 | 4176305.7391 | 7235933.7725 | 236660.4362 | 11648899.9479
8560 | 5006609.8417 | 11687874.5638 | 4476831.2983 | 21171315.7038
8561 | 11089203.7872 | 189923.1705 | 738819.2571 | 12017946.2147
8562 | 18279918.1233 | 1711620.9164 | 0 | 19991539.0396
8563 | 16538609.2647 | 8647828.025 | 969237.9802 | 26155675.2699
8564 | 7582299.2291 | 10397178.5757 | 4756718.1137 | 22736195.9186
8565 | 1875827.885 | 3091256.4599 | 0 | 4967084.3449
8566 | 7747422.5751 | 5976443.6637 | 0 | 13723866.2388
8567 | 2619991.0527 | 7622075.012 | 762773.1927 | 11004839.2573
8568 | 3922994.1397 | 1549691.5123 | 797376.2014 | 6270061.8533
8569 | 3752390.1932 | 2539731.2686 | 2170891.0002 | 8463012.4621
8570 | 4881301.4144 | 12296658.0209 | 4334865.2085 | 21512824.6438
8571 | 23265124.4533 | 3711087.7989 | 0 | 26976212.2521
8572 | 10716508.6754 | 18699167.9976 | 196580.8276 | 29612257.5006
8573 | 5510987.5994 | 10200976.4192 | 1421190.4008 | 17133154.4194
8574 | 1904162.4953 | 12004099.0495 | 687664.7547 | 14595926.2995
8575 | 4172546.8301 | 25207107.7458 | 2377253.4209 | 31756907.9967
8576 | 11678805.0887 | 2155989.447 | 12599.9964 | 13847394.5321
8577 | 9968825.4978 | 12155755.9705 | 1123710.4217 | 23248291.89
8578 | 11456313.9861 | 2608196.4542 | 574366.1523 | 14638876.5927
8579 | 26962098.4857 | 6147791.6565 | 2712687.999 | 35822578.1412
8580 | 9461129.7738 | 5329158.7432 | 2338321.4635 | 17128609.9805
8581 | 7427648.5916 | 18611647.5162 | 7349926.9947 | 33389223.1026
8582 | 4140063.3086 | 16047129.8173 | 4375285.3308 | 24562478.4567
8583 | 6272309.4346 | 62973.0699 | 0 | 6335282.5045
8584 | 18041963.2569 | 1469017.863 | 4932059.3853 | 24443040.5052
8585 | 392433.3271 | 2325827.1667 | 1270751.4471 | 3989011.9408
8586 | 3796463.8631 | 10076247.981 | 1508659.4462 | 15381371.2903
8587 | 20757067.0018 | 16694038.3284 | 628143.3888 | 38079248.7189
8588 | 3865366.4108 | 9242675.891 | 0 | 13108042.3017
8589 | 2496504.4224 | 1188774.1269 | 841226.671 | 4526505.2203
8590 | 4351056.5032 | 3271726.6972 | 250788.5958 | 7873571.7962
8591 | 9081331.6256 | 14456210.145 | 0 | 23537541.7706
8592 | 3111820.9829 | 2800800.2333 | 3067067.5977 | 8979688.8138
8593 | 29617667.379 | 11483556.9185 | 0 | 41101224.2975
8594 | 16935679.3619 | 1865046.3495 | 7066213.7768 | 25866939.4882
8595 | 3292805.3654 | 0 | 0 | 3292805.3654
8596 | 3482868.4915 | 0 | 1227047.0384 | 4709915.5299
8597 | 1036972.5199 | 8813709.8884 | 1742250.1642 | 11592932.5725
8598 | 5472986.3552 | 0 | 453017.1623 | 5926003.5175
8599 | 2622434.6296 | 15224884.1757 | 1096072.0456 | 18943390.8508
8600 | 5477013.9807 | 18890427.0721 | 0 | 24367441.0528
8601 | 4352838.4642 | 0 | 538264.3902 | 4891102.8543
8602 | 46317283.3989 | 33591007.4779 | 0 | 79908290.8767
8603 | 23583616.8062 | 3853599.9282 | 8915312.4459 | 36352529.1803
8604 | 19875507.7857 | 15756752.804 | 745167.3725 | 36377427.9622
8605 | 12626661.7034 | 7580292.0925 | 0 | 20206953.7959
8606 | 12011283.1183 | 9470989.7595 | 0 | 21482272.8778
8607 | 11210226.4168 | 18669517.392 | 3176554.4334 | 33056298.2422
8608 | 2210111.0819 | 5225508.1488 | 0 | 7435619.2307
8609 | 14213820.6568 | 3135259.3282 | 24493273.9473 | 41842353.9323
8610 | 6117387.7552 | 8830624.7811 | 443642.2692 | 15391654.8055
8611 | 5989892.3518 | 6376632.9897 | 3093768.16 | 15460293.5015
8612 | 5473426.8585 | 12644870.6447 | 2178685.0087 | 20296982.512
8613 | 2165701.9393 | 6158127.4307 | 0 | 8323829.37
8614 | 17741288.046 | 0 | 1249987.9746 | 18991276.0205
8615 | 2959715.3947 | 16957641.0061 | 8475573.5501 | 28392929.9509
8616 | 4698622.9044 | 10481652.8076 | 909608.0099 | 16089883.7219
8617 | 11263859.8643 | 5865970.155 | 152422.3216 | 17282252.341
8618 | 1920306.5759 | 8221630.7957 | 0 | 10141937.3716
8619 | 3795652.61 | 6463564.9193 | 0 | 10259217.5293
8620 | 29113690.1632 | 14276723.6232 | 65792.2928 | 43456206.0791
8621 | 5896309.5882 | 7206320.4377 | 133825.8703 | 13236455.8961
8622 | 10982327.3421 | 2531817.6374 | 5264476.1401 | 18778621.1196
8623 | 3529449.0063 | 2817107.7181 | 31268103.3438 | 37614660.0682
8624 | 11630598.6654 | 5897960.998 | 4001766.9118 | 21530326.5753
8625 | 10967263.46 | 13813151.8956 | 67632.5809 | 24848047.9364
8626 | 2775402.8892 | 0 | 1205729.2877 | 3981132.1769
8627 | 11724121.8968 | 4853959.9454 | 104994.9618 | 16683076.804
8628 | 2129761.5595 | 451527.5956 | 2196795.0276 | 4778084.1827
8629 | 21447184.3399 | 13713483.627 | 9614844.7824 | 44775512.7493
8630 | 2687619.2098 | 2907444.2271 | 1574154.4043 | 7169217.8412
8631 | 2771103.7963 | 13032718.8172 | 2265177.7515 | 18069000.365
8632 | 10190183.0441 | 9552395.3382 | 2157445.3823 | 21900023.7647
8633 | 6233507.1718 | 1074120.2182 | 2339977.1438 | 9647604.5337
8634 | 3658672.5084 | 17971495.1905 | 301390.0328 | 21931557.7317
8635 | 867404.4265 | 29971600.6688 | 0 | 30839005.0953
8636 | 12232658.6696 | 7234965.9614 | 795990.4835 | 20263615.1144
8637 | 15251412.3462 | 8083989.8038 | 1537018.4247 | 24872420.5747
8638 | 39756363.0201 | 25122174.2826 | 2213951.7669 | 67092489.0696
8639 | 6386812.1047 | 6569542.891 | 1661121.2596 | 14617476.2554
8640 | 23120394.105 | 0 | 0 | 23120394.105
8641 | 2393768.5856 | 6128626.1787 | 917572.8409 | 9439967.6052
8642 | 9123655.1055 | 3469712.7083 | 0 | 12593367.8139
8643 | 2403941.166 | 16396027.8346 | 2057796.5064 | 20857765.507
8644 | 34562878.6111 | 8414199.4396 | 0 | 42977078.0507
8645 | 5120364.8085 | 0 | 2064368.102 | 7184732.9105
8646 | 6650219.8418 | 3656294.2543 | 0 | 10306514.096
8647 | 11463683.4919 | 5102370.3463 | 1522261.7593 | 18088315.5975
8648 | 29163262.0864 | 13025487.4014 | 405345.1881 | 42594094.6758
8649 | 1830219.1913 | 8031952.5284 | 378932.3589 | 10241104.0786
8650 | 13848309.1611 | 12298836.8477 | 0 | 26147146.0088
8651 | 5040421.71 | 11975890.0528 | 0 | 17016311.7628
8652 | 20825052.0933 | 7418909.6525 | 843777.5308 | 29087739.2765
8653 | 3114770.2546 | 1599914.2748 | 0 | 4714684.5294
8654 | 9679745.0977 | 3450016.6969 | 9291098.9737 | 22420860.7683
8655 | 3217575.2165 | 26060830.5591 | 0 | 29278405.7756
8656 | 7351814.6517 | 3674971.9254 | 2134349.3335 | 13161135.9106
8657 | 21658592.5861 | 6229137.7074 | 1257991.9144 | 29145722.2078
8658 | 1738494.2937 | 2799006.1084 | 49090.9758 | 4586591.3778
8659 | 6073561.0473 | 17184739.1732 | 148656.3389 | 23406956.5594
8660 | 10490777.6138 | 8031344.5299 | 6635877.0074 | 25157999.1511
8661 | 2628961.8258 | 0 | 7725881.3118 | 10354843.1376
8662 | 6599204.1128 | 6549231.6804 | 16709473.0044 | 29857908.7975
8663 | 15528991.6704 | 4566754.48 | 0 | 20095746.1504
8664 | 17109405.8273 | 22223313.55 | 0 | 39332719.3773
8665 | 3020545.7473 | 6873241.0485 | 6091167.7443 | 15984954.5401
8666 | 24077897.1157 | 16137002.9483 | 13312604.0472 | 53527504.1112
8667 | 11614241.7978 | 9102220.4473 | 407229.4868 | 21123691.7318
8668 | 3132477.7277 | 8059954.7662 | 919328.7074 | 12111761.2012
8669 | 4157786.3433 | 6119307.7614 | 879674.1563 | 11156768.261
8670 | 12646191.527 | 4190790.6946 | 1572196.9003 | 18409179.122
8671 | 183796.6661 | 0 | 550718.4143 | 734515.0804
8672 | 5047376.399 | 5275907.3539 | 3440343.1948 | 13763626.9476
8673 | 3674789.5085 | 0 | 123577.3889 | 3798366.8974
8674 | 5587375.0604 | 11721883.577 | 16969860.4256 | 34279119.063
8675 | 10051396.4593 | 7575576.589 | 2009469.6236 | 19636442.6718
8676 | 6137687.0033 | 26451853.5301 | 990956.3592 | 33580496.8927
8677 | 13355069.968 | 25544404.9793 | 947329.5911 | 39846804.5385
8678 | 8399231.9192 | 2445291.4242 | 3024955.9135 | 13869479.2569
8679 | 7189341.7118 | 19113560.9171 | 676594.6559 | 26979497.2848
8680 | 9958978.1188 | 7764560.2926 | 0 | 17723538.4114
8681 | 1554658.8822 | 4445586.387 | 0 | 6000245.2691
8682 | 4401947.654 | 25568964.5334 | 308089.7453 | 30279001.9326
8683 | 19791387.5005 | 3459301.3049 | 632148.9746 | 23882837.78
8684 | 1613111.7251 | 9570048.2783 | 352023.1754 | 11535183.1788
8685 | 11618803.949 | 8500573.761 | 2251760.9021 | 22371138.6121
8686 | 13573317.473 | 4732717.8937 | 49668.2008 | 18355703.5676
8687 | 6457756.9093 | 5599782.9972 | 417703.5564 | 12475243.463
8688 | 1634966.8304 | 0 | 320468.0666 | 1955434.897
8689 | 8338249.2531 | 1437335.8538 | 0 | 9775585.1069
8690 | 4911518.5536 | 6790795.0163 | 3466394.2977 | 15168707.8677
8691 | 5493908.2805 | 15071309.1794 | 21824535.9021 | 42389753.362
8692 | 6751450.9457 | 12991472.4162 | 362428.6312 | 20105351.9931
8693 | 3448780.3693 | 13202786.8824 | 800847.3741 | 17452414.6258
8694 | 12912261.5121 | 5110982.5831 | 7566809.3394 | 25590053.4346
8695 | 14487285.9124 | 0 | 1662674.7391 | 16149960.6515
8696 | 8301823.3667 | 25451116.9728 | 1078552.8234 | 34831493.1628
8697 | 4031071.9082 | 8391808.8598 | 936544.0347 | 13359424.8028
8698 | 48480333.2451 | 2529735.2427 | 1838611.36 | 52848679.8478
8699 | 3809240.4445 | 1053356.5569 | 5113556.17 | 9976153.1713
8700 | 580409.2321 | 16341214.3928 | 578317.724 | 17499941.349
8701 | 13070779.9163 | 3287161.4202 | 6525818.5201 | 22883759.8565
8702 | 3531995.2658 | 0 | 4134390.1881 | 7666385.4539
8703 | 11387448.8156 | 15837800.7774 | 3356189.5337 | 30581439.1267
8704 | 7806285.2641 | 3575246.9792 | 2185199.2934 | 13566731.5367
8705 | 5529946.9102 | 8747211.4124 | 2072484.8679 | 16349643.1905
8706 | 2936078.0014 | 6742518.5524 | 4371045.8162 | 14049642.37
8707 | 421014.3944 | 12369103.8392 | 0 | 12790118.2337
8708 | 8137339.3007 | 29038983.6348 | 115930.6985 | 37292253.634
8709 | 41786661.5002 | 28199188.4122 | 1685952.4569 | 71671802.3693
8710 | 23108552.3569 | 3814878.9741 | 1042974.84 | 27966406.171
8711 | 11842550.0316 | 21019063.7725 | 2350302.591 | 35211916.3951
8712 | 8947001.5584 | 5266363.0206 | 424483.7585 | 14637848.3375
8713 | 8765532.9024 | 7137846.0292 | 278888.4687 | 16182267.4002
8714 | 12777919.9434 | 26901706.3746 | 2096565.1155 | 41776191.4335
8715 | 15754746.4932 | 3203777.0014 | 0 | 18958523.4946
8716 | 4813515.0364 | 11474875.597 | 7241914.5057 | 23530305.1391
8717 | 19296475.2162 | 2844051.6128 | 0 | 22140526.829
8718 | 4122681.5723 | 79391393.5544 | 7448660.6056 | 90962735.7323
8719 | 5312282.4754 | 16137583.1177 | 89111.2871 | 21538976.8802
8720 | 4603703.974 | 0 | 0 | 4603703.974
8721 | 7665990.2804 | 2595709.3985 | 2643568.417 | 12905268.0959
8722 | 9807381.2653 | 6455531.2677 | 2172015.1519 | 18434927.6849
8723 | 3565094.6502 | 2008894.9117 | 5254525.1039 | 10828514.6658
8724 | 987410.9053 | 5638230.5185 | 5429523.5044 | 12055164.9282
8725 | 10455988.4773 | 0 | 2673678.0688 | 13129666.5461
8726 | 6278016.1006 | 0 | 0 | 6278016.1006
8727 | 14587731.0923 | 14746697.3903 | 2869713.6104 | 32204142.093
8728 | 4790161.0017 | 5116087.8786 | 2248423.5603 | 12154672.4406
8729 | 2971615.6702 | 23186908.1881 | 4012584.4398 | 30171108.298
8730 | 17690277.3363 | 1063785.4296 | 71985.8186 | 18826048.5845
8731 | 19206491.6616 | 5191028.253 | 2009441.6492 | 26406961.5637
8732 | 7921976.8307 | 585255.4421 | 7504254.5753 | 16011486.8481
8733 | 8183212.318 | 14229458.7769 | 2140226.1937 | 24552897.2886
8734 | 6800874.0224 | 17615892.1756 | 1055528.421 | 25472294.619
8735 | 2391804.0911 | 5129667.0221 | 3628962.8869 | 11150434
8736 | 6945819.616 | 1125169.848 | 498078.9459 | 8569068.4099
8737 | 17849801.4092 | 0 | 704217.2923 | 18554018.7015
8738 | 15588659.711 | 15628245.132 | 0 | 31216904.8431
8739 | 4608589.3767 | 13968408.8069 | 5156615.8248 | 23733614.0084
8740 | 14884610.2454 | 5102594.4651 | 9532647.2675 | 29519851.978
8741 | 7211973.3042 | 0 | 1004495.4684 | 8216468.7726
8742 | 5680299.286 | 4113185.0216 | 0 | 9793484.3077
8743 | 12271546.5707 | 12355872.4789 | 1100248.7347 | 25727667.7843
8744 | 1760178.269 | 7447221.2211 | 9342302.21 | 18549701.7001
8745 | 6618738.5708 | 8897073.9165 | 5307759.5385 | 20823572.0257
8746 | 2708617.5085 | 6227804.2292 | 2369452.2173 | 11305873.955
8747 | 3295815.3157 | 7176890.2326 | 2317421.7583 | 12790127.3065
8748 | 17590044.1327 | 20063921.8199 | 3507127.4515 | 41161093.4042
8749 | 3010848.9639 | 14892930.2517 | 0 | 17903779.2156
8750 | 2743102.5305 | 4826970.0485 | 0 | 7570072.579
8751 | 6475547.8704 | 29479470.9021 | 9141078.7934 | 45096097.5659
8752 | 17994739.2127 | 0 | 15338885.6936 | 33333624.9063
8753 | 4532178.3841 | 13503349.3362 | 4075120.1812 | 22110647.9015
8754 | 16229004.782 | 40558506.5937 | 1904234.5316 | 58691745.9073
8755 | 11346009.3369 | 14750919.1989 | 16238644.6227 | 42335573.1584
8756 | 10225058.9708 | 16116872.0894 | 6341089.6566 | 32683020.7168
8757 | 5112761.2758 | 2996556.7505 | 139166.8408 | 8248484.8672
8758 | 5613488.4186 | 7221216.2872 | 999879.4393 | 13834584.1451
8759 | 5932948.5104 | 1926573.5248 | 1546117.4402 | 9405639.4754
8760 | 11062327.3428 | 0 | 306032.2563 | 11368359.5991
8761 | 5899670.6536 | 20270068.5035 | 10254750.7209 | 36424489.878
8762 | 7946644.142 | 9824822.8932 | 388718.2034 | 18160185.2386
8763 | 9339387.0116 | 4918433.8374 | 1363090.777 | 15620911.626
8764 | 1378889.4891 | 1635073.7883 | 895763.866 | 3909727.1434
8765 | 1428640.4935 | 1327655.5549 | 586389.9608 | 3342686.0092
8766 | 12433684.2317 | 5437871.9286 | 0 | 17871556.1603
8767 | 13589043.3299 | 4871612.232 | 1596743.25 | 20057398.8119
8768 | 30490821.7433 | 5396299.8311 | 0 | 35887121.5744
8769 | 13771632.7046 | 1645612.6024 | 1534503.4293 | 16951748.7363
8770 | 5722179.0713 | 3845445.5573 | 9267872.8544 | 18835497.4831
8771 | 17504520.726 | 0 | 3506427.5733 | 21010948.2993
8772 | 4257779.7026 | 2138052.1197 | 2196587.2017 | 8592419.024
8773 | 911377.3171 | 3171340.807 | 13567408.8583 | 17650126.9824
8774 | 12549497.073 | 21886627.9393 | 584206.425 | 35020331.4373
8775 | 6505167.433 | 5806435.1049 | 589215.7548 | 12900818.2927
8776 | 1845992.3112 | 3457663.9908 | 5148973.5014 | 10452629.8034
8777 | 18635122.6304 | 0 | 2452147.9254 | 21087270.5558
8778 | 13343213.2379 | 0 | 7492688.7981 | 20835902.036
8779 | 8000388.3332 | 5658603.5166 | 1310665.3234 | 14969657.1733
8780 | 5294646.7883 | 18875611.2493 | 82586.7939 | 24252844.8316
8781 | 2885506.1312 | 4662055.2933 | 1072961.1819 | 8620522.6063
8782 | 11347070.6544 | 0 | 0 | 11347070.6544
8783 | 4549781.0092 | 8950595.3581 | 744730.0362 | 14245106.4036
8784 | 4505185.3053 | 5005185.8365 | 915922.0174 | 10426293.1592
8785 | 6135623.9764 | 5813934.0805 | 4310760.9619 | 16260319.0189
8786 | 3004898.0008 | 6850372.2207 | 18278795.7122 | 28134065.9337
8787 | 10609284.044 | 9328570.0468 | 5103284.9217 | 25041139.0124
8788 | 7219016.174 | 15907703.0148 | 220261.3481 | 23346980.5369
8789 | 6365473.9117 | 0 | 1068346.2204 | 7433820.1321
8790 | 9483666.3401 | 13456367.9318 | 0 | 22940034.2719
8791 | 24213373.0541 | 29181886.6002 | 3082277.6842 | 56477537.3385
8792 | 4888358.8642 | 3535751.8095 | 5733594.6294 | 14157705.3031
8793 | 3722790.9246 | 1146904.8387 | 4013235.3083 | 8882931.0717
8794 | 8869009.8972 | 14028553.2393 | 3112463.5232 | 26010026.6596
8795 | 16780263.7004 | 0 | 16306026.1304 | 33086289.8308
8796 | 19706090.3656 | 3697726.9321 | 4439727.4422 | 27843544.7399
8797 | 3281934.8682 | 6523579.2492 | 0 | 9805514.1174
8798 | 14503520.446 | 9226557.9591 | 3254615.3526 | 26984693.7576
8799 | 2440406.7869 | 7086770.0084 | 1009381.382 | 10536558.1772
8800 | 10052924.8208 | 10590715.9435 | 800567.6711 | 21444208.4354
8801 | 12702053.1845 | 1618769.1107 | 1927290.3373 | 16248112.6325
8802 | 2009129.7338 | 838267.7393 | 47596.4992 | 2894993.9724
8803 | 7922178.3503 | 5005003.9988 | 1454771.7315 | 14381954.0806
8804 | 10602408.9063 | 31436076.6628 | 2829315.4684 | 44867801.0375
8805 | 3425619.3889 | 100009.7595 | 3158344.8891 | 6683974.0376
8806 | 10611750.3067 | 4793058.1654 | 0 | 15404808.4722
8807 | 7767265.5395 | 8087212.479 | 66621.8143 | 15921099.8328
8808 | 21178882.2925 | 10251418.7086 | 725580.818 | 32155881.8191
8809 | 1940376.2104 | 12413536.3546 | 2186952.8422 | 16540865.4071
8810 | 6960203.0766 | 6737466.9328 | 284892.6966 | 13982562.706
8811 | 4537840.9978 | 12339869.5786 | 1513667.4754 | 18391378.0517
8812 | 1297570.5022 | 9026939.7756 | 8948670.161 | 19273180.4389
8813 | 6953247.6525 | 8821549.5837 | 0 | 15774797.2362
8814 | 3327306.513 | 2717946.1077 | 4229108.7485 | 10274361.3691
8815 | 3044856.3884 | 2827893.4787 | 15980084.2445 | 21852834.1115
8816 | 2225280.8143 | 0 | 2586925.205 | 4812206.0194
8817 | 9752399.3723 | 0 | 1457058.5927 | 11209457.965
8818 | 2214646.5374 | 10567284.2499 | 713729.1744 | 13495659.9617
8819 | 7873269.8577 | 0 | 0 | 7873269.8577
8820 | 1297306.2684 | 22699306.4045 | 1901405.8648 | 25898018.5377
8821 | 22736127.1734 | 11156571.2107 | 1036116.4294 | 34928814.8135
8822 | 26672978.6296 | 1322979.3117 | 114281.9022 | 28110239.8436
8823 | 14819133.109 | 4322869.704 | 9037.2262 | 19151040.0392
8824 | 2640732.6841 | 0 | 99392.0013 | 2740124.6854
8825 | 13757492.0755 | 0 | 348900.6456 | 14106392.7211
8826 | 14922332.5423 | 3972880.0564 | 8332599.2911 | 27227811.8897
8827 | 19891000.5636 | 0 | 1876761.294 | 21767761.8576
8828 | 11612240.1951 | 22641468.9519 | 1028797.0806 | 35282506.2276
8829 | 5880736.9881 | 2864218.1628 | 1433796.061 | 10178751.2118
8830 | 2253910.4247 | 32645289.5768 | 0 | 34899200.0015
8831 | 21301122.4028 | 5278478.1151 | 217788.3471 | 26797388.8649
8832 | 8764066.6439 | 11419032.5361 | 0 | 20183099.1799
8833 | 2398998.9249 | 13081724.2119 | 0 | 15480723.1368
8834 | 11445851.2474 | 4128915.0172 | 3776077.6816 | 19350843.9462
8835 | 16246633.2026 | 0 | 7482636.6448 | 23729269.8474
8836 | 30792976.3629 | 5003856.539 | 73263.6873 | 35870096.5891
8837 | 1096740.4574 | 1282436.0995 | 2668211.1868 | 5047387.7437
8838 | 2026702.1157 | 0 | 3173998.524 | 5200700.6397
8839 | 6677990.472 | 2544548.4786 | 0 | 9222538.9506
8840 | 1392579.8478 | 2923644.3829 | 626971.2654 | 4943195.4961
8841 | 2418700.7215 | 17556469.316 | 545453.0422 | 20520623.0797
8842 | 1328950.4619 | 5188212.1204 | 0 | 6517162.5822
8843 | 10747070.2309 | 4823402.3592 | 629643.1856 | 16200115.7757
8844 | 8001610.1276 | 3187130.1139 | 267656.7518 | 11456396.9932
8845 | 6665731.1277 | 13813690.8815 | 0 | 20479422.0091
8846 | 462188.8504 | 220206.4707 | 18696516.2103 | 19378911.5315
8847 | 2302061.8247 | 1246016.287 | 1258219.7597 | 4806297.8714
8848 | 1300084.8338 | 4975315.3676 | 297218.8279 | 6572619.0293
8849 | 6718202.5436 | 4499395.6459 | 1758008.8302 | 12975607.0196
8850 | 1429681.972 | 18858351.7192 | 3458563.8445 | 23746597.5357
8851 | 3490739.562 | 11782658.9595 | 1641752.8598 | 16915151.3812
8852 | 8516548.2887 | 19504847.4155 | 2001776.7662 | 30023172.4704
8853 | 3950196.2901 | 5245717.7919 | 0 | 9195914.082
8854 | 14365210.1039 | 3540533.0597 | 2183543.8806 | 20089287.0442
8855 | 16582506.5808 | 6243049.2344 | 2220200.4942 | 25045756.3094
8856 | 14815332.1401 | 4474378.9988 | 2007340.9735 | 21297052.1123
8857 | 2586928.7447 | 0 | 155946.2972 | 2742875.0419
8858 | 7148122.041 | 7443531.0657 | 796011.0999 | 15387664.2066
8859 | 1132678.6516 | 2037146.9477 | 7885662.7748 | 11055488.3741
8860 | 5762016.7951 | 24159791.6713 | 183675.2134 | 30105483.6798
8861 | 2069118.4828 | 11398908.1429 | 61583.4285 | 13529610.0542
8862 | 2120086.7626 | 4385200.925 | 45922.8131 | 6551210.5008
8863 | 1054682.3581 | 4136869.275 | 9473614.9452 | 14665166.5783
8864 | 11279116.1704 | 14066191.6514 | 3374333.0295 | 28719640.8512
8865 | 2418981.607 | 13830681.9475 | 1364131.8087 | 17613795.3632
8866 | 7432116.5953 | 12399142.1084 | 4310842.6801 | 24142101.3838
8867 | 16930199.3833 | 2379580.4762 | 423279.3439 | 19733059.2034
8868 | 8631376.6662 | 18869787.6199 | 3274439.2785 | 30775603.5646
8869 | 4458087.8133 | 3909969.7196 | 1295392.2799 | 9663449.8128
8870 | 5959632.4624 | 5619423.001 | 17982520.1203 | 29561575.5838
8871 | 16269217.8682 | 0 | 72717.1659 | 16341935.0341
8872 | 1523854.6049 | 14544645.502 | 2988727.019 | 19057227.1258
8873 | 3908733.9757 | 23601359.7266 | 8205203.1333 | 35715296.8356
8874 | 9677446.5488 | 10470972.5946 | 0 | 20148419.1434
8875 | 5924142.5638 | 4598006.7905 | 10324041.1065 | 20846190.4608
8876 | 8041525.0574 | 2770087.6133 | 1274444.8739 | 12086057.5445
8877 | 2012440.1946 | 2676709.4853 | 62798.6377 | 4751948.3177
8878 | 8519363.8129 | 9062443.0315 | 203587.9352 | 17785394.7796
8879 | 7417387.8431 | 30868272.0926 | 0 | 38285659.9357
8880 | 19529742.2382 | 4330864.3711 | 12754561.9433 | 36615168.5525
8881 | 5250615.7545 | 4321077.4799 | 2418628.2032 | 11990321.4376
8882 | 4458382.4213 | 5275082.5471 | 71534.3924 | 9804999.3608
8883 | 10657409.8925 | 0 | 14319562.6387 | 24976972.5312
8884 | 22928465.677 | 4099451.7767 | 17260571.1668 | 44288488.6206
8885 | 9845719.9351 | 4316328.2574 | 612900.8977 | 14774949.0902
8886 | 8727750.1644 | 0 | 1062638.1741 | 9790388.3385
8887 | 7129635.9952 | 4596549.2306 | 0 | 11726185.2258
8888 | 4145329.3983 | 5810546.7337 | 6271166.4746 | 16227042.6066
8889 | 7588471.9931 | 15812335.3287 | 1252660.1771 | 24653467.4988
8890 | 12837577.3351 | 0 | 128142.183 | 12965719.5181
8891 | 3385106.9452 | 4951769.6384 | 352214.2613 | 8689090.8449
8892 | 10294866.9399 | 4585366.0942 | 8974061.4594 | 23854294.4935
8893 | 460120.4357 | 9469577.7129 | 694826.5817 | 10624524.7302
8894 | 16831347.924 | 4259216.1692 | 0 | 21090564.0933
8895 | 1034842.5799 | 3182337.6197 | 80637.9609 | 4297818.1605
8896 | 3030092.7785 | 7006867.9996 | 2559106.7432 | 12596067.5212
8897 | 17797014.503 | 0 | 19834554.48 | 37631568.9829
8898 | 6835718.6706 | 4432276.5188 | 0 | 11267995.1894
8899 | 7084693.2651 | 2228421.196 | 8396854.9823 | 17709969.4435
8900 | 6533087.0565 | 0 | 6230231.287 | 12763318.3436
8901 | 5011733.4533 | 0 | 178869.2846 | 5190602.7379
8902 | 10090200.1943 | 2821812.7978 | 3663138.4022 | 16575151.3943
8903 | 4610278.3959 | 5270043.4638 | 9120737.8113 | 19001059.671
8904 | 9096813.2479 | 6224775.5683 | 334572.8487 | 15656161.6648
8905 | 5165023.4804 | 3361321.5183 | 940086.5788 | 9466431.5774
8906 | 6243689.6231 | 6921439.642 | 13905786.7904 | 27070916.0555
8907 | 9297864.6648 | 3542301.3339 | 3317920.8638 | 16158086.8625
8908 | 3328434.7014 | 0 | 105520.9014 | 3433955.6028
8909 | 3447712.924 | 9980567.4969 | 5728032.6129 | 19156313.0338
8910 | 6074412.6968 | 13750357.0315 | 2572968.6479 | 22397738.3762
8911 | 4174415.3533 | 55874132.535 | 2554086.7694 | 62602634.6577
8912 | 21934713.4559 | 4296384.3768 | 1126756.9695 | 27357854.8022
8913 | 335894.1516 | 0 | 3697352.0165 | 4033246.1681
8914 | 1136125.6845 | 5320784.3035 | 0 | 6456909.988
8915 | 16344781.8704 | 3607836.6737 | 114640.6203 | 20067259.1644
8916 | 677189.0393 | 2779771.4517 | 1647434.2252 | 5104394.7163
8917 | 6081342.2297 | 8876083.8839 | 0 | 14957426.1136
8918 | 27934505.4098 | 15157339.1306 | 833396.6813 | 43925241.2217
8919 | 7464033.7974 | 12123926.674 | 918149.3 | 20506109.7713
8920 | 7774258.9445 | 27908970.1783 | 0 | 35683229.1228
8921 | 4070604.1448 | 10853049.7171 | 147027.5775 | 15070681.4395
8922 | 27406501.6411 | 4561466.3567 | 181760.7407 | 32149728.7385
8923 | 4350365.9579 | 10009808.9591 | 1096605.9597 | 15456780.8767
8924 | 5246745.7511 | 8709680.3573 | 1896485.1946 | 15852911.303
8925 | 7176469.1607 | 9372392.0901 | 841466.529 | 17390327.7798
8926 | 5411241.2219 | 20137343.4301 | 2086198.84 | 27634783.492
8927 | 8404096.0878 | 13668523.4301 | 1357813.595 | 23430433.1129
8928 | 15663146.5728 | 5236488.2887 | 766097.1763 | 21665732.0378
8929 | 10442531.4212 | 4264884.1796 | 156664.2726 | 14864079.8733
8930 | 8441723.0396 | 0 | 242955.16 | 8684678.1996
8931 | 3775645.6664 | 4045183.8941 | 1551065.8041 | 9371895.3647
8932 | 2437239.8505 | 5916633.6026 | 3919898.5761 | 12273772.0293
8933 | 2158700.3024 | 27996388.2894 | 3298243.5549 | 33453332.1466
8934 | 4844982.1096 | 9101346.3748 | 2192897.2899 | 16139225.7743
8935 | 4824850.0071 | 7192736.5539 | 477562.6864 | 12495149.2473
8936 | 4180344.0423 | 0 | 1104508.186 | 5284852.2283
8937 | 1998404.1148 | 7224363.9719 | 0 | 9222768.0867
8938 | 5823472.78 | 0 | 720684.6734 | 6544157.4534
8939 | 721951.694 | 7452077.9373 | 877833.1749 | 9051862.8063
8940 | 7452063.8335 | 1563746.0749 | 0 | 9015809.9083
8941 | 5774848.7278 | 7259241.8662 | 0 | 13034090.5941
8942 | 3138719.2412 | 4052799.997 | 19061750.2853 | 26253269.5235
8943 | 29822322.9691 | 2230584.6963 | 181380.1309 | 32234287.7962
8944 | 989017.1679 | 0 | 135692.3733 | 1124709.5412
8945 | 4060048.1782 | 5467557.9479 | 77634.8832 | 9605241.0094
8946 | 2573305.155 | 4835735.8048 | 0 | 7409040.9597
8947 | 9463361.1749 | 31687654.283 | 2016827.6233 | 43167843.0811
8948 | 4467123.5063 | 7463123.9293 | 340328.2639 | 12270575.6995
8949 | 7819002.2148 | 5817572.3228 | 338119.8129 | 13974694.3505
8950 | 14740682.5151 | 7188730.3635 | 138462.2475 | 22067875.1261
8951 | 2955855.9461 | 0 | 2631978.7428 | 5587834.6889
8952 | 18083210.0029 | 2200839.5065 | 4332332.4843 | 24616381.9937
8953 | 3804736.6733 | 483430.8807 | 0 | 4288167.554
8954 | 9008364.8423 | 9432551.7875 | 0 | 18440916.6299
8955 | 5479188.021 | 20351534.7667 | 7115426.7715 | 32946149.5593
8956 | 4650251.1391 | 7606462.0792 | 0 | 12256713.2183
8957 | 5019781.4065 | 2215288.3332 | 157128.8662 | 7392198.6059
8958 | 2760930.6566 | 0 | 2902139.5302 | 5663070.1868
8959 | 1565141.5902 | 5753790.6974 | 2578307.0426 | 9897239.3302
8960 | 2869704.4804 | 0 | 162298.7274 | 3032003.2079
8961 | 10600272.5184 | 4236714.111 | 941840.3789 | 15778827.0082
8962 | 785392.4247 | 8276386.5006 | 74082.6581 | 9135861.5835
8963 | 7440196.7166 | 25180086.3906 | 16566472.6476 | 49186755.7548
8964 | 3505856.1357 | 7366678.6325 | 10538604.622 | 21411139.3902
8965 | 6807289.7347 | 880635.2138 | 287343.9461 | 7975268.8946
8966 | 1603345.6429 | 7328203.8738 | 13437373.2012 | 22368922.7179
8967 | 1814212.9403 | 5037100.6296 | 3845437.4685 | 10696751.0383
8968 | 18329.4981 | 8993589.5862 | 231242.7385 | 9243161.8228
8969 | 36138989.569 | 1373363.3244 | 97674.4166 | 37610027.3101
8970 | 2400794.9096 | 4368550.5081 | 900379.4481 | 7669724.8658
8971 | 5078596.2762 | 8184291.6291 | 5077989.6783 | 18340877.5837
8972 | 3518910.4021 | 11720506.762 | 2343168.3511 | 17582585.5152
8973 | 5658285.811 | 0 | 1158745.4248 | 6817031.2358
8974 | 5681256.2803 | 9982507.9516 | 979218.7754 | 16642983.0073
8975 | 6591038.5171 | 29440223.4561 | 1963252.2494 | 37994514.2226
8976 | 4025392.0163 | 4750841.2403 | 22979.1111 | 8799212.3678
8977 | 27944411.0404 | 6570117.6878 | 138622.1283 | 34653150.8564
8978 | 2758629.8375 | 0 | 3024231.7236 | 5782861.5611
8979 | 8651709.8421 | 13796615.0249 | 28806.1367 | 22477131.0037
8980 | 2588281.8466 | 6509038.6715 | 0 | 9097320.5182
8981 | 5311806.0845 | 6830613.6481 | 527253.5077 | 12669673.2403
8982 | 7958205.2921 | 4177571.6013 | 5488057.3761 | 17623834.2695
8983 | 10876800.0779 | 1903811.2197 | 1257421.3718 | 14038032.6693
8984 | 1485469.9889 | 7814026.1933 | 5277812.9285 | 14577309.1107
8985 | 4508090.6117 | 0 | 15856581.9028 | 20364672.5146
8986 | 2167609.6497 | 27464232.0716 | 524386.3456 | 30156228.0669
8987 | 596632.8071 | 6609320.9163 | 242815.6017 | 7448769.325
8988 | 10534916.2804 | 10527060.749 | 19459.3293 | 21081436.3587
8989 | 6953132.0985 | 4698480.1871 | 366704.4772 | 12018316.7629
8990 | 17268152.8149 | 4716812.8214 | 801750.6763 | 22786716.3126
8991 | 3146196.3656 | 0 | 691207.4574 | 3837403.8229
8992 | 5020200.2775 | 10474580.7474 | 5833922.631 | 21328703.6559
8993 | 6235315.012 | 15648617.5702 | 487920.3676 | 22371852.9498
8994 | 9571390.3407 | 12630496.0149 | 1140490.3356 | 23342376.6912
8995 | 5742880.226 | 26920003.9773 | 0 | 32662884.2033
8996 | 2023888.7396 | 695023.0093 | 0 | 2718911.7489
8997 | 2354922.0561 | 8555370.8538 | 244631.6869 | 11154924.5967
8998 | 5024617.6668 | 2479405.6204 | 44450813.3398 | 51954836.627
8999 | 12360473.0244 | 13212217.9282 | 16096446.7808 | 41669137.7333
9000 | 10357723.0509 | 8994484.1072 | 2711786.7705 | 22063993.9286
9001 | 13505116.8285 | 0 | 140308.6487 | 13645425.4772
9002 | 23008372.477 | 27312582.736 | 96714.4516 | 50417669.6646
9003 | 3036425.8793 | 2857709.1494 | 2019298.0834 | 7913433.1121
9004 | 13065442.2883 | 42025791.6287 | 198321.9918 | 55289555.9089
9005 | 4699937.2646 | 2542320.7325 | 8408425.8059 | 15650683.8031
9006 | 9748336.9572 | 0 | 1013232.2204 | 10761569.1776
9007 | 6463989.1244 | 28001248.1098 | 829402.9332 | 35294640.1674
9008 | 15957736.0941 | 31075257.1352 | 3531883.7879 | 50564877.0172
9009 | 20634868.2153 | 0 | 1260029.4062 | 21894897.6215
9010 | 2506167.2498 | 23796017.4068 | 638202.5057 | 26940387.1623
9011 | 2220923.057 | 1946456.251 | 20515648.5934 | 24683027.9015
9012 | 11339758.9689 | 4495776.03 | 147366.3657 | 15982901.3646
9013 | 17497165.7594 | 104247.6287 | 0 | 17601413.3881
9014 | 4113093.0369 | 23585458.6116 | 288066.4587 | 27986618.1073
9015 | 15778639.3024 | 2492997.5641 | 794350.6612 | 19065987.5277
9016 | 4340434.4891 | 2573989.3892 | 737402.6261 | 7651826.5043
9017 | 5180815.9855 | 1949542.1447 | 1385920.5016 | 8516278.6318
9018 | 7844629.8503 | 0 | 0 | 7844629.8503
9019 | 3838455.3097 | 10029418.9493 | 5476634.9673 | 19344509.2263
9020 | 1399601.0153 | 6139202.6507 | 891705.4978 | 8430509.1638
9021 | 2864698.9788 | 0 | 0 | 2864698.9788
9022 | 5682610.019 | 8997453.6994 | 772455.4925 | 15452519.2109
9023 | 5799528.0125 | 10214321.3634 | 0 | 16013849.3758
9024 | 18987854.294 | 17987181.1892 | 90205.5981 | 37065241.0814
9025 | 26001170.2914 | 9043729.6376 | 11068507.5969 | 46113407.5259
9026 | 32302818.5112 | 0 | 1530587.0219 | 33833405.5332
9027 | 5416526.5969 | 6517470.8683 | 0 | 11933997.4652
9028 | 17327600.4165 | 3776830.6805 | 316894.0443 | 21421325.1413
9029 | 1862853.1884 | 1365258.3667 | 498726.6899 | 3726838.245
9030 | 5468097.1619 | 0 | 1182753.0661 | 6650850.228
9031 | 3387757.7198 | 43140688.1695 | 2941313.1733 | 49469759.0627
9032 | 4994945.8061 | 7214979.14 | 1727387.1265 | 13937312.0727
9033 | 6457206.8432 | 18894082.8507 | 373095.1454 | 25724384.8393
9034 | 6857325.4306 | 3886505.7337 | 10935900.4555 | 21679731.6199
9035 | 4121713.5779 | 4453206.0752 | 114950.3523 | 8689870.0054
9036 | 17429403.6993 | 4296574.5586 | 163370.9431 | 21889349.201
9037 | 2440384.6219 | 6686141.0389 | 1783367.9098 | 10909893.5706
9038 | 8334449.7604 | 8273846.2306 | 453551.4871 | 17061847.478
9039 | 3927988.3173 | 9312312.3161 | 0 | 13240300.6334
9040 | 7884661.649 | 6653070.6525 | 0 | 14537732.3015
9041 | 13471236.8238 | 8799524.957 | 11026570.7048 | 33297332.4856
9042 | 2760843.6291 | 3212898.1148 | 25287509.4524 | 31261251.1964
9043 | 7776653.8693 | 3344197.429 | 661779.9732 | 11782631.2716
9044 | 12478836.8376 | 14352099.1373 | 371993.5961 | 27202929.571
9045 | 10025087.5689 | 0 | 7161659.8891 | 17186747.4579
9046 | 29873272.816 | 16380249.898 | 0 | 46253522.714
9047 | 5396922.4063 | 0 | 464466.5923 | 5861388.9985
9048 | 3726795.9749 | 1852958.3966 | 9918749.7242 | 15498504.0958
9049 | 1453691.6243 | 2880688.5522 | 16754074.5251 | 21088454.7016
9050 | 19366170.7699 | 3935454.2714 | 1394041.9747 | 24695667.016
9051 | 7180770.3402 | 3556521.1111 | 1545738.5028 | 12283029.9541
9052 | 8005071.6822 | 0 | 0 | 8005071.6822
9053 | 2823728.2882 | 657900.9841 | 3228117.9841 | 6709747.2564
9054 | 5789822.7363 | 8283073.8397 | 494579.9538 | 14567476.5298
9055 | 9130008.5514 | 8360304.3006 | 1669034.3866 | 19159347.2386
9056 | 4749515.676 | 0 | 1594031.4637 | 6343547.1397
9057 | 7752426.2791 | 9435669.7416 | 54945.2043 | 17243041.2249
9058 | 5215161.476 | 8682264.6572 | 0 | 13897426.1332
9059 | 10243129.1873 | 15497133.9914 | 1083548.4745 | 26823811.6532
9060 | 15260314.6042 | 12524133.6657 | 890003.713 | 28674451.9829
9061 | 8173204.7692 | 2216972.05 | 10862358.5255 | 21252535.3447
9062 | 4201523.4177 | 16279894.3071 | 2174728.9773 | 22656146.702
9063 | 19896295.2193 | 8576200.8228 | 934237.7802 | 29406733.8222
9064 | 3525649.2189 | 0 | 1721077.3412 | 5246726.5601
9065 | 7020882.0201 | 8678128.8412 | 8875908.6132 | 24574919.4744
9066 | 7316619.8428 | 14099472.3232 | 17762955.6073 | 39179047.7733
9067 | 33598460.7669 | 1504830.6524 | 1232423.9893 | 36335715.4087
9068 | 3974393.7979 | 10128747.0551 | 12223348.263 | 26326489.116
9069 | 1694714.4191 | 0 | 0 | 1694714.4191
9070 | 7797616.1072 | 16577466.9465 | 4123573.9127 | 28498656.9665
9071 | 4174096.9182 | 4871011.1002 | 2976634.1058 | 12021742.1242
9072 | 4190438.8988 | 0 | 10354092.0645 | 14544530.9633
9073 | 4265615.016 | 1273158.8711 | 6967081.6448 | 12505855.5319
9074 | 1229067.6606 | 0 | 5228229.9901 | 6457297.6507
9075 | 13311015.8688 | 1577208.503 | 17674379.4622 | 32562603.8341
9076 | 7162191.2095 | 26153052.9459 | 2884492.8031 | 36199736.9585
9077 | 7278012.5563 | 5100881.1327 | 5156790.821 | 17535684.5099
9078 | 1255178.805 | 13134388.5443 | 15035724.5195 | 29425291.8688
9079 | 2027700.9534 | 0 | 2821986.1227 | 4849687.0761
9080 | 2253222.7686 | 7085043.6157 | 4636116.8502 | 13974383.2345
9081 | 2762218.0958 | 68044545.8038 | 2408405.1532 | 73215169.0528
9082 | 16349199.1923 | 9993286.4876 | 0 | 26342485.68
9083 | 11437817.8516 | 4735416.7961 | 1635137.2526 | 17808371.9003
9084 | 11091838.8369 | 0 | 1931239.8883 | 13023078.7252
9085 | 21338696.4522 | 4214200.1538 | 0 | 25552896.606
9086 | 11006731.5048 | 3365213.2571 | 886505.4008 | 15258450.1627
9087 | 6875706.5308 | 16753553.5439 | 129224.7477 | 23758484.8224
9088 | 2701629.7624 | 10500610.4896 | 2271882.9384 | 15474123.1903
9089 | 2739084.7614 | 15245213.6842 | 5371022.0629 | 23355320.5084
9090 | 175539.5701 | 0 | 4580051.4673 | 4755591.0375
9091 | 8818546.1962 | 6836038.3799 | 3106794.0855 | 18761378.6616
9092 | 32698146.1232 | 10865754.9784 | 0 | 43563901.1017
9093 | 14304192.6051 | 13180924.3039 | 1447260.6054 | 28932377.5144
9094 | 7943727.2102 | 32174485.5732 | 1554711.3543 | 41672924.1377
9095 | 3685144.7219 | 10625627.795 | 1180407.5968 | 15491180.1137
9096 | 6658085.8916 | 833249.3096 | 1015149.1362 | 8506484.3374
9097 | 9371156.6391 | 7634865.2865 | 2710039.6296 | 19716061.5551
9098 | 20370807.5515 | 3199880.6214 | 676784.5458 | 24247472.7187
9099 | 1583505.8409 | 11447221.8401 | 1740682.7866 | 14771410.4676
9100 | 10634026.7194 | 3766277.6046 | 15087990.6453 | 29488294.9693
9101 | 9882463.3684 | 14914084.6551 | 3105084.2841 | 27901632.3076
9102 | 5571249.5664 | 5284022.8005 | 1446958.8629 | 12302231.2298
9103 | 23022494.0281 | 3026768.0569 | 0 | 26049262.085
9104 | 6169983.6851 | 5178773.585 | 2855001.884 | 14203759.1541
9105 | 9694719.782 | 2035917.1834 | 8044910.8758 | 19775547.8413
9106 | 261647.3772 | 9652249.3206 | 1564406.6353 | 11478303.3331
9107 | 15216935.4598 | 1383495.9725 | 341859.0264 | 16942290.4586
9108 | 2912474.0819 | 11084996.5566 | 829010.0136 | 14826480.6522
9109 | 4077263.6342 | 1064043.752 | 1257714.6388 | 6399022.025
9110 | 5841961.5324 | 3055288.4851 | 5586850.53 | 14484100.5474
9111 | 4353593.742 | 14869366.744 | 565286.1969 | 19788246.6829
9112 | 12950895.557 | 9231536.7035 | 7209010.5196 | 29391442.78
9113 | 1666663.44 | 1904375.6236 | 13955878.4483 | 17526917.5118
9114 | 5157253.7184 | 16784368.2276 | 4996989.3715 | 26938611.3174
9115 | 4126588.0545 | 8337793.5591 | 1898713.5965 | 14363095.2101
9116 | 3059412.7253 | 0 | 616295.6356 | 3675708.3609
9117 | 3387540.931 | 6490076.1659 | 5545865.6348 | 15423482.7317
9118 | 8979166.0611 | 4738585.7607 | 0 | 13717751.8219
9119 | 7151690.5526 | 4184263.5853 | 0 | 11335954.138
9120 | 3462068.9534 | 774828.7364 | 4937895.1534 | 9174792.8432
9121 | 12626697.1165 | 3645816.7884 | 1993144.1435 | 18265658.0485
9122 | 7634958.9838 | 0 | 0 | 7634958.9838
9123 | 3767547.0939 | 7731993.0886 | 965298.8302 | 12464839.0126
9124 | 7236989.2426 | 6533927.6714 | 4881622.0083 | 18652538.9223
9125 | 9783548.214 | 5146560.6826 | 6250111.2107 | 21180220.1073
9126 | 7596164.1549 | 0 | 1787275.6761 | 9383439.8309
9127 | 6298724.3367 | 8038317.0402 | 0 | 14337041.3769
9128 | 8723600.9394 | 5457989.2072 | 182020.3922 | 14363610.5388
9129 | 10226648.9379 | 3474286.7062 | 10921.0352 | 13711856.6794
9130 | 2872869.2099 | 0 | 20771850.5823 | 23644719.7922
9131 | 12764566.1721 | 12528769.7837 | 397324.1783 | 25690660.1341
9132 | 1191582.0198 | 5942938.5599 | 1489991.5049 | 8624512.0846
9133 | 4681291.8665 | 9648583.9732 | 0 | 14329875.8397
9134 | 5237429.7061 | 4124294.2262 | 0 | 9361723.9323
9135 | 5938210.987 | 21015216.9603 | 363843.1501 | 27317271.0974
9136 | 8647974.7111 | 14584740.2161 | 3989473.2822 | 27222188.2093
9137 | 12016172.117 | 40188667.7371 | 1763718.8151 | 53968558.6693
9138 | 6512517.702 | 10245008.2309 | 1704874.9662 | 18462400.8992
9139 | 2257393.8572 | 5080586.994 | 2504605.4498 | 9842586.301
9140 | 3308483.9318 | 5384163.2762 | 1350456.9645 | 10043104.1726
9141 | 27758243.6783 | 5917173.5604 | 667269.1314 | 34342686.3701
9142 | 5898002.3098 | 1882653.5834 | 2230551.2732 | 10011207.1664
9143 | 9683360.1197 | 3684610.2179 | 875864.4996 | 14243834.8372
9144 | 5847507.2151 | 5457979.1268 | 0 | 11305486.342
9145 | 2942835.752 | 1638656.0346 | 335156.5035 | 4916648.2902
9146 | 745579.8279 | 1570332.296 | 2753078.0286 | 5068990.1525
9147 | 3245890.1646 | 0 | 11456119.0874 | 14702009.252
9148 | 11794915.4125 | 3591374.9747 | 156373.6168 | 15542664.004
9149 | 3570078.1444 | 1592137.355 | 9238093.9678 | 14400309.4672
9150 | 5251993.9041 | 5543123.4516 | 0 | 10795117.3557
9151 | 8921780.2716 | 0 | 898176.9222 | 9819957.1938
9152 | 11574153.2827 | 748346.288 | 0 | 12322499.5707
9153 | 23910338.8014 | 7534773.4385 | 3907462.2092 | 35352574.4492
9154 | 2614213.7343 | 41589227.2212 | 1500699.3411 | 45704140.2965
9155 | 2566270.0526 | 7015232.9232 | 697829.0843 | 10279332.0601
9156 | 2733340.177 | 6307372.4499 | 215411.8566 | 9256124.4835
9157 | 4651200.9879 | 2155835.3564 | 447285.2009 | 7254321.5451
9158 | 22979651.2874 | 4164137.4879 | 405386.4654 | 27549175.2408
9159 | 9654211.389 | 16232664.5626 | 947657.4605 | 26834533.4121
9160 | 8123047.4628 | 0 | 22839.8831 | 8145887.3459
9161 | 4468787.8232 | 15777009.1647 | 2838503.172 | 23084300.1599
9162 | 1830380.4436 | 1495293.923 | 597367.1542 | 3923041.5209
9163 | 11071697.5219 | 0 | 2012792.286 | 13084489.8079
9164 | 20595079.5157 | 5377285.9603 | 102922.792 | 26075288.268
9165 | 10351916.35 | 8636468.647 | 2196007.1957 | 21184392.1927
9166 | 2189409.9249 | 3656877.522 | 0 | 5846287.4468
9167 | 14707972.4118 | 4560015.7868 | 844904.9264 | 20112893.125
9168 | 17634344.3727 | 6888968.817 | 4160276.2245 | 28683589.4143
9169 | 2707574.1711 | 12951735.5817 | 263875.2671 | 15923185.0198
9170 | 2955788.2878 | 0 | 0 | 2955788.2878
9171 | 6825316.1806 | 0 | 1288837.9552 | 8114154.1358
9172 | 5075282.3161 | 3319730.959 | 1914657.3105 | 10309670.5856
9173 | 3127693.9734 | 6072987.4269 | 4546655.9249 | 13747337.3252
9174 | 13244447.1946 | 2865035.8368 | 0 | 16109483.0315
9175 | 2959922.6026 | 2431140.2238 | 0 | 5391062.8264
9176 | 11901014.8334 | 14427392.8052 | 75302.9937 | 26403710.6322
9177 | 1599606.4078 | 16967374.3966 | 0 | 18566980.8043
9178 | 3821805.8508 | 5547591.3476 | 464227.6986 | 9833624.8969
9179 | 9586659.8744 | 18810618.3849 | 134210.5248 | 28531488.7842
9180 | 20895781.5353 | 2448412.7863 | 2013901.0996 | 25358095.4212
9181 | 10126057.7554 | 15635552.4323 | 0 | 25761610.1876
9182 | 27784299.3616 | 11512180.2086 | 15799100.0514 | 55095579.6215
9183 | 4200930.0009 | 6995480.6282 | 0 | 11196410.6291
9184 | 3750492.9524 | 7644912.8871 | 3402678.8013 | 14798084.6407
9185 | 11992057.7023 | 16687274.5503 | 95295.7181 | 28774627.9708
9186 | 9209416.57 | 4374816.8987 | 1135700.3035 | 14719933.7722
9187 | 4461098.4646 | 0 | 0 | 4461098.4646
9188 | 2711351.1466 | 4144804.1545 | 12759449.8293 | 19615605.1304
9189 | 3594558.1119 | 8195486.8854 | 50031.1515 | 11840076.1488
9190 | 11604015.4102 | 6063937.5846 | 586238.0088 | 18254191.0037
9191 | 19498242.2506 | 2942632.3321 | 3394086.9775 | 25834961.5602
9192 | 6363016.9235 | 9194438.0114 | 0 | 15557454.9349
9193 | 5447701.9273 | 7730373.3 | 4149955.9434 | 17328031.1707
9194 | 21159099.9269 | 1597910.9567 | 274570.083 | 23031580.9666
9195 | 9777653.9785 | 1039254.862 | 1875702.9175 | 12692611.758
9196 | 12558840.134 | 5452306.2608 | 7683203.8721 | 25694350.2669
9197 | 13025586.1607 | 3116174.142 | 2837750.9006 | 18979511.2033
9198 | 1728554.3084 | 0 | 1159488.0479 | 2888042.3562
9199 | 2104645.3815 | 1773323.8193 | 0 | 3877969.2008
9200 | 19337164.6332 | 3457882.0713 | 0 | 22795046.7044
9201 | 8230177.6155 | 7469236.7303 | 6671980.8856 | 22371395.2315
9202 | 10971509.2611 | 8226708.3202 | 347720.6888 | 19545938.2701
9203 | 9067488.4072 | 8183229.4112 | 0 | 17250717.8184
9204 | 2616034.4421 | 29204644.9107 | 860098.0041 | 32680777.3569
9205 | 5595861.6892 | 4437876.6684 | 74033.6916 | 10107772.0492
9206 | 11475493.3871 | 7568857.358 | 327373.6359 | 19371724.3811
9207 | 1082948.0176 | 0 | 1989201.7027 | 3072149.7203
9208 | 21855584.0921 | 2366169.5276 | 9394810.7102 | 33616564.3299
9209 | 4412259.4445 | 3133353.6979 | 1400237.9777 | 8945851.1201
9210 | 708891.5733 | 20063604.4071 | 934469.1616 | 21706965.1419
9211 | 14568383.8104 | 7484462.9754 | 5822491.3617 | 27875338.1474
9212 | 7290839.1387 | 8163882.0898 | 63877.2998 | 15518598.5283
9213 | 7481426.1662 | 1568140.0505 | 2239137.2011 | 11288703.4177
9214 | 11487568.3221 | 5397150.8314 | 92536.8256 | 16977255.9791
9215 | 7336524.6268 | 0 | 576951.1574 | 7913475.7842
9216 | 17332677.8748 | 1935357.3618 | 2837846.1509 | 22105881.3875
9217 | 3140651.1922 | 5388403.8479 | 1071249.1218 | 9600304.1619
9218 | 2793936.107 | 17008197.0722 | 2950836.5741 | 22752969.7532
9219 | 7043015.5176 | 6340905.2256 | 4289040.1809 | 17672960.924
9220 | 3865316.8353 | 11139800.0512 | 1611506.2722 | 16616623.1586
9221 | 15049168.5925 | 3408772.3606 | 2670067.2366 | 21128008.1897
9222 | 7462811.0608 | 6421974.8629 | 0 | 13884785.9237
9223 | 8275023.803 | 5856010.5459 | 2128523.5275 | 16259557.8763
9224 | 2257982.0248 | 3914354.139 | 0 | 6172336.1637
9225 | 8053569.6052 | 10979309.8489 | 1191101.2669 | 20223980.721
9226 | 14484373.8721 | 1292714.3649 | 1517898.4127 | 17294986.6498
9227 | 3041271.936 | 21088795.4209 | 4568971.5918 | 28699038.9488
9228 | 7567902.7857 | 0 | 947173.5049 | 8515076.2907
9229 | 6505531.9018 | 2034826.7026 | 3736325.0202 | 12276683.6245
9230 | 7272313.4874 | 921114.0624 | 0 | 8193427.5498
9231 | 3408957.6522 | 3311632.7531 | 0 | 6720590.4052
9232 | 3949114.5495 | 3812042.1189 | 65917.18 | 7827073.8484
9233 | 4485207.7434 | 23187385.2945 | 0 | 27672593.0379
9234 | 24485180.052 | 9437912.2554 | 214922.8937 | 34138015.2011
9235 | 7501470.7606 | 0 | 0 | 7501470.7606
9236 | 4482030.401 | 8371060.3208 | 0 | 12853090.7217
9237 | 6297504.8105 | 4851860.7522 | 172315.7548 | 11321681.3176
9238 | 890821.5901 | 19512371.9148 | 2465587.6353 | 22868781.1402
9239 | 12821498.9685 | 6503793.0085 | 1204995.4889 | 20530287.4659
9240 | 1635247.5422 | 1333729.9216 | 495049.6011 | 3464027.0649
9241 | 10099007.4764 | 8566756.614 | 20953315.8537 | 39619079.9441
9242 | 6797993.0069 | 10323866.5265 | 1272913.9231 | 18394773.4566
9243 | 2395746.2948 | 21881369.7806 | 0 | 24277116.0754
9244 | 14949003.9448 | 0 | 5861695.8212 | 20810699.766
9245 | 1321792.9674 | 28301820.7436 | 140379.9204 | 29763993.6314
9246 | 19659814.311 | 10217372.619 | 1053594.7578 | 30930781.6877
9247 | 4528087.3615 | 5149234.96 | 567663.0368 | 10244985.3583
9248 | 1319285.2345 | 9849400.4985 | 0 | 11168685.733
9249 | 11908071.1639 | 4891039.5728 | 4757564.1433 | 21556674.8801
9250 | 19332027.8503 | 167299.6091 | 872039.7633 | 20371367.2227
9251 | 17901770.5162 | 4689611.2059 | 1606190.2253 | 24197571.9475
9252 | 15255319.9275 | 17852267.3492 | 48574.843 | 33156162.1197
9253 | 3207370.2816 | 1481307.8699 | 2369613.3801 | 7058291.5316
9254 | 12329494.3221 | 3062791.1562 | 0 | 15392285.4783
9255 | 6353833.9584 | 9345792.5308 | 4204443.2903 | 19904069.7795
9256 | 13155987.9518 | 0 | 909439.2961 | 14065427.2479
9257 | 5375603.3309 | 6231757.783 | 133808.6497 | 11741169.7637
9258 | 13635499.8248 | 3024575.1975 | 662187.2117 | 17322262.234
9259 | 5160874.5986 | 0 | 11263757.0208 | 16424631.6194
9260 | 3644428.0817 | 0 | 203367.3362 | 3847795.4179
9261 | 8217487.9939 | 0 | 220702.5719 | 8438190.5657
9262 | 2718036.175 | 9969611.3989 | 0 | 12687647.574
9263 | 3740092.1356 | 0 | 1887456.2939 | 5627548.4295
9264 | 3877476.563 | 6979744.7637 | 88492.9331 | 10945714.2598
9265 | 13274186.6678 | 0 | 1871875.9163 | 15146062.5842
9266 | 15263271.9833 | 6503684.0394 | 6776271.543 | 28543227.5657
9267 | 16836984.7672 | 0 | 5925644.9408 | 22762629.708
9268 | 6691991.5536 | 0 | 0 | 6691991.5536
9269 | 3982799.7116 | 3257301.8634 | 97664.9362 | 7337766.5112
9270 | 22203898.6573 | 23523253.1227 | 200688.5869 | 45927840.367
9271 | 1529563.604 | 6403430.3707 | 3933506.6912 | 11866500.6659
9272 | 18119937.7043 | 7014193.5782 | 1875866.7259 | 27009998.0084
9273 | 9550924.2978 | 516542.5764 | 708351.8442 | 10775818.7184
9274 | 4843534.0012 | 3330714.8363 | 2671441.326 | 10845690.1635
9275 | 11800249.9466 | 1261912.5221 | 0 | 13062162.4687
9276 | 3698701.9248 | 5706564.4214 | 6163313.4824 | 15568579.8285
9277 | 5394426.7431 | 18643441.0535 | 3277563.1514 | 27315430.948
9278 | 17596929.2262 | 4629036.9076 | 13593.0102 | 22239559.144
9279 | 7469739.3638 | 2102473.3955 | 1038160.2411 | 10610373.0004
9280 | 8216668.3672 | 12398608.5269 | 2450801.6503 | 23066078.5444
9281 | 12038285.9911 | 13918145.2883 | 4415050.3938 | 30371481.6733
9282 | 6027108.3587 | 3177080.1589 | 2154644.9078 | 11358833.4254
9283 | 2708192.8857 | 7124183.2344 | 3356766.3507 | 13189142.4708
9284 | 5560972.7492 | 31033041.0074 | 513440.3899 | 37107454.1466
9285 | 2127359.0871 | 6625314.5959 | 0 | 8752673.683
9286 | 3363383.6991 | 7327026.2963 | 173428.6353 | 10863838.6307
9287 | 29245297.8353 | 0 | 167615.3286 | 29412913.1638
9288 | 4518884.4309 | 2720297.7939 | 4356482.7568 | 11595664.9816
9289 | 1948788.0084 | 0 | 4655858.8774 | 6604646.8858
9290 | 3338398.7778 | 0 | 1011054.1371 | 4349452.9149
9291 | 1377266.3058 | 5285622.1059 | 2584410.5117 | 9247298.9233
9292 | 4334028.7326 | 8967864.6475 | 148475.5153 | 13450368.8953
9293 | 17388655.0131 | 2821427.5922 | 333176.7559 | 20543259.3612
9294 | 2073213.0402 | 11382535.283 | 2377235.746 | 15832984.0691
9295 | 4822150.961 | 22449778.5762 | 7008976.5588 | 34280906.0959
9296 | 4853048.3521 | 7195981.5443 | 295135.6725 | 12344165.5689
9297 | 14225690.7781 | 0 | 0 | 14225690.7781
9298 | 10542284.2785 | 3462673.5782 | 1619277.8053 | 15624235.662
9299 | 4344701.9709 | 6480452.3339 | 11010061.6751 | 21835215.9799
9300 | 3344242.1232 | 1199986.5294 | 7601296.5487 | 12145525.2013
9301 | 8031020.1306 | 5402395.6196 | 3894842.5909 | 17328258.3411
9302 | 6228137.932 | 5594982.1676 | 934239.0227 | 12757359.1222
9303 | 9383404.9231 | 5852124.1537 | 2333201.7528 | 17568730.8296
9304 | 12634019.7699 | 7451188.6918 | 4668634.7537 | 24753843.2153
9305 | 11018307.1292 | 6159138.0629 | 43232.1881 | 17220677.3802
9306 | 10493489.4236 | 0 | 13786262.143 | 24279751.5665
9307 | 9855230.8726 | 2928893.5313 | 0 | 12784124.4039
9308 | 13325195.4079 | 0 | 587329.9912 | 13912525.3991
9309 | 12367106.9317 | 17797893.5504 | 1886935.3196 | 32051935.8018
9310 | 5294102.584 | 2141539.4731 | 2197968.2462 | 9633610.3032
9311 | 3257610.7126 | 3085577.6952 | 102253.734 | 6445442.1417
9312 | 6865302.5117 | 9689623.3619 | 1253735.269 | 17808661.1426
9313 | 8038071.6694 | 1620726.8052 | 0 | 9658798.4747
9314 | 10890089.9814 | 1609351.1135 | 1790796.4691 | 14290237.564
9315 | 9316545.17 | 12146639.0923 | 1140188.9848 | 22603373.247
9316 | 2925463.4533 | 19252795.8864 | 886535.2955 | 23064794.6352
9317 | 17433688.9635 | 15068740.9229 | 3761755.6702 | 36264185.5566
9318 | 10096904.8392 | 372097.1325 | 0 | 10469001.9717
9319 | 13110773.6861 | 0 | 279752.9367 | 13390526.6228
9320 | 19488418.2441 | 22652443.393 | 1795160.5812 | 43936022.2184
9321 | 11695991.0552 | 0 | 3650834.9481 | 15346826.0033
9322 | 14856640.357 | 2342727.991 | 1625122.6819 | 18824491.0299
9323 | 266708.9726 | 6080070.6001 | 463062.6385 | 6809842.2112
9324 | 5100697.4079 | 10706713.7789 | 1118101.2931 | 16925512.48
9325 | 10585678.6037 | 4569079.0423 | 382781.9784 | 15537539.6245
9326 | 7067833.6813 | 10868447.4169 | 2851315.7586 | 20787596.8569
9327 | 3335433.294 | 3657340.1378 | 1429178.195 | 8421951.6269
9328 | 9791594.6748 | 9994800.8617 | 60091.968 | 19846487.5045
9329 | 486367.975 | 7287508.5614 | 7209866.9533 | 14983743.4897
9330 | 3372033.663 | 16800117.6496 | 7259346.4999 | 27431497.8125
9331 | 1427515.9791 | 20911987.3439 | 0 | 22339503.3231
9332 | 2487045.7751 | 10314596.781 | 1044507.8214 | 13846150.3776
9333 | 1649010.1633 | 2645195.2997 | 228887.3597 | 4523092.8227
9334 | 5196989.7128 | 6151853.2247 | 629664.2295 | 11978507.1671
9335 | 6777801.6894 | 19946772.5018 | 5656161.2983 | 32380735.4895
9336 | 5931376.2354 | 2063362.5662 | 63574.0321 | 8058312.8336
9337 | 24715941.2303 | 8027109.0616 | 124299.641 | 32867349.9329
9338 | 7049289.2763 | 9385814.5717 | 0 | 16435103.8479
9339 | 15427013.6242 | 0 | 818535.2871 | 16245548.9113
9340 | 6097654.9166 | 9345795.4645 | 2191441.2343 | 17634891.6154
9341 | 4299788.1232 | 2092043.5981 | 8616507.8919 | 15008339.6132
9342 | 11738460.4816 | 4317446.5826 | 16794764.9896 | 32850672.0538
9343 | 5313800.8611 | 993991.1025 | 18224707.7433 | 24532499.7069
9344 | 22242919.3763 | 9195862.7192 | 786654.9322 | 32225437.0277
9345 | 9298589.0522 | 3130249.7673 | 408577.7908 | 12837416.6103
9346 | 17371903.5494 | 0 | 439555.3293 | 17811458.8787
9347 | 18386482.7379 | 16020927.1388 | 562926.3021 | 34970336.1788
9348 | 4315218.0063 | 12860447.3729 | 0 | 17175665.3792
9349 | 5104315.7822 | 22914576.7767 | 5852076.6452 | 33870969.2041
9350 | 7952040.6219 | 10089676.2972 | 1684555.7886 | 19726272.7077
9351 | 3660779.4162 | 3810623.6982 | 0 | 7471403.1145
9352 | 4448887.6783 | 5395487.7793 | 4750827.6982 | 14595203.1558
9353 | 12687161.5417 | 24163730.4059 | 126362.581 | 36977254.5286
9354 | 3799415.8452 | 8145048.6321 | 5858937.2502 | 17803401.7275
9355 | 2144206.6238 | 23562488.641 | 2605429.0283 | 28312124.2931
9356 | 18396405.3544 | 14213898.4208 | 241235.0831 | 32851538.8583
9357 | 2907587.1715 | 13470254.5249 | 287363.6396 | 16665205.336
9358 | 7261488.9915 | 8957274.1215 | 12997983.4514 | 29216746.5644
9359 | 9466549.6084 | 47685106.1444 | 2146647.4317 | 59298303.1845
9360 | 2673473.3899 | 0 | 3690420.2848 | 6363893.6747
9361 | 3544573.7112 | 11064147.229 | 6899452.0078 | 21508172.948
9362 | 432074.0225 | 1761161.5388 | 15720846.8242 | 17914082.3854
9363 | 6671258.0205 | 3287542.9816 | 7531149.3689 | 17489950.371
9364 | 27812584.2747 | 32123952.8689 | 91749.0429 | 60028286.1865
9365 | 19269733.5032 | 5426694.1916 | 0 | 24696427.6948
9366 | 2983041.5761 | 9289978.5227 | 0 | 12273020.0988
9367 | 4179601.5216 | 3654756.2658 | 3962823.4385 | 11797181.2259
9368 | 6053198.0254 | 8778723.1196 | 1804679.6624 | 16636600.8074
9369 | 5861257.0731 | 1547232.0767 | 877920.9083 | 8286410.0581
9370 | 9589613.5585 | 3307406.0923 | 199416.9229 | 13096436.5738
9371 | 7463935.083 | 14184831.3537 | 37404.8985 | 21686171.3351
9372 | 6119472.449 | 403708.8084 | 0 | 6523181.2574
9373 | 2250652.5678 | 3375377.6619 | 1535840.8627 | 7161871.0924
9374 | 2002508.1023 | 19161663.6032 | 306957.7532 | 21471129.4588
9375 | 43659689.5469 | 0 | 236760.4315 | 43896449.9784
9376 | 4145531.7415 | 8497860.5557 | 108427.1255 | 12751819.4228
9377 | 4696974.8877 | 0 | 0 | 4696974.8877
9378 | 10549483.7491 | 3771415.6224 | 2971040.3969 | 17291939.7684
9379 | 2599002.0531 | 0 | 4604489.852 | 7203491.9051
9380 | 6375630.8196 | 19195153.8282 | 90784.156 | 25661568.8038
9381 | 9736828.3028 | 3477549.9654 | 0 | 13214378.2682
9382 | 12384630.4341 | 14009433.1195 | 873277.774 | 27267341.3275
9383 | 7307106.037 | 15424503.4759 | 160634.5831 | 22892244.096
9384 | 18805182.4481 | 28885297.3887 | 5388485.9237 | 53078965.7605
9385 | 739833.8332 | 3290885.9729 | 639728.6583 | 4670448.4643
9386 | 14737172.6277 | 1852331.7801 | 3890151.7948 | 20479656.2025
9387 | 13282222.9342 | 4363438.6947 | 269935.5445 | 17915597.1734
9388 | 7287148.7965 | 7935520.1798 | 989829.3463 | 16212498.3226
9389 | 4465713.0989 | 0 | 2026002.06 | 6491715.159
9390 | 1392469.3782 | 13256117.8424 | 60944.3956 | 14709531.6162
9391 | 5682046.3013 | 0 | 688513.7543 | 6370560.0556
9392 | 5128490.2484 | 2855346.3866 | 105513.2789 | 8089349.9139
9393 | 6308735.865 | 1719568.8125 | 0 | 8028304.6775
9394 | 6269001.9612 | 2980722.3183 | 0 | 9249724.2796
9395 | 6799097.7631 | 2128754.4829 | 428467.6459 | 9356319.8919
9396 | 9239693.3382 | 7409482.8116 | 70343.8967 | 16719520.0464
9397 | 6399756.8729 | 6332606.7902 | 7090230.4819 | 19822594.1449
9398 | 13414995.3493 | 2450748.459 | 8694611.992 | 24560355.8003
9399 | 7536664.2227 | 4882810.9915 | 162031.1917 | 12581506.4059
9400 | 2768300.3221 | 0 | 2566294.0375 | 5334594.3597
9401 | 8583357.268 | 3893030.8256 | 1096873.6461 | 13573261.7397
9402 | 14669769.2477 | 5445708.1867 | 1010907.3004 | 21126384.7348
9403 | 6377164.5737 | 3417934.3925 | 2260086.7945 | 12055185.7607
9404 | 5737881.4945 | 2370681.4085 | 3410587.6888 | 11519150.5918
9405 | 10264634.4445 | 3164224.6608 | 178941.6498 | 13607800.7551
9406 | 8491469.8399 | 1299409.6398 | 5083442.4664 | 14874321.9461
9407 | 5222587.9997 | 4459045.6863 | 888905.3106 | 10570538.9966
9408 | 3506600.2633 | 9183198.6966 | 2818669.3429 | 15508468.3027
9409 | 904961.8301 | 2703456.964 | 227893.0505 | 3836311.8446
9410 | 16953697.3329 | 5899619.8572 | 26650.3722 | 22879967.5624
9411 | 10685843.7128 | 15090378.0184 | 1975998.3978 | 27752220.129
9412 | 3781489.0621 | 4784621.669 | 495740.4851 | 9061851.2162
9413 | 206052.7643 | 7490424.1512 | 1044098.9212 | 8740575.8367
9414 | 11401322.4258 | 9456514.7237 | 2095126.0106 | 22952963.1601
9415 | 4268254.1483 | 10230784.4595 | 1319123.1723 | 15818161.78
9416 | 12156350.7544 | 0 | 273420.1781 | 12429770.9325
9417 | 12834893.5761 | 8819395.0091 | 497947.252 | 22152235.8372
9418 | 561469.1005 | 6352441.6441 | 0 | 6913910.7446
9419 | 2600090.3002 | 5040585.4926 | 0 | 7640675.7928
9420 | 12437544.4495 | 10552147.9557 | 315884.8874 | 23305577.2926
9421 | 4516986.533 | 946051.4314 | 2668659.318 | 8131697.2825
9422 | 2865057.0091 | 4097266.3031 | 0 | 6962323.3122
9423 | 4842642.7104 | 0 | 38591.7263 | 4881234.4367
9424 | 16604882.2647 | 30781489.4978 | 1254162.3233 | 48640534.0859
9425 | 21033905.1906 | 7285963.0967 | 2059823.2734 | 30379691.5607
9426 | 3372320.5839 | 31866616.5524 | 412061.1802 | 35650998.3165
9427 | 11686277.1651 | 815566.8088 | 0 | 12501843.9739
9428 | 16349797.4239 | 22142145.9013 | 339638.393 | 38831581.7182
9429 | 3881799.3825 | 10146709.5042 | 0 | 14028508.8867
9430 | 19478840.4481 | 10690063.8258 | 3153187.8794 | 33322092.1532
9431 | 11225850.3832 | 0 | 579646.4985 | 11805496.8817
9432 | 24730133.8838 | 2806696.8635 | 997353.057 | 28534183.8043
9433 | 3605458.2952 | 2256040.3246 | 241453.7229 | 6102952.3427
9434 | 11100507.7833 | 5984461.9293 | 7858087.5222 | 24943057.2349
9435 | 2197123.2437 | 5151439.7512 | 39392.4785 | 7387955.4734
9436 | 15198718.8745 | 2519623.9395 | 1192696.5277 | 18911039.3416
9437 | 5293059.74 | 6090813.1812 | 430916.4522 | 11814789.3734
9438 | 17725874.76 | 3003349.448 | 665185.5449 | 21394409.753
9439 | 13827164.0285 | 8811933.9165 | 4426526.647 | 27065624.592
9440 | 12658565.3732 | 27995381.4083 | 729423.6722 | 41383370.4537
9441 | 8068226.858 | 13784711.3963 | 21222.2628 | 21874160.5171
9442 | 17402885.5065 | 23351049.0686 | 1558346.8082 | 42312281.3834
9443 | 9381502.9473 | 3751731.1868 | 6122010.4516 | 19255244.5857
9444 | 1888580.0538 | 0 | 967667.1363 | 2856247.1901
9445 | 4201241.6801 | 3266668.0882 | 1657652.1815 | 9125561.9498
9446 | 9191065.7252 | 15062970.7239 | 81685.8937 | 24335722.3428
9447 | 3793792.6567 | 1791859.7474 | 1038987.6969 | 6624640.1009
9448 | 6751724.8419 | 0 | 3700039.9258 | 10451764.7676
9449 | 3502622.8895 | 2919743.798 | 1533306.0187 | 7955672.7062
9450 | 5201830.9205 | 0 | 5161533.4362 | 10363364.3567
9451 | 4460974.8327 | 10043254.0126 | 0 | 14504228.8453
9452 | 1203711.5269 | 8092241.746 | 275941.7527 | 9571895.0256
9453 | 2392326.2799 | 21696754.6332 | 2945464.6795 | 27034545.5926
9454 | 12254322.3329 | 1251669.1939 | 144504.6987 | 13650496.2254
9455 | 14337767.3432 | 6745978.4803 | 1773547.1674 | 22857292.9909
9456 | 2211583.8137 | 6511889.1221 | 6287651.4129 | 15011124.3487
9457 | 2554512.454 | 0 | 821826.5422 | 3376338.9962
9458 | 22992899.9512 | 8710701.9538 | 660351.1052 | 32363953.0103
9459 | 7121043.4186 | 3563316.8127 | 785756.5578 | 11470116.7891
9460 | 2193650.9146 | 1681762.1446 | 2834892.7396 | 6710305.7988
9461 | 11214660.2924 | 8853337.2774 | 593150.7396 | 20661148.3094
9462 | 9641380.823 | 0 | 93588.3455 | 9734969.1685
9463 | 16440596.0502 | 4037620.5212 | 2214885.7472 | 22693102.3186
9464 | 5233287.9534 | 17491836.994 | 767895.9322 | 23493020.8797
9465 | 5660991.0637 | 0 | 2207088.9047 | 7868079.9684
9466 | 5203552.8922 | 8431942.8593 | 2318780.1787 | 15954275.9301
9467 | 2369235.4232 | 5052356.523 | 976781.649 | 8398373.5952
9468 | 2080143.7018 | 870990.0312 | 1762047.355 | 4713181.088
9469 | 11131264.8001 | 8344913.8872 | 0 | 19476178.6872
9470 | 158255.524 | 30547319.8406 | 0 | 30705575.3646
9471 | 25054895.4784 | 8389051.5158 | 956904.6722 | 34400851.6664
9472 | 5628420.2831 | 12933664.6216 | 3375733.9865 | 21937818.8912
9473 | 8334834.6363 | 0 | 2075673.3072 | 10410507.9435
9474 | 689131.9469 | 12730664.6355 | 1068937.1794 | 14488733.7618
9475 | 17575606.094 | 3532088.3838 | 0 | 21107694.4778
9476 | 4814919.7852 | 3512963.4855 | 917964.6846 | 9245847.9552
9477 | 3880618.62 | 37801862.8694 | 1683220.6582 | 43365702.1476
9478 | 3235556.8873 | 10734936.0746 | 227969.0073 | 14198461.9692
9479 | 12119680.1999 | 13393251.2074 | 2337795.3237 | 27850726.731
9480 | 9273262.0038 | 0 | 1311575.017 | 10584837.0208
9481 | 16637866.1216 | 7278281.7514 | 852230.9355 | 24768378.8086
9482 | 10623176.5059 | 8110840.785 | 4486302.3505 | 23220319.6414
9483 | 2983171.284 | 8233992.3408 | 6671353.0962 | 17888516.7211
9484 | 1066198.0592 | 5481872.8171 | 6472850.7754 | 13020921.6517
9485 | 8582960.5873 | 20739040.299 | 1094305.2161 | 30416306.1024
9486 | 16251760.8131 | 6674466.4936 | 3991022.6135 | 26917249.9202
9487 | 8981360.1598 | 2272513.7608 | 0 | 11253873.9206
9488 | 16872189.1363 | 5862060.4504 | 6829218.3567 | 29563467.9434
9489 | 4744352.3992 | 8822551.2274 | 2746543.1659 | 16313446.7925
9490 | 14477695.5597 | 22300215.882 | 1249165.2372 | 38027076.6789
9491 | 10703600.6772 | 35368101.8127 | 0 | 46071702.4899
9492 | 7121458.6406 | 8491919.6471 | 2635962.5357 | 18249340.8233
9493 | 3256566.4692 | 0 | 546845.8238 | 3803412.293
9494 | 19283299.6514 | 8558604.8066 | 10991319.6792 | 38833224.1372
9495 | 5160456.7765 | 6311807.0299 | 1828157.6606 | 13300421.4671
9496 | 1999985.0779 | 0 | 1666148.6434 | 3666133.7213
9497 | 4755246.5594 | 0 | 1600437.996 | 6355684.5554
9498 | 39926817.647 | 20826507.8815 | 250773.7079 | 61004099.2364
9499 | 2694572.4971 | 6102824.2047 | 2532862.2731 | 11330258.9748
9500 | 14662717.6162 | 14288051.2923 | 1979033.0235 | 30929801.932
9501 | 5646430.7409 | 3848792.0209 | 2760830.2601 | 12256053.022
9502 | 5813864.8316 | 8285103.7389 | 14269308.6498 | 28368277.2202
9503 | 2175386.1143 | 0 | 1359773.1574 | 3535159.2717
9504 | 4165618.2981 | 16155532.0366 | 923896.3803 | 21245046.715
9505 | 4902612.7427 | 0 | 1879145.6115 | 6781758.3542
9506 | 10246932.6876 | 6642900.4311 | 258835.7064 | 17148668.8251
9507 | 6756298.5706 | 15602125.4948 | 1624371.2573 | 23982795.3227
9508 | 7430296.6053 | 11263442.9696 | 0 | 18693739.5749
9509 | 4909009.162 | 10452526.9547 | 1412335.7497 | 16773871.8665
9510 | 10804964.3436 | 10825839.6291 | 125375.5088 | 21756179.4815
9511 | 16055083.0898 | 10751524.1556 | 2931002.1692 | 29737609.4146
9512 | 5346900.7793 | 5854749.5241 | 136802.0997 | 11338452.4031
9513 | 3737129.9807 | 0 | 759939.8915 | 4497069.8723
9514 | 3597608.4364 | 14161165.6759 | 128021.6924 | 17886795.8047
9515 | 3629931.4798 | 3453752.9698 | 494233.2056 | 7577917.6552
9516 | 13999415.8005 | 5437255.6151 | 2906543.6386 | 22343215.0542
9517 | 1242428.7993 | 0 | 0 | 1242428.7993
9518 | 1175231.3916 | 11242905.8721 | 1328249.9783 | 13746387.242
9519 | 11315160.554 | 9297960.2125 | 3687316.0828 | 24300436.8492
9520 | 16107338.1344 | 16431588.5878 | 45994761.1227 | 78533687.8449
9521 | 5524559.0144 | 14758021.7442 | 0 | 20282580.7587
9522 | 7627940.8588 | 9530612.2792 | 3497132.0467 | 20655685.1847
9523 | 4535264.2693 | 21174372.8525 | 1473734.3613 | 27183371.4831
9524 | 13595159.764 | 3510292.9097 | 325334.2929 | 17430786.9666
9525 | 2867534.4649 | 9707351.3565 | 1997897.9062 | 14572783.7276
9526 | 11744422.9574 | 15557464.5023 | 1800115.6741 | 29102003.1339
9527 | 1765125.3154 | 10896260.9944 | 2615993.837 | 15277380.1469
9528 | 5021256.3276 | 2576350.7271 | 73655.1818 | 7671262.2365
9529 | 6436973.4927 | 24722720.6083 | 1721271.4837 | 32880965.5847
9530 | 16218501.9372 | 7737524.0861 | 4842907.5532 | 28798933.5764
9531 | 470490.0311 | 2862394.613 | 6773102.4646 | 10105987.1087
9532 | 11170516.9807 | 15748397.0504 | 4088884.9342 | 31007798.9654
9533 | 1236478.6782 | 2888868.1653 | 0 | 4125346.8435
9534 | 10657995.6945 | 0 | 0 | 10657995.6945
9535 | 7811446.0665 | 5475805.7352 | 583962.4615 | 13871214.2633
9536 | 8799401.4619 | 0 | 33168.3597 | 8832569.8217
9537 | 10753581.0843 | 1961694.9921 | 1490687.5178 | 14205963.5942
9538 | 5696596.2109 | 10901373.7408 | 240920.6835 | 16838890.6353
9539 | 2546301.552 | 12221309.4821 | 1532738.56 | 16300349.5941
9540 | 724287.9097 | 15993214.1276 | 9066126.7892 | 25783628.8264
9541 | 32329596.6442 | 30055428.7465 | 0 | 62385025.3907
9542 | 1235943.5198 | 17075630.5237 | 3058343.2315 | 21369917.275
9543 | 13257296.5412 | 8692707.4378 | 15134376.1649 | 37084380.1439
9544 | 13015113.4983 | 0 | 163680.9489 | 13178794.4472
9545 | 3007097.7707 | 951975.3386 | 1373405.3001 | 5332478.4094
9546 | 1998868.5901 | 6026385.6806 | 987902.0315 | 9013156.3021
9547 | 5125319.0683 | 10334041.9722 | 522991.2575 | 15982352.2979
9548 | 15414508.4098 | 3582882.2999 | 56393.9652 | 19053784.6749
9549 | 1703455.6963 | 10814814.5659 | 2470736.5687 | 14989006.8309
9550 | 2606087.3869 | 0 | 0 | 2606087.3869
9551 | 5687745.3193 | 7514219.3838 | 1321973.215 | 14523937.9181
9552 | 737843.8022 | 7500038.0377 | 41999.4544 | 8279881.2943
9553 | 14132151.5297 | 5064073.9386 | 7739057.2982 | 26935282.7664
9554 | 24310876.537 | 3502045.393 | 0 | 27812921.93
9555 | 9746373.1696 | 6080720.1175 | 82911.3432 | 15910004.6303
9556 | 5883794.5208 | 17031936.4621 | 0 | 22915730.9829
9557 | 3871370.1805 | 2013614.2135 | 2327718.2051 | 8212702.5991
9558 | 8561108.3 | 19456686.7226 | 712283.4583 | 28730078.481
9559 | 664840.1095 | 4937616.1222 | 1554147.5456 | 7156603.7773
9560 | 12114356.5051 | 8578950.2591 | 2332964.592 | 23026271.3562
9561 | 6702645.7555 | 945185.2311 | 1264264.4864 | 8912095.473
9562 | 33230616.7604 | 0 | 2528768.986 | 35759385.7464
9563 | 30452296.6994 | 5156187.7817 | 2261569.9914 | 37870054.4725
9564 | 15778634.0213 | 5043103.0732 | 1024487.7128 | 21846224.8072
9565 | 13685459.0997 | 6340551.2364 | 951888.2429 | 20977898.579
9566 | 5857005.159 | 2728124.6087 | 39382.5931 | 8624512.3608
9567 | 5717848.0385 | 0 | 11307197.0129 | 17025045.0515
9568 | 11685016.7132 | 2619890.8868 | 1429395.8585 | 15734303.4586
9569 | 22899882.6305 | 6018717.5566 | 746841.9612 | 29665442.1483
9570 | 9764845.6538 | 15989400.8646 | 0 | 25754246.5184
9571 | 12618341.2961 | 7306470.6463 | 3660491.5357 | 23585303.4781
9572 | 35484023.6714 | 6080571.8232 | 4816408.4092 | 46381003.9038
9573 | 4927603.4599 | 7176550.4737 | 857842.7363 | 12961996.67
9574 | 8958206.8449 | 17795416.2519 | 250336.9425 | 27003960.0393
9575 | 1165015.5126 | 0 | 9965640.0042 | 11130655.5168
9576 | 5981134.5871 | 28056502.4268 | 10126479.8832 | 44164116.8972
9577 | 22284812.7128 | 10102690.781 | 3505643.029 | 35893146.5228
9578 | 6076641.1096 | 10360679.2483 | 2247379.2031 | 18684699.561
9579 | 2009503.2166 | 4911049.8072 | 1925359.1623 | 8845912.1861
9580 | 7189659.216 | 0 | 652620.4928 | 7842279.7087
9581 | 15819814.9537 | 3581404.7501 | 2611504.0439 | 22012723.7477
9582 | 8957931.5664 | 5770069.5746 | 2146503.6597 | 16874504.8007
9583 | 7250833.2243 | 9186135.1886 | 0 | 16436968.413
9584 | 14538066.6154 | 1520603.6351 | 521817.2733 | 16580487.5238
9585 | 4683553.9827 | 50043756.9393 | 17572575.8817 | 72299886.8037
9586 | 6112273.774 | 9788619.9918 | 0 | 15900893.7658
9587 | 2601526.8719 | 5538066.5881 | 0 | 8139593.46
9588 | 15158711.8174 | 3598149.0127 | 0 | 18756860.8301
9589 | 2833286.2994 | 2978813.7176 | 9726021.0357 | 15538121.0527
9590 | 2993845.3873 | 32633538.5958 | 303562.265 | 35930946.2482
9591 | 1428715.6624 | 7280214.7995 | 12152366.9398 | 20861297.4017
9592 | 4451194.4163 | 0 | 6283842.77 | 10735037.1863
9593 | 25073440.2111 | 9438542.1803 | 62509.9506 | 34574492.342
9594 | 4991901.3191 | 0 | 5332672.8782 | 10324574.1973
9595 | 4062429.8328 | 2691056.6015 | 0 | 6753486.4343
9596 | 12139461.452 | 4271843.0516 | 955410.2123 | 17366714.716
9597 | 14638520.4119 | 5972122.7566 | 2108697.7328 | 22719340.9013
9598 | 8392956.4446 | 0 | 2370565.5085 | 10763521.9532
9599 | 3795330.7324 | 0 | 1511388.9795 | 5306719.7119
9600 | 5560136.4142 | 10586592.711 | 0 | 16146729.1252
9601 | 3072587.4146 | 9046418.0223 | 744661.3972 | 12863666.8341
9602 | 11464028.2179 | 9787978.5526 | 0 | 21252006.7705
9603 | 3666213.6336 | 15282611.7867 | 3524202.5913 | 22473028.0115
9604 | 1880171.7521 | 0 | 0 | 1880171.7521
9605 | 13393736.2455 | 5126057.9555 | 938809.0972 | 19458603.2981
9606 | 8382682.0123 | 3054062.668 | 1364205.8946 | 12800950.5748
9607 | 9463961.2294 | 12755875.5886 | 3353841.7634 | 25573678.5814
9608 | 7807556.5841 | 11073648.7725 | 0 | 18881205.3566
9609 | 2238269.3096 | 10842338.5523 | 92519.1246 | 13173126.9865
9610 | 4539831.0581 | 6583815.1344 | 4286788.9928 | 15410435.1853
9611 | 7392117.7749 | 14625380.2382 | 0 | 22017498.0131
9612 | 21825414.9182 | 3681210.1386 | 0 | 25506625.0568
9613 | 7451698.5693 | 4717578.313 | 71994.6883 | 12241271.5707
9614 | 727200.841 | 13618862.6368 | 3591384.3311 | 17937447.8089
9615 | 7537881.9633 | 3321049.9956 | 10180298.1673 | 21039230.1262
9616 | 4768296.7447 | 1980236.817 | 1617575.4282 | 8366108.99
9617 | 4557502.4859 | 16167733.4388 | 3110439.339 | 23835675.2638
9618 | 8201640.6124 | 2250894.4271 | 7297884.2612 | 17750419.3007
9619 | 3525165.3873 | 5041195.4816 | 2005058.8385 | 10571419.7073
9620 | 4350391.1185 | 5313006.7889 | 2882807.7434 | 12546205.6508
9621 | 4059801.3153 | 10581696.7054 | 5330661.6746 | 19972159.6953
9622 | 14102585.0843 | 0 | 63823.3995 | 14166408.4838
9623 | 2527510.3612 | 4948525.6379 | 3503101.132 | 10979137.1311
9624 | 15361481.4361 | 6813298.4603 | 3161227.9264 | 25336007.8228
9625 | 5333283.6287 | 0 | 2362572.5187 | 7695856.1475
9626 | 2124324.4373 | 0 | 3388377.73 | 5512702.1673
9627 | 11405050.7152 | 13002999.6164 | 1381320.6794 | 25789371.011
9628 | 12123305.3815 | 734840.4351 | 400854.4353 | 13259000.252
9629 | 4431567.8995 | 19188466.0829 | 0 | 23620033.9824
9630 | 5034625.9869 | 9255599.9038 | 9568188.9263 | 23858414.817
9631 | 5854967.5775 | 12379035.3475 | 945958.5316 | 19179961.4566
9632 | 362254.2657 | 10493230.3178 | 4936192.133 | 15791676.7165
9633 | 1548381.2804 | 15177121.4848 | 0 | 16725502.7652
9634 | 3111078.4802 | 3622786.7943 | 145814.5753 | 6879679.8497
9635 | 9504362.8115 | 0 | 2979236.3478 | 12483599.1593
9636 | 10104124.033 | 2051529.0354 | 3056163.1994 | 15211816.2678
9637 | 24288747.4533 | 14434445.4689 | 657506.9588 | 39380699.881
9638 | 1669384.2422 | 5101135.3681 | 473087.4291 | 7243607.0394
9639 | 26140311.1392 | 2615728.847 | 4658393.2942 | 33414433.2804
9640 | 2203810.4045 | 20791084.9363 | 1598009.6749 | 24592905.0157
9641 | 3711085.8577 | 0 | 1824863.7112 | 5535949.5689
9642 | 6577326.1484 | 3374924.196 | 68740.7497 | 10020991.0941
9643 | 4339177.9825 | 12127237.8706 | 4719046.4868 | 21185462.34
9644 | 3679499.0116 | 3965557.2743 | 2228646.5336 | 9873702.8195
9645 | 5048423.6909 | 7923453.6042 | 0 | 12971877.2951
9646 | 6481508.4069 | 13310525.5675 | 77665.5854 | 19869699.5599
9647 | 12678044.9118 | 16426168.2199 | 31963359.1842 | 61067572.316
9648 | 7501108.11 | 4374748.5887 | 285215.1991 | 12161071.8978
9649 | 5015404.6875 | 8889403.8506 | 261465.4056 | 14166273.9437
9650 | 12127339.2478 | 0 | 9826699.9971 | 21954039.2449
9651 | 4198068.6045 | 12982118.6091 | 0 | 17180187.2136
9652 | 5256189.6885 | 0 | 0 | 5256189.6885
9653 | 7809468.7953 | 7016040.7963 | 912372.241 | 15737881.8326
9654 | 38796175.2501 | 10030088.7915 | 1286922.4045 | 50113186.4461
9655 | 1293200.683 | 0 | 5146793.6707 | 6439994.3538
9656 | 2954713.6004 | 3926688.1113 | 3490143.6872 | 10371545.3989
9657 | 4220143.5162 | 0 | 2166677.836 | 6386821.3521
9658 | 2379954.6014 | 8422321.0582 | 0 | 10802275.6595
9659 | 6597572.0845 | 17434184.8608 | 541568.7125 | 24573325.6578
9660 | 6336971.3368 | 14131824.6906 | 25820.2221 | 20494616.2495
9661 | 1684011.0154 | 14692426.4962 | 15632057.5966 | 32008495.1082
9662 | 7644105.9936 | 10282464.805 | 580006.9154 | 18506577.7139
9663 | 6895475.8024 | 4824969.4374 | 5554069.5404 | 17274514.7802
9664 | 3178843.9455 | 3344174.5023 | 6431107.7566 | 12954126.2043
9665 | 5969722.2934 | 12736635.8046 | 0 | 18706358.098
9666 | 5730903.5315 | 2275828.0919 | 2844498.8921 | 10851230.5155
9667 | 5181936.7077 | 16082155.7924 | 6958041.0688 | 28222133.5689
9668 | 10275698.1714 | 16106818.5203 | 1148812.2462 | 27531328.9379
9669 | 4397560.1061 | 12212156.893 | 1694091.601 | 18303808.6001
9670 | 10005029.3866 | 18250162.7481 | 2236932.2403 | 30492124.375
9671 | 21110862.6171 | 2793732.628 | 3222280.3053 | 27126875.5504
9672 | 5189225.3912 | 3062098.2354 | 31314.8063 | 8282638.4329
9673 | 3200821.2351 | 6717452.312 | 0 | 9918273.5471
9674 | 800762.765 | 5151444.7452 | 2029513.6655 | 7981721.1757
9675 | 3627588.5955 | 3561502.2262 | 168314.2373 | 7357405.059
9676 | 5608959.0407 | 6908894.914 | 731944.0204 | 13249797.9751
9677 | 9743526.9429 | 5010515.101 | 0 | 14754042.0439
9678 | 2194834.5682 | 0 | 316001.8582 | 2510836.4264
9679 | 7081742.3375 | 0 | 0 | 7081742.3375
9680 | 4562799.8145 | 1689522.8818 | 4872208.4379 | 11124531.1342
9681 | 3261583.9918 | 15829525.6724 | 132777.6073 | 19223887.2715
9682 | 9369765.4694 | 0 | 11136195.1701 | 20505960.6395
9683 | 5742732.317 | 4225336.866 | 50657.698 | 10018726.881
9684 | 6798085.8672 | 6978093.4552 | 8658212.9563 | 22434392.2787
9685 | 6941615.8867 | 1462872.1717 | 2825464.8168 | 11229952.8752
9686 | 7636753.3783 | 13037063.0768 | 27299.9768 | 20701116.432
9687 | 775990.8358 | 3592117.0284 | 1744095.3257 | 6112203.1899
9688 | 9426344.9489 | 4299458.2831 | 552735.1302 | 14278538.3622
9689 | 42874795.8175 | 0 | 472653.296 | 43347449.1135
9690 | 2628737.3536 | 0 | 3800961.6349 | 6429698.9885
9691 | 25162465.459 | 13566403.7202 | 1883479.8482 | 40612349.0274
9692 | 8600816.7297 | 8846125.4113 | 1040716.9057 | 18487659.0467
9693 | 19541642.0789 | 8334564.4152 | 63847.5857 | 27940054.0797
9694 | 6562871.6792 | 6048770.6139 | 457096.5462 | 13068738.8393
9695 | 1439006.6573 | 6763796.1946 | 256370.7757 | 8459173.6277
9696 | 2602992.9803 | 6772808.1035 | 830676.2941 | 10206477.3779
9697 | 3707634.899 | 753025.6331 | 6896894.3645 | 11357554.8967
9698 | 16014318.6962 | 1157727.8054 | 215693.0851 | 17387739.5867
9699 | 19091766.2329 | 6974294.8574 | 3039227.1017 | 29105288.192
9700 | 183824.8658 | 2327369.2883 | 5279342.6699 | 7790536.8239
9701 | 8715986.2968 | 0 | 1370750.9025 | 10086737.1992
9702 | 19495045.1243 | 4490054.3808 | 302565.4883 | 24287664.9934
9703 | 5538918.6731 | 20910979.3649 | 611804.1357 | 27061702.1737
9704 | 20468211.9961 | 18500423.3676 | 3833357.0979 | 42801992.4616
9705 | 2168277.1572 | 9643246.9622 | 9915206.0842 | 21726730.2037
9706 | 3906246.7106 | 12215463.0803 | 0 | 16121709.7909
9707 | 11473305.1481 | 923642.3314 | 0 | 12396947.4796
9708 | 4147385.5246 | 31192447.09 | 296871.5832 | 35636704.1978
9709 | 2730960 | 6140281.108 | 688840.3713 | 9560081.4793
9710 | 3064480.5921 | 0 | 4306025.7954 | 7370506.3875
9711 | 1276315.6325 | 4030730.1067 | 0 | 5307045.7392
9712 | 10740086.4835 | 6400445.4444 | 3345769.2719 | 20486301.1999
9713 | 9778697.5835 | 139801.945 | 1473442.9506 | 11391942.4791
9714 | 14833779.093 | 11305921.4049 | 1316044.3496 | 27455744.8475
9715 | 1217149.7921 | 3075133.6843 | 508510.5983 | 4800794.0747
9716 | 9520400.654 | 1656652.4319 | 2117435.514 | 13294488.5999
9717 | 9190007.1051 | 5156986.8818 | 1607218.6974 | 15954212.6843
9718 | 9074075.4331 | 1518423.4709 | 0 | 10592498.9041
9719 | 12944270.5347 | 6364428.8137 | 1752341.1672 | 21061040.5156
9720 | 6890685.5513 | 0 | 1268495.3707 | 8159180.922
9721 | 188204.2124 | 2660937.4125 | 1918244.4585 | 4767386.0834
9722 | 9330977.4521 | 24612122.2985 | 270110.2841 | 34213210.0348
9723 | 10081375.5391 | 0 | 61400.7177 | 10142776.2568
9724 | 9866862.404 | 11812704.2275 | 180315.0088 | 21859881.6402
9725 | 8162834.7185 | 2532376.4865 | 170027.5829 | 10865238.788
9726 | 2843516.4632 | 8694226.6161 | 803645.6229 | 12341388.7023
9727 | 6677261.8561 | 6727137.1896 | 311613.2163 | 13716012.2621
9728 | 9801578.8486 | 1487435.7144 | 2160205.4472 | 13449220.0102
9729 | 11591187.4653 | 16742850.4126 | 791620.2216 | 29125658.0995
9730 | 13793135.8583 | 15364234.9345 | 248591.2059 | 29405961.9987
9731 | 7497539.869 | 682113.3437 | 7887232.8507 | 16066886.0634
9732 | 3028332.2148 | 3839320.604 | 1508445.3118 | 8376098.1306
9733 | 1264271.7763 | 7441458.1242 | 2785314.9849 | 11491044.8854
9734 | 2369798.4508 | 5342163.1475 | 9036975.6494 | 16748937.2477
9735 | 5017399.5233 | 4596633.1576 | 1458248.3221 | 11072281.003
9736 | 6782200.7061 | 10993338.3845 | 1108790.6159 | 18884329.7066
9737 | 1292744.6666 | 0 | 2223399.2791 | 3516143.9457
9738 | 7419344.3337 | 2849545.1756 | 547570.6672 | 10816460.1765
9739 | 18304900.2646 | 26195603.267 | 188484.8373 | 44688988.369
9740 | 13098880.58 | 5437182.6765 | 93631.3966 | 18629694.6531
9741 | 16029147.2297 | 13717691.6196 | 1953263.6989 | 31700102.5482
9742 | 2252131.6526 | 4957245.2671 | 1344437.7357 | 8553814.6555
9743 | 19123655.4613 | 5237773.9361 | 651648.625 | 25013078.0224
9744 | 6039092.8732 | 5531592.0476 | 122534.8366 | 11693219.7574
9745 | 3921389.7989 | 6196082.1933 | 311272.9389 | 10428744.9311
9746 | 4882912.8017 | 3639423.6482 | 809639.9339 | 9331976.3838
9747 | 12150763.9135 | 1207359.2189 | 1545576.2254 | 14903699.3579
9748 | 4651611.4678 | 0 | 5936657.1244 | 10588268.5922
9749 | 2622112.3661 | 29974156.9039 | 0 | 32596269.27
9750 | 3298040.9233 | 15771072.1291 | 0 | 19069113.0523
9751 | 8763874.1129 | 10150783.3131 | 1072233.9319 | 19986891.358
9752 | 13048274.8095 | 5815939.0684 | 1819009.3209 | 20683223.1988
9753 | 3890006.7055 | 1023510.3934 | 1308356.6753 | 6221873.7742
9754 | 7302418.3542 | 9831413.6822 | 12168394.6851 | 29302226.7215
9755 | 3153092.0447 | 16009673.0772 | 4247242.1986 | 23410007.3206
9756 | 9785556.8281 | 14363232.8614 | 532116.4258 | 24680906.1153
9757 | 12901514.9414 | 20737451.1534 | 12651729.4844 | 46290695.5791
9758 | 7136595.3752 | 13314038.5133 | 5674800.3542 | 26125434.2427
9759 | 23715487.336 | 0 | 2238680.4685 | 25954167.8045
9760 | 7597339.431 | 11371101.3571 | 3012600.8759 | 21981041.664
9761 | 5350090.2864 | 6445340.5622 | 8929764.4231 | 20725195.2716
9762 | 10452702.6287 | 7612136.5058 | 2805449.8506 | 20870288.985
9763 | 4444640.6445 | 15644613.8814 | 3564999.5775 | 23654254.1035
9764 | 6087534.3267 | 3410711.0029 | 7942809.1562 | 17441054.4859
9765 | 7144531.6214 | 6144456.6635 | 6306558.4081 | 19595546.693
9766 | 9314144.986 | 19697156.5856 | 0 | 29011301.5715
9767 | 1370591.3179 | 17796025.9453 | 994648.3928 | 20161265.656
9768 | 5739088.2505 | 15993722.9034 | 1355871.8802 | 23088683.0341
9769 | 16574681.3094 | 8391327.0072 | 347771.6829 | 25313779.9995
9770 | 4547545.4937 | 1106541.3171 | 1821363.7332 | 7475450.5441
9771 | 3350078.1458 | 20196194.2957 | 1956007.3079 | 25502279.7494
9772 | 697152.2831 | 15155096.0848 | 2089869.5341 | 17942117.9019
9773 | 7522326.9506 | 7289400.2671 | 0 | 14811727.2177
9774 | 7292003.589 | 14272382.3932 | 545669.7983 | 22110055.7805
9775 | 13766397.6973 | 14254545.2084 | 0 | 28020942.9057
9776 | 2674585.6885 | 2633465.5703 | 0 | 5308051.2588
9777 | 4543444.6243 | 3643470.3798 | 0 | 8186915.0042
9778 | 18574602.4758 | 4876415.2212 | 1435725.2586 | 24886742.9555
9779 | 8608098.9685 | 2581928.1317 | 10747518.833 | 21937545.9332
9780 | 1654049.4292 | 11126325.5243 | 1081054.7598 | 13861429.7132
9781 | 5418755.3074 | 13840914.2064 | 448669.5149 | 19708339.0287
9782 | 17579604.7974 | 0 | 3060173.6796 | 20639778.477
9783 | 8258474.021 | 0 | 675845.6724 | 8934319.6935
9784 | 35198144.7871 | 26021905.2685 | 1039636.4348 | 62259686.4904
9785 | 14212113.3612 | 17559994.5346 | 1402238.472 | 33174346.3678
9786 | 4195231.409 | 4286250.5139 | 3879976.6354 | 12361458.5583
9787 | 4213023.1544 | 4773308.8205 | 2330062.2932 | 11316394.2681
9788 | 11983373.7041 | 0 | 85700.3046 | 12069074.0087
9789 | 22349798.093 | 0 | 1671497.1103 | 24021295.2033
9790 | 10453808.6099 | 3031267.7229 | 2296392.9414 | 15781469.2742
9791 | 16049685.1865 | 0 | 550398.5694 | 16600083.7559
9792 | 6929032.6711 | 0 | 11073268.9338 | 18002301.6049
9793 | 17919572.4545 | 7048920.9428 | 0 | 24968493.3973
9794 | 5089296.7976 | 11758197.3868 | 1278110.4652 | 18125604.6496
9795 | 4031794.8907 | 16094943.6574 | 3943268.4921 | 24070007.0402
9796 | 4154758.1059 | 7105733.2014 | 2205727.447 | 13466218.7543
9797 | 2120022.3279 | 8872617.6656 | 8735969.2461 | 19728609.2397
9798 | 7910228.9662 | 0 | 0 | 7910228.9662
9799 | 1634248.1322 | 0 | 17293107.6855 | 18927355.8177
9800 | 5129531.5046 | 6784485.8819 | 69384.1431 | 11983401.5296
9801 | 39381573.2897 | 0 | 490723.7361 | 39872297.0258
9802 | 8599805.1988 | 0 | 1782878.6432 | 10382683.842
9803 | 5696508.5475 | 8224389.6815 | 274766.4367 | 14195664.6657
9804 | 8107654.1722 | 1473643.8154 | 543841.0882 | 10125139.0757
9805 | 7072092.6314 | 29746051.4832 | 9363793.8017 | 46181937.9162
9806 | 4376541.831 | 951265.0176 | 1464160.4803 | 6791967.329
9807 | 23878719.0751 | 19558017.0734 | 0 | 43436736.1485
9808 | 11387873.5496 | 14665401.2766 | 3677256.2462 | 29730531.0724
9809 | 3274725.8024 | 12440989.4401 | 1802381.8163 | 17518097.0588
9810 | 7363422.3111 | 5476235.6828 | 16495396.3597 | 29335054.3537
9811 | 13931092.3407 | 7702774.1171 | 258211.9903 | 21892078.4482
9812 | 4859636.2382 | 4270080.9931 | 2917441.5292 | 12047158.7606
9813 | 5738681.5584 | 487528.2477 | 2778479.9802 | 9004689.7864
9814 | 4426065.6653 | 9323295.4051 | 2108648.9702 | 15858010.0406
9815 | 7722341.2325 | 8892206.9024 | 25588893.1232 | 42203441.258
9816 | 11058893.7982 | 7571530.5583 | 530141.1061 | 19160565.4626
9817 | 6916324.5642 | 8375567.7782 | 169841.3251 | 15461733.6676
9818 | 17091266.2353 | 14572935.6819 | 213594.1341 | 31877796.0513
9819 | 1851764.1277 | 6496461.6066 | 9179881.0646 | 17528106.7988
9820 | 4215020.4455 | 2129846.8184 | 1659878.5966 | 8004745.8605
9821 | 4011060.3167 | 7401211.0347 | 2822519.4215 | 14234790.7729
9822 | 25298925.0911 | 3266314.2019 | 431361.6654 | 28996600.9583
9823 | 10800979.8382 | 10487295.633 | 61013.837 | 21349289.3082
9824 | 21473643.1814 | 8414600.4718 | 1791458.6753 | 31679702.3285
9825 | 13400842.3237 | 11900270.9132 | 0 | 25301113.2369
9826 | 4387563.3307 | 0 | 718489.8369 | 5106053.1677
9827 | 33337173.4689 | 8982320.1646 | 289315.2841 | 42608808.9176
9828 | 20800865.8949 | 6447625.2066 | 410643.9992 | 27659135.1007
9829 | 12757139.9322 | 2297707.3845 | 1738067.1679 | 16792914.4846
9830 | 970568.2439 | 1254889.0621 | 1280521.1646 | 3505978.4707
9831 | 16316360.3891 | 3783392.881 | 244792.2101 | 20344545.4802
9832 | 21182340.5076 | 1608786.0118 | 1732463.6436 | 24523590.163
9833 | 2044679.2296 | 2762505.5547 | 713039.8149 | 5520224.5992
9834 | 8788159.2013 | 8481358.7255 | 531482.5941 | 17801000.5208
9835 | 2869868.7077 | 5091416.0885 | 0 | 7961284.7962
9836 | 21063640.6802 | 12125631.466 | 296007.0262 | 33485279.1724
9837 | 1445758.7517 | 15499342.9954 | 270598.1124 | 17215699.8594
9838 | 3327605.2865 | 21620526.3376 | 1653277.8515 | 26601409.4756
9839 | 15595662.1743 | 28793955.2663 | 59487.337 | 44449104.7776
9840 | 6258666.452 | 0 | 0 | 6258666.452
9841 | 2861525.37 | 14142013.1952 | 3127476.9608 | 20131015.526
9842 | 6781592.0318 | 2351293.5418 | 1901680.2712 | 11034565.8448
9843 | 2577079.5589 | 13763552.5342 | 18938459.6103 | 35279091.7034
9844 | 5949494.9162 | 14324402.109 | 3465683.1181 | 23739580.1433
9845 | 3513811.1927 | 9217694.7883 | 1271416.2435 | 14002922.2245
9846 | 11193135.2495 | 8128427.7634 | 5145227.7848 | 24466790.7977
9847 | 3729733.5002 | 18061655.4829 | 1459312.643 | 23250701.626
9848 | 15897768.1996 | 16915812.3311 | 879779.293 | 33693359.8237
9849 | 7669335.5583 | 6083352.2553 | 13788503.181 | 27541190.9946
9850 | 17232370.7381 | 9968051.1554 | 3565725.2877 | 30766147.1812
9851 | 1498640.8006 | 12552583.1493 | 0 | 14051223.9499
9852 | 6053380.2884 | 0 | 190977.9913 | 6244358.2798
9853 | 9662318.7952 | 3882138.2602 | 2411091.4632 | 15955548.5186
9854 | 3799955.9036 | 17072454.1976 | 2240054.1359 | 23112464.2372
9855 | 9234271.1199 | 3417631.0725 | 989470.0097 | 13641372.2021
9856 | 7233015.371 | 4386337.5714 | 0 | 11619352.9424
9857 | 9956885.1928 | 12397752.6248 | 1321653.005 | 23676290.8226
9858 | 4905359.664 | 14547162.3033 | 1995632.6981 | 21448154.6655
9859 | 3182398.6279 | 11874877.2542 | 4997802.2335 | 20055078.1156
9860 | 8836667.5742 | 12467459.9482 | 3347052.349 | 24651179.8714
9861 | 6524810.9556 | 1889935.8629 | 2165463.8609 | 10580210.6794
9862 | 3714142.7591 | 2388422.8475 | 0 | 6102565.6067
9863 | 6628080.3122 | 2750142.7046 | 6174301.225 | 15552524.2418
9864 | 13094732.6685 | 7672397.3831 | 0 | 20767130.0516
9865 | 1703272.2161 | 2409149.648 | 1697292.0846 | 5809713.9487
9866 | 217301.5239 | 2657914.2911 | 2552600.8419 | 5427816.6569
9867 | 7689591.9398 | 11879000.5089 | 6826177.7936 | 26394770.2423
9868 | 7993132.2163 | 9922702.242 | 1144355.6214 | 19060190.0797
9869 | 2404608.3735 | 4837531.4985 | 4386495.1945 | 11628635.0666
9870 | 1408500.5265 | 6130854.736 | 1225005.7211 | 8764360.9836
9871 | 7526135.5583 | 4090973.5189 | 83831.9996 | 11700941.0767
9872 | 23202708.1803 | 1159208.4837 | 0 | 24361916.664
9873 | 10858445.5663 | 0 | 662182.7625 | 11520628.3288
9874 | 10178724.8127 | 7454725.3772 | 2379291.1759 | 20012741.3659
9875 | 5424111.9255 | 1194998.9891 | 6885849.0097 | 13504959.9244
9876 | 6628816.44 | 10656829.9924 | 1035198.2786 | 18320844.711
9877 | 13945246.8892 | 18462273.2795 | 270507.9022 | 32678028.0708
9878 | 7757718.6903 | 0 | 88547.3652 | 7846266.0555
9879 | 14432922.7195 | 8980514.6055 | 522927.728 | 23936365.0529
9880 | 995209.7972 | 9681566.6273 | 0 | 10676776.4245
9881 | 1262143.2388 | 5844951.1807 | 16030.5513 | 7123124.9708
9882 | 9039041.844 | 15666913.8974 | 6206184.9169 | 30912140.6582
9883 | 1365726.2087 | 11456410.7251 | 2871778.0031 | 15693914.9369
9884 | 15658510.9137 | 8022992.7885 | 0 | 23681503.7022
9885 | 6988365.6701 | 10250840.3157 | 3459471.0832 | 20698677.069
9886 | 1395799.9833 | 0 | 0 | 1395799.9833
9887 | 7380539.232 | 13835257.9196 | 361096.1948 | 21576893.3464
9888 | 9098259.0325 | 4294995.7428 | 12498897.3636 | 25892152.1389
9889 | 5351451.0865 | 0 | 10616152.5467 | 15967603.6332
9890 | 6368040.1758 | 3709897.977 | 6436060.2648 | 16513998.4177
9891 | 12110419.8964 | 5427999.5361 | 935108.727 | 18473528.1594
9892 | 26398984.0466 | 13043713.4989 | 6039310.8576 | 45482008.4032
9893 | 3490937.4667 | 4187838.722 | 8614029.5656 | 16292805.7543
9894 | 5471349.165 | 0 | 572857.2482 | 6044206.4132
9895 | 8765394.9125 | 14834181.6954 | 245131.1603 | 23844707.7682
9896 | 2915923.6594 | 3646627.9836 | 1526480.2929 | 8089031.9358
9897 | 5711967.2872 | 0 | 864625.9617 | 6576593.2488
9898 | 73967731.2128 | 4421492.2928 | 871419.7134 | 79260643.219
9899 | 12055561.7628 | 0 | 18473584.9126 | 30529146.6753
9900 | 3809457.8007 | 0 | 687281.6481 | 4496739.4488
9901 | 1687083.7062 | 5177841.1297 | 4975177.3475 | 11840102.1834
9902 | 13840126.1572 | 3390598.9394 | 0 | 17230725.0967
9903 | 24464068.1205 | 10291302.0104 | 579453.0362 | 35334823.1672
9904 | 5333175.9433 | 11533582.2204 | 5326758.6976 | 22193516.8613
9905 | 567319.5481 | 0 | 5685656.4154 | 6252975.9635
9906 | 3658961.3226 | 0 | 6600908.3589 | 10259869.6815
9907 | 7909290.4705 | 1136410.3203 | 500214.1337 | 9545914.9245
9908 | 1175775.5732 | 4100622.4795 | 0 | 5276398.0527
9909 | 2650692.4956 | 11138163.7744 | 964686.6156 | 14753542.8856
9910 | 8649066.1212 | 0 | 419627.8951 | 9068694.0162
9911 | 5780913.6359 | 0 | 0 | 5780913.6359
9912 | 4152740.6793 | 12187168.9362 | 0 | 16339909.6155
9913 | 3649730.3466 | 6651577.1444 | 9765045.5075 | 20066352.9984
9914 | 19910889.5932 | 7178242.2387 | 962157.6843 | 28051289.5162
9915 | 2715876.3204 | 3442271.9082 | 1067551.7665 | 7225699.9952
9916 | 9387888.3584 | 8477686.6573 | 186648.6987 | 18052223.7144
9917 | 4212907.9278 | 5964219.4432 | 5042970.2533 | 15220097.6243
9918 | 4063244.8109 | 0 | 116812.616 | 4180057.4269
9919 | 1722116.0741 | 13828209.1406 | 0 | 15550325.2148
9920 | 9430580.0063 | 1044475.9895 | 245635.0047 | 10720691.0005
9921 | 6594391.0552 | 1588438.4263 | 98206.0282 | 8281035.5097
9922 | 108010451.4174 | 4560946.4962 | 2702952.4481 | 115274350.3618
9923 | 5438300.9372 | 0 | 873672.1595 | 6311973.0967
9924 | 6045826.721 | 4280559.9053 | 1793243.3023 | 12119629.9287
9925 | 1189462.4793 | 7328417.5072 | 1698470.7496 | 10216350.7361
9926 | 1041545.3008 | 1525808.3212 | 4192934.7335 | 6760288.3556
9927 | 11597730.045 | 11448853.0119 | 1055948.6523 | 24102531.7092
9928 | 16090864.9702 | 2743143.3793 | 2622609.3272 | 21456617.6767
9929 | 3262024.892 | 3710955.5434 | 968901.4939 | 7941881.9293
9930 | 7417045.66 | 6014415.5413 | 675088.7404 | 14106549.9417
9931 | 11023252.7203 | 5506145.5371 | 3495340.2912 | 20024738.5486
9932 | 16523311.0474 | 4449378.4763 | 13103850.9216 | 34076540.4453
9933 | 11926074.6202 | 4543868.8431 | 2501723.066 | 18971666.5293
9934 | 9435877.4597 | 1317371.9258 | 3649185.6883 | 14402435.0738
9935 | 7526046.5048 | 377006.4071 | 141428.0529 | 8044480.9648
9936 | 8113808.5657 | 5672610.6729 | 696966.5098 | 14483385.7484
9937 | 546485.9955 | 1947252.2532 | 5000483.1241 | 7494221.3728
9938 | 10344934.7191 | 3813021.7441 | 3980946.048 | 18138902.5112
9939 | 10073901.5633 | 11316876.7874 | 6375024.1195 | 27765802.4701
9940 | 13075140.6946 | 25365379.8971 | 15857414.4562 | 54297935.0479
9941 | 10084476.7302 | 0 | 247170.3016 | 10331647.0318
9942 | 2754462.7742 | 7178259.8328 | 1985948.4537 | 11918671.0607
9943 | 4333516.7064 | 1483287.9007 | 19171.868 | 5835976.4751
9944 | 7583715.2715 | 9050357.5186 | 589773.4257 | 17223846.2158
9945 | 4355647.5594 | 4778182.9822 | 1341930.5663 | 10475761.108
9946 | 15293902.0166 | 6725274.0734 | 1781404.1613 | 23800580.2513
9947 | 522504.0354 | 0 | 209641.2516 | 732145.287
9948 | 4972373.5738 | 1767931.4192 | 0 | 6740304.9931
9949 | 5323660.9583 | 0 | 2986224.886 | 8309885.8444
9950 | 5947079.0573 | 16455787.4028 | 0 | 22402866.4602
9951 | 61776813.7996 | 13258930.5291 | 1484109.9029 | 76519854.2315
9952 | 12623018.1844 | 3131546.7536 | 0 | 15754564.9381
9953 | 6993861.6277 | 1518708.16 | 0 | 8512569.7877
9954 | 28773505.8142 | 19437408.9866 | 55596.5645 | 48266511.3653
9955 | 8181573.2202 | 1337883.8327 | 11707730.9322 | 21227187.985
9956 | 20553247.9255 | 6015704.0469 | 2268156.6374 | 28837108.6098
9957 | 2604899.6216 | 9302470.3462 | 12424149.15 | 24331519.1178
9958 | 6386454.5876 | 19638556.6333 | 8302153.4892 | 34327164.7101
9959 | 4224857.2146 | 12298922.1012 | 5613016.9688 | 22136796.2845
9960 | 3768550.8995 | 6057686.6807 | 4338041.8001 | 14164279.3804
9961 | 17624524.0179 | 22325057.9378 | 1084535.6115 | 41034117.5673
9962 | 14339280.2763 | 2190231.8747 | 1233813.9781 | 17763326.1291
9963 | 19937781.6599 | 3113311.4255 | 1281622.0466 | 24332715.132
9964 | 4429532.6515 | 0 | 3962385.1199 | 8391917.7714
9965 | 1256245.426 | 5803247.2302 | 237802.5706 | 7297295.2268
9966 | 4530246.0036 | 2095996.1863 | 0 | 6626242.19
9967 | 7916871.0791 | 10952697.4051 | 1547261.623 | 20416830.1072
9968 | 5907507.4851 | 11900995.8236 | 2401474.8323 | 20209978.141
9969 | 11994945.7702 | 25030524.5051 | 1074136.2018 | 38099606.4771
9970 | 4275462.3609 | 7916066.4906 | 0 | 12191528.8515
9971 | 4113157.9662 | 6414983.5012 | 0 | 10528141.4674
9972 | 8516576.7735 | 8000841.4319 | 4666897.4435 | 21184315.6489
9973 | 10128863.3044 | 1440462.1242 | 1622133.4487 | 13191458.8772
9974 | 3404345.6296 | 699989.7786 | 93484.6589 | 4197820.0671
9975 | 2468066.8199 | 11798214.8594 | 448207.432 | 14714489.1113
9976 | 8267797.7194 | 9341641.119 | 5315027.6363 | 22924466.4747
9977 | 10895615.7846 | 8777683.4582 | 0 | 19673299.2428
9978 | 9514331.3828 | 7639399.3204 | 0 | 17153730.7032
9979 | 5389647.1581 | 5113301.3786 | 8032354.5035 | 18535303.0402
9980 | 3935879.2126 | 0 | 434626.1375 | 4370505.3501
9981 | 4854955.8085 | 2209152.8811 | 0 | 7064108.6896
9982 | 12764435.5639 | 12314212.7783 | 2292358.1852 | 27371006.5274
9983 | 17046267.0982 | 3343389.8511 | 2955463.4571 | 23345120.4065
9984 | 4458898.6623 | 936622.086 | 21491025.81 | 26886546.5582
9985 | 4144566.6996 | 4890809.3063 | 1142276.0693 | 10177652.0752
9986 | 3518346.6045 | 0 | 1956202.1583 | 5474548.7628
9987 | 15301950.6938 | 12499890.1975 | 8498994.339 | 36300835.2303
9988 | 19392392.0274 | 21070162.3447 | 0 | 40462554.3721
9989 | 23578807.2347 | 12096379.1315 | 618885.9053 | 36294072.2715
9990 | 29109392.9705 | 14279452.7813 | 2690906.7816 | 46079752.5335
9991 | 4816007.9687 | 1831079.6936 | 183462.8224 | 6830550.4847
9992 | 4181789.0103 | 9660087.5115 | 4081221.1292 | 17923097.6511
9993 | 2375519.2858 | 6905502.5166 | 803366.1016 | 10084387.904
9994 | 4692855.0838 | 2381235.8169 | 2707747.8798 | 9781838.7805
9995 | 3071524.9928 | 9888518.2131 | 170277.0871 | 13130320.293
9996 | 7783309.5087 | 0 | 2855379.7387 | 10638689.2474
9997 | 6278348.1117 | 9570000.633 | 961733.372 | 16810082.1166
9998 | 14336614.587 | 1106319.03 | 0 | 15442933.617
9999 | 8177619.5106 | 3429984.8125 | 481882.9376 | 12089487.2607
10000 | 423596.1874 | 30408113.9773 | 453549.994 | 31285260.1587
This curve is the sum of the other curves